Ministry of Finance

Republic of Maldives

BIDDING DOCUMENT

for

Construction of Ha.Dhidhdhoo Jetty

TES/2019/W-133

July 26

Issued by: National Tender

Ministry of Finance

Republic of Maldives

Standard Tendering Document

Table of Contents

PART 1  Tendering Procedures	3

Section I - Instructions to Tenderers	4

Section II - Bid Data Sheet (BDS)	24

Section III - Evaluation and Qualification Criteria	28

Section IV - Tendering Forms	36

Section V - Eligible Countries	60

PART 2 – Employer’s Requirements	…..61

Section VI - Employer’s Requirements	62

PART 3 –Contract	68

Section VII.  General Conditions of Contract for the Procurement of Works	69

Section VIII.  Particular Conditions of Contract	89

Section IX - Contract Forms	93

PART 1 Tendering Procedures

Section I - Instructions to Tenderers

Table of Clauses

A.	General	6

1.	Scope of Tender	6

2.	Source of Funds	6

3.	Fraud and Corruption	6

4.	Eligible Tenderers	7

5.	Eligible Materials, Equipment and Services	9

B.	Contents of Tendering Document	9

6.	Sections of Tendering Document	9

7.	Clarification of Tendering Document, Site Visit, Pre-Tender Meeting	10

8.	Amendment of Tendering Document	11

C.	Preparation of Tenders	11

9.	Cost of Tendering	11

10.	Language of Tender	11

11.	Documents Comprising the Tender	11

12.	Letter of Tender and Schedules	12

13.	Alternative Tenders	12

14.	Tender Prices and Discounts	12

15.	Currencies of Tender and Payment	13

16.	Documents Comprising the Technical Proposal	13

17.	Documents Establishing the Qualifications of the Tenderer	13

18.	Period of Validity of Tenders	13

19.	Tender Security	14

20.	Format and Signing of Tender	15

D.	Submission and Opening of Tenders	15

21.	Sealing and Marking of Tenders	15

22.	Deadline for Submission of Tenders	16

23.	Late Tenders	16

24.	Withdrawal, Substitution, and Modification of Tenders	16

25.	Tender Opening	17

E.	Evaluation and Comparison of Tenders	17

26.	Confidentiality	18

27.	Clarification of Tenders	18

28.	Deviations, Reservations, and Omissions	18

29.	Determination of Responsiveness	18

30.	Nonconformities, Errors, and Omissions	19

31.	Correction of Arithmetical Errors	19

32.	Conversion to Single Currency	20

33.	Margin of Preference	20

34.	Evaluation of Tenders	20

35.	Comparison of Tenders	21

36.	Qualification of the Tenderer	21

37.	Employer’s Right to Accept Any Tender, and to Reject Any or All Tenders	21

F.	Award of Contract	21

38.	Award Criteria	21

39.	Notification of Award	21

40.	Signing of Contract	22

41.	Performance Security	22

42.	Adjudicator	22

Section I - Instructions to Tenderers (ITT)

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Scope of Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer, as indicated in the BDS, issues this Tender Document for the procurement of the Works as specified in Section VI (Employer’s Requirements). The name, identification, and number of contracts (lots) of this tendering are provided in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Throughout this Tendering Document: - (a) the term “in writing” means communicated in written form and delivered against receipt; - (b) except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and - (c) “day” means calendar day. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Source of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Procuring Entity (Employer) has an approved budget from the Government of the Maldives which has been allocated towards the project indicated in the BDS. The Procuring Entity intends to apply the allocated funds to eligible payments under contract(s) for which this Tender Document is issued. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Payments will be made only at the request of the Procuring Entity in accordance with contact terms and conditions and in accordance with financial legislation in force. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Fraud and Corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - It is the Government’s policy to require that Procuring Entities, as well as Tenderers, suppliers, contractors and their subcontractors observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Government: (a) defines, for the purposes of this provision, the terms set forth below as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) "obstructive practice" is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Government investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or (bb) acts intended to materially impede the exercise of the Government’s inspection and audit rights provided for under sub-clause 3.1 (e) below. (b) will reject a proposal for award if it determines that the Tenderer recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for the contract in question; (c) will cancel in whole or in part a contract if it determines at any time that representatives of the Procuring Entity engaged in corrupt, fraudulent, collusive, or coercive practices during the procurement or the execution of that contract, without the Government having taken timely and appropriate action satisfactory to address such practices when they occur; (d) will suspend a firm or individual from participation in public procurement, by declaring it ineligible for a stated period of time, to be awarded a Government funded contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for, or in executing, a Government funded contract. The list of suspended firms is available at the electronic address specified in the BDS; and (e) will have the right to require that a provision be included in tender documents and in contracts, requiring Tenderers, suppliers, and contractors and their sub-contractors to permit the Employer to inspect their accounts and records and other documents relating to the Tender submission and contract performance and to have them audited by auditors appointed by the Government. - Furthermore, tenderers shall be aware of the provision stated in GCC Sub-Clauses 22.2 and 56.2 (h). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Eligible Tenderers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer may be a natural person, private entity, or government-owned entity—subject to ITB 4.6—or any combination of them in the form of a joint venture, under an existing agreement, or with the intent to constitute a legally-enforceable joint venture. Unless otherwise stated in the BDS, all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer, and all parties constituting the Tenderer, shall have the nationality of an eligible country, in accordance with Section V (Eligible Countries). A Tenderer shall be deemed to have the nationality of a country if the Tenderer is a citizen or is constituted, or incorporated, and operates in conformity with the provisions of the rules and regulation of Maldives. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract including related services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer shall meet the following criteria to be eligible to participate in public procurement: - have the legal capacity to enter into the contract; - not be insolvent, in receivership, bankrupt or being wound up, its affairs not being administered by a court or a judicial officer, its business activities not being suspended and not the subject of legal proceedings for any of the foregoing; - have fulfilled its obligations to pay taxes. - not have been, and its directors or officers not have been, convicted of any criminal offence related to their professional conduct or the making of false statements or misrepresentations as to their qualifications to enter into a contract within a period of five years preceding the commencement of the procurement proceedings; and - not have a conflict of interest in relation to the procurement requirement in accordance with Sub-Clause 4.4. - shall be a contractor who falls in to the grades of National Contractors Registry as specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer shall not have a conflict of interest. All Tenderers found to have a conflict of interest shall be disqualified. A Tenderer may be considered to have a conflict of interest with one or more parties in this tendering process, if : - they have a controlling partner in common; or - they receive or have received any direct or indirect subsidy from any of them; or - they have the same legal representative for purposes of this Tender; or - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about or influence on the Tender of another Tenderer, or influence the decisions of the Employer regarding this tendering process; or - a Tenderer participates in more than one Tender in this tendering process. Participation by a Tenderer in more than one Tender will result in the disqualification of all Tenders in which the party is involved. However, this does not limit the inclusion of the same subcontractor in more than one Tender; or - a Tenderer or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the contract that is the subject of the Tender; or - a Tenderer, or any of its affiliates has been hired (or is proposed to be hired) by the Employer as Engineer for the contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer that has been suspended from participation in public procurement by the Government in accordance with ITB 3, at the date of the deadline for Tender submission or thereafter, shall be disqualified. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Government-owned enterprises in the Employer’s country shall be eligible only if they can establish that they are legally and financially autonomous and operate under commercial law, and that they are not a dependent agency of the Employer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenderers shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In case a prequalification process has been conducted prior to the tendering process, this tendering is open only to prequalified Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Eligible Materials, Equipment and Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The materials, equipment and services to be supplied under the Contract shall have their origin in eligible source countries as defined in ITB 4.2 above and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, Tenderers may be required to provide evidence of the origin of materials, equipment and services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - For purposes of ITB 5.1 above, “origin” means the place where the materials and equipment are mined, grown, produced or manufactured, and from which the services are provided. Materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that differs substantially in its basic characteristics or in purpose or utility from its components. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Contents of Tendering Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Sections of Tendering Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tendering Document consist of Parts 1, 2 and 3 which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART 1 Tendering Procedures Section I - Instructions to Tenderers (ITB) Section II - Bid Data Sheet (BDS) Section III - Evaluation and Qualification Criteria Section IV - Tendering Forms Section V - Eligible Countries PART 2 Requirements Section VI – Employer’s Requirements PART 3 Conditions of Contract and Contract Forms Section VII - General Conditions of Contract (GCC) Section VIII - Particular Conditions (PCC) Section IX - Contract Forms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Invitation for Tenders issued by the Employer is not part of the Tendering Document. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer is not responsible for the completeness of the Tendering Document and their Addenda, if they were not obtained directly from the source stated by the Employer in the Invitation for Tenders. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer is expected to examine all instructions, forms, terms, and specifications in the Tendering Document. Failure to furnish all information or documentation required by the Tendering Document may result in the rejection of the Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Clarification of Tendering Document, Site Visit, Pre-Tender Meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A prospective Tenderer requiring any clarification of the Tendering Document shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise his inquiries during the pre-Tender meeting if provided for in accordance with ITB 7.4. The Employer will respond in writing to any request for clarification, provided that such request is received the number of days given in the BDS prior to the deadline for submission of Tenders. The Employer shall forward copies of its response to all Tenderers who have acquired the Tendering Document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Tendering Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 22.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer is encouraged to visit and examine the Site of Works and its surroundings and obtain for itself, on its own risk and responsibility, all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Tenderer’s own expense. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Tenderer, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer’s designated representative is invited to attend a pre-Tender meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer is requested, as far as possible, to submit any questions in writing, to reach the Employer not later than one week before the meeting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Minutes of the pre-Tender meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Tenderers who have acquired the Tendering Document in accordance with ITB 6.3. Any modification to the Tendering Document that may become necessary as a result of the pre-Tender meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-Tender meeting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Nonattendance at the pre-Tender meeting will not be a cause for disqualification of a Tenderer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Amendment of Tendering Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - At any time prior to the deadline for submission of Tenders, the Employer may amend the Tendering Document by issuing addenda. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Any addendum issued shall be part of the Tendering Document and shall be communicated in writing to all who have obtained the Tendering Document from the Employer in accordance with ITB 6.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To give prospective Tenderers reasonable time in which to take an addendum into account in preparing their Tenders, the Employer may, at its discretion, extend the deadline for the submission of Tenders, pursuant to ITB 22.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Preparation of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Cost of Tendering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer shall bear all costs associated with the preparation and submission of its Tender, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the tendering process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Language of Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tender, as well as all correspondence and documents relating to the Tender exchanged by the Tenderer and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Tender may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Tender, such translation shall govern. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Documents Comprising the Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tender shall comprise the following: - Letter of Tender; - completed Schedules, in accordance with ITB 12 and 14, or as stipulated in the BDS; - Tender Security or Tender Securing Declaration, in accordance with ITB 19; - alternative Tenders, at the Tenderer’s option, and if permissible, in accordance with ITB 13; - written confirmation authorizing the signatory of the Tender to commit the Tenderer, in accordance with ITB 20.2; - documentary evidence in accordance with ITB 17 establishing the Tenderer’s qualifications to perform the contract; - Technical Proposal in accordance with ITB 16; - In the case of a Tender submitted by a joint venture (JV), the JV agreement, or letter of intent to enter into a JV including a draft agreement, indicating at least the parts of the Works to be executed by the respective partners; and - Any other document required in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Letter of Tender and Schedules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Letter of Tender, Schedules, and all documents listed under Clause 11, shall be prepared using the relevant forms in Section IV (Tendering Forms), if so provided. The forms must be completed without any alterations to the text, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Alternative Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Unless otherwise indicated in the BDS, alternative Tenders shall not be considered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS. If permitted, the method for their evaluation will be stipulated in Section III (Evaluation and Qualification Criteria). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - When specified in the BDS pursuant to ITB 13.1, and subject to ITB 13.4 below, Tenderers wishing to offer technical alternatives to the requirements of the Tendering Document must first price the Employer’s design as described in the Tendering Document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated tenderer conforming to the basic technical requirements shall be considered by the Employer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - When specified in the BDS, Tenderers are permitted to submit alternative technical solutions for specified parts of the Works. Such parts will be identified in the BDS and described in Section VI (Employer’s Requirements). If permitted, the method for their evaluation will be stipulated in Section III (Evaluation and Qualification Criteria). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tender Prices and Discounts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The prices and discounts quoted by the Tenderer in the Letter of Tender and in the Schedules shall conform to the requirements specified below. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer shall submit a Tender for the whole of the works described in ITB 1.1 by filling in prices for all items of the Works, as identified in Section IV, Tendering Forms. In case of admeasurement contracts, the Tenderer shall fill in rates and prices for all items of the Works described in the Bill of Quantities. Items against which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bill of Quantities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The price to be quoted in the Letter of Tender shall be the total price of the Tender, excluding any discounts offered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Unconditional discounts, if any, and the methodology for their application shall be quoted in the Letter of Tender, in accordance with ITB 12.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If so indicated in ITB 1.1, Tenders are invited for individual contracts (lots) or for any combination of contracts (packages). Tenderers wishing to offer any price reduction for the award of more than one Contract shall specify in their Tender the price reductions applicable to each package, or alternatively, to individual Contracts within the package. Price reductions or discounts shall be submitted in accordance with ITB 14.3, provided the Tenders for all contracts are submitted and opened at the same time. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Unless otherwise provided in the BDS and the Conditions of Contract, the prices quoted by the Tenderer shall be fixed. If the prices quoted by the Tenderer are subject to adjustment during the performance of the Contract in accordance with the provisions of the Conditions of Contract, the Tenderer shall furnish the indices and weightings for the price adjustment formulae in the Schedule of Adjustment Data in Section IV (Tendering Forms) and the Employer may require the Tenderer to justify its proposed indices and weightings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of Tenders, shall be included in the rates and prices and the total Tender price submitted by the Tenderer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Currencies of Tender and Payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The currency(ies) of the Tender shall be as specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenderers may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the prices shown in the appropriate form(s) of Section IV, in which case a detailed breakdown of the foreign currency requirements shall be provided by Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Documents Comprising the Technical Proposal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule and any other information as stipulated in Section IV (Tendering Forms), in sufficient detail to demonstrate the adequacy of the Tenderers’ proposal to meet the work requirements and the completion time. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Documents Establishing the Qualifications of the Tenderer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To establish its qualifications to perform the Contract in accordance with Section III (Evaluation and Qualification Criteria) the Tenderer shall provide the information requested in the corresponding information sheets included in Section IV (Tendering Forms). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Period of Validity of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenders shall remain valid for the period specified in the BDS after the Tender submission deadline date prescribed by the Employer. A Tender valid for a shorter period shall be rejected by the Employer as nonresponsive. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In exceptional circumstances, prior to the expiration of the Tender validity period, the Employer may request Tenderers to extend the period of validity of their Tenders. The request and the responses shall be made in writing. If a Tender security is requested in accordance with ITB 19, it shall also be extended for a corresponding period. A Tenderer may refuse the request without forfeiting its Tender security. A Tenderer granting the request shall not be required or permitted to modify its Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In the case of fixed price contracts, if the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial Tender validity, the Contract price shall be adjusted by a factor specified in the request for extension. Tender evaluation shall be based on the Tender Price without taking into consideration the above correction. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tender Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Unless otherwise specified in the BDS, the Tenderer shall furnish as part of its Tender, in original form, either a Tender Securing Declaration or a Tender security as specified in the BDS. In the case of a Tender security, the amount shall be as specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tender Securing Declaration shall use the form included in Section IV Tendering Forms. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If a Tender security is specified pursuant to ITB 19.1, the Tender security shall be, at the Tenderer’s option, in any of the following forms: - an unconditional guarantee, issued by a bank or surety; - a cashier’s or certified check; or - another security indicated in the BDS. - from a reputable source from an eligible country. If the unconditional guarantee is issued by an insurance company or bonding company located outside the Employer’s Country, it shall have a correspondent financial institution located in the Republic of Maldives. In the case of a bank guarantee, the Tender security shall be submitted either using the Tender Security Form included in Section IV (Tendering Forms) or in another substantially similar format approved by the Employer prior to Tender submission. In either case, the form must include the complete name of the Tenderer. The Tender security shall be valid for twenty-eight days (28) beyond the original validity period of the Tender, or beyond any period of extension if requested under ITB 18.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Any Tender not accompanied by an enforceable and substantially compliant Tender security or Tender Securing Declaration, if required in accordance with ITB 19.1, shall be rejected by the Employer as nonresponsive. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If a Tender security is specified pursuant to ITB 19.1, the Tender security of unsuccessful Tenderers shall be returned as promptly as possible upon the successful Tenderer’s furnishing of the performance security pursuant to ITB 41. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If a Tender security is specified pursuant to ITB 19.1, the Tender security of the successful Tenderer shall be returned as promptly as possible once the successful Tenderer has signed the Contract and furnished the required performance security. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tender security may be forfeited or the Tender Securing Declaration executed: - if a Tenderer withdraws its Tender during the period of Tender validity specified by the Tenderer on the Letter of Tender, except as provided in ITB 18.2 or - if the successful Tenderer fails to: #### sign the Contract in accordance with ITB 40; or #### furnish a performance security in accordance with ITB 41. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tender Security or the Tender Securing Declaration of a JV shall be in the name of the JV that submits the Tender. If the JV has not been constituted into a legally-enforceable JV, at the time of tendering, the Tender Security or the Tender Securing Declaration shall be in the names of all future partners as named in the letter of intent mentioned in ITB 4.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Format and Signing of Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Tenderer shall prepare one original of the documents comprising the Tender as described in ITB 11 and clearly mark it “Original”. Alternative Tenders, if permitted in accordance with ITB 13, shall be clearly marked “Alternative”. In addition, the Tenderer shall submit copies of the Tender in the number specified in the BDS, and clearly mark each of them “Copy.” In the event of any discrepancy between the original and the copies, the original shall prevail. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The original and all copies of the Tender shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Tenderer. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Tender. The name and position held by each person signing the authorization must be typed or printed below the signature. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialled by the person signing the Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Submission and Opening of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Sealing and Marking of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenderers may always submit their Tenders by mail or by hand. When so specified in the BDS, Tenderers shall have the option of submitting their Tenders electronically. Procedures for submission, sealing and marking are as follows: - (a) Tenderers submitting Tenders by mail or by hand shall enclose the original and each copy of the Tender, including alternative Tenders, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “Original”, “Alternative” and “Copy.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. The rest of the procedure shall be in accordance with ITB sub-Clauses 22.2 and 22.3. - (b) Tenderers submitting Tenders electronically shall follow the electronic Tender submission procedures specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The inner and outer envelopes shall: - (a) bear the name and address of the Tenderer; - (b) be addressed to the Employer as provided in the BDS pursuant to ITB 22.1; - (c) bear the specific identification of this tendering process indicated in accordance with ITB 1.1; and - (d) bear a warning not to open before the time and date for Tender opening. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Deadline for Submission of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenders must be received by the Employer at the address and no later than the date and time indicated in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer may, at its discretion, extend the deadline for the submission of Tenders by amending the Tendering Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Tenderers previously subject to the deadline shall thereafter be subject to the deadline as extended. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Late Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall not consider any Tender that arrives after the deadline for submission of Tenders, in accordance with ITB 22. Any Tender received by the Employer after the deadline for submission of Tenders shall be declared late, rejected, and returned unopened to the Tenderer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Withdrawal, Substitution, and Modification of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A Tenderer may withdraw, substitute, or modify its Tender after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 20.2, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the Tender must accompany the respective written notice. All notices must be: - (a) prepared and submitted in accordance with ITB 20 and ITB 21 (except that withdrawal notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” “Substitution,” “Modification;” and - (b) received by the Employer prior to the deadline prescribed for submission of Tenders, in accordance with ITB 22. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tenders requested to be withdrawn in accordance with ITB 24.1 shall be returned unopened to the Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - No Tender may be withdrawn, substituted, or modified in the interval between the deadline for submission of Tenders and the expiration of the period of Tender validity specified by the Tenderer on the Letter of Tender or any extension thereof. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tender Opening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall open the Tenders in public at the address, date and time specified in the BDS in the presence of Tenderers` designated representatives and anyone who choose to attend. Any specific electronic Tender opening procedures required if electronic tendering is permitted in accordance with ITB 21.1, shall be as specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - First, envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding Tender shall not be opened, but returned to the Tenderer. No Tender withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at Tender opening. Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding Tender being substituted, and the substituted Tender shall not be opened, but returned to the Tenderer. No Tender substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at Tender opening. Envelopes marked “Modification” shall be opened and read out with the corresponding Tender. No Tender modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at Tender opening. Only envelopes that are opened and read out at Tender opening shall be considered further. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - All other envelopes shall be opened one at a time, reading out: the name of the Tenderer and the Tender Price(s), including any discounts and alternative Tenders and indicating whether there is a modification; the presence of a Tender security or Tender securing Declaration, if required; and any other details as the Employer may consider appropriate. Only discounts and alternative offers read out at Tender opening shall be considered for evaluation. No Tender shall be rejected at Tender opening except for late Tenders, in accordance with ITB 23.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall prepare a record of the Tender opening that shall include, as a minimum: the name of the Tenderer and whether there is a withdrawal, substitution, or modification; the Tender Price, per contract if applicable, including any discounts and alternative offers; and the presence or absence of a Tender security, if one was required. The Tenderers’ representatives who are present shall be requested to sign the record. The omission of a Tenderer’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Evaluation and Comparison of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Confidentiality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Information relating to the examination, evaluation, comparison, and post-qualification of Tenders and recommendation of contract award, shall not be disclosed to Tenderers or any other persons not officially concerned with such process until information on Contract award is communicated to all Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Any attempt by a Tenderer to influence the Employer in the evaluation of the Tenders or Contract award decisions may result in the rejection of its Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Notwithstanding ITB 25.2, from the time of Tender opening to the time of Contract award, if any Tenderer wishes to contact the Employer on any matter related to the tendering process, it may do so in writing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Clarification of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To assist in the examination, evaluation, and comparison of the Tenders, and qualification of the Tenderers, the Employer may, at its discretion, ask any Tenderer for a clarification of its Tender. Any clarification submitted by a Tenderer that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the prices or substance of the Tender shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Tenders, in accordance with ITB 31. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If a Tenderer does not provide clarifications of its Tender by the date and time set in the Employer’s request for clarification, its Tender may be rejected. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Deviations, Reservations, and Omissions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - During the evaluation of Tenders, the following definitions apply: - (a) “Deviation” is a departure from the requirements specified in the Tendering Document; - (b) “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Tendering Document; and - (c) “Omission” is the failure to submit part or all of the information or documentation required in the Tendering Document. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Determination of Responsiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer’s determination of a Tender’s responsiveness is to be based on the contents of the Tender itself, as defined in ITB11. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A substantially responsive Tender is one that meets the requirements of the Tendering Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - (a) if accepted, would: #### (i) affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or #### (ii) limit in any substantial way, inconsistent with the Tendering Document, the Employer’s rights or the Tenderer’s obligations under the proposed Contract; or - (b) if rectified, would unfairly affect the competitive position of other Tenderers presenting substantially responsive Tenders. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall examine the technical aspects of the Tender submitted in accordance with ITB 16, Technical Proposal, in particular, to confirm that all requirements of Section VI (Employer’s Requirements) have been met without any material deviation, reservation or omission. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If a Tender is not substantially responsive to the requirements of the Tendering Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Nonconformities, Errors, and Omissions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provided that a Tender is substantially responsive, the Employer may waive any nonconformities in the Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provided that a Tender is substantially responsive, the Employer may request that the Tenderer submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Tender related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Tender. Failure of the Tenderer to comply with the request may result in the rejection of its Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provided that a Tender is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Tender Price. To this effect, the Tender Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. The adjustment shall be made using the methods indicated in Section III (Evaluation and Qualification Criteria). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Correction of Arithmetical Errors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provided that the Tender is substantially responsive, the Employer shall correct arithmetical errors on the following basis: - (a) only for unit price contracts, if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected; - (b) if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and - (c) if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Tenderer that submitted the lowest evaluated Tender does not accept the correction of errors, its Tender shall be declared non-responsive. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conversion to Single Currency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - For evaluation and comparison purposes, the currency(ies) of the Tender shall be converted into a single currency as specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Margin of Preference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A margin of preference shall not apply, unless otherwise specified in the BDS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Evaluation of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall use the criteria and methodologies listed in this Clause. No other evaluation criteria or methodologies shall be permitted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To evaluate a Tender, the Employer shall consider the following: - (a) the Tender price, excluding Provisional Sums and the provision, if any, for contingencies in the Summary Bill of Quantities for admeasurement contracts or Schedule of Prices for lump sum contracts, but including Day-work items, where priced competitively; - (b) price adjustment for correction of arithmetic errors in accordance with ITB 31.1; - (c) price adjustment due to discounts offered in accordance with ITB 14.3; - (d) converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 32; - (e) adjustment for nonconformities in accordance with ITB 30.3; - (f) application of all the evaluation factors indicated in Section III (Evaluation and Qualification Criteria); |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in Tender evaluation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If this Tendering Document allows Tenderers to quote separate prices for different contracts (lots), and to award multiple contracts to a single Tenderer, the methodology to determine the lowest evaluated price of the contract combinations, including any discounts offered in the Letter of Tender, is specified in Section III (Evaluation and Qualification Criteria). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the lowest Evaluated Tender for an admeasurement contract is, in the opinion of the Employer, seriously unbalanced, front loaded or substantially below updated estimates, the Employer may require the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, taking into consideration the schedule of estimated Contract payments, the Employer may require that the amount of the performance security be increased at the expense of the Tenderer to a level sufficient to protect the Employer against financial loss in the event of default of the successful Tenderer under the Contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Comparison of Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall compare all substantially responsive Tenders in accordance with ITB 34.2 to determine the lowest evaluated Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Qualification of the Tenderer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall determine to its satisfaction whether the Tenderer that is selected as having submitted the lowest evaluated and substantially responsive Tender meets the qualifying criteria specified in Section III (Evaluation and Qualification Criteria). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The determination shall be based upon an examination of the documentary evidence of the Tenderer’s qualifications submitted by the Tenderer, pursuant to ITB 17.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - An affirmative determination of qualification shall be a prerequisite for award of the Contract to the Tenderer. A negative determination shall result in disqualification of the Tender, in which event the Employer shall proceed to the next lowest evaluated Tender to make a similar determination of that Tenderer’s qualifications to perform satisfactorily. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Employer’s Right to Accept Any Tender, and to Reject Any or All Tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer reserves the right to accept or reject any Tender, and to annul the tendering process and reject all Tenders at any time prior to contract award, without thereby incurring any liability to Tenderers. In case of annulment, all Tenders submitted and specifically, Tender securities, shall be promptly returned to the Tenderers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Award of Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Award Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Subject to ITB 37.1, the Employer shall award the Contract to the Tenderer whose offer has been determined to be the lowest evaluated Tender and is substantially responsive to the Tendering Document, provided further that the Tenderer is determined to be qualified to perform the Contract satisfactorily. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Notification of Award |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prior to the expiration of the period of Tender validity, the Employer shall notify the successful Tenderer, in writing, via the Letter of Acceptance included in the Contract Forms, that its Tender has been accepted. At the same time, the Employer shall also notify all other Tenderers of the results of the tendering. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Until a formal contract is prepared and executed, the Letter of Acceptance shall constitute a binding Contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall promptly respond in writing to any unsuccessful Tenderer who, after notification of award in accordance with ITB 39.1, requests in writing the grounds on which its Tender was not selected. - Any Tenderer may seek administrative review by a written inquiry to the Procuring Entity (Employer), which it considers to be in breach of the Financial Regulations. Any application for review must be submitted in writing to the Accountable Officer of the Procuring Entity, within ten working days from the date the Tenderer knew, or should have known, of the circumstances giving rise to the complaint. If the Accountable Officer does not issue a decision within ten days, or the Tenderer is not satisfied with the decision, the Tenderer may submit a complaint to the Public Procurement Division. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Signing of Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Promptly upon notification, the Employer shall send the successful Tenderer the Contract Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Tenderer shall sign, date, and return it to the Employer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Performance Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Within twenty-eight (28) days of the receipt of notification of award from the Employer, the successful Tenderer shall furnish the performance security in accordance with the conditions of contract, subject to ITB 34.5, using for that purpose the Performance Security Form included in Section IX (Contract Forms), or another form acceptable to the Employer. If the performance security furnished by the successful Tenderer is in the form of a bond, it shall be issued by a bonding or insurance company that has been determined by the successful Tenderer to be acceptable to the Employer. A foreign institution providing a bond shall have a correspondent financial institution located in the Employer’s Country. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Failure of the successful Tenderer to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the Tender security. In that event the Employer may award the Contract to the next lowest evaluated Tenderer whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Adjudicator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at the hourly fee specified in the BDS, plus reimbursable expenses. If the Tenderer disagrees with this proposal, the Tenderer should so state in his Tender. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator, the Employer will request the Appointing Authority designated in the Particular Conditions of Contract (PCC) pursuant to Clause 23.1 of the General Conditions of Contract (GCC), to appoint the Adjudicator. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Section II - Bid Data Sheet (BDS)

| ITT reference | Tender data that supplements the ITT |
| --- | --- |
| A. Introduction |  |
| ITT 1.1 | The name of the tendering process is: International Competitive Bidding (ICB) The procurement reference number of the tendering process is: (IUL)13-K/13/2019/269 Project number: TES/2019/W-133 |
| ITT 2.1 | The name of the Project is : Construction of Ha.Dhidhdhoo Jetty, Maldives |
| ITT 3.1(d) | A list of firms suspended from participating in Government funded projects is available at http://www.finance.gov.mv |
| ITT 4.1 | The individuals or firms in a JV shall be jointly and severally liable. |
| ITT 4.3 (f) | The following grades of contractors registered under National Contractors Registry will be eligible to participate in this tender. HC01, Grade 1 ,2,3 & 4 |
| B. Tendering Documents |  |
| ITT 7.1 | For clarification purposes only, the Employer’s address is: Ahmed Jinah Ibrahim Procurement Officer National Tender Ministry of Finance Ameenee Magu, Male’, 20379 Republic of Maldives Tel: (960) 334 9102, (960) 334 9106, (960) 334 9115 E-mail: ahmed.jinah @finance.gov.mv CC: tender@finance.gov.mv Requests for clarification should be received by the Employer no later than 1300hrs, 23rd October 2019. |
| ITT 7.4 | A Pre-Tender meeting shall take place. If a Pre-Tender meeting will take place, it will be at the following date, time and place: Date: Time: Venue: |
| C. Preparation of Tenders |  |
| ITT 10.1 | The language of the Tender is: English |
| ITT 11.1(b) | The following schedules shall be submitted with the Tender: - Bill of Quantities - Work Schedule |
| ITT 11.1 (i) | The Tenderer shall submit with its Tender the following additional documents: The Tenderer shall submit the following additional documents in its tender: - Power of Attorney to confirm authorization of the signatory of the Bid to commit the Bidder, in accordance with ITT Clause 20.2. - Business Registration Certificate. International bidders shall seek all applicable foreign investment registration requirements of Maldives prior to bid submission. For more information please visit : http://www.trade.gov.mv/ - GST Registration Certificate. International foreign companies who are already engaged in any work in Maldives, or have re-registered their entity in the Maldives, or have incorporated a company in Maldives shall be eligible to pay local taxes under tax regulations of the Maldives. For more information please visit: https://www.mira.gov.mv/ - National Contractors Registry Certificate. All contractors should adhere to National Contractors Registry and all relevant guidelines and shall sought any permits, if required, applicable at the time of submission of the tender. For more information please visit: http://www.planning.gov.mv/ |
| ITT 13.1 | Alternative Tenders shall not be permitted. |
| ITT 13.2 | Alternative times for completion shall not be permitted. |
| ITT 13.4 | Alternative technical solutions shall be permitted for the following parts of the Works: N/A |
| ITT 14.6 | The prices quoted by the Tenderer shall not be subject to adjustment during the performance of the Contract. |
| ITT 14.7 | All bids shall be quoted inclusive of all applicable local taxes and GST. Where bid prices quoted is not indicated or mentioned as “exclusive” of GST, the Purchaser have the right to take the quoted bid price deemed to be inclusive of GST. |
| ITT 15.1 | - The prices shall be quoted by the Tenderer in: Maldivian Rufiya (MVR) |
| ITT 18.1 | The Bids shall be valid for 120 days from the date of bid submission. |
| ITT 19.1 | The Tenderer shall furnish a Bid security in the amount of : MVR 17,500.00 The validity of the bid security shall be: 28 days beyond the validity of the Tender. |
| ITT 19.3(d) | None |
| ITT 20.1 | In addition to the Original of the Tender, the number of copies required is: 1 authentic hard copy (stamped) , 1 authentic soft copy (stamped & scanned) |
| ITT 20.2 | The written confirmation of authorization to sign on behalf of the Tenderer shall indicate: - The name and description of the documentation required to demonstrate the authority of the signatory to sign the Tender such as a Power of Attorney; and - In the case of Tenders submitted by an existing or intended JV an undertaking signed by all parties (i) stating that all parties shall be jointly and severally liable, if so required in accordance with ITB 4.1(a), and (ii) nominating a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the tendering process and, in the event the JV is awarded the Contract, during contract execution.”] |
| D. Submission and Opening of Tenders |  |
| ITT 21.1 | Tenderers shall not have the option of submitting their Tenders electronically. |
| ITT 22.1 | For Tender submission purposes only, the Employer’s address is: Mr. Ahmed Mujuthaba, Chief Procurement Executive, National Tender Ministry of Finance Ameenee Magu, Male’, 20379 Republic of Maldives Tel: 1617 E-mail: ahmed.jinah@finance.gov.mv tender@finance.gov.mv The deadline for Tender submission is: Date: 7th November 2019 Time: 1100hrs |
| ITT 25.1 | The Tender opening shall take place at: Street Address: National Tender Ministry of Finance Ameenee Magu, Male’, 20379 Republic of Maldives Date: 7th November 2019 Time: 1100hrs |
| E. Evaluation and Comparison of Tenders |  |
| ITT 32.1 | The single currency for price conversions is: United States Dollar The source of official selling rates is: Maldives Monetary Authority The date of exchange rates is: 7 days prior to bid submission date. |
| ITT 42.1 | The Adjudicator proposed by the Employer is: Ministry of Finance |

Section III - Evaluation and Qualification Criteria

This section contains all the criteria that the Employer shall use to evaluate Tenders, and qualify Tenderers if the tendering was not preceded by a prequalification exercise and post qualification is applied. In accordance with ITB 34 and ITB 36, no other methods, criteria and factors shall be used. The Tenderer shall provide all the information requested in the forms included in Section IV (Tendering Forms).

## Table of Criteria

1.1	Adequacy of Technical Proposal	29

1.2	Multiple Contracts	29

1.3	Completion Time	29

1.4	Technical Alternatives	29

2.	Qualification	30

2.1 	Eligibility	30

2.3 	Financial Situation	31

2.4 	Experience	33

2.5	Personnel	34

2.6	Equipment	34

# Evaluation and Qualification Criteria

# 1.	Evaluation

In addition to the criteria listed in ITB 34.1 (a) – (e) the following criteria shall apply;

- Tax clearance of the lowest evaluated bidder shall be checked prior to contract award.

- NCR grading and Tendering Limit of all the bidders shall be assessed. All bidders should adhere to NCR Grading and tendering limits and no bidder shall bid above the Tendering Limit specified in the corresponding NCR Grade and in case of such, the bid shall be disqualified.

- Lowest Evaluated bidder shall be assessed for any past work commitments with in the last 2 years with Government of Maldives which had been terminated due to poor performance. In addition, past work completed by the lowest evaluated bidder will be assessed by the concerned stakeholder for their overall performance.

- Employer’s requirement (issued with the bidding document) for the project must be met.

1.1	Adequacy of Technical Proposal

Evaluation of the Bidder's Technical Proposal will include an assessment of the Bidder's technical capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section V (Employer's Requirements).

Omission of information on non-significant equipment and personnel requirements described in Section V (Employer’s Requirements) shall not be a ground for bid rejection and such non-compliance will be subject to clarification during bid evaluation and rectification prior to contract award.

1.3	Completion Time

# An alternative Completion Time, if permitted under ITB 13.2, will be evaluated as follows:

# Not Applicable

1.4	Technical Alternatives

Technical alternatives, if permitted under ITB 13.4, will be evaluated as follows:

Not Applicable

2.	Qualification

| Factor | 2.1 Eligibility |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Tenderer |  |  |  |  |
|  |  | Single Entity | Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| 2.1.1 Nationality | Nationality in accordance with ITB 4.2. | Must meet requirement | Existing or intended JV must meet requirement | Must meet requirement | N/A | Form ELI –1.1 and 1.2, with attachments |
| 2.1.2 Conflict of Interest | No conflicts of interests as described in ITB 4.4. | Must meet requirement | Existing or intended JV must meet requirement | Must meet requirement | N/A | Letter of Tender |
| 2.1.3 Government Suspension | Not having been suspended from participation in public procurement by the Government as described in ITB 4.5. | Must meet requirement | Existing JV must meet requirement | Must meet requirement | N / A | Letter of Bid |
| 2.1.4 Government Owned Entity | Compliance with conditions of ITB 4.6 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Form ELI –1.1 and 1.2, with attachments |

| Factor | 2.2 Litigation History |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2.2.1 Pending Litigation | Bidder’s financial position and prospective long-term profitability sound according to criteria established in 2.3.1 below and assuming that all pending litigation will be resolved against the Bidder | Must meet requirement | N/A | Must meet requirement | N/A | Form CON – 1 |
| 2.2.2 Litigation History | No consistent history of court/arbitral award decisions against the Bidder during the past 5 years preceding the deadline for bid submission. | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Form CON – 1 |

| Factor | 2.2 Financial Situation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Tenderer |  |  |  |  |
|  |  | Single Entity | Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| 2.3.1 Historical Financial Performance | Submission of audited balance sheets or if not required by the law of the Tenderer’s country, other financial statements acceptable to the Employer, for the last three (3) years to demonstrate the current soundness of the Tenderers financial position and its prospective long term profitability. | Must meet requirement | N/A | Must meet requirement | N/A | Form FIN – 2.1 with attachments |
| 2.3.2. Average Annual Turnover | Minimum average annual turnover of MVR 1,750,000.00 million, within the last three (3) years. | Must meet requirement | Must meet requirement | Must meet five percent (5 %) of the requirement | Must meet Twenty percent (20%) of the requirement | Form FIN –2.2 |
| 2.3.3. Financial Resources | The Tenderer must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet: (i) the following cash-flow requirement: MVR 525,000.00 | Must meet requirement | Must meet requirement | Must meet Five percent (5 %) of the requirement | Must meet Twenty percent (20%) of the requirement | Form FIN –2.3 |

| Factor | 2.3 Experience |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Tenderer |  |  |  |  |
|  |  | Single Entity | Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| 2.4.1 General Experience | Experience under contracts in the role of contractor, subcontractor, or management contractor for at least the last 3 years prior to the applications submission deadline. | Must meet requirement | N/A | Must meet requirement | N/A | Form EXP-2.4 |
| 2.4.2 Specific Experience | Participation as contractor, management contractor, or subcontractor, in at least 2 contracts within the last 5 years , each with a value of at least MVR 1,225,000.00 that have been successfully and substantially completed and that are similar to the proposed Works. The similarity shall be based on the physical size, complexity, methods/technology or other characteristics as described in Section VI, Employer’s Requirements. | Must meet requirement | Must meet requirements for all characteristics | N / A | Must meet requirement for one characteristic | Form EXP 2.4.2 |

2.4	Personnel

The Tenderer must demonstrate that it will have the personnel for the key positions that meet the following requirements:

|  | Position | No.s | Total Work Experience (years) | In Similar Works Experience (years) |
| --- | --- | --- | --- | --- |
| 1 | Project Manager | 1 | 5 | 3 |
| 2 | Project Engineer | 1 | 5 | 3 |

The Tenderer shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section IV, Tendering Forms.

2.5	Equipment

The Tenderer must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

| No. | Equipment Type and Characteristics |  |
| --- | --- | --- |

The Tenderer shall provide further details of proposed items of equipment using the relevant Form in Section IV.

Section IV - Tendering Forms

Table of Forms

Letter of Tender	36

Price Schedules	41

Bill of Quantities or Schedules of Activity	41

Form of Tender Security (Bank Guarantee)	42

Technical Proposal	42

Technical Proposal Forms	42

Forms for Personnel	42

Forms for Equipment	42

Tenderer’s Qualifications	42

Tenderer Information Sheet	42

Party to Joint Venture Information Sheet	42

Current Contract Commitments/Works in Progress	42

Financial Situation	42

Average Annual Turnover	42

Financial Resources	42

General Experience	42

Specific Experience	42

Letter of Tender

NOTE TO TENDERERS: Letter of Tender shall be in the Company Letter head. Note: All italicized text is for use in preparing these form and shall be deleted from the final products.

Date: _______________

Tenderer’s Reference No.: _______________	Procurement Reference No.: _______________

To: Ahmed Mujuthaba,

Director General,

National Tender

Ministry of Finance

Male’, Republic of Maldives

We, the undersigned, declare that:

- We have examined and have no reservations to the Tendering Documents, including Addenda issued in accordance with Instructions to Tenderers (ITT) Clause 8;

- We offer to execute in conformity with the Tendering Documents of the following Works:

{TES/2019/W-133 – Construction of  Ha.Dhidhdhoo Jetty, Maldives };

- The total lump-sum fixed price of our Tender, excluding Goods and Services Tax (GST) in item (d) and excluding any discounts offered in item (e) below is: …………………………………………………………….;[amount in numbers & words]

- The amount for Goods and Services Tax (GST) is …………………………………………. [amount in numbers & words]

- The discounts offered and the methodology for their application are: ………………………………;

- We undertake, if our Bid is accepted, to commence the Works as soon as is reasonably possible and to complete the whole of the Works comprised in the Contract within …………………….. (days).

- Our Tender shall be valid for a period of ________ {insert validity period as specified in ITB 18.1.] days from the date fixed for the Tender submission deadline in accordance with the Tendering Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If price adjustment provisions apply, the Table(s) of Adjustment Data shall be considered part of this Tender;

- If our Tender is accepted, we commit to obtain a performance security in accordance with the Tendering Document;

- Our firm, including any subcontractors or suppliers for any part of the Contract, have nationalities from eligible countries;

- We, including any subcontractors or suppliers for any part of the contract, are eligible in accordance with ITT Sub-Clause 4.3 and do not have any conflict of interest in accordance with ITB 4.4;

- We are not participating, as a Tenderer or as a subcontractor, in more than one Tender in this tendering process in accordance with ITB 4.4, other than alternative offers submitted in accordance with ITB 13;

- Our firm, its affiliates or subsidiaries, including any Subcontractors or Suppliers for any part of the contract, has not been suspended from public procurement by the Government, under the laws or official regulations of the Republic of Maldives;

- We are not a government owned entity/We are a government owned entity but meet the requirements of ITB 4.6;

- We have paid, or will pay the following commissions, gratuities, or fees with respect to the tendering process or execution of the Contract:

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |

- We understand that this Tender, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed;

- We understand that you are not bound to accept the lowest evaluated Tender or any other Tender that you may receive; and

- If awarded the contract, the person named below shall act as Contractor’s Representative: …………………………………………………………………….

| Signed: | ……………………........…{insert signature of authorised person} |
| --- | --- |
| Name: | ………………………..…{insert complete name of person signing} |
| In the capacity of: | …………….……….........{insert legal capacity of person signing} |
| Duly authorized to sign the tender for and on behalf of | ……………..…………….{insert complete name of Tenderer and Company stamp} |
| Date: | ……... day of ……….…………….. …………. {DD/MM/YY} |

Price Schedules

Bill of Quantities

[Note: Bidders shall submit fully priced Bills of Quantities for the projects mentioned below].

Each page of the Bills of Quantities or the Schedule of Activities should be signed by a person with the proper authority to sign documents for the Bidder].

The Bill of Quantities ( BoQ) attached with this Tender Document are;

| Bill of Quantities |  |
| --- | --- |
| Project Number | Project Name |
| TES/2019/W -133 | Construction of Ha.Dhidhdhoo Jetty |

Work Schedule

Note: Bidders shall submit work schedule for each project separately. Project name, Project number, client and duration should be clearly indicated.

Each page of the Work Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

The work schedule should be submitted for the following projects;

| Work Schedule |  |
| --- | --- |
| Project Number | Project Name |
| TES/2019/W -133 | Construction of Ha.Dhidhdhoo Jetty |

Form of Tender Security (Bank Guarantee)

The Issuing Bank shall fill in this Bank Guarantee Form in accordance with the instructions indicated.

………………………………… {Bank’s Name, and Address of Issuing Branch or Office}

Beneficiary:  					 {Name and Address of Employer}

Date:

TENDER GUARANTEE No.: __________________________

We have been informed that __________________________ {name of the Tenderer} (hereinafter called "the Tenderer") has submitted to you its Tender dated ___________ (hereinafter called "the Tender") for the execution of ________________ {name of contract} under Invitation for Tenders No. ___________  (“the IFB”).

Furthermore, we understand that, according to your conditions, Tenders must be supported by a Tender guarantee.

At the request of the Tenderer, we ____________________ {name of Bank} hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________ [amount in figures] (____________) [amount in words] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Tenderer is in breach of its obligation(s) under the Tender conditions, because the Tenderer:

(a) 	has withdrawn its Tender during the period of Tender validity specified by the Tenderer in the Form of Tender; or

(b) 	having been notified of the acceptance of its Tender by the Employer during the period of Tender validity, (i) fails or refuses to execute the Contract Form, if required, or (ii) fails or refuses to furnish the performance security, in accordance with the ITB.

This guarantee will expire: (a) if the Tenderer is the successful Tenderer, upon our receipt of copies of the contract signed by the Tenderer and the performance security issued to you upon the instruction of the Tenderer; and (b) if the Tenderer is not the successful Tenderer, upon the earlier of (i) our receipt of a copy your notification to the Tenderer of the name of the successful Tenderer; or (ii) {insert date}twenty-eight days after the expiration of the Tenderer’s Tender.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758

[signature(s]

Technical Proposal

Technical Proposal Forms

Personnel

Equipment

Site Organization

Method Statement

Mobilization Schedule

Construction Schedule

Others

Forms for Personnel

Form PER – 1: Proposed Personnel

Tenderers should provide the names of suitably qualified personnel to meet the specified requirements for each of the positions listed in Section III (Evaluation and Qualification Criteria). The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position |
| --- | --- |
|  | Name |
| 2. | Title of position |
|  | Name |
| 3. | Title of position |
|  | Name |
| 4. | Title of position |
|  | Name |
| 5. | Title of position |
|  | Name |
| 6. | Title of position |
|  | Name |
| 7. | Title of position |
|  | Name |

Form PER – 2:  Resume of Proposed Personnel

The Tenderer shall provide all the information requested below. Fields with asterix (*) shall be used for evaluation.

| Position* |  |  |
| --- | --- | --- |
| Personnel information | Name * | Date of birth |
|  | Professional qualifications: |  |
| Present employment | Name of Employer |  |
|  | Address of Employer |  |
|  | Telephone | Contact (manager/personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present Employer |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| From* | To* | Company, Project , Position, and Relevant Technical and Management Experience* |
| --- | --- | --- |

Forms for Equipment

The Tenderer shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III (Evaluation and Qualification Criteria). A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Tenderer. The Tenderer shall provide all the information requested below, to the extent possible. Fields with asterisk (*) shall be used for evaluation.

| Type of Equipment* |  |  |
| --- | --- | --- |
| Equipment Information | Name of manufacturer | Model and power rating |
|  | Capacity* | Year of manufacture* |
| Current Status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

The following information shall be provided only for equipment not owned by the Tenderer.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Tenderer’s Qualifications

To establish its qualifications to perform the contract in accordance with Section III (Evaluation and Qualification Criteria) the Tenderer shall provide the information requested in the corresponding Information Sheets included hereunder

Form ELI 1.1

Tenderer Information Sheet

[The Tenderer shall fill in this Form in accordance with the instructions indicated below. No alterations to its format shall be permitted and no substitutions shall be accepted.]

Date: [insert date (as day, month and year) of Tender Submission]

Tenderer’s Reference No: [Insert reference no]

Procurement Reference No.: [insert reference number]

Page _____ of_ ______ pages

| 1. Tenderer’s Legal Name | {insert Tenderer’s legal name} |
| --- | --- |
| 2. In case of JV, legal name of each party: | {insert legal name of each party in JV} |
| 3. Tenderer’s actual or intended Country of Registration: | {insert actual or intended Country of Registration} |
| 4. Tenderer’s Year of Registration: | {insert Tenderer’s year of registration} |
| 5. Tenderer’s Legal Address in Country of Registration: | {insert Tenderer’s legal address in country of registration} |
| 6. Tenderer’s Authorized Representative Information |  |
| Name: | {insert Authorized Representative’s name} |
| Address: | {insert Authorized Representative’s Address} |
| Telephone/Fax numbers: | {insert Authorized Representative’s tel/fax numbers} |
| Email Address: | {insert Authorized Representative’s email address} |
| 7. Attached are copies of original documents of: {check the box(es) of the attached original documents} |  |
|  Articles of Incorporation or Registration of firm named in 1, above, in accordance with ITB Sub-Clauses 4.1 and 4.2. - In case of JV, letter of intent to form JV including a draft agreement, or JV agreement, in accordance with ITB Sub-Clauses 4.1  In case of government owned entity from the Employer’s country, documents establishing legal and financial autonomy and compliance with the principles of commercial law, in accordance with ITB Sub-Clause 4.6. |  |

Form ELI 1.2

Party to Joint Venture Information Sheet

[The Tenderer shall fill in this Form in accordance with the instructions indicated below].

Date: [insert date (as day, month and year) of Tender Submission]

Tenderer’s Reference No: [Insert reference no]

Procurement Reference No.: [insert reference]

Page ___ of ___ pages

| 1. Tenderer’s Legal Name: | {insert Tenderer’s legal name} |
| --- | --- |
| 2. JV’s Party legal name: | {insert JV’s Party legal name} |
| 3. JV’s Party Country of Registration: | {insert JV’s Party country of registration} |
| 4. JV’s Party Year of Registration: | {insert JV’s Part year of registration} |
| 5. JV’s Party Legal Address in Country of Registration: | {insert JV’s Party legal address in country of registration} |
| 6. JV’s Party Authorized Representative Information |  |
| Name: | {insert name of JV’s Party authorized representative} |
| Address: | {insert address of JV’s Party authorized representative} |
| Telephone/Fax numbers: | {insert telephone/fax numbers of JV’s Party authorized representative} |
| Email Address: | {insert email address of JV’s Party authorized representative} |
| 7. Attached are copies of original documents of: {check the box(es) of the attached original documents} |  |
|  Articles of Incorporation or Registration of firm named in 1, above, in accordance with ITB Sub-Clauses 4.1 and 4.2.  In case of government owned entity from the Purchaser’s country, documents establishing legal and financial autonomy and compliance with the principles of commercial law, in accordance with ITB Sub-Clause 4.6. |  |

Form CCC

Current Contract Commitments/Works in Progress

Tenderers and each partner to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

| No | Name of contract | Employer, contact address/tel/fax | Value of outstanding work (current MVR equiv) | Estimated completion date | Average monthly invoicing over last six months (MVR/month) |
| --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |
| 2. |  |  |  |  |  |
| 3. |  |  |  |  |  |
| 4. |  |  |  |  |  |
| 5. |  |  |  |  |  |

Form FIN – 2.1

Financial Situation

Historical Financial Performance

To be completed by the Tenderer and, if JV, by each partner

Tenderer’s Legal Name: _______________________     	Date:  _____________________

JV Partner Legal Name: _______________________ 	Tendering No.:  __________________

Page _______ of _______ pages

| Financial information (US$ equiv) | Historic information for previous ____ years (MVR equiv in ,000s) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2018 | 2017 | 2016 | Avg. | Avg. Ratio |
| Information from Balance Sheet |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |

	Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:

- Must reflect the financial situation of the Tenderer or partner to a JV, and not sister or parent companies

- Historic financial statements must be audited by a certified accountant

- Historic financial statements must be complete, including all notes to the financial statements

- Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

Form FIN – 2.2

Average Annual Turnover

Tenderer’s Legal Name:  ___________________________     	Date:  _____________________

JV Partner Legal Name: ____________________________ 	Tendering No.:  ______________

Page _______ of _______ pages

| Annual turnover data |  |  |
| --- | --- | --- |
| Year | Amount and Currency | MVR equivalent |
| 2018 |  |  |
| 2017 |  |  |
| 2016 |  |  |
| *Average Annual Turnover |  |  |

*Average annual turnover calculated as total certified payments received for work in progress or completed over the number of years specified in Section III (Evaluation and Qualification Criteria), Sub-Factor 2.3.2, divided by that same number of years.

Form FIN2.3

Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section III (Evaluation and Qualification Criteria)

| Source of financing | Amount (MVR equivalent) |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

**Credit reference letters should be attached with the form.

Form EXP 2.4

General Experience

Tenderer’s Legal Name:  ___________________     	Date:  _____________________

JV Partner Legal Name:  _________________________	Tendering No.:  ________________

Page _______ of _______ pages

| Starting Month / Year | Ending Month / Year | Years* | Contract Identification | Role of Tenderer |
| --- | --- | --- | --- | --- |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Tenderer: Name of Employer: Address: |  |

*List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year

Form EXP – 2.4.2

Specific Experience

Tenderer’s Legal Name:  _________________________     	Date:  __________________

JV Partner Legal Name: _________________________  Procurement Ref No:  ___________

Page _______ of _______ pages

| Similar Contract Number: …….. [insert specific number] of ……. [insert total number of contracts required]. | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification Number |  |  |  |
| Contract Name |  |  |  |
| Award date |  |  |  |
| Completion date |  |  |  |
| Role in Contract |  Contractor |  Management Contractor |  Subcontractor |
| Total contract amount |  |  | MVR |
| If partner in a JV or subcontractor, specify participation of total contract amount | % |  | MVR |
| Description of the similarity [in accordance with Sub-Factor 2.4.2a) of Section III (Evaluation and Qualification Criteria)] in: |  |  |  |
| Physical size |  |  |  |
| Complexity |  |  |  |
| Methods/Technology |  |  |  |
| Employer’s Name: |  |  |  |
| Address: |  |  |  |
| Telephone/fax number: |  |  |  |
| E-mail: |  |  |  |

**Reference Letters should be attached with the forms.

Section V - Eligible Countries

Eligibility for the Provision of Works in Public Procurement

1.	The Government of the Maldives permits firms and individuals from all countries to offer works for publically funded contracts.

2.	As an exception, firms of a Country or goods manufactured in a Country may be excluded if:

i)	as a matter of law or official regulation, the Republic of Maldives prohibits commercial relations with that Country, or

ii)	by an Act of Compliance with a Decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Republic of Maldives prohibits any import of goods from that Country or any payments to persons or entities in that Country.

2.	For the information of Tenderers, at the present time firms, goods, works and services from the following countries are excluded from this tendering:

No countries at excluded from tendering.

PART 2 – Employer’s Requirements

Section VI - Employer’s Requirements

Table of Contents

Scope of Works	42

Specifications	42

Drawings	42

Bill of Quantities or Activity Schedule	42

Supplementary Information	42

Scope of Works

Brief Description of Works

Construction of an Official Jetty at Ha.Dhidhdhoo

Location(s) of Works

Ha.Dhidhdhoo

[Additional information that may be included is:

- Site location

- Climate and weather information

- Site investigation studies and reports

- Topographical data

- Access details

- Details of other ongoing or future works to be carried out by other contractors during the Contract period

- Information regarding disposal, borrow and quarry areas including royalty payments as applicable

- any other pertinent information regarding the site and the works

A description of approximately 1-2 pages would be appropriate for most contracts].

Specifications

# Technical Specifications

# CONCRETE WORKS

# 5.1 Concrete formwork

1 : General

1.1 Description

This section covers formwork for all concrete.

All forms shall be accurately and properly placed and finished, so that concrete may be placed as indicated on the Approved Design Drawings, the Approved Shop Drawings and as specified. The forms shall produce a smooth concrete finish, free from offsets, or irregularities.

1.1.1 Coordination.

Work performed, and materials used, in conjunction with formwork, for concrete, shall be coordinated with work under the Concrete Works Section.

1.2 Applicable Codes and Standards:

The Codes and Standards, generally applicable to the work under this section, are listed. Codes and Standards current at the time of bid shall be used. In case of contradictions between different standards, the BS shall prevail.

1.2.1 DIN 	-	Deutches Institute fur Normung

DIN 1045

1.2.2 BSI 	-	British Standard Institute

1.2.3 ASTM 	-	American society for Testing and Materials

2 : Products

2.1 Materials:

2.1.1 Material List.

Material used shall be:

- Forms

- Steel 	     -	Straight, uniform and free of surface defects.

- Plywood 	     -	Product Standard PS 1, Waterproof, resin-bonded.

- Lumber 	     - 	Straight, uniform width and thickness, and free from knots,

offsets, holes, dents, and other surface defects.

- Chamfer Strips -	Clear lumber, surface against concrete planed.

- Form Coating   -	Single  component, pigmented copolymer resin type, applied

in accordance with the manufacturer’s recommendations.

2.2 Design Criteria:

Forms, for cast in place or precast concrete, shall be designed to produce hardened concrete, having the shape, lines, and dimensions indicated on the approved Drawings. For all structures, forms for surfaces shall be prefabricated plywood panel forms, steel, or forms that are lined with plywood of fibreboard. Forms for exposed surfaces shall be laid out in a regular and uniform pattern, and all joints aligned. The forms shall produce finished surface that are free from offsets, ridges, waves, and concave, or convex areas, the maximum deviation from a true plane shall not exceed 3mm in 2m.

Formwork shall be constructed to attain the required surface texture of the structures and to be such accuracy, strength and rigidity as to carry the weight and pressure from the concrete to be placed without any deformation, and remaining grout tight during the placing and setting of concrete. When required by engineer, joints between shutter facing boards shall be sealed with foam rubber, sealing strips or other approved material.

Formwork shall be sufficiently rigid so as to prevent any grout loss during concreting and shall not distort due to environmental effects and concreting operations so that member dimensions, shape, required finish and texture are within the tolerances specified Walers, studs, internal ties, and other form supports shall be sized and spaced so that acceptable working stresses are not exceeded. Plywood or lined forms will not be required for surface of concrete not required to fair faced.

Wherever the top of a wall will be exposed to weathering, the forms on at least one side shall not extend above the top of the wall, and shall be brought to true line and grade. At other locations, forms for concrete, which is to be finished to a specified elevation, slope, or contour, shall be brought to a true line grade; otherwise, or a wooden guide strip shall be provided at the proper location on the forms so that the top surface can be finished with a screed or template. At horizontal construction joints in walls, the forms on one side shall not extend more than 0.6 meters above the joint.

Temporary openings shall bee provided at the bottom of wall forms and at other points, where necessary, to facilitate cleaning and inspection.

Face of framework shall be free of projecting nails, adhering grout and other imperfections or defects which would prevent the specified surface finish from being attained. Before each concreting operation is commenced, form work shall be carefully examined and cleaned out and the concrete contact faces of the works shall be treated with an approved release agent comes in contact with reinforcement.

Forms for all exposed surfaces shall be constructed of plywood, metal or glass reinforced plastics at the option of the Contractor.

No concreting shall commence until the Engineer has inspected and approved the erected formwork. Shooting height of concrete shall not be greater than 2 meters. The formwork shall be designed accordingly.

2.2.1 Form Ties.

Forms ties shall be of the removable or permanently embedded body type, and shall have sufficient strength and rigidity to support and maintain the form in proper position and alignment without the use of auxiliary spreaders. Cones, for the permanent embedded type shall be provided on the outer ends of each tie and the permanently embedded portion shall be at least 25mm back from adjacent outer concrete faces shall not be nearer the surface than the specified thickness of cover to the reinforcement. Form ties for indirect tutch with water walls, shall be provided with waterseal washers located on the permanently embedded portions of form ties, and approximately at the centre of the wall. Permanently embedded portions of form ties, which are not provided with threaded ends, shall be constructed so that the removable ends are readily broken off without damage to the concrete. The type of form ties used shall be acceptable to the Engineer.

Form ties in exposed surface shall be uniformly spaced and aligned in horizontal and vertical rows.

2.2.2 Edges and Corners.

Chamfer strips shall be placed in forms to bevel all salient edges and corners, for all vertical and horizontal corners, unless specifically shown otherwise on the Approved Drawings. Unless otherwise noted, bevels shall be 25mm wide.

2.3 Formed Surfaces – Class of Finish:

Finishes to formed concrete surfaces shall be classified as F1, F2, or F3. Where the class of finish is not specified, the concrete shall be finished to class F2. All reinforced concrete shall have a F AIR-F ACED finishing. Concrete surfaces for the various classes of formed finishes specified, shall comply with the tolerances shown in Table 1.

TABLE 1: MAXIMUM TOLERANCE (mm)

Class of 			   Abrupt	Gradual

Finish	        Line and Level	  Irregularity 	Irregularity 	Dimension

F1	          -15 to +15	        5		      5 		+15 to -5	      F2	          -5 to +5	      	        5		      5 		+15 to -5

F3	          -5 to +5	    	        0		      5 		- 5 to +5

In Table 1, “Line and level” and “Dimension” shall mean the lines, levels, and cross- sectional dimensions indicated on the drawings.

Surface irregularities shall be classified as “abrupt” or “gradual”. Abrupt irregularities shall be tested by direct measurement. They include, but are not limited to, offsets and fins caused by displaced or misplaced formwork, and loose knots and other defects in formwork materials. Gradual irregularities shall be tested by means of a 1.5 meter length straight template, for plane surfaces, or its suitable equivalent for curved surface.

2.3.1 Class F3.

Formwork for class F3 finish shall be lined with panels of non-staining material, with a smooth unblemished surface, such as sand plywood, or hard compressed fibre-board. The panels shall be as large as possible, and shall e arranged in a uniform acceptable pattern, and fixed to the back of formwork by oval nails. Unfaced wrought boarding or standard steel panels shall not be permitted.

2.3.2 Class F2.

Formwork for class F2 finish shall be faced with wrought tongue and groove boards, plywood or metal panels arranged in a uniform acceptable pattern, free from defects likely to detract from the appearance of the surface.

2.3.3 Class F1.

Formwork for class F1 finish shall be constructed of timber, sheet metal, or any suitable material which will prevent loss of grout when the concrete is vibrated. Surfaces, subsequently to be rendered, plastered, or tiled shall be adequately scabbled, or roughened, as soon as the formwork is removed to reduce the irregularities to no more than half the thickness of such rendering, plastering, or bedding for tiles, and to provide a satisfactory key.

3 : Products

3.1 Inspection:

3.1.1 Preplacement Inspection.

Prior to rigidly securing all forms, reinforcement, anchor bolts, and embedded parts in their proper position, all dirt, mud, water, and debris shall be removed from the space to be occupied by concrete and all surfaces encrusted with dried concrete from previous placement operations shall be cleaned.

3.2 Installation:

3.2.1 Execution.

Forms shall be constructed to ensure that the finished concrete members will have true surfaces free of offset, waviness, or bulges, and will conform to the indicated shapes, dimensions, lines, elevations, and positions, within the specified tolerances. For the pre-cast units the Contractor shall prepare and submit to the Engineer for approval.

# 5.2 Concrete reinforcement

1 : General

1.1 Description

This section covers steel reinforcement, for all concrete.

The contractor shall provide all bars, bar supports, ties, spacers, bolsters, inserts, screeds, and other accessories required to maintain fabricated reinforcement in its proper position, and permit proper placement of concrete.

1.1.1 Coordination.

All reinforcing material and work shall be coordinated with related work specified in the Cast-in-Place Concrete Section.

A. Work Specified Elsewhere:

Other items of work that relate to and are referenced in this section include, but are not limited to the requirement shown.

1.2 Applicable Codes and Standards:

The Codes and Standards, generally applicable to the work under this section, are listed. Codes and Standards current at the time of bid shall be used. In case of contradictions between different standards, the British Code Standard shall prevail.

1.2.1 DIN 	 -	Deutsches Institut fur Normung

DIN 1045

1.2.2 BSI 	 -	British Standard Institute

1.2.3 ASTM 	 -	American society for Testing and Materials

1.2.4 AASHTO-	American Association of State Highway and

Transportation Officials.

1.2.5 ACI  	 -	American Concrete Institute.

Generally all clauses mentioned in BSI 8007, BSI 8110 shall be thoroughly followed for all types of joints as well as ACI, ASTM, AASHTO & DIN Requirements.

1.3 Product handling:

1.3.1 Protection:

Material shall be delivered, stored, and handled in accordance with the General Equipment and Material Stipulations.

Rubber and plastic materials shall be stored in a cool place and shall not be exposed to direct sunlight.

2 : Products

Unless otherwise specified in other sections of these specifications, the following products shall be utilized:-

2.1.1 Material List.

- Expansion Joint Filler.

- Preformed sponge rubber.

2.2 Performance and Design Requirements:

2.2.1 Construction Joints:

Construction joints, shall be made at locations indicated on the Approved Design Drawings and Shop Drawings, or as specified or directed by the engineer.

Construction joints, shall not be made at other locations, without the concurrence of the Engineer. All joints shall be provided in compliance with the structural Engineer Practice and shall comply with BS 8007 and 8110.

- Location:

Construction joints shall be located as follows:

- In beam and Girders:

At the middle of the span, unless a beam intersects a girder at that point, in which case the joint in girder shall be offset a distance equal to twice the width of the beam. Provisions satisfactory to the Engineer shall be made for transfer of shear and other forces through the construction joint.

- Watertight Joints:

2.2.2 Contraction Joints:

Contraction joints shall be provided at the locations indicated on the Approved Drawings. Also, they shall comply with BS 8007 and 8110 requirements and according to Engineering Structural calculations and Practice to the satisfaction of Engineer. Accessible edges of each contraction joint shall be sealed as specified in the Sealants and Caulking Section.

2.2.3 Expansion Joints:

Expansion joints shall be provided at the locations indicated on the Approved Drawings. Also, they shall comply with BS 8007 and 8110 requirements and according to Engineering Structural calculations and Practice to the satisfaction of the Engineer. Expansion joint filler shall be firmly bonded to the previously poured joint face with a suitable adhesive, and the new concrete shall be poured directly against the joint filler. Accessible edge of each expansion joint shall be sealed as specified in the Sealants and Caulking Section.

3 : Execution:

3.1 Installation:

3.1.1 Placement sequence:

Construction joints not indicated on the Design Drawings shall be spaced at intervals for reducing, (to a minimum), the effect of shrinkage in production cracks as recommended by the cement manufacturer, and acceptable to the Engineer.

No two abutting sections shall be placed within a period of 72 hours, unless otherwise authorized by the Engineer. Works shall comply with BS 807 and BS 8110.

4 : Measurement:

Expansion joint filler shall be measured per linear meter, complete in place, and will be paid for at the contract unit price per linear meter working drawings with method statement for the executing of these units. Form surfaces that will be in contact with concrete shall be thoroughly cleaned before each use. No concreting shall commence until the Engineer has inspected and approved the erected formed.

3.2.2 Form Removal:

Forms shall not be removed or disturbed until the concrete has attained sufficient strength to safely support all dead loads, live loads and to be lifted, transported installed. Forms for beam and girder sides, columns, and similar vertical structural members, may be removed after 48 hours, provided concrete is sufficiently hard, not to be injured thereby.

Care shall be taken to avoid spoiling the concrete surface or damaging concrete edges. Wood forms shall be completely removed.

3.2.2 –B Tie Rods.

Toe rods, to be entirely removed from the wall, shall be loosened 24 hours after concrete is placed, and form ties, except for a sufficient number to hold forms in place, may be removed at that time. Ties wholly withdraw from the wall, shall be pulled toward the face that will be concealed from view, in the permanent work.

# 5.3 Concrete Works

1 : General

1.1 Description

This section covers all concrete works, which shall be completely provided by the Contractor, including labour materials, proportioning, batching, mixing, delivering, testing, receiving, placing, compacting, finishing, curing, and other appurtenant work.

The Concrete shall be proportioned and mixed as specified herein.

All concrete shall be accurately formed and properly placed and finished as indicated on the Drawings, and as specified herein.

The contractor shall inform the Engineer at least 24 hours in advance of the times and places at which he intends to place concrete, for inspection and approval, and shall present and approve the works by Concrete Cast Permits as per the requirements of the Engineer.

1.1.1 Related Work

Other items of work that relate to and are referenced to work specified in this section are included in the following sections:

Concrete Formwork

Concrete Reinforcement

Concrete Accessories

1.2 Applicable Codes and Standards:

The Codes and Standards, generally applicable to the work under this section, are listed. Codes and Standards current at the time of bid shall be used. In case of contradictions between different standards, British Code Standard shall prevail.

1.2.1 DIN 	 -	Deutsches Institut fur Normung

DIN 1045

1.2.2 BSI 	 -	British Standard Institute

1.2.3 ASTM 	 -	American society for Testing and Materials

1.2.4 AASHTO-	American Association of State Highway and

Transportation Officials.

1.2.5 ACI  	 -	American Concrete Institute.

1.3 Quality Assurance:

1.3.1 Tolerances:

Tolerances formed surfaces shall be as specified in BSI, ASTM & ACI code.

1.4 Submittals:

1.4.1 Material Report:

At least 31 days prior to start of concrete delivery, the following shall be submitted by the contractor to the Engineer for review.

Submittals should be as specified below.

    - Recommended suppliers and sources of all ingredients for making concrete, including cement, water, fine (sand) and coarse aggregates, and additives. (Item 1 Schedule 2).

    - Recommended suppliers and product data of the following:

      - Materials for curing concrete

      - Joint sealants

      - Joint filler

      - Bonding compound

      - Non-shrink grout

      - Reinforcement supports

    - A quality inspection plan to ensure continuing quality control of ingredients by periodic sampling, testing, and reporting to the Engineer on the quality of materials being supplied. (Item 2 Schedule 2).

    - All design mixes, using the “Standard mix Design Presentation”, Schedule 3, for each class of concrete, indicating that the concrete ingredients and proportions will result in a concrete mix meeting requirements specified (Item 3 Schedule 2).

    - The proposed program, methods, and details of plant and equipment to be used for batching and mixing of concrete. (Item 5 Schedule 2).

The Contractor shall submit the mix design as a report with his recommendation to obtain Engineer’s acceptance prior to commencement of concreting work. This report shall compare the proposed mix design with specified requirements and shall be summarized on a form similar to that shown in schedule 3.

1.4.2 Hot Weather concreting:

A report shall be submitted for proposed methods of compliance wit hot weather concreting requirements. (Item 6 Schedule 2).

1.4.3 Certificates:

Laboratory test reports and mill or manufacturer’s certificates attesting to conformance of ingredients with the specifications shall be submitted with each mix design. (Item 8 Schedule 2).

In case the source, brand or characteristics properties of the ingredients need to be varied during the term of the Contract, a revised laboratory mix report shall be submitted. (Item 1, 2, & 3 of Schedule 2).

1.4.4 Test Reports:

The Contractor shall keep (or obtain from his concrete supplier if any) copies of the results of all tests, which shall become part of the Contractors Weekly Quality Control report to the Engineer.

1.4.5 Summary of Submittals:

Schedule 2 is the complete list and frequency of reports which the Contractor shall prepare (or obtain from his concrete supplier if any) and submit.

1.4.6 Field Report:

Filed test reports shall be submitted as specified in this section, and in accordance with the Submittals and Quality Control Sections.

1.4.7 Reinforcements:

Certifications of tests on reinforcements shall be submitted for review as specified in the Concrete Reinforcement Section.

1.4.8 Layout of Joints and Lifts:

The Contractor shall submit to the Engineer for review as soon as practicable after the Issue of Order to Commence and not less than three weeks  before the commencement of concreting, detailed drawings showing his proposals for placing concrete on which the position of all construction joints shall be indicated. These shall take into account any specific requirements detailed on the Drawings and specified in the Concrete Accessories Section. No concreting shall be started until the Engineer has accepted the method of placing, the positions and form of the construction joints.

1.5 Delivery storage and handling:

Do not deliver concrete until vapor barriers, forms, reinforcement, embedded items, and chamfer strips are in place and ready for concrete placement.

Materials shall be handled and stored as follows:-

1.5.1 Aggregates:

Coral aggregates shall not be accepted to be used for producing concrete.

Aggregates shall be transported and stockpiled separately according to their sources and gradations. Aggregates shall be handled in manner which will prevent segregation and contamination with earth or foreign materials.

If aggregates show segregation, or if the different grades become mixed, the aggregates shall be re-screened before placing in the proportioning bins. Contaminated aggregates will not be used.

Muddy or oil-leaking equipment shall not be allowed to operate on the stockpiles. The moisture content in the aggregate shall be frequently checked and taken in consideration during mixing to fulfil the design mix water content.

1.5.2 Package Cement:

If the cement is delivered in bags it shall be stored in a dry and waterproof shed or building. The bags shall not be laid directly on ground, to prevent deterioration or contamination from any cause, a 20cm gap shall be maintained from ground by wooden platforms. Any bag that contains lumps of hardened cement it will not be used and will be removed from the Site.

Bags of cement which vary in weight by more than 3 percent shall not be accepted.

The bags shall be made of several layers (more than 4) to be strong enough for handling and storing. Any bag that found broken will be removed from stores and will not be used.

Cement shall be fresh when delivered to site and the consignments shall be used in the order of their delivery. The manufacturer name and brand of cement and weight shall be written on each bag.

1.5.3 Bulk Cement:

Bulk cement shall be stored separately from package cement. Bulk cement shall be stored in dry, weather-tight, well-ventilated bins with provisions for prevention of moisture absorption or the intrusion of foreign matter.

Facilities for sampling of cement shall be provided at the weighing hopper, or at the feed line immediately before entering the hopper.

Different brands of cement, or the same brand of cement from different sources, shall not be used without prior notification by the Contractor.

1.5.4 Admixtures:

Dry admixtures shall be stored in dry, weather-tight, well-ventilated housing or silos. Liquid admixtures shall be stored in clean, weather-tight tanks.

1.5.5 Temperature Limits:

TABLE 1.5.5: Temperature Under Limits at Point of Placement

Concrete Thickness 		Temperature of Concrete

(mm)			at time of Placement (in ºC)

Not greater than 400mm		38 ºC

Not greater than 750mm		32 ºC

Greater than 750mm			25 ºC

1.5.6 Temperature Control:

The concrete supplier shall provide procedures and facilities to control or reduce the temperature of all materials used in the concrete mix during “hot weather” as defined by air temperature over 32 ºC. Some hot weather concreting difficulties can be reduced by the use of concrete with up to 100 percent flaked ice lieu of mixing water. The Contractor shall place concrete with as much ice as deemed necessary by the Engineer to surmount hot weather concreting difficulties. Separate payment shall not be made for any ice.

The following may also have to be used to assist in lowering the temperature of concrete to meet the temperature limits at the point of placement.

- Exposed water tanks and piping, the roofs and vertical walls of cement storage silos or buildings, the tops and vertical walls of mixer discharge hoppers, and the sides of truck bodies carrying  batched aggregate or mixed concrete may be painted white or silver.

- Weighing hoppers, mixer drums, and tops of mixer discharge hoppers may be shaded from the ray of the sun when it is 30 ºC or more above the horizon, and may also be protected from drying winds by screens.

- Water for concrete may be chilled by the use of heat exchanger coils, or by the addition of flaked ice.

- Shade may be used to cover the aggregates and elevating conveyor of the batching plant from direct sun.

1.6 Quality Assurance:

1.6.1 Concrete Mixture Design:

At least 30 days prior to concrete placement, submit proportions for a concrete mixture for each strength and type of concrete. Submit a complete list of materials including type; brand; source and amount of cement, aggregate, fly ash, (or slag pozzolans), silica fume, ground slag, polypropylene fibers, anti-washout and other admixtures for underwater concreting, corrosion inhibitors; and applicable reference specifications. Submit additional data regarding concrete aggregates if the source of aggregate changes. Submittal shall clearly indicate where each mixture will be used when more than one mix design is submitted. An identical concrete mixture previously approved within the past 12 months by MCPI may be used without further approval within further approval, if copies of the previous approval and aggregate, fly ash, silica fume, and pozzolan test results are submitted. The approval of aggregate, fly ash, silica fume, and pozzolan tests results shall have been within 6 months of submittal date. Obtain acknowledgement of receipt prior to concrete placement. The mixture shall be prepared under the direction of a licensed/ registered civil engineer, who shall sign all reports and designs.

1.6.2 Drawings:

1.6.2.1 Reinforcing Steel:

Provide bending and cutting diagrams, assembly diagrams, splicing placement and laps of bars, shapes, dimensions, and concrete cover. Do not scale dimensions from structural drawings to determine lengths of reinforcing bars. Only complete drawings will be accepted.

1.6.2.2 Formwork:

Include design calculations indicating arrangement of forms, sizes and grade of supports (lumber), panels, and related components. Indicate placement schedule, construction, and location and method of forming control joints. Include locations of inserts, pipework, conduit, sleeves, and other embedded items.

1.6.3 Certificates:

1.6.3.1 Curing concrete elements:

Submit proposed materials and methods for curing concrete elements.

1.6.3.2 Form removal schedule:

Submit schedule for form removal indicating element and minimum length of time for form removal. Submit technical literature of forming material or liner, form release agent, form ties, and gasketing to prevent leakage at form and construction joints. Provide a full description of materials and methods to be used to patch form-tie holes.

1.6.3.3 Concrete Placement and Compaction:

- Submit technical literature for equipment and methods proposed for use in placing concrete. Include pumping or conveying equipment including type, size and material for pipe, valve characteristics, and the maximum length and height concrete be pumped. No adjustments shall be made to the mixture design to facilitate pumping and or placing.

- Submit technical literature for equipment and methods proposed for vibrating and compacting concrete. Submittal shall include technical literature describing the equipment including vibrator diameter, length, frequency, amplitude, centrifugal force, and manufacturer’s description of the radius of influence under load. Where flat work is to be cast, provide similar information relative to the proposed compacting screed or other method to ensure dense placement.

1.6.3.4 Quality Assurance:

Develop and submit for approval a quality control plan in accordance with the guidelines as specified herein. The plan shall include plans for the concrete supplier, the reinforcing steel supplier, and installer.

1.6.3.5 Field Testing Technician and Testing Agency:

Submit data on qualifications of proposed testing agency and technicians for approval by the Contracting Officer to performing any work.

1.6.3.6 Mixture Designs:

Provide a detailed report of materials and methods used, test results, the field test strength (fcr) for marine concrete required to meet durability requirements.

1.6.4 Test reports:

1.6.4.1 Concrete Mixture Proportions:

Submit copies of test reports by independent test labs showing that the mixture has been successfully tested to produce concrete with the properties specified and that mixture will be suitable for the job conditions. Test reports shall be submitted along with the concrete mixture proportions. Obtain approval before concrete placement.

1.6.4.2 Aggregates:

Submit test results for aggregate quality in accordance with ASTM C 33, and the combined graduation curve for grading proposed for use in the work and used in the mixture qualification. Where there is potential for alkali-silica reaction, provide results of tests conducted in accordance with ASTM C 227 or ASTM C 1260. Submit results of all tests during progress of the work in tabular and graphical form as noted above, describing the cumulative combined aggregate grading and the percent of the combined aggregate retained on each sieve.

1.6.4.3 Cement:

Submit current mil data

1.6.5 Field Samples:

Install minimum of 4m of quay wall and finish as required by the specifications.

- Products:

2.1 Materials:

2.1.1 General:

Generally, all materials used shall comply with the requirements of the BS (12), ASTM, AASHTO, ACI or DIN requirements of each material. The Engineer shall be provided with Reports of Laboratory Tests or samples assuring this compliance.

The Reports shall clearly record that the materials comply with the mentioned standards to the satisfaction of the Engineer.

2.1.2 Cement:

The cement used for all reinforced concrete works shall be:

A low heat Portland pulverised fuel ash cement complying with BS 6588.

Equivalent cement suitable for marine environment and the actual works subject to the Engineers approval.

The cement used for lean concrete C20 may be ordinary Portland cement shall comply with BS (12) except otherwise mentioned.

Sulphate resisting cement shall be used for embedded concrete as mentioned on Contract drawings.

Each consignment of cement shall be accompanied by the manufacturer’s certificate documenting the following:

Specific surface (fineness)

Setting time (Vicat apparatus)

Bending strength and compression strength of motor prism,

Cement: Aggregate = 1:3, w/c = 0.5

Chemical Composition

Heat of hydration ( Solution method ).

If  his certificate is not made available, then samples may be taken from different bags or of the consignments suitably packed and send for testing to any approved laboratory or the laboratory on site, at the Contractors expense.

2.1.3 Admixtures and Additives:

Chemical admixtures are not to be used until the supplier has verified their use in accordance with the Specifications and has also demonstrated by trail batches that two (2) times the admixture proposed can be used and still meet the specified concrete strength without noticeable deleterious effect.

The admixtures shall comply with BS (81110 & 5075), ASTM and DIN Requirements.

Chemical admixtures may be:

- Type A. Water reducing admixtures.

- Type D. Water reducing and retarding admixture (Acceptance based on Contractor’s report and recommendation shall be obtained from the Engineer before using).

- Type F. High range water reducer (super plasticizers) based upon sulfonated melamine or mapthelens formaldehyde condensates.

Provide minimum concentration of corrosion-including chemicals as shown in Table below.

Limits on Corrosion-Inducing Chemicals

Chemical *		Limits, Percent **		Test Method

Chlorides			0.01			ASTM D 512

Fluorides			0.01			ASTM D 1179

Sulphites			0.13			ASTM D 1339

Nitrates				0.17			ASTM D 3867

*  Limits refers to water-soluble chemicals

** Limits are expressed as a percentage of the mass of the total cementitious

materials.

2.1.4 Water:

Water to be used for cooling and washing aggregates and for mixing and curing concrete, shall be clean and free from injurious amounts of oil, acid, salt, alkali, organic matter or other deleterious substances. Concreting water shall not be used until tested and until the report of testing has been reviewed by the Engineer showing its compliance with BS (3148), BS (5328), ASTM and DIN Standards.

Mixing water for use with cement shall be suitable to ensure that the salts content of the total concrete mix does not exceed the limitations set out in Table 2-2.5A “TOTAL ALLOWABLE SALTS CONTENT”. Mixing water shall not contain more than 500 parts per million of chlorides as C1 and not more than 100 parts per million of sulfates as SO4.

2.1.5 Fine Aggregate:

Fine aggregate shall consist of natural sand, and shall be composed of clean, hard, durable spherical particles in conformance with BSI, ASTM and DIN Specifications. CORAL SAND SHOULD NOT BE USED FOR ANY CONCRETE WORKS.

The salt content of fine aggregate shall not exceed the limitations as set out in Table 2-1.5A “ TOTAL ALLOWABLE SALTS CONTENT” as well as all the given standards specified.

TABLE 2-1.05A

Total Allowable Salts Content, and

Maximum Allowable Percentages

Salt		In fine aggregate	In coarse		Total by weight

By weight of fine	aggregate by		of cement

Aggregate		weight of coarse

Aggregate

Chlorides 	0.06			0.10			0.20* for OPC

(NaCl)**							0.40* for OPC

Sulphates	0.40			0.50			4.00* BS (8110)

(SO3)

* Include salts in cement and water.

** Equipment determined by chloride ion x 1.6

The total chloride content of the concrete mix arising from the aggregate together with that from any admixtures and any other source expressed as a percentage of chloride ion shall not in any circumstances exceed 0.1 %.

Deleterious substances shall be limited in fine aggregate to the amounts shown in TABLE 2-1.5B, “ALLOWABLE DELETERIOUS SUBSTANCES IN FINEWE AGGREGATE”.

TABLE 2-1.5B

Allowable Deleterious Substances in Fine Aggregate.

Item 							Maximum Allowable

Percentage by Mass

Clay lump and friable particles					1.0

deleterious substances (such as shale,

alkali, mica, coated grains, soft					5.0

particles)

Material finer than 75 micron,					5.0

ASTM (No . 200) sieve

Fineness module for fine aggregate shall be between (2.3 – 3.1) + 0.2 . the grading of fine aggregate shall comply with BS 812, BS(882 and 120 I), BS 8007, BS 8110, BS 5328, ASTM 04.02 and DIN 1045.

2.1.6 Coarse Aggregate:

Coarse aggregate shall consist of crushed gravel, crushed stone or a combination of the two, and shall be composed of clean, hard, uncoated particles. The Laboratory Test Report shall prove its compliance with all requirements of BS 812, BS 882 and 1201, BS 8007, BS 8110, BS 5328, ASTM 04.02 and Din 1045. CORAL AGGREGATES SHOULD NOT BE USED FOR ANY CONCRETE WORKS.

The salt content of coarse aggregate shall not exceed the limitations as set out in TABLE 2-1.5A “TOTAL ALLOWABLE SALTS CONTENT”.

Deleterious substances shall be limited in coarse aggregate to the amount shown in TABLE 2-1.6A “ALLOWABLE DELETERIOUS SUBSTANCES IN COARSE AGGREGATE”.

TABLE 2-1.06A

Allowable Deleterious Substances in Coarse and Medium Aggregate

Item 					Maximum Allowable	Percent by Mass

(Coarse)		(Medium)

Clay lumps				2.00			1.5

Material passing

0.075mm (No. 200) sieve		1.50			4.0

Other deleterious substances

(such as shale, alkali, mica,		5.00

Coated grains, soft particles)

Wearing Resistance of aggregate when tested in accordance with Los Angeles abrasion test, AASHTO (T96) should not exceed 40%.

Water absorption of aggregate should not exceed 6% when tested in according with AASHTO (T84).

Specification gravity of aggregate should be minimum of (2.5) when tested in accordance with AASHTO (T19)	.

Sodium and Magnesium Sulphate soundnesses, when tested according to AASHTO (T-104), should not exceed 10% and 16% respectively.

Flakeness and Elongation when determined according to BS 812 should not exceed 25% for each.

The grading of combined aggregate shall comply with BS (812, 882 and 1201,  8007 & 5238).

The maximum aggregate size to be used for Reinforced Concrete shall be 20mm (3/4 inch); through a size may be used (32mm) upon the special approval of Engineer foe specific places, in BOTH cases special compliance with BS 812 BS 882 and BS 5328 Grading and Sieve Analysis is compulsory.

2.2 Performance and Design Requirements:

Generally concrete shall be specified, produced and tested for compliance with BS 5328 or Equipment ASTM, DIN standards, unless other clauses of this section are more strict or higher standards.

2.2.1 Classes of Concrete:

Classes of concrete are denoted by designations which consist of a letter followed by a numeral indicating the 28-day compressive strength in mega Pascal (MPa) as determined by BS 1881, BS 5328 and BS 8110, and as shown in Schedule 1.

Each class of concrete may consist of one or more mixes determined by the maximum size of aggregate, slump and types of admixtures used.

Each mix within a class shall be considered a specific type, requiring acceptance of the design mix.

2.2.2 Concrete Mix Design Criteria:

Design concrete mixes shall have minimum cement content per cubic meter of concrete consistent with the required slump, a water content corresponding to the appropriate water-cement ratio, the specified maximum size of coarse aggregate, and the required grading of aggregates, in accordance with those limits as set forth in Schedule 1. Design mix proportions shall be as recommended by BSI, ASTM & DIN Specifications, unless otherwise specified herein. Trail mix water= cement ratio shall be used ion accordance with BS (5328), ASTM & DIN Specifications, or the supplier’s previously obtained field data for proportioning the design mix, as determined by the type of structure and exposure conditions, and  shall be adjusted to meet specified design mix requirements. Design mixes shall be tested and reported on as specified herein.

The design mixes for each class of concrete shall be as determined by the Contractor through an acceptable design laboratory and accepted by the Engineer to produce the results as specified herein.

For each class of concrete there shall be as many mix designs as there are different combinations of ingredients anticipated to cover the requirements of the work Mix designs may vary to meet field conditions, but after acceptance by the Engineer no change shall be made without notice to and acceptance by the Engineer based on the Contractors report and recommendation.

Unless otherwise specified, strength requirements shall be based on 28-day compressive strength determined on 150mm cubic specimens.

- Design Mix

When a design mix for any class of concrete has been accepted by the Engineer, it shall not be changed as to source, quality, proportioning, grading of materials, or in any other way that reduces  durability.

All proposed changes shall be accomplished by preparing a new design mix as specified herein.

- Sampling and Testing

Prior to use, all concrete ingredients shall be sampled and tested by a laboratory acceptable to the Engineer in accordance with the methods specified to determine compliance with this Section. Sampling and testing of fresh and hardened concrete shall be done in accordance with BS 1881 & DIN 1048 with all equipment, material transport & labour shall be provided by the contractor.

- Slump

The slump range as specified shall be maintained for concrete at the point of delivery.

- Minimum Cement Content

The minimum cement content per cubic meter shall be as specified in Schedule 1 for each class of concrete as determined by analysis of fresh concrete.

2.2.3 Structural Concrete:

Coarse aggregate shall be Class C35A, C30, C25, and C20 Concrete.

2.2.4 Concrete Fill:

Concrete fill shall be provided in the locations indicated on the Design Drawings and shall be Class C20 concrete.

2.2.5 Cement Mortar:

Cement mortar shall be composed of fine aggregate and cement in the proportions of 3 to1 by volume.

The ingredients shall be thoroughly mixed while dry by machine or hand until the cement colour can no longer be distinguished from the fine aggregate in any part of the mass and then shall be uniformly wetted by means of hose while undergoing further thorough mixing.

The mortar shall be prepared and used in quantities such that no longer than 30 minutes shall elapse between the first wetting and complete use of mortar in the Works and, if mixed by hand, no single batch shall exceed ¼ cubic meter.

2.2.6 Blinding Concrete:

Blinding concrete (mud mat) shall be Class C20 concrete and shall be as specified and not less than 75mm thick. In aggressive soil conditions Class C25 concrete shall be used for blinding (Reference should be made to the Soil Investigation Report).

2.3 Proportioning:

2.3.1 Mix Design:

Mix design shall be determined by one of two methods:

- Proportioning on the basis of field experience.

- Proportioning by laboratory trail batches.

- Proportioning on the Basis of Field Experience

  - where a concrete production facility has a record, based on at least 30 consecutive strength test results that represent similar materials and conditions to those expected, required average compressive strength used as the basis for selecting concrete proportions shall exceed required design strength at designated test age by at least the following required margins based on standard deviation of existing strength test result:

Required Margin		Standard Deviation

(MPa)				(MPa)

4.1				2.0 to 3

5.7				3.1 to 4

7.4				4.1 to 5

9.0				5.1 to 6

11.5				6.1 to 8

  - Strength test data for determining standard deviation shall be considered to comply with Subsection (2.3.1 A.1), if data represents a group of at least 30 consecutive results.

  - Strength test results used to establish standard deviation shall represent concrete produced to meet a specified strength or strength within 5.0 MPa of that specified for the proposed class.

  - Variation of materials and proportions within the population of background test results used to establish standard deviation shall not have been more tightly controlled than for the proposed.

- Proportioning on the Basis of Laboratory Trail Batches.

  - When laboratory trail batches are used as the basis for selecting concrete proportions, strength tests shall be made in accordance with BS 1881, on cubes prepared in accordance with BS 1881.

  - A curve shall be established showing the relationship between the water content and the compressive strength. The curve shall be based on at least three points, each point being the average of at least three cubes tested at 28 days, and representing batches which produce strengths above and below the required average compressive strength. The required average compressive strength shall be 30% greater than the design strength (i.e. the minimum characteristic concrete strength).

  - the minimum cement content for any concrete shall be that show by the curve to produce the average compressive strength required for that class, unless a higher cement content is required by the value shown in Schedule I.

- Reduction of Margin Based on Field Data

After sufficient test data becomes available from the job, the margin (the amount by which the average strength must exceed the design strength) can be reduce below those values indicated in Subsection 3. 0 I, A.1, in accordance with ACI 214 “Recommended Particle for Evaluation of Compressive Test Results of Concrete”, provided:

  - That the probable frequency of strength tests falling more than 3.5 MPa below the design strength will not exceed 1 in 100.

  - That the probable frequency of the average of three consecutive strength tests falling below he design strength will not exceed 1 in 100.

  - That the acceptance of the Engineer has been obtained for such reduction on the basis of the Contractor’s report and recommendation.

2.3.2 Plant and Mixture Trail Runs:

Prior to the delivery of any concrete to the Work Site, the Contractor shall demonstrate the suitability of the mix designs by plant trail mixes.

Trail batches of concrete shall be produced for all the classes of concrete proposed, and shall be designed in accordance with Subsection 2.3.01. Trail mixtures shall be designed for maximum permitted slump, air content, and ambient temperature range of use.

A minimum of six (6) test cubes shall be made and cured in accordance with BS 1881, for each water-cement ratio, using mix materials all of which shall be in the same temperature range of the materials which will be used in the concrete to be delivered to the Work Site. Ambient temperatures and the temperature of each trail batch shall be recorded and made part of the test report.

The report shall be submitted to the Engineer for acceptance based on the Contractorls recommendation (Item 9 Schedule 2).

2.3.3 Batching and Mixing:

Concrete shall be either batched and mixed at a central batching and mixing plant, or batched at a central batching plant and mixed in a truck mixer. The amount of concrete mixed in anyone batch shall not be  more than the rated capacity of the mixer, nor less than the mixer  manufacturer’s recommended minimum mix volume.

- Batching

Batching of cement in any plant shall be by weight.

Batching of aggregates shall be by weight in any plant whose noted capacity id less than100 cu.m/hr.

Batching of water and of admixtures may be by weight or volume.

The accuracy of the measuring equipment shall be:

Cement 	(+/-) 1 percent

Water 		(+/-) 1 percent

Aggregates 	(+/-) 3 percent

Admixtures	(+/-) 3 percent

Batching accuracy shall be assured by the Contractor by calibration test of all measuring devices. Reports of calibration and of adjustments made shall be obtained, and also accompanied by a statement as to the accuracy of all measuring devices. This record shall be maintained at all times by the Contractor, and shall be available for inspection by the Engineer at any time.

- Mixing

Central Mixing Plant:

Measuring tolerances, and mixing capability and time shall be as stated herein.

The fine and coarse aggregates and the cement shall be mixed for not less than four turns of the drum or paddle before the water is added. Water is to be added gradually while the drum or paddle remains in motion, and the concrete shall be mixed until a uniform consistency and colour have been obtained.

The quality of water added to each batch shall be the net water, excluding moisture content for aggregate and free water, if any, but including water that will be absorbed by the aggregate, dependent on absorption and moisture content values determined daily and before any mixing takes place.

Water shall be added to the batch of concrete by means of a measuring device with an automatic cut-off of entry water while emptying into the mixer. All valves, etc. shall be regularly maintained to ensure there is no leakage of water into the mixing drum. The gauging receptacle shall be kept clean and must be completely emptied after each batch.

The whole of the mixed batch shall be removed before materials for a fresh batch enter the drum, unless the plant is designed for continuous mixing.

Retempering of concrete which has partially hardened by the addition of cement aggregate or water shall not be allowed. Concrete which has been overmixed to the extent that addition of water is necessary to preserve the required consistency during discharge shall not be used.

- Transportation

The temperature of concrete leaving the mixing plant shall be such that at the time of placement, the maximum temperature does not exceed that specified for is placement, in Subsection 1-5. 05.

Concrete shall be so transported and placed that contamination, segregation, or loss of the constituent materials does not occur.

Concrete shall be compacted in its final position within 30 minutes from the time of introduction of the cement into the aggregates, but in all cases at least ninety (90) minutes less than the certified initial set time of the cement.

The slump of delivered concrete shall be determined on-site and shall not exceed the working limit shown below:

Working Limit		Margin for Error 	Rejection Limit

100mm		           20mm 		        120mm

The margin for error can only be used for a maximum of one truckload out of ten consecutive truckloads of concrete.

Contractor is to assess slump at jobsite for acceptable workability special high slump easily worked mixes shall be used as required provided prior acceptance by the engineer has been granted as based on the contractor’s report and recommendations.

Where the slump is deemed in appropriate for acceptable workability, the contractorls quality control supervisor can authorized adding additional admixture and/or water to the mix to obtain acceptable workability, but within the limitations of the water-cement ratio as required by this specification. However, plasticizers shall be used upon the convenience of the engineer.

- Execution:

  - Inspection:

    - Preplacement Inspection.

Before concrete is placed, forms, reinforcements, water stops, anchor bolts, and embedment shall be rigidly secured in proper position. Furthermore, dirt, sand, water, and debris shall be removed from the space to be occupied by concrete. All surfaces encrusted with dried concrete from previous placement operations shall be cleaned, and the entire installation shall be subjected to the approval of to the Engineer.

  - Preparation:

    - Limit of Pours.

The limits of each concrete pour shall be predetermined by the Contractor and shall be acceptable to the Engineer. All concrete within such limits shall be placed in one continuous operation.

    - Embedments.

Anchor bolts, castings, steel shapes, sleeves, and other materials that are to be embedded in the concrete shall be accurately positioned in the forms and securely anchored.

Unless installed in pipe sleeves, anchor bolts shall have sufficient threads to permit a nut to be installed on the concrete side of the form or template. A second nut shall be installed on the other side of the form or template, and the two nuts shall be adjusted so that the bolt will be held rigidly in proper position.

Embedments shall be clean when installed. After concrete placement, surfaces not in contact with concrete shall be cleaned of concrete spatter and other foreign substances.

    - Bonding to hardened concrete.

The surface of the hardened concrete upon which fresh concrete is to be placed shall be rough, clean, and damp. Surface mortar shall be removed to expose the aggregate. The hardened surface shall be cleaned of all foreign substances (including curing compound ), washed with clean water, and kept saturated during the 24 hour period preceding placement of fresh concrete.

  - Installation:

    - Placement.

The limits of each concrete pour shall be predetermined by the contractor and shall be acceptable to the Engineer. All concrete within such limits shall be placed in one continuous operation.

Before concrete is placed, forms, reinforcements, anchor bolts, and embedments shall be rigidly secured in proper position; all dirt, mud, water, and debris shall be removed from the space to be occupied by concrete; all surfaces encrusted with dried concrete from previous placement operations shall be cleaned; and entire installation shall be acceptable to the Engineer.

All horizontal and sloping excavated surfaces on which concrete is to be placed and excavated shall be covered with blinding concrete immediately after completion of the final trimming of excavation.

Place concrete as soon as practicable after the forms and the reinforcement have been inspected and approved. Do not place concrete when weather conditions prevent proper placement and consolidation; in uncovered areas during periods of precipitation; or in standing water. Prior to placing concrete, remove dirt, construction debris, water from within the forms. Deposit concrete as close as practicable to the final position in the forms. Do not exceed a free vertical drop of one m from the point of discharge. Place concrete in one continuous operation from one end of the structure towards the other lifts for vertical construction.

- Conveying Concrete.

Concrete shall be conveyed to the point of final deposit by methods which will prevent separation or loss of ingredients. Concrete shall be placed in final position without being moved laterally in the forms more than 1.5 m.

- Placing Concrete.

Concrete shall be placed in approximately horizontal layers of proper depth for effective compaction; however, the depth of a layer shall not exceed 0.5 In Each layer of concrete shall be plastic when covered with the following layer and the forms shall be filled at a rate of vertical rise of not more than 0.5 m per hour. Vertical construction joints shall be provided as necessary to comply with these requirements.

Concrete shall be thoroughly settled when top finished. All laitance, debris, and surplus water shall be removed from concrete surfaces, scraping, or other effective means. Wherever the top the finished concrete will be exposed to weathering, the forms shall be filled completely and after the concrete has settled, the excess shall be screeded off and the top surface shall be finished smoothly.

Unless otherwise agreed by the Engineer on the basis of satisfactory site trails, concrete shall not be dropped in to place from a height exceeding 2 meters. Chutes or funnel tubes shall be used where heights exceed 2 meters.

The top part of all reinforced concrete walls shall be given special consideration to avoid segregation of fine and coarse aggregates, that may occur during vibration and gives lowered compression strength in the wall crest. To avoid this effect the concrete shall be filled to at least 3.0 cm over the final wall crest elevation before the concrete is hardened the upper surplus layer of the wall crest has to be drawn off to the final elevation.

3.3.2 Compaction.

During and immediately after placement, concrete shall be thoroughly compacted and worked around all reinforcements and embedments and into the corners of the forms. Mechanical vibrators shall be used which will maintain at least 9,000 cycles per minute when immersed in the concrete. Each vibrator shall be driven by a motor not smaller than 1.1 KW. Number and type of vibrators shall be acceptable to the Engineer.

Compaction by hand may be used only with the prior approval of the Engineer.

3.3.3 Hot Weather Concreting.

Except as modified herein, hot weather concreting shall comply with ACI 305. At air temperature of the concrete when placed in the work shall kept as cool as possible during placement and curing. The temperature of the concrete when placed in the work shall not exceed 32° C. If the ambient temperature reaches 40° C, which is unlikely happen in Maldives Concentrating operations shall be discontinued the Contractor has the adequate means of cooling the ingredients and keeping the temperature of mixed concrete below 32° C.

Plastic shrinkage cracking, due to rapid evaporation of moisture, shall be prevented Concrete shall not be placed when the evaporation rate (actual or anticipated) equals or exceeds I kg per square meter per hour.

To achieve the specified requirements, the Contractor shall provide sunshades over stockpiles of aggregate, cement silos, mixing water tanks, parked concrete trucks, 
in addition shall carry out one or more of the following procedures which shall be submitted to the Engineer for review.

1. Cool the mixing water and/or replace part of the water by chipped ice. The ice shall be completely melted by the time mixing is completed. Shade or wet the outside of the formwork.

3. Apply a fine moisture (fog) spray of clean cool water to shaded areas immediately prior to placing concrete.

4. Pour concrete at night.

Water used for cooling purposes shall be as specified.

In all times the surface of freshly placed concrete shall be protected against drying by covering it with wet hessian cloth or burlaps and where practical continuous water curing shall be applied during the first few hours after placement. In addition to DIN 1045 it has to be considered that spraying cold water for ulterior treatment of concrete in hot weather leads to quenching and surface cracks. Only fine sprinklers will be allowed.

3.3.5 Underwater Concrete.

Structural reinforced concrete shell not be placed under water. Instead, proper dewatering system shall be used to avoid such Concrete shall not be deposited under water except with the specific written permission of the Engineer. For concrete deposited under water, the limiting requirements shall be adjusted to provide not more than 150 mm of slump and to increase the cement factor by 50 kilograms per cubic meter.

Underwater concreting shall be carried out through tremies having hoppers at the upper end. After the flow of concrete is started, the lower end of the tremie shall be kept below the surface of the deposited concrete. Stirring of the deposited concrete shall be avoided. The tremie shall be moved by lifting it free of the concrete and lowering it vertically at the new location. The entire mass of concrete shall be placed as quickly as possible so that it will flow into place without the necessity of horizontal shifting below water.

The water shall be quiescent when concrete is deposited therein. Velocity of water flow shall not exceed 0.6 m per minute in any direction within the space where the concrete is placed. After concrete is placed, the water level in the space shall be kept static until the concrete has hardened.

3.3.6 Concrete Placement in Large Pours.

Subject to the requirements for construction and movement joints and for preliminary test blocks specified herein, the Contractor shall not be limited to the size of individual pours of concrete. With large pours, defined as a pour where the least dimension is greater than 1.5 meters, the following precautions shall be taken to limit thermal gradients and internal stresses:

1. The temperature of the concrete at the time of placing shall not bemore than 32°C and, in any event, shall be such as to ensure that the maximum internal temperature attained during setting does not exceed 70 ° C.

2. Final batch of concrete in a large pour shall be a layer approximately 150 mm thick, the placing of which shall be completed within one hour of placing of the concrete at any point beneath it.

3. Concrete shall be protected as soon as practicable, after placing, by covering the surface with a minimum thickness of either100 mm of water of 50 mm of sand (kept wet) and by shading from direct sunlight.

4. Sets of thermometers shall be provided in the concrete to measure the temperature at the centre and near each face of the concrete, the sets being at centers not exceeding 5m or as otherwise agreed with the Engineer.

5. Formwork shall be at least 19 mm thick, or such other combination of materials having an equivalent insulation value, which shall not be removed until there has been sufficient time for the temperature difference between the centre and any face of the concrete to drop to less than 20°C.

3.4  Finishing Unformed Surfaces:

Concrete encasement will require no finishing except that necessary to obtain the required surface elevations or contours. The unformed surfaces of loading unloading area at the top shall be screeded and given an initial float finish followed by additional floating, and toweling where required. All top of walls shall have a Class U3 finish.

3.4.1 Class of Finish.

Finishes to unformed surfaces of concrete shall be classified as Ui, U2, U3, “spaded” or “bonded concrete”. Where the class of finish is not specified or indicated on the Drawings the concrete shall be finished to Class tJ2.

A. Screeding (Class Ul).

Screeding Class Ui shall provide a concrete surface conforming to the proper elevation and contour with all aggregates completely embedded in mortar. All screeded surfaces shall be free of surface irregularities with a height or depth in excess of 15 mm as measured from a 3 m straightedge.

B. Floating: (Class U2).

Screeded Class Ui surfaces shall be given an initial float finish as soon as the concrete has stiffened sufficiently for proper working. Any piece of coarse aggregate which is disturbed by the float or which causes a surface irregularity shall be removed and replaced with mortar. Initial floating shall produce a
surface of uniform texture and appearance with no unnecessary working of the surface.

Initial floating shall be followed by a second floating at the time of initial set. The second floating shall produce a finish of uniform texture and colour.

Floating shall be performed with hand floats or suitable mechanical compactor- floats.

C. Towelling: (Class U3)

Interior floor surfaces which will be exposed after construction is completed, surfaces to be covered with floor coverings, the exposed portion of the top of equipment bases, the top of curbs, and other surfaces designated on the Drawings shall be steel trowel finished. Towelling shall be performed after the second floating when the surface has hardened sufficiently to prevent an excess of fines being drawn to the Towelling shall produce a dense, smooth, uniform surface free from blemishes and trowel marks.

D. Finishing: Surfaces for Bonding.

All surfaces to be covered with concrete or topping shall be float finished. All laitance, surface mortar, and unsound material shall be removed by brushing or air blasting at the time of initial set. Surfaces shall be rough, clean, and sound. Floors and other flatwork surfaces to receive topping shall be given a broom finish following the second floating.

E. Spaded Finish.

A spaded finish shall be a surface free from voids and brought to a uniform appearance by the use of shovels as it is placed in the work.

F. Edging.

Unless specified to be bevelled, exposed edges of floated or towelled surfaces shall be edged with a tool having 6mm corner radius.

G. Concrete Surface Tolerances

Concrete surfaces for the various classes of uniformed finishes specified shall comply with the tolerances shown in Table 3-4.1 except where different tolerances are expressly required by the specifications or indicated on the Drawings.

TABLE 3-4.1

Maximum Tolerance (mm)

| Class of Finish | Line and level | Abrupt irregularity | Gradual Irregularity |
| --- | --- | --- | --- |
| U1 | (+ / -) 15 | 5 | 5 |
| U2 | (+ / -) 5 | 0 | 5 |
| U3 | (+ / -) 5 | 0 | 5 |

In table 3-4.1, “Line and level” shall mean the lines, and levels, indicated on the Drawings.

Surface irregularities shall be classified as “abrupt” or “gradual” Abrupt irregularities include, but shall not be limited to, offsets and fins caused by displaced or misplaced form work materials, and shall be tested by direct measurement.

Gradual irregularities shall be tested by means of a straight template for plane surfaces or its suitable equivalent for curved surfaces, the template being 3.0m long for unformed surfaces.

Defects in unformed surfaces shall be repaired in accordance with the relevant requirements of this section.

3.5 Finishing Formed Surfaces:

Fins and other surface projections shall be removed from all formed surfaces except exterior surfaces that will be in contact with sand backfill and surfaces not specified to be damp-proofed. A power grinder shall be used, if necessary, to remove projections and provide a flush surface. Surfaces to be damp-proofed shall have fins removed and tie holes filled, but no additional finishing will be required.

All reinforced formed concrete shall have a fairface surface finish.

3.3.1 Tie Holes.

Tie holes in all formed surfaces shall be cleaned, wetted, and filled with patching mortar. Tie hole patches shall be finished flush and shall match the texture of the adjacent concrete.

3.6 Curing:

Concrete shall be protected from loss of moisture for at least 14 days after placement (according to DIN.1045) Curing of concrete shall be by methods which will keep the concrete surfaces adequately wet during the specified curing period. Precast members should not be placed in seawater before completion of specified curing.

3.6.1 Water Curing.

Water saturation of concrete surfaces shall begin as quickly as possible after initial set of the concrete and shall e continuous for an initial curing period of 14 days. The rate of water application shall be regulated to provide complete surface coverage with a minimum of runoff. The application of water to walls may be interrupted for grout cleaning only over the areas being cleaned at the time, and the concrete surface shall not be permitted to become dry during such interruption. Horizontal concrete surface shall be cured by ponding and vertical surfaces shall be wrapped with met Hessian. Other means can be used to the approved of the Engineer. Only portable water should be used for wet curing.

3.6.2 Membrane Curing.

Membrane curing compound may be used in lieu of water curing on concrete which will not be covered later with topping, mortar, or additional concrete.

Membrane curing compound shall be spray applied at coverage of not more than 5.0 square meters per litre. A second coat shall be applied within 4 hours of initial coating or as recommended by the manufacturer. Unformed surfaces shall be covered with curing compound within 30 minutes after final finishing or following the initial 7 day water curing period. If forms are removed before the end of the specified curing period, curing compound shall be immediately applied to the formed surfaces before they dry out.

Curing compound shall be suitably protected against exposure to direct sunlight and abrasion during the curing period. The curing compound shall be degradable pigmented type.

3.7 Field Quality Control:

3.7.1 Testing.

Field control tests, consisting of aggregate tests, slump tests, air content tests, and making compression tests, shall be performed as directed by the Engineer.

All tests to be performed according to BSI and ASTM and DIN standards and results shall not be approved unless proving its compliance with given specifications and standards.

All tests required for preliminary review shall be made at the expanse of the contractor. Tests required during the progress of the work shall also be made at the expense of the contractor.

The frequency specified herein for each field control tests is a minimum. If additional field control tests are necessary, in the opinion of the Engineer, all such tests shall be made.

- Aggregate:

Aggregate tests shall be performed as specified by the Engineer and to comply with BSI, ASTM and DIN requirements. The test shall include crushing, abrasion, absorption, grading and chemical composition.

2.   Sampling Concrete:

Representative samples of fresh concrete shall be obtained in the field, according with BS 1881 or equivalent standards.

- Slump:

A slump test shall be made for each 5 to 7 cu.m. of  concrete or as directed by the Engineer. Slump shall be determined in accordance with ASTM, AASHTO and BSI Specifications. Tolerances shall not exceed 20 mm.

- Air Content:

An air content test shall be made from one of the first three batches mixed each day, and from each batch of concrete from which concrete compression test cubes are made. Air content shall be determined in accordance with ASTM, AASHTO and BSI Specifications.

- Water:

Water shall be tested as specified by the Engineer and according to ASTM and BS (3148) Standards.

- Compression tests:

One set of six concrete compression test cubes shall be made each day when less than 10 cubic meters of concrete are placed. If quantity placed per day within 50 MC then two sets of six cubes will be taken, or a set for each type of concrete. If quantity of placed concrete per day is more than 50 MC then, one set of six cubes will be taken for every 25 MC and for every type of concrete, or as directed by the Engineer. Two cubes of each set shall be tested at age of 7 days, another two cubes shall be tested an age of 28 days. The third two will be crushed if the 28 days results are odd and need to be verified. Compression tests will be evaluated in accordance with BS 1881.

Test specimens shall be made, cured and tested in accordance with BS 1881. While still in the field, the test cubes shall be stored and cured after transport to the laboratory, in accordance with BS 1881.

Each set of compression test specimens shall be marked of tagged with the date and time of day the specimens were made, the location in the work where the concrete represented by the specimens was placed, the delivery truck or batch number, the air content, and the slump.

    - Test Reports.

Test reports shall be prepared and distributed by the Contractor in accordance with the Quality Control Section.

  - Adjust and clean:

    - Repairing Defective Concrete

Defects in formed Concrete surfaces shall be repaired within 24 hours, to the satisfaction of the Engineer, defective concrete shall be replaced within 48 hours after the adjacent forms have been removed. All concrete which is honeycombed or otherwise defective shall be cut out and removed to sound concrete, with edges square cut to avoid feathering.

Concrete repair work shall be performed in a manner that will not interfere with through curing of surrounding concrete. Repair work shall be adequately cured.

3.9     cracks:

All cracks over 0.2 mm wide in concrete surfaces shall be cut out and the groove filled with epoxy grout.

3.10    Protection of buried concrete:

All concrete surface of walls and anchor block in contact with soil shall be protected by applying a waterproofing layer to it. The waterproofing material used shall comply with B.S and ASTM requirements and the other given specifications to the satisfaction of the Engineer.

SCHEDULE 1

Concrete Mix Design Standard Parameters

| Concrete Class Designations | 28 day Minimum Characteristic Compressive Strength MPa | Minimum Cement Content kg/cu.m | Maximum Free water Cement Ratio (ByWei@t) | Maximum Slump mm | Max Chloride ion content by wt of cement % |  |
| --- | --- | --- | --- | --- | --- | --- |
| **C35A | 35 | 370 | 0.40 | 110 | 0.20 | R.C structures |
| C30 | 30 | 360 | 0.50 | 100 | 0.20 | R.C structures |
| C25 | 25 | 310 | 0.55 | 100 | 0.30 | Blinding in aggressive soils |
| C20 | 20 | 280 | 0.55 | 120 | 0.40 | Blinding and Fill Concrete |
| C15 | 15 | 220 | 0.60 | 120 |  | Concrete Fill material |

** Super plasticizer or plasticizer admixture shall be used to achieve slump. This concrete shall comply with BS 8007 requirements. Slump may be increased upon the Engineer and to his convenience.

Notes for above table:

- Water-reducing admixtures shall be used as required to meet the limits specified in this table.

- Special high slump easily worked mixes may be used, if required, provided the other limits of this table are not exceeded and prior Engineer acceptance has been granted, as based on the contractors report and recommendation.

- Cement content shall not be less than quantities specified in BS8110 table 6.1 and 6.2.

- (SRPC) Sulphate Resistant Portland Cement shall be used for buried concretes where mentioned.

- Slump may be increased upon the convenience of the Engineer and shall be increased by means of water reducing / plasticizing admixture.

- 28 day characteristic compressive strengths shown are based on cube samples according to BSI Standards.

- Nominal maximum aggregate size shall be 20 mm.

\

SCHEDULE 2

Reports to be submitted by the contractor in regard to concrete works

| NO. | TITLE | REPORT SUBMITTED | FREQUENCY OF REPORT |
| --- | --- | --- | --- |
| 1 | Sources of Materials | - 31 days prior to delivery of concrete. b) On apparent change. | a) One time. b) As required. |
| 2 | Supplier Quality (if any) | - 31 days prior to delivery of concrete. | a) One time. |
| 3 | Mix design for all classes of concrete (Reference Schedule 3) | a) 31 days prior to delivery of concrete. b) When mix is redesigned for any purpose. | a) One time. b) As required. |
| 4 | Certificate for cement from manufacturer | a) 31 days prior to delivery of concrete. b) For each new delivery from manufacturer. | a) One time. b) As required. |
| 5 | Certificate for admixtures from manufacturer | a) 31 days prior to delivery of concrete. b) If any changes occurs. | a) One time. b) As required. |
| 6 | Report on plant trial mixes with 7 day & 28 day test results for all classes of concrete required for the work. | a) 31 days prior to delivery of concrete. b) If changed. | a) One time. b) As required. |
| 7 | Reports on concrete cube strength Tests. | a) 7+7 days after casting b) 28+7 days after casting | a) After each 25m3 of casting. b) As required. |
| 8 | Concrete casting check list | 24 hours before casting | Before each casting |
| 9 | Reports of the following tests on water (if it is not from the public service) for mixing concrete, washing and/ or cooling aggregates and curing: 1) Sulphates (as SO3) 2) Chlorides (as NaCl) | a) 31 days prior to delivery of concrete. b) During production of concrete. | a) One time. b) Monthly. |

TIMBER WORKS

Material - Hardwearing durable Yellow Balau decking.

Class - D50 strength rating.

Density - average weight 980 kilos per m3.

Decay resistance – high, longevity - 25 years +.

5.1.2	MATERIAL PROPERTIES

- Compressive strength of 1250 psi (8.618 x 103 KN/m2)

- Bending stress of 1950 psi (1.34 x 104 KN/m2)

- Shear strength of 160 psi (1.1 x 103 KN/m2)

- Elastic modulus of 1500000 psi (1.03 x 107 KN/m2)

Drawings

[Insert here a list of Drawings.  The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder].

| List of Drawings |  |  |
| --- | --- | --- |
| Project Number | Drawing Number | Drawing Title |

Bill of Quantities or Activity Schedule

[The following units of measurement and abbreviations are recommended for use].

| Unit | Abbreviation | Unit | Abbreviation |
| --- | --- | --- | --- |
| cubic meter hectare hour kilogram lump sum meter metric ton (1,000 kg) | m3 or cu m ha h kg sum m t | millimetre month number square meter square millimetre week | mm mon nr m2 or sq m mm2 or sq mm wk |

Supplementary Information

PART 3 –Contract

Section VII.  General Conditions of Contract for the Procurement of Works

## Table of Clauses

A.  General	42

1.	Definitions	42

2.	Interpretation	42

3.	Language and Law	42

4.	Project Manager’s Decisions	42

5.	Delegation	42

6.	Communications	42

7.	Subcontracting	42

8.	Other Contractors	42

9.	Personnel and Equipment	42

10.	Employer’s and Contractor’s Risks	42

11.	Employer’s Risks	42

12.	Contractor’s Risks	42

13.	Insurance	42

14.	Site Data	42

15.	Contractor to Construct the Works	42

16.	The Works to Be Completed by the Intended Completion Date	42

17.	Approval by the Project Manager	42

18.	Safety	42

19.	Discoveries	42

20.	Possession of the Site	42

21.	Access to the Site	42

22.	Instructions, Inspections and Audits	42

23.	Appointment of the Adjudicator	42

24.	Procedure for Disputes	42

B.  Time Control	42

25.	Program	42

26.	Extension of the Intended Completion Date	42

27.	Acceleration	42

28.	Delays Ordered by the Project Manager	42

29.	Management Meetings	42

30.	Early Warning	42

C.  Quality Control	42

31.	Identifying Defects	42

32.	Tests	42

33.	Correction of Defects	42

34.	Uncorrected Defects	42

D.  Cost Control	42

35.	Contract Price	42

36.	Changes in the Contract Price	42

37.	Variations	42

38.	Cash Flow Forecasts	42

39.	Payment Certificates	42

40.	Payments	42

41.	Compensation Events	42

42.	Tax		42

43.	Currencies	42

44.	Price Adjustment	42

45.	Retention	42

46.	Liquidated Damages	42

47.	Bonus		42

48.	Advance Payment	42

49.	Securities	42

50.	Dayworks	42

51.	Cost of Repairs	42

E.  Finishing the Contract	42

52.	Completion	42

53.	Taking Over	42

54.	Final Account	42

55.	Operating and Maintenance Manuals	42

56.	Termination	42

57.	Fraud and Corruption	42

58.	Payment upon Termination	42

59.	Property	42

60.	Release from Performance	42

General Conditions of Contract for the Procurement of for Works

| A. General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Definitions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The following words and expressions shall have the meanings hereby assigned to them: - The Accepted Contract Amount means the amount accepted in the Letter of Acceptance for the execution and completion of the Works and the remedying of any defects. - The Activity Schedule is a schedule of the activities comprising the construction, installation, testing, and commissioning of the Works in a lump sum contract. It includes a lump sum price for each activity, which is used for valuations and for assessing the effects of Variations and Compensation Events. - The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in GCC 23. - Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender. - Compensation Events are those defined in GCC Clause 41 hereunder. - The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with GCC Sub-Clause 52.1. - The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in the Contract Agreement. - The Contractor is the party whose Tender to carry out the Works has been accepted by the Employer. - The Contractor’s Tender is the completed tendering document submitted by the Contractor to the Employer. - The Contract Price is the Accepted Contract Amount stated in the Letter of Acceptance and thereafter as adjusted in accordance with the Contract. - Days are calendar days; months are calendar months. - Dayworks are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant. - A Defect is any part of the Works not completed in accordance with the Contract. - The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor. - The Defects Liability Period is the period named in the PCC pursuant to Sub-Clause 33.1 and calculated from the Completion Date. - Adjudicator means the single person appointed under Clause 23. - Drawings means the drawings of the Works, as included in the Contract, and any additional and modified drawings issued by (or on behalf of) the Employer in accordance with the Contract, include calculations and other information provided or approved by the Project Manager for the execution of the Contract. - The Employer is the party who employs the Contractor to carry out the Works, as specified in the PCC. - Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. - “In writing” or “written” means hand-written, type-written, printed or electronically made, and resulting in a permanent record; - The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. - The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the PCC. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. - Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. - Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. - The Project Manager is the person named in the PCC (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. - The Procuring Entity means the entity purchasing the Works as specified in the PCC, and shall be otherwise be referred to as the Employer. - PCC means Particular Conditions of Contract. - The Site is the area defined as such in the PCC. - Site Investigation Reports are those that were included in the tendering documents and are factual and interpretative reports about the surface and subsurface conditions at the Site. - Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. - The Start Date is given in the PCC. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. - A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. - Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. - A Variation is an instruction given by the Project Manager which varies the Works. - The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the PCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Interpretation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In interpreting these GCC, words indicating one gender include all genders. Words indicating the singular also include the plural and words indicating the plural also include the singular. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager shall provide instructions clarifying queries about these GCC. - If sectional completion is specified in the PCC, references in the GCC to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contract shall be either: (a) an Admeasurement Contract with a Bill of Quantities, or (b) a Lump Sum Contract with an Activity Schedule, as indicated in the PCC. - For Admeasurement Contracts: (a) the Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. (b) the Bill of Quantities will be used to calculate the Contract Price. The Contractor shall be paid for the quantity of the work actually done at the rate in the Bill of Quantities for each item. - For Lump Sum Contracts: (a) the Activity Schedule shall contain items for the construction, installation, testing and commissioning of works to be carried out by the Contractor. (b) the Activity Schedule will be used calculate the total Contract Price and the Contractor shall be paid the accepted lump sums amounts for each activity or the total lump sum price tendered for the activity or activities completed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Language and Law |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The language of the Contract and the law governing the Contract are stated in the PCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Project Manager’s Decisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Except where otherwise specifically stated in the PCC, the Project Manager shall decide contractual matters between the Employer and the Contractor in the role representing the Employer. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Delegation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Unless otherwise specified in the PCC, the Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may revoke any delegation after notifying the Contractor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Communications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Subcontracting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Other Contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the PCC. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Personnel and Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall employ the key personnel and use the equipment identified in its Tender, to carry out the Works or other personnel and equipment approved by the Project Manager. The Project Manager shall approve any proposed replacement of key personnel and equipment only if their relevant qualifications or characteristics are substantially equal to or better than those proposed in the Tender. - If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Employer’s and Contractor’s Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Employer’s Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - From the Start Date until the Defects Liability Certificate has been issued, the following are Employer’s risks: - The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to - use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works or - negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor. - The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed. - From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to - a Defect which existed on the Completion Date, - an event occurring before the Completion Date, which was not itself an Employer’s risk, or - the activities of the Contractor on the Site after the Completion Date. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Contractor’s Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.1 From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks are Contractor’s risks. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Insurance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the PCC for the following events which are due to the Contractor’s risks: - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death. - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. - If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. - Both parties shall comply with any conditions of the insurance policies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Site Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall be deemed to have examined any Site Data referred to in the PCC, supplemented by any information available to the Contractor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Contractor to Construct the Works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Works to Be Completed by the Intended Completion Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval by the Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, for his approval. - The Contractor shall be responsible for design of Temporary Works. - The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. - The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required. - All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before this use. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall be responsible for the safety of all activities on the Site. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Discoveries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Possession of the Site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the PCC, the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Access to the Site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Instructions, Inspections and Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located. - The Contractor shall permit the Government and/or persons appointed by the Government to inspect the Site and/or the accounts and records of the Contractor and its sub-contractors relating to the performance of the Contract, and to have such accounts and records audited by auditors appointed by the Government if required by the Government. The Contractor’s attention is drawn to Sub-Clause 57.1 which provides, inter alia, that acts intended to materially impede the exercise of the Government’s inspection and audit rights provided for under Sub-Clause 22.2 constitute a prohibited practice subject to contract termination (as well as to a determination of suspension under Government Financial Regulations). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Appointment of the Adjudicator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Adjudicator shall be appointed jointly by the Employer and the Contractor, at the time of the Employer’s issuance of the Letter of Acceptance. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator, the Employer will request the Appointing Authority designated in the PCC, to appoint the Adjudicator within 14 days of receipt of such request. - Should the Adjudicator resign or die, or should the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator shall be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within 30 days, the Adjudicator shall be designated by the Appointing Authority designated in the PCC at the request of either party, within 14 days of receipt of such request. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Procedure for Disputes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within 14 days of the notification of the Project Manager’s decision. - The Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the PCC, together with reimbursable expenses of the types specified in the PCC, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s decision shall be final and binding. - The arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place specified in the PCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Time Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Within the time stated in the PCC, after the date of the Letter of Acceptance, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. In the case of a lump sum contract, the activities in the Program shall be consistent with those in the Activity Schedule. - An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the PCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the PCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted. In the case of a lump sum contract, the Contractor shall provide an updated Activity Schedule within 14 days of being instructed to by the Project Manager. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Extension of the Intended Completion Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. - The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Acceleration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager shall obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date shall be adjusted accordingly and confirmed by both the Employer and the Contractor. - If the Contractor’s priced proposals for an acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Delays Ordered by the Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Management Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure. - The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Early Warning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price, or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C. Quality Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Identifying Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tests |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Correction of Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the PCC. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Uncorrected Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager shall assess the cost of having the Defect corrected, and the Contractor shall pay this amount. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D. Cost Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Contract Price |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In the case of an admeasurement contract, the Bill of Quantities shall contain priced items for the Works to be performed by the Contractor. The Bill of Quantities is used to calculate the Contract Price. The Contractor will be paid for the quantity of the work accomplished at the rate in the Bill of Quantities for each item. - In the case of a lump sum contract, the Activity Schedule shall contain the priced activities for the Works to be performed by the Contractor. The Activity Schedule is used to monitor and control the performance of activities on which basis the Contractor will be paid. If payment for Materials on Site shall be made separately, the Contractor shall show delivery of Materials to the Site separately on the Activity Schedule. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Changes in the Contract Price |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - In the case of an admeasurement contract: - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change. - The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. - In the case of a lump sum contract, the Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Variations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - All Variations shall be included in updated Programs, and, in the case of a lump sum contract, also in the Activity Schedule, produced by the Contractor. - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven (7) days of the request or within any longer period stated by the Project Manager and before the Variation is ordered. - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. - In the case of an admeasurement contract, if the work in the Variation corresponds to an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 38.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Cash Flow Forecasts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - When the Program, or, in the case of a lump sum contract, the Activity Schedule, is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. The cash flow forecast shall include different currencies, as defined in the Contract, converted as necessary using the Contract exchange rates. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Payment Certificates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor. - The value of work executed shall be determined by the Project Manager. - The value of work executed shall comprise: - In the case of an admeasurement contract, the value of the quantities of work in the Bill of Quantities that have been completed; or - In the case of a lump sum contract, the value of work executed shall comprise the value of completed activities in the Activity Schedule. - The value of work executed shall include the valuation of Variations and Compensation Events. - The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Payments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Payments shall be adjusted for deductions for advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made. - If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. - Unless otherwise stated, all payments and deductions shall be paid or charged in the proportions of currencies comprising the Contract Price. - Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Compensation Events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The following shall be Compensation Events: - The Employer does not give access to a part of the Site by the Site Possession Date pursuant to GCC Sub-Clause 20.1. - The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - The Project Manager unreasonably does not approve a subcontract to be let. - Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to Tenderers (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site. - The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons. - Other contractors, public authorities, utilities, or the Employer does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor. - The advance payment is delayed. - The effects on the Contractor of any of the Employer’s Risks. - The Project Manager unreasonably delays issuing a Certificate of Completion. - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager shall assume that the Contractor shall react competently and promptly to the event. - The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tax |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of Tenders for the Contract and the date of the last Completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of GCC Clause 44. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Currencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Where payments are made in currencies other than Maldivian Rufiya, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Tender. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Adjustment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the PCC. If so provided, the amounts certified in each payment certificate, before deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency. A separate formula of the type indicated below applies to each Contract currency: Pc = Ac + Bc Imc/Ioc where: Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c.” Ac and Bc are coefficients specified in the PCC, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c;” and Imc is the index prevailing at the end of the month being invoiced and Ioc is the index prevailing 28 days before Tender opening for inputs payable; both in the specific currency “c.” - If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Retention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall retain from each payment due to the Contractor the proportion stated in the PCC until Completion of the whole of the Works. - Upon the issue of a Certificate of Completion of the Works by the Project Manager, in accordance with GCC 51.1, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. The Contractor may substitute retention money with an “on demand” Bank guarantee. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Liquidated Damages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the PCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the PCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. - If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC Sub-Clause 40.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Bonus |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall be paid a Bonus calculated at the rate per calendar day stated in the PCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Project Manager shall certify that the Works are complete, although they may not be due to be complete. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Advance Payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall make advance payment to the Contractor of the amounts stated in the PCC by the date stated in the PCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest shall not be charged on the advance payment. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Securities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount specified in the PCC, by a bank or surety acceptable to the Employer, and denominated in the types and proportions of the currencies in which the Contract Price is payable. The Performance Security shall be valid until a date 28 days from the date of issue of the Certificate of Completion in the case of a Bank Guarantee, and until one year from the date of issue of the Completion Certificate in the case of a Performance Bond. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Dayworks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If applicable, the Dayworks rates in the Contractor’s Tender shall be used only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Cost of Repairs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E. Finishing the Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall request the Project Manager to issue a Certificate of Completion of the Works, and the Project Manager shall do so upon deciding that the whole of the Works is completed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Taking Over |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer shall take over the Site and the Works within seven days of the Project Manager’s issuing a certificate of Completion. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Final Account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Operating and Maintenance Manuals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the PCC. - If the Contractor does not supply the Drawings and/or manuals by the dates stated in the PCC pursuant to GCC Sub-Clause 55.1, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the PCC from payments due to the Contractor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Termination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but shall not be limited to, the following: - the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager; - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days; - the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate; - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor does not maintain a Security, which is required; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the PCC; or - if the Contractor, in the judgment of the Employer, has engaged in corrupt or fraudulent practices in competing for or in executing the Contract, pursuant to GCC Clause 57.1. - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC Sub-Clause 56.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Employer may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Fraud and Corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57.1 If the Employer determines that the Contractor has engaged in corrupt, fraudulent, collusive, coercive or obstructive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 56 shall apply as if such expulsion had been made under Sub-Clause 56.5 [Termination by Employer]. 57.2 Should any employee of the Contractor be determined to have engaged in corrupt, fraudulent, collusive, coercive, or obstructive practice during the execution of the Works, then that employee shall be removed in accordance with Clause 9. 57.3 For the purposes of this Sub-Clause: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede an Employer’s investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or (bb) acts intended to materially impede the exercise of the Employer’s inspection and audit rights provided for under Sub-Clause 22.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Payment upon Termination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the PCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. - If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Property |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Release from Performance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Section VIII.  Particular Conditions of Contract

| GCC reference | Particular Conditions that amend or supplement the General Conditions of Contract for the Procurement of Works |
| --- | --- |
| A. General |  |
| 1.1(r) & 1.1(z) | The Employer (Procuring Entity) is [insert name and address of Employer, and name of authorized representative]. |
| 1.1 (v) | The Intended Completion Date for the whole of the Works shall be [insert date] [If different dates are specified for completion of the Works by section (“sectional completion” or milestones), these dates should be listed here] |
| 1.1 (y) | The Project Manager is [insert name and address of Project Manager]. |
| 1.1 (bb) | The Site is located at [insert address of Site] and is defined in drawings No. [insert numbers] |
| 1.1 (ee) | The Start Date shall be [insert date]. |
| 1.1 (ii) | The Works consist of [insert brief summary, including relationship to other contracts under the Project]. |
| 2.2 | Sectional Completions are: [insert nature and dates, if appropriate] |
| 2.3 | This Contract is Lumpsum. |
| 3.1 | The language of the contract is English The law that applies to the Contract is the law of the Republic of Maldives [or amend if a different law applies]. |
| 5.1 | The Project Manager [insert may or may not] delegate any of his duties and responsibilities. |
| 8.1 | Schedule of other contractors: [insert Schedule of Other Contractors, if appropriate] |
| 13.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: [insert currency and amount]. (b) For loss or damage to Equipment: [insert currency and amount]. (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract [insert currency and amount]. (d) for personal injury or death: - of the Contractor’s employees: [insert currency and amount]. - of other people: [insert currency and amount]. |
| 14.1 | Site Data are: [list Site Data] |
| 20.1 | The Site Possession Date(s) shall be: [insert location(s) and date(s)] |
| 23.1 & 23.2 | Appointing Authority for the Adjudicator: Ministry of Finance |
| 24.3 | Hourly rate and types of reimbursable expenses to be paid to the Adjudicator:N/A |
| 24.4 | Disputes shall be referred to arbitration in accordance with the Arbitration Act of the Republic of Maldives [10/2013]. The place of arbitration shall be: Republic of Maldives In case, an Arbitration system is not yet established, Court of Law of Republic of Maldives shall prevail. |
| B. Time Control |  |
| 25.1 | The Contractor shall submit for approval a Program for the Works within 14 days from the date of the Letter of Acceptance. |
| 25.3 | The period between Program updates is 30 days. The amount to be withheld for late submission of an updated Program is 10% of the monthly progress bill. |
| C. Quality Control |  |
| 33.1 | The Defects Liability Period is: 365 months. |
| D. Cost Control |  |
| 44.1 | The Contract is not subject to price adjustment. |
| 45.1 | The proportion of payments retained is: 10% of each bill up to a limit of 5% of contract. |
| 46.1 | The rate per day for liquidated damages shall be calculated as follows: The liquidated damages for the whole of the Works are as: (CP*0.0025*LD) CP (Contract Price) LD (Late Duration) The maximum amount of liquidated damages for the whole of the works is 15% (fifteen percent) of the final contact price. |
| 47.1 | Not applicable |
| 48.1 | The Advance Payments shall be: XX% and shall be paid to the Contractor no later than 45 days upon signing of the contract and as per the conditions of contract. Advance payment guarantee shall be in the form of a bank guarantee for the equivalent amount and in the form provided in the bidding documents or another form acceptable to the Employer. |
| 49.1 | The Performance Security is XX% of the Contract Price. The Performance Security shall be in the form of: a Bank Guarantee. The Performance security shall be denominated in a freely convertible currency acceptable to the Purchaser; and shall be in the format stipulated in Section IX. - The validity of the performance security shall be: Until the date of issue of the Defects Liability Certificate. |
| E. Finishing the Contract |  |
| 55.1 | The date by which operating and maintenance manuals are required is one month after intended completion date. The date by which “as built” drawings are required is one month after intended completion date. |
| 55.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required in GCC 58.1 is |
| 56.2 (g) | The maximum number of days is: Sixty (60) days. |
| 58.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is [insert percentage]. |

Section IX - Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Tenderer after contract award.

Table of Forms

Letter of Acceptance	42

Contract Agreement	42

Performance Security	42

Advance Payment Security	42

Letter of Acceptance

[To be produced on letterhead paper of the Employer/Procuring Entity]

To:

[name and address of the Contractor ]

Subject:	Notification of Award of Contract:

This is to notify you that your Tender dated………………. [insert date] for the execution of the . . . . . . . . . .[insert name of the contract and procurement reference number, as given in the Invitation to Tender] for the Accepted Contract Amount of the equivalent of . . . . . . . . [insert amount in numbers and words and name of currency], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract, using for that purpose the of the Performance Security Form included in Section IX (Contract Forms) of the Tendering Document.

[Choose one of the following statements:]

We accept that ………………………………. [insert the name of Adjudicator proposed by the Tenderer]  be appointed as the Adjudicator.

[or]

We do not accept that ……………………………. [insert the name of the Adjudicator proposed by the Tenderer] be appointed as the Adjudicator, and by sending a copy of this Letter of Acceptance to …………………………………… [insert name of the Appointing Authority], the Appointing Authority, we are hereby requesting such Authority to appoint the Adjudicator in accordance with ITB 42.1 and GCC 23.1.

| Signed: | ………………….……...…{insert signature of authorised person} |
| --- | --- |
| Name: | ………………………{insert complete name of person signing} |
| In the capacity of: | …………….………....{insert legal capacity of person signing} |
| Duly authorized to sign the tender for and on behalf of | ……………..…………….{insert complete name of Procuring Entity} |
| Date: | ……... day of ……….…………….. ………….{DD/MM/YY} |

Attachment:  Contract Agreement

Contract Agreement

THIS AGREEMENT made the [insert date] day of [insert month], [insert  year], between [name of the Employer] (hereinafter “the Employer”), of the one part, and [name of the Contractor] (hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as [name of the Contract] should be executed by the Contractor, and has accepted a Tender by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

    - the Letter of Acceptance

    - the Contractor’s Tender

    - the Particular Conditions

    - the General Conditions;

    - the Specification

    - the Drawings; and

    - the completed Schedules,

3.	In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of the Republic of Maldives on the day, month and year indicated above.

For and on behalf of the Employer/Procuring Entity

| Signed: | ……………………………………….. |
| --- | --- |
| Name: |  |
| In the capacity of: | [Title or other appropriate designation] |

For and on behalf of the Contractor

| Signed: | ……………………………………….. |
| --- | --- |
| Name: |  |
| In the capacity of: | [Title or other appropriate designation] |

[Note:  If the Consultant consists of more than one entity, all these entities should appear as signatories, e.g., in the following manner:]

For and on behalf of each member of the Joint Venture

| Signed: | ……………………………………….. |
| --- | --- |
| Name of member: |  |
| In the capacity of: | [Title or other appropriate designation] |

| Signed: | ……………………………………….. |
| --- | --- |
| Name of member: |  |
| In the capacity of: | [Title or other appropriate designation] |

Performance Security

[The issuing bank, as requested by the successful Contractor, shall fill in this form in accordance with the instructions indicated]

Date: [insert date (as day, month, and year)]

Title of the procurement:  [Insert general title of the procurement]

Procurement Reference No: [insert reference]

Bank’s Branch or Office: [insert complete name of Guarantor]

Beneficiary: [insert complete name of Employer/Procuring Entity]

Performance Guarantee No:

We have been informed that …….. [name of the Contractor], (hereinafter called “the Contractor”) has entered into Contract No. . . . . . [procurement reference number of the Contract]. dated [insert day and month], [insert year], with you, for the execution of ……………….. [name of contract and brief description of Works] (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we …………………. [name of the Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ………………………… [name of the currency and amount in figures] 1…. (. . . . . [amount in words]) such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the . . . . . day of . . . . . . . . . . , . . . . . .  2, and any demand for payment under it must be received by us at this office on or before that date.  The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed ….[six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . 
[Seal of Bank and Signature(s)]

Note –

All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

1	The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Contract and denominated either in the currency(ies) of the Contract or a freely convertible currency acceptable to the Employer.

2	Insert the date twenty-eight days after the expected completion date. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee.

Advance Payment Security

[The bank, as requested by the successful Contractor, shall fill in this form in accordance with the instructions indicated.]

Date: [insert date (as day, month, and year)]

Title of the procurement:  [Insert general title of the procurement]

Procurement Reference No: [insert reference]

[Issuing bank’s letterhead]

Beneficiary:	[insert legal name and address of Procuring Entity]

ADVANCE PAYMENT GUARANTEE No.: [insert Advance Payment Guarantee no.]

Advance Payment Guarantee No:

We have been informed that ………. [name of the Contractor] (hereinafter called “the Contractor”) has  entered into Contract No……. [procurement reference number of the Contract],  dated [insert day and month], [insert year] with you, for the execution of …………………….. [name of contract and brief description of Works] (hereinafter called “the Contract”).

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum …….. [name of the currency and amount in figures] 1 (…... [amount in words]) is to be made against an advance payment guarantee.

At the request of the Contractor, we ……... [name of the Bank]. hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ……... [name of the currency and amount in figures]* (……. [amount in words]) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number ……….[Contractor’s account number]. at ……... [name and address of the Contractor’s Bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that eighty (80) percent of the Contract Price has been certified for payment, or on the …... day of ………….. 2, whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date. The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

. . . . . . . . . . . . . . [Seal of Bank and Signature(s)]. . . . . . . . . . . . . .

Note –

All italicized text is for guidance in preparing this demand guarantee and shall be deleted from the final document.

1	The Guarantor shall insert an amount representing the amount of the advance payment denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.

2	Insert the expected expiration date of the Time for Completion.  The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee

The Bidder shall provide accurate information on the Letter of Bid about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five years. A consistent history of court/arbitral awards against the Bidder or any member of a joint venture may result in disqualifying the Bidder.

Include if price adjustment provisions apply in the Contract in accordance with PCC Sub-Clause 13.8 Adjustments for Changes in Cost.

Use one of the two options as appropriate.

If none has been paid or is to be paid, indicate “none”.

The sum of the two coefficients Ac and Bc should be 1 (one) in the formula for each currency.  Normally, both coefficients shall be the same in the formulae for all currencies, since coefficient A, for the nonadjustable portion of the payments, is a very approximate figure (usually 0.15) to take account of fixed cost elements or other nonadjustable components.  The sum of the adjustments for each currency are added to the Contract Price.]