## BOQ
SL.NO | DESCRIPTION | QTY | UNIT | RATE (IN MVR) | TOTAL AMOUNT (IN MVR)
Bill No: 01
Toilet Renovations
Since this is a Renovation project, all measurements, site conditions shall be checked on site before bidding by the bidders.
1.1 | Since the project is to be carried out in a full functioning health facility, the duration shall be given with considering this situtation.
1 ) | All machineries, labors and materials shall be provided by the bidder/contractor. Water and electricity for the works shall be provided by the client (Ministry of Health)
Accomodation for the labors shall be provided by the contractor.
All materials utilized for this project shall be approved by consultant before utilization. Contractor has to submit all the materials used for this project.
m3 - cubic meter
m2 - square meter
Lm - Linear meter
t - tonnes
incl - including
mm - millimeter
dia - diameter
SS - Stainless Steel
GI - Galvanised Iron
Bkt - Buckets
1.2 | TOILET RENOVATIONS
General
(a) Rates shall include for: Dismantling and removal of existing sanitary fixtures to Health Facility, Replacing the existing sanitary fixtures with cotto or equivalent fixtures, which shall include all the provision for all the other necessary works
(b) For wall cabinets, Cotto or equivalent towel bar with mirror shall be used. Rates shall include for supplying and fixing of mirrors and towel bars.
(c ) water closets, wash basins, wash basin faucets shall be of cotto/American standard or equivalent. Water closets shall have an anti-bacterial glazed. Also dual, top flushing feature.
(d) Replacement of toilet floor tiles; rates shall include dismantling of existing fixtures and re-fixing/reinstalling of the fixtures upon completion of floor tiles replacement. Existing fixtures shall be dismantled without any damages, if any fixtures get damages during dismantling and re-fixing contractor shall replace the damaged fixture with a new fixture.
(e) Rates shall include removal of existing floor tiles, retiling the toilet floor, using 300x300mm ROCELL/LANKA TILES or equivalent ceramic non-skid tiles.
(f) For all tiling works, tiling cement shall be used. And for grouting works, a hospital graded grout (Lakticrete or equivalent epoxy grout-hospital graded) shall be used. Rates shall include all necessary works.
All tiling surfaces shall be ready for tiling prior to tiling.
1.2.1 | Replacing of floor tiles (toilet -1) | 58 | sq.ft |  | 0
1.2.2 | Replacing of floor tiles (toilet -2) | 58 | sq.ft |  | 0
1.2.3 | Replacing the exisiting Water closet (with Flush Cistern), and reinstallation of exisiting wash closet at Toilet 1 & Toilet 2 | 2 | items |  | 0
1.2.4 | Replacing the existing wash basin, reinstallation of existing wash basin at Toilet 1 & Toilet 2 | 2 | items |  | 0
1.2.5 | Replacing existing muslim shower, supply and full installation of cotto/American standard or equivalent muslim showers. Toilet 1 & Toilet 2 | 2 | items |  | 0
1.2.6 | Replacing and installation of cotto or equivalent stop valve (for muslim Shower) Toilet 1 & Toilet 2 | 2 | items |  | 0
TOTAL OF BILL NO. 01 (TOILET RENOVATIONS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 02
DOORS AND WINDOWS
2.1 | DOORS AND WINDOWS
General
a)All Door & Windows shall be fabricated as per Drawings. Door frames shall be fabricated with treated timber (unless otherwise mentioned), Timber without cracks, defects, and knots. Timber Door panels shall be of readymade Treated Timber Panel doors, unless otherwise mentioned. b)Rates shall include for: locks, latches, closers, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware. c)Rates shall include Removal of Existing Door/window units with all necessary works, demolition of wall edges, removal of rubbles, re-fixing of door/window units, re-plastering works and all other necessary provisions.
2.2 | All hinges shall be of Stainless steel all timber doors/windows shall be coated with NIPPON/SIGMA or equivalent enamel paint
d) All Aluminium windows shall be white powder coated aluminium.
e) All timber doors shall be solid timber panneled door with varnish finish.
f) All glazing shall be 6mm Thick Clear Glass.
(Aluminum framing Profiles to be approved by Consultant).
2.3 | Aluminum / Timber Door
2.3.1 | D1 | 2 | items |  | 0
2.4 | Window Units
2.4.1 | W1 | 14 | items |  | 0
2.5 | Window Curtains
a) Replacing existing Curtains, rates shall include removal of curtains and fabrication of new curtains, and fixing the curtains with new hooks to the existing rails. Curtains shall be opaque fabric, contractor shall submit material for approval. Curtain material shall be approved by the consultant via a written document. Supply/fabrication and complete installation of window curtains for following doors, quality of window curtain should be sun protected medium quality, Size of finished curtain shall be 300mm above FFL & 300mm added to the width of the window. Each window shall have two parts (divided in half along the width of the window), Rates should be complete installation of curtain with railing.
b) rates shall include Rates shall include fixing of alumium rails, fixing rail brackets, sewing fixing, fitting of hook tape and full installation of curtains.
2.5.1 | Window W1 (each item 8ft by 9ft) | 34 | items |  | 0
TOTAL OF BILL NO. 02 (DOORS AND WINDOWS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 03
RECEPTION COUNTER WORKS
3.1 | General
Fabrication of the reception counter as per the drawings
Rates shall include fabrication of reception counter with 18mm plywood.
All edges shall be Edge banded.
All Surfaces shall be finished with PVC roll Formica
All joints shall be Glued (prior of screwing)
All joints shall be screwed using timber purpose Course threaded Screws. All screw heads shall be counter board and seal with a air tight stop
Upon completion of the counter the counter shall be placed at the assigned space provided by the health facility.
3.1.1 | Reception Counter, Fabrication of the counter as per the drawings (6ft = length) | 1 | item |  | 0
TOTAL OF BILL NO. 03 (RECEPTION COUNTER WORKS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 04
ELECTRICAL WORKS
4.1 | General
Replacement of Outdoor Lights.
(a)Rates shall include removal of existing (florescent tubes/energy saving lights with holder) lights, replace using ceiling mounted holders with PHILIPS or equivalent LED Bulb (9W, 1400 LUMENS, Cool Daylight Base E27)
(b) Removal of existing ceiling fans, supply and full installation of 48inch dia. Ceiling fans orient/usha or equivalent. Rates shall include all necessary works.
4.1.1 | Removal of existing (florescent tubes/energy saving lights with holder) lights, replace using ceiling mounted holders with PHILIPS or equivalent LED Bulb (9W, 1400 LUMENS, Cool Daylight Base E27) | 17 | items |  | 0
4.1.2 | Removal of existing ceiling fans, supply and full installation of 48inch dia. Ceiling fans orient/usha or equivalent. Rates shall include all necessary works. | 5 | items |  | 0
TOTAL OF BILL NO. 04 (ELECTRICAL WORKS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 05
ROOF RENOVATION WORKS
5.1 | General
(a) Rates shall include complete removal of existing gutter (east side), fabrication of gutter with lysaght total coated thickness 0.042mm or equivalent gutter fabrication material. Also rates shall include complete fixing of the fabricated gutter and connection of existing downpipes.
(b) Rates of shall include, drilling, screwing for installation of brackets, leveling of gutter, and all other necessary works
5.1.1 | Complete removal of existing gutter (east side), fabrication of gutter with lysaght total coated thickness 0.042mm or equivalent gutter fabrication material. | 60 | ft |  | 0
TOTAL OF BILL NO. 05 (ROOF RENOVATION WORKS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 06
SUPPLY OF PAINT
6.1 | General
Rates shall include Procurement and supplying of paint (emulsion and Enamel) to the health facility
All paints shall be Sigma/seamaster or equivalent exterior paint
For emulsion paint all buckets/barrels shall be supplied in 20 liters
For enamel paint all buckets/barrels shall be supplied in 05liters
The Color codes shall be approved by the consultant
6.2 | Emulsion paint
6.2.1 | Procurement and supplying of exterior mulsion paint Sigma/Seamaster of equivalent (20litre Bucket) | 5 | Bkt |  | 0
6.3 | Enamel paint
6.3.1 | Procurement and supplying of exterior enamel paint Sigma/Seamaster of equivalent (05 litre Bucket) | 6 | Bkt |  | 0
TOTAL OF BILL NO. 06 (SUPPLY OF PAINT) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 07
ADDITIONS
Bill No: 01
Bill No: 02
Bill No: 03
Bill No: 04
Bill No: 05
Bill No: 06
TOTAL OF BILL NO. 07 (ADDITIONS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)
Bill No: 08
OMISSIONS
Bill No: 01
Bill No: 02
Bill No: 03
Bill No: 04
Bill No: 05
Bill No: 06
TOTAL OF BILL NO. 08 (OMISSIONS) |  |  |  |  | 0
(CARRIED OVER TO THE GENERAL SUMMARY)

## SUMMARY
SUMMARY OF BILLS OF QUANTITIES
PROJECT: RENOVATION OF EXISTING HEALTH CENTER AT H.DH. KURINBI
SL.NO | BILL NAME | AMOUNT (MVR)
1 ) | TOTAL OF BILL NO. 01 (TOILET RENOVATIONS) | 0
2 ) | TOTAL OF BILL NO. 02 (DOORS AND WINDOWS) | 0
3 ) | TOTAL OF BILL NO. 03 (RECEPTION COUNTER WORKS) | 0
4 ) | TOTAL OF BILL NO. 04 (ELECTRICAL WORKS) | 0
5 ) | TOTAL OF BILL NO. 05 (ROOF RENOVATION WORKS) | 0
7 ) | TOTAL OF BILL NO. 06 (SUPPLY OF PAINT) | 0
14 ) | TOTAL OF BILL NO. 07 (ADDITIONS)
15 ) | TOTAL OF BILL NO. 08 (OMISSIONS)
SUB TOTAL |  | 0
6 % OF GOODS AND SERVICES TAX (GST) |  | 0
GRAND TOTAL |  | 0
PROJECT DURATION ………….(DAYS)

## Cover
BILL OF QUANTITIES
PROJECT: RENOVATION OF EXISTING HEALTH CENTER AT H.DH. KURINBI
CLIENT:MINISTRY OF HEALTH
….JULY 2016