## Cover
Bill of Quantities
N, Kudafaree - MULTIPURPOSE HALL AND 8 CLASS ROOM BLOCK
CLIENT
MINISTRY OF EDUCATION
REPUBLIC OF MALDIVES
PREPARED BY
EPOCH ASSOCIATES PVT LTD

## Summary
PROJECT: N, Kudafaree - MULTIPURPOSE HALL AND 8 CLASS ROOM BLOCK
SUMMARY OF BILL OF QUANTITIES
Bl.no | Item Description | Amount
1 | PRELIMINARIES
2 | GROUND WORKS
3 | CONCRETE WORKS
4 | MASONRY & PLASTERING
5 | FLOORING & TILING
6 | DOORS & WINDOWS
7 | CEILING
8 | PAINTING
9 | METAL WORK
10 | HYDRAULICS & DRAINAGE
11 | ELECTRICAL INSTALLATIONS
12 | FIRE FIGHTING SYSTEM
13 | ADDITIONS
14 | OMISSIONS
| TOTAL Mvr | 0
| 6% GST Mvr | 0
| GRAND TOTAL Mvr | 0

## Boq
PROJECT : N, Kudafaree - MULTIPURPOSE HALL AND 8 CLASS ROOM BLOCK
Item | Description | Unit | Qty | Material Rate | Labour Rate | Total
BILL No: 01
PRELIMINARIES
1.1.0 | General Notes
1 ) | Abbreviations
m - metre
no - numbers
m³ - cubic metre
m² - square metre
m - metre
t - tonnes
incl - including
mm - millimetre
dia - diameter
SS - Stainless Steel
GI - Galvanised Iron
1.2.0 | Site Management Costs
1 ) | Allow for all on and off site management cost including costs of foreman and assistants, temporary services, telephone, fax, hoardings, fences, Crane/Concrete pump, Machinaries and similar items | Item | 1
1.3.0 | Sign Board
1 ) | Allow for sign board. | nos | 1
1.4.0 | SAFETY
1 ) | Safety - Providing and fixing scaffolding with G.I. pipes and clamps and pvc netting alaround building during construction | Item | 1
1.5.0 | Clean-up
1 ) | Allow for clean-up of completed works and site upon completion. | Item | 1
1.6.0 | Insurance, Bonds, Guarantees and Warranties
1 ) | Insurance as stated in the General Consditions. | Item | 1
1.7.0 | As-Built Drawings
1 ) | Preparation and submission of "as-built" Drawings. | Item | 1
BILL No: 01 PRELIMINARIES
TOTAL OF BILL No: 01 - Carried over to summary
BILL NO : 02
GROUND WORK
2.1.0 | General
(a) Rates shall include for: leveling, grading, trimming, compacting to faces of excavation, keep sides plumb, backfilling, consolidating, additional working space and disposing surplus soil.
2.2.0 | Site clearance
| Clearing site - Demolition of Existing building and dispatch all debris, clearing and dispose all unwanted materials away from site and prepare site ready for proposed construction. | m² | 865
2.3.0 | Shoring
| Charges for construction of 150mm thick solid block Masonry wall complete including plastering, below existing adjacent building to protect side buildings. | m² | 50
2.4.0 | Excavation
(a) Excavation quantities are measured to the faces of concrete members. Rates shall include for all additional excavation required to place the formwork , back fill , dewatering and others
2.4.1 | Excavation
1 ) | Foundations F1 | m³ | 106.032
2 ) | Foundations F2 | m³ | 7.776
3 ) | Foundations F3 | m³ | 35.1
4 ) | Foundations F4 | m³ | 42.108
5 ) | Foundations F5 | m³ | 6.468
6 ) | Tie Beam TB | m³ | 95.1
7 ) | Tie Beam WF | m³ | 43.8
2.4.2 | Back filling
(a) Rates shall include for: leveling, grading, trimming and compacting.
(b) Ground need to be compacted to the density required by the consultant
1 ) | 300mm thick highly compacted hard core from Ground floor to below ground floor slab | m² | 865
2 ) | 50mm thick Cement/sand blinding layer (1:10 - Cement & Local Sand mix) to receive damp proof membrane below ground floor slab | m² | 865
2.4.3 | Damp Proof Membrane
(a) Rates shall include for: dressing around and sealing to all penetrations, laps and turnups.
1 ) | Polythene damp proof membrane (500 gauge) laid on blinding layer. | m² | 280.32
BILL No: 02 GROUND WORKS
TOTAL OF BILL No: 02 - Carried over to summary
BILL NO : 03
3.0.0 | CONCRETE
(a) Rates shall include for: placing in position; making good after removal of formwork and casting in all required items; additional concrete required to conform to structural and excavated tolerances.
(b) Mix ratio for reinforced concrete shall be 1:2:3 and lean concrete shall be 1:2:6 by volume.
(c) Quantity is measured to the edges of concrete foundation members. Rates shall be inclusive for any additional concrete required to place the formwork.
3.1.0 | LEAN CONCRETE
50mm thick lean concrete below Foundation
| Foundation Footings & Tie beams | m² | 163.48
3.2.0 | REINFORCED CONCRETE
3.2.1 | FOUNDATIONS
1 ) | Foundations F1 | m³ | 33.135
2 ) | Foundations F2 | m³ | 2.43
3 ) | Foundations F3 | m³ | 8.775
4 ) | Foundations F4 | m³ | 10.527
5 ) | Foundations F5 | m³ | 1.617
6 ) | Tie Beam TB | m³ | 27.7375
7 ) | Tie Beam WF | m³ | 10.95
3.2.2 | GROUND FLOOR
COLUMNS
1 ) | C1 | m3 | 26.6
2 ) | C2 | m3 | 3.6
3 ) | C3 | m3 | 7.25
4 ) | C4 | m3 | 3
STAIRCASE
5 ) | R.c.c. Staircase | m3 | 3.1
R.C.C. GROUND FLOOR SLAB
6 ) | 100mm thick R.C. slab | m3 | 47.36
3.2.3 | FIRST FLOOR
SLAB BEAMS
1 ) | B2 | m3 | 12.925
2 ) | B3 | m3 | 5.6375
3 ) | B4 | m3 | 16.275
FLOOR SLAB
4 ) | 150mm thick R.c.c. Floor Slab | m3 | 46.05
5 ) | 160mm thick R.c.c. Floor Slab | m3 | 12.64
COLUMNS
6 ) | C1 | m3 | 23.275
7 ) | C2 | m3 | 3.15
8 ) | C3 | m3 | 6.3438
9 ) | C4 | m3 | 2.625
STAIRCASE
10 ) | R.c.c. Staircase | m3 | 3.1
3.2.4 | SECOND FLOOR
SLAB BEAMS
1 ) | B1 | m3 | 50.4
2 ) | B1A | m3 | 10.08
3 ) | B2 | m3 | 5.3625
4 ) | B3 | m3 | 1.925
5 ) | B4 | m3 | 13.9125
FLOOR SLAB
6 ) | 150mm thick R.c.c. Floor Slab | m3 | 103.65
COLUMNS
7 ) | C1 | m3 | 23.275
8 ) | C2 | m3 | 3.15
9 ) | C3 | m3 | 6.3438
10 ) | C4 | m3 | 2.625
3.2.5 | ROOF LEVEL
ROOF BEAMS
1 ) | B2 | m3 | 11.4125
2 ) | B2 @ LR& SRB | m3 | 1.375
3 ) | B3 | m3 | 0.9625
4 ) | B3 @ LR& SRB | m3 | 0.9625
5 ) | B4 | m3 | 9.275
6 ) | B4 @ LR& SRB | m3 | 0.81
7 ) | WCB | m3 | 2.28
3.3.0 | FORM WORK
(a) Exposed surface shall have fair finish while remaining may have rough finish.
(b) Timber used for unexposed concrete surface shall sound dressed and seasoned good quality common timber while for exposed concrete surfaces dressedand matched boards uniformly thick and not more than 251mm wide.
c) Plywood used for forms shall be of commercial standard, moisture resistane conrete form plywoodnot lessthan 6mm thick and atleast 12mm thick.
(d) Rates shall include for; all necessary boarding,supports, erecting, framing, temporary cambering cutting, perforations for reinforcing bars, bolts,straps,ties, hangers, pipes and removal of formwork.
3.3.1 | FOUNDATIONS
1 ) | Foundations F1 | m2 | 3.525
2 ) | Foundations F2 | m2 | 2.7
3 ) | Foundations F3 | m2 | 1.8
4 ) | Foundations F4 | m2 | 1.32
5 ) | Foundations F5 | m2 | 0.84
6 ) | Tie Beam TB | m2 | 221.9
7 ) | Tie Beam WF | m2 | 43.8
3.3.2 | GROUND FLOOR
COLUMNS
1 ) | C1 | m2 | 208
2 ) | C2 | m2 | 44.8
3 ) | C3 | m2 | 116
4 ) | C4 | m2 | 48
STAIRCASE
5 ) | R.c.c. Staircase | m2 | 28.5
R.C.C. GROUND FLOOR SLAB
6 ) | 100mm thick R.C. slab including Entrance Steps | m2 | 18.315
3.3.3 | FIRST FLOOR
SLAB BEAMS
1 ) | B2 | m2 | 98.7
2 ) | B3 | m2 | 43.05
3 ) | B4 | m2 | 158.1
FLOOR SLAB
4 ) | 150mm thick R.c.c. Floor Slab | m2 | 307
5 ) | 160mm thick R.c.c. Floor Slab | m2 | 79
COLUMNS
6 ) | C1 | m2 | 182
7 ) | C2 | m2 | 39.2
8 ) | C3 | m2 | 101.5
9 ) | C4 | m2 | 42
STAIRCASE
10 ) | R.c.c. Staircase | m2 | 30
3.3.4 | SECOND FLOOR
SLAB BEAMS
1 ) | B1 | m2 | 244.8
2 ) | B1A | m2 | 48.96
3 ) | B2 | m2 | 40.95
4 ) | B3 | m2 | 14.7
5 ) | B4 | m2 | 135.15
FLOOR SLAB
6 ) | 150mm thick R.c.c. Floor Slab | m2 | 691
COLUMNS
7 ) | C1 | m2 | 182
8 ) | C2 | m2 | 39.2
9 ) | C3 | m2 | 101.5
10 ) | C4 | m2 | 42
3.3.5 | ROOF LEVEL
ROOF BEAMS
1 ) | B2 | m2 | 87.15
2 ) | B2 @ LR& SRB | m2 | 8.5
3 ) | B3 | m2 | 7.35
4 ) | B3 @ LR& SRB | m2 | 5.95
5 ) | B4 | m2 | 90.1
6 ) | B4 @ LR& SRB | m2 | 10.8
7 ) | WCB | m2 | 38
3.4.0 | REINFORCEMENT WORK
(a) Main reinforcement steel shall be high tensile steel hot rolled deformed bars complying with BS 1119 or BS 1172 Characteristic strength not less than 160N/mm2.
(b) Stirrups shall be hot rolled mildsteel round bars complying with BS 1119, Characteristic strength not less than 250N/mm2
(c ) Rates shall include for; distribution steel, cleaning, fabrication, placing, the provision for all necessary temporary fixings, and supports including chairs and tie wire , laps and wastage.
3.4.1 | BELOW GROUND
FOUNDATIONS
1 ) | Foundations F1
| 12mm dia deformed bars - 6m | kg | 1737.1664
2 ) | Foundations F2
| 12mm dia deformed bars - 6m | kg | 415.2384
3 ) | Foundations F3
| 10mm dia deformed bars - 6m | kg | 139.5
4 ) | Foundations F4
| 10mm dia deformed bars - 6m | kg | 40.3441
5 ) | Foundations F5
| 10mm dia deformed bars - 6m | kg | 6.6161
6 ) | Tie Beam TB
| 16mm dia deformed bars - 6m | kg | 2003.44
| 6mm dia deformed bars - 6m | kg | 844.488
7 ) | Tie Beam WF
| 12mm dia deformed bars - 6m | kg | 519.76
| 6mm dia deformed bars - 6m | kg | 172.864
3.4.2 | GROUND FLOOR
COLUMNS
1 ) | C1
| 20mm dia deformed bars - 6m | kg | 2371.2
| 6mm dia deformed bars - 6m | kg | 615.68
2 ) | C2
| 20mm dia deformed bars - 6m | kg | 632.32
| 6mm dia deformed bars - 6m | kg | 132.608
3 ) | C3
| 16mm dia deformed bars - 6m | kg | 1466.24
| 6mm dia deformed bars - 6m | kg | 343.36
4 ) | C4
| 12mm dia deformed bars - 6m | kg | 606.72
| 6mm dia deformed bars - 6m | kg | 142.08
STAIRCASE
5 ) | 10mm dia deformed bars - 6m | kg | 86.8
GROUND FLOOR SLAB
6 ) | 10mm dia deformed bars - 6m | kg | 4557
3.4.3 | FIRST FLOOR
SLAB BEAM
1 ) | B2
| 20mm dia deformed bars - 6m | kg | 1393.08
| 12mm dia deformed bars - 6m | kg | 167.32
| 6mm dia deformed bars - 6m | kg | 534.2208
2 ) | B3
| 20mm dia deformed bars - 6m | kg | 405.08
| 10mm dia deformed bars - 6m | kg | 50.84
| 6mm dia deformed bars - 6m | kg | 116.5056
3 ) | B4
| 16mm dia deformed bars - 6m | kg | 1837.68
| 6mm dia deformed bars - 6m | kg | 396.4032
FLOOR SLAB
| 10mm dia deformed bars - 6m | kg | 5952
COLUMNS
4 ) | C1
| 20mm dia deformed bars - 6m | kg | 2074.8
| 6mm dia deformed bars - 6m | kg | 538.72
5 ) | C2
| 20mm dia deformed bars - 6m | kg | 553.28
| 6mm dia deformed bars - 6m | kg | 116.032
6 ) | C3
| 16mm dia deformed bars - 6m | kg | 1282.96
| 6mm dia deformed bars - 6m | kg | 300.44
7 ) | C4
| 12mm dia deformed bars - 6m | kg | 530.88
| 6mm dia deformed bars - 6m | kg | 124.32
STAIRCASE
8 ) | 10mm dia deformed bars - 6m | kg | 86.8
3.4.4 | SECOND FLOOR
SLAB BEAM
1 ) | B1
| 25mm dia deformed bars - 6m | kg | 8870.4
| 16mm dia deformed bars - 6m | kg | 910.08
| 6mm dia deformed bars - 6m | kg | 1150.848
2 ) | B1A
| 25mm dia deformed bars - 6m | kg | 1774.08
| 16mm dia deformed bars - 6m | kg | 182.016
| 6mm dia deformed bars - 6m | kg | 230.1696
3 ) | B2
| 20mm dia deformed bars - 6m | kg | 1393.08
| 12mm dia deformed bars - 6m | kg | 167.32
| 6mm dia deformed bars - 6m | kg | 534.2208
4 ) | B3
| 20mm dia deformed bars - 6m | kg | 405.08
| 10mm dia deformed bars - 6m | kg | 50.84
| 6mm dia deformed bars - 6m | kg | 116.5056
5 ) | B4
| 16mm dia deformed bars - 6m | kg | 1837.68
| 6mm dia deformed bars - 6m | kg | 396.4032
FLOOR SLAB
6 ) | 10mm dia deformed bars - 6m | kg | 12152
COLUMNS
7 ) | C1
| 20mm dia deformed bars - 6m | kg | 2074.8
| 6mm dia deformed bars - 6m | kg | 538.72
8 ) | C2
| 20mm dia deformed bars - 6m | kg | 553.28
| 6mm dia deformed bars - 6m | kg | 116.032
9 ) | C3
| 16mm dia deformed bars - 6m | kg | 1282.96
| 6mm dia deformed bars - 6m | kg | 300.44
10 ) | C4
| 12mm dia deformed bars - 6m | kg | 530.88
| 6mm dia deformed bars - 6m | kg | 124.32
3.4.5 | ROOF BEAMS
ROOF BEAMS
1 ) | B2
| 20mm dia deformed bars - 6m | kg | 1230.06
| 12mm dia deformed bars - 6m | kg | 147.74
| 6mm dia deformed bars - 6m | kg | 471.7056
B2 @ LR& SRB
| 20mm dia deformed bars - 6m | kg | 148.2
| 12mm dia deformed bars - 6m | kg | 17.8
| 6mm dia deformed bars - 6m | kg | 49.728
2 ) | B3
| 16mm dia deformed bars - 6m | kg | 88.48
| 6mm dia deformed bars - 6m | kg | 33.152
B3 @ LR& SRB
| 16mm dia deformed bars - 6m | kg | 88.48
| 6mm dia deformed bars - 6m | kg | 29.008
3 ) | B4
| 16mm dia deformed bars - 6m | kg | 1047.28
| 6mm dia deformed bars - 6m | kg | 225.9072
4 ) | B4 @ LR& SRB
| 16mm dia deformed bars - 6m | kg | 177.84
| 6mm dia deformed bars - 6m | kg | 28.7712
5 ) | WCB
| 12mm dia deformed bars - 6m | kg | 270.56
| 6mm dia deformed bars - 6m | kg | 94.4832
FLOOR SLAB
6 ) | 10mm dia deformed bars - 6m | kg | 370.3467
3.4.6 | OTHER CONCRETE WORKS
a ) | WINDOW SILL & LINTELS
| Charges for construction of R.c.c. Sills and Lintels for the windows and doors as per details. Rate shall include for shuttering and Reinforcement works complete. | item | 1
b ) | PARAPET WALL
| Charges for construction of 100mm thick R.c.c.Parapet wall at First floor and Second floor as per details. (Refer drawing no:A 18) Rate shall include for Shuttering and Reinforcement work complete. | item | 1
d ) | GROUND WATER WELL
| Charges for Construction and Installation of 1200mm dia. R.c.c. Ground water well, Base slab & Top cover slab as per drawing details. Rate shall include for; Excavation, form work, reinforcement, Lifting hooks, gravel filling etc complete. | item | 1
e ) | WASH BASIN COUNTER SLAB
| Charges for Construction and Installation of 75mm thick R.c.c. Counter slab for washbasin at Toilet block (Ground floor, First floor and Second floor) as per drawing details. Rate shall include for; form work, reinforcement etc complete. | item | 1
3.4.7 | WATER PROOFING & ADD MIXTURES
(a) | Apply Rubberised bitumin water proofing paint, Moya Shield RBE, 2 coats to all exposed concrete and masonry surface below ground level. | item | 1
(b) | Add approved water proofing admixture Mega Add WL1 as per specification to all concrete below ground level. | item | 1
(c) | Add Plasticiser admixture Mega Flow P as per specification to all concrete Substreucture and Super structure. | item | 1
BILL No: 03 - CONCRETE WORKS
TOTAL OF BILL No: 03 - Carried over to summary
BILL No: 04
MASONRY AND PLASTERING
4.0.0 | General
a )Rates shall include for cleaning out cavities, forming rebated reveals and pointing and cleaning down to reveals where necessary; fractional size blocks, all necessary machine cutting, cutting or forming chases or edges of floor slabs.
b )Cutting or leaving holes and openings as recesses for and building in pipes, conduits , sleeves and similar as required for all trades; leaving surfaces rough or raking out joints for plastering and flashings, bedding frames or plates, building in joints.
c ) All external wall and all inetrenal walls shall be 100mm thick Solid cement blocks and for masonry mix ratio 1:5 (cement and river sand)
4.1.0 | MASONRY
4.1.1 | BELOW GROUND LEVEL
1 ) | 150mm thick Solid block wall
a ) | 300 x150 x 150mm solid block single wall - 150mm thick above all Tie beams. | m2 | 468
4.1.2 | GROUND FLOOR
1 ) | External walls
a ) | 300x150x150mm solid block single wall - 150mm thick | m2 | 240.96
2 ) | Interior walls
a ) | 300x150x150mm solid block single wall - 150mm thick | m2 | 144
4.1.3 | FIRST FLOOR
1 ) | External walls
a ) | 300x150x150mm solid block single wall - 150mm thick | m2 | 231.42
2 ) | Interior walls
a ) | 300x150x150mm solid block single wall - 150mm thick | m2 | 54
4.1.4 | SECOND FLOOR
1 ) | External walls
a ) | 300x150x200mm solid block single wall - 200mm thick | m2 | 179.11
2 ) | Interior walls
a ) | 300x150x200mm solid block single wall - 200mm thick | m2 | 314.87
4.1.5 | ABOVE ROOF BEAM
1 ) | External walls 150mm thick
a ) | 300x150x150mm solid block wall | m2 | 118
4.2.0 | PLASTERING
(a) 20mm thick Cement plastering on Exterior surface of External masonry walls and concrete surfaces and 15mm thick plastering on interior walls and concrete surface as specified incl. wire mesh shall be fixed at the joints of concrete surfaces and walls before plastering. Quantity is measured including concrete surfaces - Parapetwalls, Liftwalls, columns & beams.
(b)Rates shall include for External plastering shall 20mm thick (12+8mm) 2 coats in 1:4 cement and river sand mix ratio
c) Rates shall include for approved brand water proofing compound shall be mixed with cement mortar for external wall plastering as per manufacturers specifications.
4.2.1 | BELOW GROUND LEVEL
1 ) | 15mm thick Plastering
a ) | Both surface of below ground walls | m2 | 936
4.2.2 | GROUND FLOOR
1 ) | External Plastering
a ) | External surface of exeterior wall | m2 | 240.96
2 ) | Internal Plastering
a ) | Internal surface of external wall and both surface of Interior walls | m2 | 528.96
4.2.3 | FIRST FLOOR
1 ) | External Plastering
a ) | External surface of exeterior wall | m2 | 231.42
2 ) | Internal Plastering
a ) | Internal surface of external wall and both surface of Interior walls | m2 | 339.42
4.2.4 | SECOND FLOOR
1 ) | External Plastering
a ) | External surface of exeterior wall | m2 | 195.55
2 ) | Internal Plastering
a ) | Internal surface of external wall and both surface of Interior walls | m2 | 759.55
4.2.5 | ROOF LEVEL
1 ) | External Plastering
a ) | External surface of exeterior wall | m2 | 118
2 ) | Internal Plastering
a ) | Internal surface of external wall | m2 | 118
BILL No: 04 - MASONRY AND PLASTERING
TOTAL OF BILL No: 04 - Carried over to summary
BILL N0: 05
FLOORING & TILING
5.0.0 | General
(a) Rates shall include for laying 50mm thick cement mortar in 1 : 5 mix ratio,cleaning down to reveals where necessary and water proofing of Toilet and Balcony floors & Terrace.
5.1.0 | SCREEDING
50mm thick Floor Screeding
5.1.1 | GROUND FLOOR
1 ) | Hall Area | m2 | 392.94
2 ) | Corridor Area | m2 | 225.32
3 ) | Store | m2 | 21
4 ) | Changing room | m2 | 10.92
5 ) | Toilet | m2 | 20.85
6 ) | Staircase | m2 | 16.93
5.1.2 | FIRST FLOOR
1 ) | Corridor | m2 | 258.66
2 ) | Store | m2 | 7
3 ) | Control room | m2 | 6.95
4 ) | Cat walk | m2 | 73.42
5 ) | Staircase | m2 | 16.93
5.1.3 | SECOND FLOOR
1 ) | Class rooms | m2 | 427.88
2 ) | Balcony & Corridor | m2 | 189.19
3 ) | Janitor Store | m2 | 9.55
4 ) | Store | m2 | 13.82
5 ) | Toilet | m2 | 16.41
5.2.0 | TILING
(a) Rates shall include for: Fixing, bedding, grouting, and pointing materials, making good around pipes, sanitary fixtures, and similar; cleaning & Polishing.
(b) All Tiling work in accordance with specifications and finishes schedule.
(c) Tiles rate shall be given as specified in the drawing.
5.2.1 | GROUND FLOOR
FLOOR TILING
1 ) | Changing Rm (F) | m2 | 5.19
2 ) | Changing Rm (M) | m2 | 5.73
3 ) | Store 1 | m2 | 14.31
4 ) | Store 2 | m2 | 5.9
5 ) | Toilet (F) | m2 | 7.12
6 ) | Toilet (M) | m2 | 13.73
WALL TILING
7 ) | Toilet walls @ 3M height | m2 | 66
8 ) | Wash room walls @ 3m H | m2 | 30
5.2.2 | FIRST FLOOR
FLOOR TILING
1 ) | Controll Room | m2 | 6.95
2 ) | Store 3 | m2 | 7
5.2.3 | SECOND FLOOR
FLOOR TILING
1 ) | Class 01 | m2 | 53.13
2 ) | Class 02 | m2 | 52.84
3 ) | Class 03 | m2 | 52.9
4 ) | Class 04 | m2 | 54.07
5 ) | Class 05 | m2 | 53.78
6 ) | Class 06 | m2 | 53.78
7 ) | Class 07 | m2 | 54.16
8 ) | Class 08 | m2 | 53.22
9 ) | Janitor Store 1 | m2 | 4.49
10 ) | Janitor Store 2 | m2 | 5.06
11 ) | Store 4 | m2 | 13.82
12 ) | Toilet (F) | m2 | 7.99
13 ) | Toilet (M) | m2 | 8.42
WALL TILING
14 ) | Toilet walls @ 3M height | m2 | 54
15 ) | Wash room walls @ 3m H | m2 | 48
5.3.1 | WATER PROOFING
Apply 2 coats of Water proofing Compound, on wet surfaces - Toilets, Balcony and Terrace Floors.
1 ) | Toilets | item | 1
2 ) | Corridor | item | 1
5.4.1 | TILE ADHESIVE
| Charges for supplying special tiles grout for fixing tiles to all floors. | item | 1
BILL No: 05 -FLOORING AND TILING
TOTAL OF BILL No: 05 - Carried over to summary
BILL N0: 06
DOORS AND WINDOWS
6.0.0 | General
(a) Rates shall include for locks, latches, closers, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware.
(b) Rates shall include for door frames and window frames, mullions, transoms, trims, glazing, tinting, timber panels, boardings, framing, lining, fastenings and all fixings and installation.
(c) All Timber door frames shall be treated timber. Rate shall include for Paint/Varnish finish.
(d) All louvres, windows and sliding doors shall be 30 micron powder coated aluminium as per details given in Door/Window schedule.
(e) All doors and windows shall be accordance with door/window drawing details.
6.1.1 | DOOR AND WINDOW FOR THE WHOLE BUILDING
DOOR AND WINDOW UNITS
1 ) | D01 | nos | 7
2 ) | D02 | nos | 2
3 ) | D03 | nos | 16
4 ) | D04 | nos | 9
5 ) | D05 | nos | 1
6 ) | D06 | nos | 3
7 ) | D07 | nos | 6
8 ) | D08 | nos | 8
9 ) | D09 | nos | 2
11 ) | W01 | nos | 15
12 ) | W02 | nos | 3
13 ) | W03 | nos | 4
14 ) | W04 | nos | 6
15 ) | W05 | nos | 7
16 ) | W06 | nos | 8
17 ) | W07 | nos | 16
BILL N0: 06 - DOORS AND WINDOWS
TOTAL OF BILL No: 06 - Carried over to summary
BILL No: 07
WOOD WORK & CEILING
7.0.0 | General
(a) Rates shall include for: all labour in framing, notching and fitting around projections, pipes, light fittings, hatches, grilles and similar and complete with cleats, packers, wedges and similar and all nails,bolts & screws.
(b) Rates shall include for applying approved quality wood preservators as per manufactures instructions for all Timber structures.
(c) Rates shall include for 9mm thick Cement board fixed on 35 x 50mm Timber frame,trimming, nails, screws,hooks, hangers, clips and similar.
7.1.1 | GROUND FLOOR
CEILING
1 ) | Toilet (F) | m2 | 7.12
2 ) | Toilet (M) | m2 | 13.73
7.1.2 | SECOND FLOOR
CEILING
1 ) | Class 01 | m2 | 53.13
2 ) | Class 02 | m2 | 52.84
3 ) | Class 03 | m2 | 52.9
4 ) | Class 04 | m2 | 54.07
5 ) | Class 05 | m2 | 53.78
6 ) | Class 06 | m2 | 53.78
7 ) | Class 07 | m2 | 54.16
8 ) | Class 08 | m2 | 53.22
9 ) | Janitor Store 1 | m2 | 4.49
10 ) | Janitor Store 2 | m2 | 5.06
11 ) | Store 4 | m2 | 13.82
12 ) | Toilet (F) | m2 | 7.99
13 ) | Toilet (M) | m2 | 8.42
7.2.1 | WOOD WORK
1 ) | Timber Fascia Board: Supply and Fixing 25 x 250mm wide Timber Fascia board complete including Paint finishes. | mtr | 70
7.3.1 | STAGE WORK
1 ) | Stage work as detail given in the drawing | item | 1
BILL No: 07 - WOOD WORK & CEILING
TOTAL OF BILL No: 07 - Carried over to summary
BILL No: 08
PAINTING
8.0.0 | General
(a) Rates shall include for: the provision, erection and removal of scaffolding, preparation, rubbing down between coats and similar work, the protection and/or masking floors, fittings and similar work, removing and replacing door and window furniture.
(b) All painting work shall be carried in accordance with the Specifications
(c)Rate shall include for weather proof paint finish for exterior surfaces of the wall complete including application of two coats of oil based wall sealer and two coats of weather bond paint
(d)Rate shall include for putty and paint finish for interior surfaces of the wall and ceilings complete including application of two coats of wall sealer, two coats of putty finish and two coats of emulsion paint finish on top for Interior painting.
8.1.1 | GROUND FLOOR
1 ) | Painting exterior surfaces of External Wall, Columns & beams. | m2 | 240.96
2 ) | Painting interior surfaces Wall, Columns & beams) | m2 | 528.96
3 ) | Painting Soffit of slab (Ceiling) | m2 | 650
8.2.1 | FIRST FLOOR
1 ) | Painting exterior surfaces of External Wall, Columns & beams. | m2 | 231.42
2 ) | Painting interior surfaces Wall, Columns & beams) | m2 | 339.42
3 ) | Painting Soffit of slab (Ceiling) | m2 | 347
8.3.1 | SECOND FLOOR
1 ) | Painting exterior surfaces of External Wall, Columns & beams. | m2 | 179.11
2 ) | Painting interior surfaces Wall, Columns & beams) | m2 | 759.55
3 ) | Painting Soffit of slab (Ceiling) | m2 | 365
8.4.1 | ROOF LEVEL
1 ) | Painting exterior surfaces of External Wall, Columns & beams. | m2 | 118
2 ) | Painting interior surfaces Wall, Columns & beams) | m2 | 118
3 ) | Eave Ceiling | m2 | 70
BILL No: 08 - PAINTING
TOTAL OF BILL No: 08 - Carried over to summary
BILL No: 09
METAL WORK
9.0.0 | General
(a) Rates shall include for ; all labour in framing, cutting, welding, cleats, baseplates, flanges,screws, nails, bends, and similar complete with grinding, surface smoothening and polish finishes.
9.1.0 | RAILING
9.1.1 | GROUND FLOOR
1 ) | GI. Railing - Staircase | nos
a ) | Supply, Fabrication and Fixing GI.S.Railing -Staircase as per details | item | 1
9.1.2 | FIRST FLOOR
1 ) | GI. Railing - BALCONY | nos
a ) | Supply, Fabrication and Installation of GI.Railing - Staircase as per details (Refer drawing - A12) | item | 1
2 ) | GI. Railing - Staircase | nos
a ) | Supply, Fabrication and Fixing GI.S.Railing -Staircase as per details | item | 1
9.1.3 | SECOND FLOOR
1 ) | GI. Railing - BALCONY | nos
a ) | Supply, Fabrication and Installation of GI.Railing - Staircase as per details (Refer drawing - A12) | item | 1
9.2.1 | ROOFING
Roof Truss - Supply, Fabrication and Fixing Roof Trusses complete with Base plates, Bolts, nuts, Washers etc including Paint Finishes. Refer drawing details
1 ) | TR1 (21.6m) | nos | 10
2 ) | BR1 (3.2m) | nos | 9
3 ) | Supply and Fixing C - Purlins 50x100x2.5mm C purlins @ 900 C/C (36m) | nos | 28
4 ) | Roof Covering - Supply and Fixing BHP Lysaght Roofing sheet | m2 | 810
5 ) | 50mm thick double side Aluminium Foiled Rock wool Insulation laid as heat resistant below roofing sheet. | m2 | 810
6 ) | 25mm grid G.I. mesh laid as support to under the Rock wool insulation | m2 | 810
7 ) | Capping - Supply and Fixing 600mm wide Lysaght Ridge Capping | mtr | 36
8 ) | Capping - Supply and Fixing 600mm wide Lysaght Flashing at Gable ends | mtr | 27
9 ) | Gutter - Supply and Fixing 150 x 200mm Lysaght Gutter complete including brackets and clips. | mtr | 72
BILL No: 09 - METAL WORK
TOTAL OF BILL No: 09 - Carried over to summary
BILL No: 10
HYDRAULICS & DRAINAGE
10.0.0 | General
(a) Design provide and install plumbing network for the entire building complete in accordance to standard set by the local governing body MWSC
(b) The following items and description and the plumbing drawings are given as guidance as to the nature of the information to be returned by the contractor.
(c) Ground water connection shall be made as specified in the drawings.
(d) The cost shall include for; sockets, running joints, connectors, elbows, junctions, reducers, expansion joints, back nuts and similar, incidental fittings, clips, saddles, brackets, straps, hangers, screws, nails , pvc glues, threadseals and fixing complete, including cutting and forming holes, excavating, laying pipes , backfilling trenches.
(e) All pipes shall be High Pressure uPVC "Mutha" or equivalent brand.
10.1.0 | GROUND FLOOR
10.1.1 | HYDRAULICS
a ) | Charges for Piping for fresh water Pipe work | item | 1
b ) | Charges for Piping for Ground water supply pipe work. | item | 1
c ) | Charges for Providing and Fixing Heavy duty water pump Davey brand for Ground water supply to all floors - ground water net work. | nos | 1
10.1.2 | SANITARY FIXTURES &ACCESSORIES
1 ) | Basin Faucet | nos | 3
2 ) | Bidet Shower | nos | 4
3 ) | Wash Basin | nos | 3
4 ) | Water Closet | nos | 4
5 ) | Gate Valve | nos | 5
6 ) | Floor Drain | nos | 4
7 ) | Gully Trap | nos | 1
8 ) | Manhole | nos | 1
9 ) | Bottle Trap | nos | 3
10 ) | Clean Out Point | nos | 2
11 ) | Angle Valve with Cap for Water Closet from Ground Water Supply | nos | 4
10.1.3 | DRAINAGE
1 ) | SEWERAGE & DRAINAGE: Charges for piping for all discharge pipes, sewerage and drainage pipes including connection Main junctions from the Fixtures. | item | 1
2 ) | INSPECTION CHAMBERS: Charges for construction and Pipe connection of Inspection chambers as per drawing | item | 1
3 ) | SOAK PIT : Charges for Construction and Installation of 1800mm dia. R.c.c. Soak Pit as per drawing details. Rate shall include for; Excavation, form work, reinforcement, Lifting hooks, gravel filling etc complete. | item | 1
10.2.0 | FIRST FLOOR
10.2.1 | HYDRAULICS
1 ) | Charges for Piping for fresh water Pipe work | item | 1
2 ) | Charges for Piping for Ground water supply pipe work. | item | 1
10.2.2 | SANITARY FIXTURES &ACCESSORIES
1 ) | Floor Drain | nos | 4
10.2.3 | DRAINAGE
1 ) | SEWERAGE & DRAINAGE: Charges for piping for all discharge pipes, sewerage and drainage pipes including connection Main junctions from the Fixtures. | item | 1
10.3.0 | SECOND FLOOR
10.3.1 | HYDRAULICS
1 ) | Charges for Piping for fresh water Pipe work | item | 1
2 ) | Charges for Piping for Ground water supply pipe work. | item | 1
10.3.2 | SANITARY FIXTURES &ACCESSORIES
1 ) | Basin Faucet | nos | 2
2 ) | Bidet Shower | nos | 4
3 ) | Wash Basin | nos | 2
4 ) | Water Closet | nos | 4
5 ) | Gate Valve | nos | 6
6 ) | Floor Drain | nos | 6
7 ) | Gully Trap | nos | 2
8 ) | Bottle Trap | nos | 2
9 ) | Angle Valve with Cap for Water Closet from Ground Water Supply | nos | 4
10.3.3 | DRAINAGE
1 ) | SEWERAGE & DRAINAGE: Charges for piping for all discharge pipes, sewerage and drainage pipes including connection Main junctions from the Fixtures. | item | 1
10.4.0 | ROOF LEVEL
10.4.1 | DRAINAGE
1 ) | RAINWATER DOWN PIPES: Charges for piping for all discharge pipes and Drainage pipes including fittings and fixtures from the Gutter to Ground floor. | item | 1
BILL No: 10 - HYDRAULICS AND DRAINAGE
TOTAL OF BILL No: 10 - Carried over to summary
BILL No: 11
ELECTRICAL INSTALLATIONS
11.0.0 | General
(a) Rates shall include for: screws, nails, bolts, nuts, standard cable fixing or supporting clips, brackets, straps, rivets, plugs and all incidental accessories
(b) Rates for work in trench shall include for: excavation, maintaining faces of excavations, backfilling, compaction, appropriate cable covers, warning tape and disposal of surplus spoil
(c) Rates shall include for electrical conduits, fittings, equipment and similar all fixings to various building surfaces and also all elecetrical work shall be carried out according to STELCO standards and specifications.
(d) Each Light/ light fixture and its switch is measured as one one point; similarly each fan or each socket outlet is measured as one point;
(e) Rates shall include for supply and complete installation of fittings and fixtures.
11.1.0 | GROUND FLOOR
11.1.1 | ELECTRIC BOARDS
1 ) | Supply and Installation of Utility Regulatory Authority approved Main Panel Board with kWh Meter | item | 1
2 ) | Wiring connection to Main Panel Board from Main Electricity network | item | 1
3 ) | Supply and Installation of Utility Regulation Authority approved brand Distribution board | nos | 2
11.1.2 | ELECTRIC FIXTURES
1 ) | Ceiling Light (12W) | nos | 6
2 ) | Ceiling Light (18W) | nos | 2
3 ) | Recessed Ceiling Light (12W) | nos | 7
4 ) | Weather Proof Wall Light IP55 (12W) | nos | 20
5 ) | Ceiling Mounted Exhaust Fan | nos | 4
6 ) | Light Switch (1 Gang ) | nos | 8
7 ) | Light Switch (2 Gang ) | nos | 6
8 ) | Light Switch (3 Gang ) | nos | 3
9 ) | Light Switch (4 Gang ) | nos | 14
10 ) | Light Switch (5 Gang ) | nos | 12
11 ) | 13A Power Socket | nos | 9
12 ) | 13A Twin Socket | nos | 31
13 ) | Emergency Light | nos | 9
14 ) | Wall Mounted Speaker | nos | 10
11.1.3 | ELECTRICAL WIRING
1 ) | 2.5mm2 Wiring to Light Points | points | 82
2 ) | 2.5mm2 Wiring to Power Points | points | 40
3 ) | 16mm2 Cabling to DBs | item | 2
4 ) | Cabling - Connection of speaker to public address system | points | 10
11.2.0 | FIRST FLOOR
11.2.1 | ELECTRIC BOARDS
1 ) | Supply and Installation of Utility Regulatory Authority approved brand Distribution board |  | 1
11.2.2 | ELECTRIC FIXTURES
1 ) | Ceiling Light (12W) | nos | 5
2 ) | Ceiling Light (18W) | nos | 2
3 ) | Weather Proof Wall Light IP55 (12W) | nos | 18
4 ) | 2 x 50W PLL Tube Light | nos | 52
5 ) | 48 inch To 48 inch Ceiling Fan | nos | 40
6 ) | Light Switch (1 Gang ) | nos | 2
7 ) | Light Switch (3 Gang ) | nos | 3
8 ) | 13A Power Socket | nos | 8
9 ) | 13A Twin Socket | nos | 15
10 ) | Computer Network Outlet | nos | 1
11 ) | Emergency Light | nos | 8
12 ) | Telephone Outlet | nos | 1
13 ) | Public Address System | nos | 1
14 ) | Wall Mounted Speaker | nos | 4
11.2.3 | ELECTRICAL WIRING
1 ) | 2.5mm2 Wiring to Light Points | points | 122
2 ) | 2.5mm2 Wiring to Power Points | points | 23
3 ) | 16mm2 Cabling to DBs | item | 1
4 ) | Cabling - Telephone points | points | 1
5 ) | Cabling - Data Network points (CAT6) | points | 1
6 ) | Cabling - Connection of speaker to public address system | points | 4
11.3.0 | SECOND FLOOR
11.3.1 | ELECTRIC BOARDS
1 ) | Supply and Installation of Utility Regulatory Authority approved brand Distribution board | nos | 10
11.3.2 | ELECTRIC FIXTURES
1 ) | Ceiling Down Light (18W) - Weather Proof | nos | 14
2 ) | Ceiling Light (12W) | nos | 3
3 ) | Ceiling Light (18W) | nos | 4
4 ) | Recessed Ceiling Light (12W) | nos | 6
5 ) | 3 Ft Led Tube Light | nos | 72
6 ) | 42 inch To 48 inch Ceiling Fan | nos | 48
7 ) | Ceiling Mounted Exhaust Fan | nos | 4
8 ) | Light Switch (1 Gang ) | nos | 4
9 ) | Light Switch (2 Gang ) | nos | 8
10 ) | Light Switch (3 Gang ) | nos | 1
11 ) | Light Switch (4 Gang ) | nos | 2
12 ) | Light Switch (5 Gang ) | nos | 24
13 ) | 13A Power Socket | nos | 11
14 ) | 13A Twin Socket | nos | 35
15 ) | Computer Network Outlet | nos | 8
16 ) | Emergency Light | nos | 13
17 ) | HDMI Socket | nos | 32
18 ) | Wall Mounted Speaker | nos | 8
11.3.3 | ELECTRICAL WIRING
1 ) | 2.5mm2 Wiring to Light Points | points | 190
2 ) | 2.5mm2 Wiring to Power Points | points | 46
3 ) | 16mm2 Cabling to DBs | item | 10
4 ) | Cabling - Data Network points (CAT6) | points | 8
5 ) | Cabling - HDMI Points | points | 32
6 ) | Cabling - Connection of speaker to public address system | points | 8
BILL No: 11 - ELECTRICAL INSTALLATIONS
TOTAL OF BILL No: 11 - Carried over to summary
BILL No: 12
FIRE FIGHTING SYSTEM
12.0.0 | GENERAL
a )Rates shall include for: sockets, running joints, connectors, elbows, junctions, reducers, expansion joints, back nuts, and similar incidental fittings, clips, saddles, brackets, straps, hangers screws nails and fixing complete including cutting and forming holes.
b ) Rate shall include for pipe works and inner and outer surface of all pipe work shall be galvanized steel.
c )All wiring and pipe work shall be done as specified in the drawing.
d )Shop drawings of the system shall be prepared to the standard of the government's relevant authority and submitted to the Consultant for approval.
12.1.0 | FIRE ALARM SYSTEM
Heat Resistant cable shall be laid for connecting the detectors.
12.1.1 | GROUND FLOOR
1 ) | CO2 Extinguisher (load 2kg) In Polycarbonate Enclosure | nos | 5
2 ) | H2O Extinguisher (load 9L) In Polycarbonate Enclosure | nos | 5
3 ) | Manual Call Point | nos | 12
4 ) | Smoke Detector | nos | 4
5 ) | Beacon | nos | 2
6 ) | Sounder Bell | nos | 1
7 ) | End Of Line Resistance | nos | 1
8 ) | Exit Sign | nos | 12
9 ) | Fire Alarm Control Panel |  | 1
12.1.2 | FIRST FLOOR
1 ) | CO2 Extinguisher (load 2kg) In Polycarbonate Enclosure | nos | 3
2 ) | H2O Extinguisher (load 9L) In Polycarbonate Enclosure | nos | 3
3 ) | Manual Call Point | nos | 7
4 ) | Smoke Detector | nos | 2
5 ) | Beacon | nos | 1
6 ) | Sounder Bell | nos | 1
7 ) | Exit Sign | nos | 11
12.1.3 | SECOND FLOOR
1 ) | CO2 Extinguisher (load 2kg) In Polycarbonate Enclosure | nos | 2
2 ) | H2O Extinguisher (load 9L) In Polycarbonate Enclosure | nos | 2
3 ) | Manual Call Point | nos | 2
4 ) | Smoke Detector | nos | 11
5 ) | Beacon | nos | 2
6 ) | Sounder Bell | nos | 1
7 ) | Exit Sign | nos | 4
BILL No: 12 - FIRE FIGHTING SYSTEM
TOTAL OF BILL No: 12 - Carried over to summary
BILL No: 13
ADDITIONS
13.1 | General
Provision to include quantities as per the drawing which is missed in the bill of quantities.
BILL No: 13 - ADDITIONS
TOTAL OF BILL No: 13 - Carried over to summary
BILL No: 14
OMISSIONS
14.1 | General
Provision to remove the excess quantity given in the bill quantities if any as per the drawing details
BILL No: 14 - OMISSIONS
TOTAL OF BILL No: 14 - Carried over to summary