## Summary
c
ACCOMODATION BUILDING
CLIENT:
SUMMARY SHEET
DATE: 18/01/18
BOQ - SUMMARY
No. | Description |  | Amount
1 | SITE MANAGEMENT
Site management cost for concrete works
Site management cost for Finishing works
2 | GROUND WORKS
Ground works
3 | FOUNDATION WORK
Concrete Works
4 | GROUND FLOOR
Concrete Works
Masonry , plastering & finishing work
5 | FIRST FLOOR
Concrete Works
Masonry , plastering & finishing work
6 | SECOND FLOOR
Concrete Works
Masonry , plastering & finishing work
7 | THIRD FLOOR
Concrete Works
Masonry , plastering & finishing work
8 | TERRACE FLOOR
Concrete Works
Masonry , plastering & finishing work
9 | MISCELLANEOUS WORK
10 | ADDITION & OMMISION
TOTAL FOR CONCRETE
TOTAL FOR MASONRY, PLASTERING & FINISHING
TOTAL FOR MISCELLANEOUS WORK
SUB TOTAL
6% OF G.S.T
GRAND TOTAL
| DURATION | Months
| Building completion |  |  | 0

## SPEC (hidden)
| PROJECT: | #REF!
| CLIENT: | #REF!
MATERIALS SPECIFICATIONS SUMMARY
SN | Details
1 | Masonry Works
1.01 | Mortar Mix 1:5, External wall, Municipality Solid Blocks (200X 100 X 65 MM)
1.02 | Mortar Mix 1:5, Internal wall, Municipality Hollow Blocks (300 X 100 X 150 MM)
1.03 | Imported Sand and Standard Portland Cement will be used
2 | Plastering
2.01 | Mortar Mix 1:4, External wall, 2 Coat Plastering (12mm First coat, 6mm Second Coat)
2.02 | Mortar Mix 1:4, Internal wall, 1 Coat Plastering (12mm First coat)
2.03 | Plastic Net will be used in every masonry wall and concrete joints
2.04 | Imported Sand and Standard Portland Cement will be used
3 | Screeding
3.01 | Mortar Mix 1:5, (Screeding thickness will be 35-75mm)
3.02 | Imported Sand and Standard Portland Cement will be used
4 | Concrete
4.01 | Foundation
4.02 | An approved, application of water proofing will be applied on foundation / substructures
4.03 | All concrete works will be completed with approved admixture (Sika Plastocrete Plus)
5 | Form work
5.01 | Formwork will be done in new 12mm plywood and timber
6 | Reinforcements in Concrete
6.01 | Reinforcement in structures will be used, good condition reinforc. available in market
7 | Services and Finishes
7.01 | W/C Price from 2000 to 1500 rufiyaa
7.02 | Wash Basin from 1000 to 500 rufiyaa
7.03 | Ceramic tiles 300x300 tiles shall be not higher then 10 rufiyaa
7.04 | Ceramic tiles 200x200 tiles shall be not higher then 6 rufiyaa
7.05 | Ceramic tiles 200x250 tiles shall be not higher then 7 rufiyaa
7.06 | All other Sanitary Fixtures shall be normal standard
7.07 | All tiles design and colour shall be approved by client
7.08 | POFF HYGURAD or Equivalent shall be used in toilets
7.09 | Staircase and Balconies Handrails shall be S.S pipes
7.1 | Paint shall be used Nipon or equivalent, (Sealer L/ 98 rufiyaa, Paint L/ 115 rufiyaa)
7.11 | Electrical wires shall be approved by STELCO
7.12 | Light Fixtures will be approved by client, (not exceeding Price in BOQ)
7.13 | Switches shall be CLIPSAL or ABB or or Equivalent
7.14 | Aluminium windows, section thk 1.3mm 72mm outer frame, (Colour: brown anodised)
7.15 | Doors shall be Timber Doors (Complete finish in BOQ price)

## MATER (hidden)
| PROJECT: | #REF!
| CLIENT: | #REF!
MAIN MATERIALS
SN | Details
Note: The BOQ is given based on the Main Materials Prices Below,
| Price on Date: |  | 1st March 2009
| Main Supplier: |  | STO Conctruction Materials,
MAJOR MATERIALS
1 | CEMENT BAG |  |  | 95
1.01 | SAND BAG |  |  | 40
1.02 | AGGRIGATE BAG |  |  | 40
1.03 | 6mm Dia. PLAIN STEEL BAR 6 METER |  |  | 31
1.04 | 10mm Dia. DEFORMED STEEL BAR 6 METER |  |  | 74
1.05 | 12mm Dia. DEFORMED STEEL BAR 6 METER |  |  | 105
1.06 | 16mm Dia. DEFORMED STEEL BAR 6 METER |  |  | 198
1.07 | 20mm Dia. DEFORMED STEEL BAR 6 METER |  |  | 280
1.08 | 25mm Dia. DEFORMED STEEL BAR 6 METER |  |  | 460
1.09 | 12mm Plywood |  |  | 340
1.1 | Timber (2" x 6" x 12') |  |  | 235
1.11 | Municipality Solid Blocks (2"x4"x8") |  |  | 2
1.12 | Municipality Hollow Blocks (6"x4"x12") |  |  | 5.5

## FOrecast (hidden)
e
| VIEW BUILDERS PVT LTD | [13 empty] | Phone: +960 332 9467
| Ma.Vahffaru, Buruzumagu, | [13 empty] | Fax: +960 332 9468
| Male' - Maldives | [13 empty] | email:projects@viewbuilders.com.mv, Url:www.viewbuilders.com.mv
Exepected Progress Values / Forecasted
M.MUDHOO (EIGHT STOREY BUILDING)
ITEM | DESCRIPTION | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01
1 | Demolition
| Demolition | 2010-04-01: #REF!
2 | Ground Works
site preparation & Government permission
| Masonry works for Boundry protection | 2010-06-01: #REF!
| Dewatering & Excavation | 2010-06-01: #REF!
| Dewatering & Lean Concrete | 2010-07-01: #REF!
Preparation for Foundation Reinforcement
Foundation Reinforcement
3 | Concrete Works
| Foundation Raft Concrete | 2010-07-01: #REF!
| Foundation Beam Concrete | 2010-07-01: #REF!
| Lift, Stair & Columns up to First Slab | 2010-07-01: #REF!
| Damp proofing And Masonry works at Below Ground | 2010-08-01: #REF!
| First Slab Beams & Slab | 2010-08-01: #REF!
| First floor Columns, Lift & Stair | 2010-08-01: #REF!
| Second Slab Beam & Slab | 2010-08-01: #REF!
| Second floor Columns, Lift & Stair | 2010-09-01: #REF!
| Third Slab Beam & Slab | 2010-09-01: #REF!
| Third floor Columns, Lift & Stair | 2010-09-01: #REF!
| Fourth Slab Beam & Slab | 2010-10-01: #REF!
| Fourth floor Columns, Lift & Stair | 2010-10-01: #REF!
| Fifth Slab Beam & Slab | 2010-11-01: #REF!
| Fifth floor Columns, Lift & Stair | 2010-11-01: #REF!
| Sixth Slab Beam & Slab | 2010-11-01: #REF!
| Sixth floor Columns, Lift & Stair | 2010-12-01: #REF!
| Seventh Slab Beam & Slab | 2010-12-01: #REF!
| Seventh floor Columns, Lift & Stair | 2010-12-01: #REF!
Eighth Slab Beam & Slab | bar: 2011-01-01
Eighth floor Columns, Lift & Stair | bar: 2011-01-01
Ninth Slab Beam & Slab | bar: 2011-01-01
Ninth floor Columns, Lift & Stair
| Terrace Slab Beam & Slab | 2011-01-01: #REF!
| Terrace floor Columns & Lift | 2011-01-01: #REF!
| Roof Slab Beam & Slab | 2011-01-01: #REF!
4 | Masonry, Plastering Wiring, Plumbing & Screeding
| Ground Floor | 2010-09-01: #REF!
| First Floor | 2010-10-01: #REF!
| Second Floor | 2010-11-01: #REF!
| Third Floor | 2010-12-01: 399141.23
| Fourth Floor | 2011-01-01: 407114.58
| Fifth Floor | 2011-01-01: 407114.58
| Sixth Floor | 2011-02-01: 407114.58
| Seventh Floor | 2011-03-01: #REF!
Eighth Floor
Nineth Floor
| Terrace | 2011-04-01: #REF!
5 | Finishing Works
| Ground Floor - ( Including Penal Board & 2 Booster Pump) | 2010-11-01: #REF!
| First Floor | 2010-12-01: #REF!
| Second Floor | 2011-01-01: #REF!
| Third Floor | 2011-01-01: #REF!
| Fourth Floor | 2011-02-01: 384077.94
| Fifth Floor | 2011-03-01: 384077.94
| Sixth Floor | 2011-04-01: 384077.94
| Seventh Floor | 2011-04-01: #REF!
Eighth Floor
Nineth Floor
| Terrace (Including Lift) | 2011-05-01: #REF!
| BOQ ACTUAL AMOUNT | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 791192.52 | #REF! | #REF! | #REF! | 0 | 0 | #REF!
| ADMIN & MANAGEMENT COST | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12717.0621 | #REF! | #REF! | #REF! | 0 | 0 | #REF!
| TOTAL FOR BOQ ACTUAL AMOUNT & MANAGEMENT COST | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 803909.5821 | #REF! | #REF! | #REF! | 0 | 0 | #REF!

## BOQ
BILL OF QUANTITIES
NO | DESCRIPTION | UNIT | QTY | RATE | AMOUNT | TOTAL
1 | SITE MANAGEMENT
| Site Management Cost for concrete works | item | 1
| Site management Cost for Finishing works | item | 1
2 | GROUND WORKS
| Dewatering | item | 1
| Excavation | cub.mtr | 163.61
| Backfilling | item | 1
| Lean concrete (50mm Thick) | cub.mtr | 4.98
| Lean concrete (75mm Thick) | cub.mtr | 0.88
| Damp Proofing | item | 1
3 | FOUNDATION WORKS
Footing F1
| Concrete | cub.mtr | 11.907
| Steel Deformed Bar 12mm | mtr | 555.66
| Formwork | sq.mtr | 111.132
Footing F2
| Concrete | cub.mtr | 1.694
| Steel Deformed Bar 12mm | mtr | 101.64
| Formwork | sq.mtr | 20.328
Footing F3
| Concrete | cub.mtr | 13.69
| Steel Deformed Bar 12mm | mtr | 479.15
| Formwork | sq.mtr | 143.745
Footing F5
| Concrete | cub.mtr | 3.8115
| Steel Deformed Bar 12mm | mtr | 152.46
| Formwork | sq.mtr | 45.738
Footing F6
| Concrete | cub.mtr | 0.92575
| Steel Deformed Bar 12mm | mtr | 37.03
| Formwork | sq.mtr | 11.109
Footing F7
| Concrete | cub.mtr | 1.0938
| Steel Deformed Bar 12mm | mtr | 43.75
| Formwork | sq.mtr | 13.125
Footing F9
| Concrete | cub.mtr | 4.046
| Steel Deformed Bar 12mm | mtr | 121.38
| Formwork | sq.mtr | 48.552
Tie Beam TB
| Concrete | cub.mtr | 17.2463
| Steel Deformed Bar 16mm | mtr | 1400.2205
| Steel Round Bar 6mm | mtr | 1393.4684
| Formwork | sq.mtr | 193.9245
Column(s) C1
| Concrete | cub.mtr | 0.147
| Steel Deformed Bar 16mm | mtr | 19.1811
| Steel Round Bar 6mm | mtr | 48.4557
| Formwork | sq.mtr | 2.541
Column(s) C2
| Concrete | cub.mtr | 0.4725
| Steel Deformed Bar 16mm | mtr | 57.5433
| Steel Round Bar 6mm | mtr | 145.3671
| Formwork | sq.mtr | 7.623
Column(s) C3
| Concrete | cub.mtr | 0.56
| Steel Deformed Bar 16mm | mtr | 51.1496
| Steel Round Bar 6mm | mtr | 70.481
| Formwork | sq.mtr | 11.088
Column(s) C4
| Concrete | cub.mtr | 0.035
| Steel Deformed Bar 16mm | mtr | 3.1969
| Steel Deformed Bar 12mm | mtr | 0.77186
| Steel Round Bar 6mm | mtr | 4.4051
| Formwork | sq.mtr | 0.693
Staircase
| Concrete | cub.mtr | 0.1725
| Steel Deformed Bar 10mm | mtr | 16.8
| Formwork | sq.mtr | 21.5
4 | GROUND FLOOR
4A | Concrete Works
Column(s) C1
| Concrete | cub.mtr | 0.63
| Steel Deformed Bar 16mm | mtr | 82.2047
| Steel Round Bar 6mm | mtr | 207.6673
| Formwork | sq.mtr | 10.89
Column(s) C2
| Concrete | cub.mtr | 2.025
| Steel Deformed Bar 16mm | mtr | 246.6142
| Steel Round Bar 6mm | mtr | 623.0018
| Formwork | sq.mtr | 32.67
Column(s) C3
| Concrete | cub.mtr | 2.4
| Steel Deformed Bar 16mm | mtr | 219.2126
| Steel Round Bar 6mm | mtr | 302.0615
| Formwork | sq.mtr | 47.52
Column(s) C4
| Concrete | cub.mtr | 0.15
| Steel Deformed Bar 16mm | mtr | 13.7008
| Steel Deformed Bar 12mm | mtr | 3.308
| Steel Round Bar 6mm | mtr | 18.8788
| Formwork | sq.mtr | 2.97
Beam(s) B1
| Concrete | cub.mtr | 8.9345
| Steel Deformed Bar 16mm | mtr | 474.4583
| Steel Round Bar 6mm | mtr | 842.6425
| Formwork | sq.mtr | 121.1357
Beam(s) B2
| Concrete | cub.mtr | 0.4257
| Steel Deformed Bar 16mm | mtr | 22.6063
| Steel Deformed Bar 12mm | mtr | 17.4662
| Steel Round Bar 6mm | mtr | 40.149
| Formwork | sq.mtr | 5.7717
Beam(s) B3
| Concrete | cub.mtr | 1.0062
| Steel Deformed Bar 12mm | mtr | 51.6046
| Steel Round Bar 6mm | mtr | 94.8976
| Formwork | sq.mtr | 13.6422
Beam(s) B4
| Concrete | cub.mtr | 0.59168
| Steel Deformed Bar 16mm | mtr | 69.125
| Steel Round Bar 6mm | mtr | 55.8031
| Formwork | sq.mtr | 8.0221
Beam(s) B5
| Concrete | cub.mtr | 0.5031
| Steel Deformed Bar 16mm | mtr | 46.7539
| Steel Deformed Bar 12mm | mtr | 5.1605
| Steel Round Bar 6mm | mtr | 47.4488
| Formwork | sq.mtr | 6.8211
Beam(s) B6
| Concrete | cub.mtr | 0.7998
| Steel Deformed Bar 16mm | mtr | 59.4614
| Steel Round Bar 6mm | mtr | 150.8629
| Formwork | sq.mtr | 10.8438
Beam(s) B7
| Concrete | cub.mtr | 0.1806
| Steel Deformed Bar 16mm | mtr | 11.9882
| Steel Round Bar 6mm | mtr | 34.0658
| Formwork | sq.mtr | 2.4486
Beam(s) B8
| Concrete | cub.mtr | 0.42484
| Steel Deformed Bar 16mm | mtr | 22.5606
| Steel Deformed Bar 12mm | mtr | 5.4471
| Steel Round Bar 6mm | mtr | 40.0679
| Formwork | sq.mtr | 5.76
Floor Slab
| Concrete | cub.mtr | 32.1314
| Steel Deformed Bar 10mm | mtr | 7542.8187
| Formwork | sq.mtr | 232.6676
Staircase
| Concrete | cub.mtr | 1.92
| Steel Deformed Bar 10mm | mtr | 184.5
| Formwork | sq.mtr | 18.3
balcony wall
| Concrete | cub.mtr | 0.132
| Steel Deformed Bar 10mm | mtr | 17.6
| Formwork | sq.mtr | 2.64
4B | Finishing Works
Masonry & Plastering
| 150mm Thick Solid Block Parapet wall (below ground) | sq.mtr | 73.8415
| 100mm Thick Solid Block Parapet wall (below ground) | sq.mtr | 23.69
| 100mm Thick Solid Block Wall Below Ground Level | sq.mtr | 110.376
| 150mm Thick Solid Block Exterior walls | sq.mtr | 81.06
| 150mm Thick Hollow Block Interior | sq.mtr | 160.2
| Plastering 15mm Thick Exterior | sq.mtr | 93.219
| Plastering 12mm Thick Interior | sq.mtr | 289.512
Floor Screed
| 75mm Thick Ground Slab | cub.mtr | 20.274
| Flooring 65mm thick | sq.mtr | 270.32
Tiling
| 300x300 White Homogenous Tiles (A) | sq.mtr | 33.13
| Brown Parquet/Vinyl Flooring (B) | sq.mtr | 11.2
| Grey Parquet/Vinyl Flooring (C) | sq.mtr | 95.12
| Timber Deck Flooring (D) | sq.mtr | 104.93
| 600x600 White Homogenous Tiles (E) | sq.mtr | 14.07
| 300x450 Ceramic Tiles on Toilet Walls | sq.mtr | 43.2
| 600x250 Ceramic Tiles on Staircase | sq.mtr | 4.85
Doors & Windows
| D1 | nos | 2
| D2 | nos | 2
| D3 | nos | 4
| D4 | nos | 5
| D5 | nos | 1
| W1 | nos | 1
| W2 | nos | 1
| W3 | nos | 2
| W4 | nos | 1
| W5 | nos | 3
| W6 | nos | 3
Putty & Painting
| Painting on Exterior Surfaces of Wall | sq.mtr | 93.219
| Putty & Painting on interior surfaces of wall | sq.mtr | 289.512
| Putty & Painting on ceiling / sofits of slab | sq.mtr | 270.32
Hydraulics & Drainage
| Sewerage/waste water main connection | nos | 1
| Inspection chamber | nos | 1
| Water meter for whole building | nos | 1
| Well water pump | nos | 1
| Plumbing works inc.pipe line accessories for whole building | nos | 1
| Plumbing work internal | nos | 3
| WC | nos | 3
| Muslim shower | nos | 3
| Wash basin | nos | 4
| Wash basin tap | nos | 4
| Toilet paper holder | nos | 3
| Towel hook | nos | 1
| Soap holder | nos | 1
| Shower | nos | 1
| Mirror set | nos | 2
| Tap | nos | 3
| Floor trap | nos | 3
Electrical Works
| Electrical main connection | item | 1
| Electrical wiring to Lights and Fans | points | 69
| Electrcal wiring to socket outlets | points | 36
| Ceiling recessed Halogen light | nos | 40
| Waterproof ceiling down light | nos | 9
| Waterproof ceiling down light | nos | 7
| Emergency light | nos | 1
| One way switch | nos | 17
| 13A single socket outlet | nos | 25
| 13A double socket outlet | nos | 24
| 15A single socket outlet | nos | 3
| Shaver socket outlet | nos | 3
| waterproof service socket outlet | nos | 2
| Fan regulator | nos | 9
| Ceiling Fan | nos | 9
| Heater | nos | 1
| TV/cable outlet | nos | 3
| Data/Network outlet | nos | 2
| Distribution Board | nos | 1
Ceiling
| 6mm Thick ceiling | sq.mtr | 33.13
Kitchen Cupboards
| Kitchen Cupboard (concrete works) | item | 1
Metal Works
| Staircase Railing | item | 1
Balcony wood work
| 100x50 thck Timber Rail | mtr | 0.95
Roof Works
| Lysaght Front Roof covering ( incl roof frame) | sq.mtr | 46.25
Fire Saety Works
| Break Glass Manual call point | item | 1
| Smoke Detector | nos | 12
| Fire Alarm Bell | nos | 1
| Portable Extinguisher(H2O) | nos | 4
| Portable Extinguisher(CO2) | nos | 4
| Junction Box | nos | 1
| Conventional Fire Alarm panel | nos | 1
| Exit Sign | nos | 1
5 | FIRST FLOOR
5A | Concrete Works
Column(s) C1
| Concrete | cub.mtr | 0.63
| Steel Deformed Bar 16mm | mtr | 82.2047
| Steel Round Bar 6mm | mtr | 207.6673
| Formwork | sq.mtr | 10.89
Column(s) C2
| Concrete | cub.mtr | 2.025
| Steel Deformed Bar 16mm | mtr | 246.6142
| Steel Round Bar 6mm | mtr | 623.0018
| Formwork | sq.mtr | 32.67
Column(s) C3
| Concrete | cub.mtr | 2.4
| Steel Deformed Bar 16mm | mtr | 219.2126
| Steel Round Bar 6mm | mtr | 302.0615
| Formwork | sq.mtr | 47.52
Column(s) C4
| Concrete | cub.mtr | 0.15
| Steel Deformed Bar 16mm | mtr | 13.7008
| Steel Deformed Bar 12mm | mtr | 3.308
| Steel Round Bar 6mm | mtr | 18.8788
| Formwork | sq.mtr | 2.97
Beam(s) B1
| Concrete | cub.mtr | 8.9345
| Steel Deformed Bar 16mm | mtr | 474.4583
| Steel Round Bar 6mm | mtr | 842.6425
| Formwork | sq.mtr | 121.1357
Beam(s) B2
| Concrete | cub.mtr | 0.4257
| Steel Deformed Bar 16mm | mtr | 22.6063
| Steel Deformed Bar 12mm | mtr | 17.4662
| Steel Round Bar 6mm | mtr | 40.149
| Formwork | sq.mtr | 5.7717
Beam(s) B3
| Concrete | cub.mtr | 1.0062
| Steel Deformed Bar 12mm | mtr | 51.6046
| Steel Round Bar 6mm | mtr | 94.8976
| Formwork | sq.mtr | 13.6422
Beam(s) B5
| Concrete | cub.mtr | 0.5031
| Steel Deformed Bar 16mm | mtr | 46.7539
| Steel Deformed Bar 12mm | mtr | 5.1605
| Steel Round Bar 6mm | mtr | 47.4488
| Formwork | sq.mtr | 6.8211
Beam(s) B6
| Concrete | cub.mtr | 0.7998
| Steel Deformed Bar 16mm | mtr | 59.4614
| Steel Round Bar 6mm | mtr | 150.8629
| Formwork | sq.mtr | 10.8438
Beam(s) B7
| Concrete | cub.mtr | 0.1806
| Steel Deformed Bar 16mm | mtr | 11.9882
| Steel Round Bar 6mm | mtr | 34.0658
| Formwork | sq.mtr | 2.4486
Beam(s) B8
| Concrete | cub.mtr | 1.0165
| Steel Deformed Bar 16mm | mtr | 53.9811
| Steel Deformed Bar 12mm | mtr | 13.0335
| Steel Round Bar 6mm | mtr | 95.871
| Formwork | sq.mtr | 13.7821
Floor Slab
| Concrete | cub.mtr | 32.9
| Steel Deformed Bar 10mm | mtr | 7462.7
| Formwork | sq.mtr | 236.6
Staircase
| Concrete | cub.mtr | 1.92
| Steel Deformed Bar 10mm | mtr | 184.5
| Formwork | sq.mtr | 18.3
Balcony
| Concrete | cub.mtr | 1.44
| Steel Deformed Bar 10mm | mtr | 212
| Formwork | sq.mtr | 14.08
5B | Finishing Works
Masonry & Plastering
| 150mm Thick Solid Block Exterior walls | sq.mtr | 206.8
| 150mm Thick Hollow Block Interior | sq.mtr | 241.4
| Plastering 15mm Thick Exterior | sq.mtr | 227.48
| Plastering 12mm Thick Interior | sq.mtr | 793.04
Floor Screed
| Flooring 65mm thick | sq.mtr | 238.5
Tiling
| 300x300 White Homogenous Tiles (A) | sq.mtr | 31.68
| Brown Parquet/Vinyl Flooring (B) | sq.mtr | 93.4
| Grey Parquet/Vinyl Flooring (C) | sq.mtr | 19.33
| 600x600 Rough Homogenous Tiles (F) | sq.mtr | 31.72
| 300x450 Ceramic Tiles on Toilet Walls | sq.mtr | 79.92
| 600x250 Ceramic Tiles on Staircase | sq.mtr | 4.85
Doors & Windows
| D3 | nos | 10
| D4 | nos | 8
| D5 | nos | 8
| W4 | nos | 1
| W6 | nos | 8
Putty & Painting
| Painting on Exterior Surfaces of Wall | sq.mtr | 227.48
| Putty & Painting on interior surfaces of wall | sq.mtr | 793.04
| Putty & Painting on ceiling / sofits of slab | sq.mtr | 238.5
Hydraulics & Drainage
| Plumbing works internals | nos | 8
| WC | nos | 8
| Muslim shower | nos | 8
| Wash basin | nos | 8
| Wash basin tap | nos | 8
| Toilet paper holder | nos | 8
| Towel hook | nos | 8
| Soap holder | nos | 8
| Shower | nos | 8
| Mirror set | nos | 8
| Tap | nos | 8
| Floor trap | nos | 8
Electrical Works
| Electrical wiring to Lights and Fans | points | 97
| Electrcal wiring to socket outlets | points | 104
| Ceiling recessed Halogen light | nos | 73
| Waterproof ceiling down light | nos | 16
| Emergency light | nos | 2
| 13A single socket outlet | nos | 40
| 13A double socket outlet | nos | 26
| 15A single socket outlet | nos | 8
| Shaver socket outlet | nos | 16
| waterproof service socket outlet | nos | 14
| One way switch | nos | 36
| Fan regulator | nos | 8
| Ceiling Fan | nos | 8
| TV/cable outlet | nos | 8
| Data/Network outlet | nos | 8
| Distribution Board | nos | 4
Ceiling
| 6mm Thick ceiling | sq.mtr | 24.8
Metal Works
| Staircase Railing | item | 1
Roof Works
| Lysaght Front Roof covering ( incl roof frame) | sq.mtr | 41.15
Fire Saety Works
| Break Glass Manual call point | item | 2
| Smoke Detector | nos | 8
| Fire Alarm Bell | nos | 2
| Portable Extinguisher(H2O) | nos | 6
| Portable Extinguisher(CO2) | nos | 6
| Junction Box | nos | 2
| Conventional Fire Alarm panel | nos | 2
| Exit Sign | nos | 2
Wood work (Balcony & Corridor)
| 100x50 timber | mtr | 28.6
| 100x50 timber | mtr | 108.68
| 100x50 thck Timber Rail | mtr | 12.6
6 | SECOND FLOOR
6A | Concrete Works
Column(s) C1
| Concrete | cub.mtr | 0.63
| Steel Deformed Bar 16mm | mtr | 82.2047
| Steel Round Bar 6mm | mtr | 207.6673
| Formwork | sq.mtr | 10.89
Column(s) C2
| Concrete | cub.mtr | 2.025
| Steel Deformed Bar 16mm | mtr | 246.6142
| Steel Round Bar 6mm | mtr | 623.0018
| Formwork | sq.mtr | 32.67
Column(s) C3
| Concrete | cub.mtr | 2.4
| Steel Deformed Bar 16mm | mtr | 219.2126
| Steel Round Bar 6mm | mtr | 302.0615
| Formwork | sq.mtr | 47.52
Column(s) C4
| Concrete | cub.mtr | 0.15
| Steel Deformed Bar 16mm | mtr | 13.7008
| Steel Deformed Bar 12mm | mtr | 3.308
| Steel Round Bar 6mm | mtr | 18.8788
| Formwork | sq.mtr | 2.97
Beam(s) B1
| Concrete | cub.mtr | 8.9345
| Steel Deformed Bar 16mm | mtr | 474.4583
| Steel Round Bar 6mm | mtr | 842.6425
| Formwork | sq.mtr | 121.1357
Beam(s) B2
| Concrete | cub.mtr | 0.4257
| Steel Deformed Bar 16mm | mtr | 22.6063
| Steel Deformed Bar 12mm | mtr | 17.4662
| Steel Round Bar 6mm | mtr | 40.149
| Formwork | sq.mtr | 5.7717
Beam(s) B3
| Concrete | cub.mtr | 1.0062
| Steel Deformed Bar 12mm | mtr | 51.6046
| Steel Round Bar 6mm | mtr | 94.8976
| Formwork | sq.mtr | 13.6422
Beam(s) B5
| Concrete | cub.mtr | 0.5031
| Steel Deformed Bar 16mm | mtr | 46.7539
| Steel Deformed Bar 12mm | mtr | 5.1605
| Steel Round Bar 6mm | mtr | 47.4488
| Formwork | sq.mtr | 6.8211
Beam(s) B6
| Concrete | cub.mtr | 0.7998
| Steel Deformed Bar 16mm | mtr | 59.4614
| Steel Round Bar 6mm | mtr | 150.8629
| Formwork | sq.mtr | 10.8438
Beam(s) B7
| Concrete | cub.mtr | 0.1806
| Steel Deformed Bar 16mm | mtr | 11.9882
| Steel Round Bar 6mm | mtr | 34.0658
| Formwork | sq.mtr | 2.4486
Beam(s) B8
| Concrete | cub.mtr | 1.0165
| Steel Deformed Bar 16mm | mtr | 53.9811
| Steel Deformed Bar 12mm | mtr | 13.0335
| Steel Round Bar 6mm | mtr | 95.871
| Formwork | sq.mtr | 13.7821
Floor Slab
| Concrete | cub.mtr | 32.9
| Steel Deformed Bar 10mm | mtr | 7462.7
| Formwork | sq.mtr | 236.6
Staircase
| Concrete | cub.mtr | 1.92
| Steel Deformed Bar 10mm | mtr | 184.5
| Formwork | sq.mtr | 18.3
Balcony
| Concrete | cub.mtr | 1.44
| Steel Deformed Bar 10mm | mtr | 212
| Formwork | sq.mtr | 14.08
6B | Finishing Works
Masonry & Plastering
| 150mm Thick Solid Block Exterior walls | sq.mtr | 206.8
| 150mm Thick Hollow Block Interior | sq.mtr | 241.4
| Plastering 15mm Thick Exterior | sq.mtr | 227.48
| Plastering 12mm Thick Interior | sq.mtr | 793.04
Floor Screed
| Flooring 65mm thick | sq.mtr | 238.5
Tiling
| 300x300 White Homogenous Tiles (A) | sq.mtr | 31.68
| Brown Parquet/Vinyl Flooring (B) | sq.mtr | 93.4
| Grey Parquet/Vinyl Flooring (C) | sq.mtr | 19.33
| 600x600 Rough Homogenous Tiles (F) | sq.mtr | 31.72
| 300x450 Ceramic Tiles on Toilet Walls | sq.mtr | 79.92
| 600x250 Ceramic Tiles on Staircase | sq.mtr | 4.85
Doors & Windows
| D3 | nos | 10
| D4 | nos | 8
| D5 | nos | 8
| W4 | nos | 1
| W6 | nos | 8
Putty & Painting
| Painting on Exterior Surfaces of Wall | sq.mtr | 227.48
| Putty & Painting on interior surfaces of wall | sq.mtr | 793.04
| Putty & Painting on ceiling / sofits of slab | sq.mtr | 238.5
Hydraulics & Drainage
| Plumbing works internals | nos | 8
| WC | nos | 8
| Muslim shower | nos | 8
| Wash basin | nos | 8
| Wash basin tap | nos | 8
| Toilet paper holder | nos | 8
| Towel hook | nos | 8
| Soap holder | nos | 8
| Shower | nos | 8
| Mirror set | nos | 8
| Tap | nos | 8
| Floor trap | nos | 8
Electrical Works
| Electrical wiring to Lights and Fans | points | 97
| Electrcal wiring to socket outlets | points | 104
| Ceiling recessed Halogen light | nos | 73
| Waterproof ceiling down light | nos | 16
| Emergency light | nos | 2
| 13A single socket outlet | nos | 40
| 13A double socket outlet | nos | 26
| 15A single socket outlet | nos | 8
| Shaver socket outlet | nos | 16
| waterproof service socket outlet | nos | 14
| One way switch | nos | 36
| Fan regulator | nos | 8
| Ceiling Fan | nos | 8
| TV/cable outlet | nos | 8
| Data/Network outlet | nos | 8
| Distribution Board | nos | 4
Ceiling
| 6mm Thick ceiling | sq.mtr | 24.8
Metal Works
| Staircase Railing | item | 1
Roof Works
| Lysaght Front Roof covering ( incl roof frame) | sq.mtr | 41.15
Fire Saety Works
| Break Glass Manual call point | item | 2
| Smoke Detector | nos | 8
| Fire Alarm Bell | nos | 2
| Portable Extinguisher(H2O) | nos | 6
| Portable Extinguisher(CO2) | nos | 6
| Junction Box | nos | 2
| Conventional Fire Alarm panel | nos | 2
| Exit Sign | nos | 2
Wood work (Balcony & Corridor)
| 100x50 timber | mtr | 28.6
| 100x50 timber | mtr | 108.68
| 100x50 thck Timber Rail | mtr | 12.6
7 | THIRD FLOOR
7A | Concrete Works
Column(s) C1
| Concrete | cub.mtr | 0.63
| Steel Deformed Bar 16mm | mtr | 82.2047
| Steel Round Bar 6mm | mtr | 207.6673
| Formwork | sq.mtr | 10.89
Column(s) C2
| Concrete | cub.mtr | 2.025
| Steel Deformed Bar 16mm | mtr | 246.6142
| Steel Round Bar 6mm | mtr | 623.0018
| Formwork | sq.mtr | 32.67
Column(s) C3
| Concrete | cub.mtr | 2.4
| Steel Deformed Bar 16mm | mtr | 219.2126
| Steel Round Bar 6mm | mtr | 302.0615
| Formwork | sq.mtr | 47.52
Column(s) C4
| Concrete | cub.mtr | 0.15
| Steel Deformed Bar 16mm | mtr | 13.7008
| Steel Deformed Bar 12mm | mtr | 3.308
| Steel Round Bar 6mm | mtr | 18.8788
| Formwork | sq.mtr | 2.97
Beam(s) B1
| Concrete | cub.mtr | 8.9345
| Steel Deformed Bar 16mm | mtr | 474.4583
| Steel Round Bar 6mm | mtr | 842.6425
| Formwork | sq.mtr | 121.1357
Beam(s) B2
| Concrete | cub.mtr | 0.4257
| Steel Deformed Bar 16mm | mtr | 22.6063
| Steel Deformed Bar 12mm | mtr | 17.4662
| Steel Round Bar 6mm | mtr | 40.149
| Formwork | sq.mtr | 5.7717
Beam(s) B3
| Concrete | cub.mtr | 1.0062
| Steel Deformed Bar 12mm | mtr | 51.6046
| Steel Round Bar 6mm | mtr | 94.8976
| Formwork | sq.mtr | 13.6422
Beam(s) B5
| Concrete | cub.mtr | 0.5031
| Steel Deformed Bar 16mm | mtr | 46.7539
| Steel Deformed Bar 12mm | mtr | 5.1605
| Steel Round Bar 6mm | mtr | 47.4488
| Formwork | sq.mtr | 6.8211
Beam(s) B6
| Concrete | cub.mtr | 0.7998
| Steel Deformed Bar 16mm | mtr | 59.4614
| Steel Round Bar 6mm | mtr | 150.8629
| Formwork | sq.mtr | 10.8438
Beam(s) B7
| Concrete | cub.mtr | 0.1806
| Steel Deformed Bar 16mm | mtr | 11.9882
| Steel Round Bar 6mm | mtr | 34.0658
| Formwork | sq.mtr | 2.4486
Beam(s) B8
| Concrete | cub.mtr | 1.4414
| Steel Deformed Bar 16mm | mtr | 76.5417
| Steel Deformed Bar 12mm | mtr | 18.4806
| Steel Round Bar 6mm | mtr | 135.9389
| Formwork | sq.mtr | 19.5422
Floor Slab
| Concrete | cub.mtr | 14.6953
| Steel Deformed Bar 10mm | mtr | 3994.3895
| Formwork | sq.mtr | 134.2122
Staircase
| Concrete | cub.mtr | 1.92
| Steel Deformed Bar 10mm | mtr | 184.5
| Formwork | sq.mtr | 18.3
Balcony
| Concrete | cub.mtr | 1.44
| Steel Deformed Bar 10mm | mtr | 212
| Formwork | sq.mtr | 14.08
7B | Finishing Works
Masonry & Plastering
| 150mm Thick Solid Block Exterior walls | sq.mtr | 206.8
| 150mm Thick Hollow Block Interior | sq.mtr | 241.4
| Plastering 15mm Thick Exterior | sq.mtr | 227.48
| Plastering 12mm Thick Interior | sq.mtr | 793.04
Floor Screed
| Flooring 65mm thick | sq.mtr | 238.5
Tiling
| 300x300 White Homogenous Tiles (A) | sq.mtr | 31.68
| Brown Parquet/Vinyl Flooring (B) | sq.mtr | 93.4
| Grey Parquet/Vinyl Flooring (C) | sq.mtr | 19.33
| 600x600 Rough Homogenous Tiles (F) | sq.mtr | 31.72
| 300x450 Ceramic Tiles on Toilet Walls | sq.mtr | 79.92
| 600x250 Ceramic Tiles on Staircase | sq.mtr | 4.85
Doors & Windows
| D3 | nos | 10
| D4 | nos | 8
| D5 | nos | 8
| W4 | nos | 1
| W6 | nos | 8
Putty & Painting
| Painting on Exterior Surfaces of Wall | sq.mtr | 227.48
| Putty & Painting on interior surfaces of wall | sq.mtr | 793.04
| Putty & Painting on ceiling / sofits of slab | sq.mtr | 238.5
Hydraulics & Drainage
| Plumbing works internals | nos | 8
| WC | nos | 8
| Muslim shower | nos | 8
| Wash basin | nos | 8
| Wash basin tap | nos | 8
| Toilet paper holder | nos | 8
| Towel hook | nos | 8
| Soap holder | nos | 8
| Shower | nos | 8
| Mirror set | nos | 8
| Tap | nos | 8
| Floor trap | nos | 8
Electrical Works
| Electrical wiring to Lights and Fans | points | 97
| Electrcal wiring to socket outlets | points | 104
| Ceiling recessed Halogen light | nos | 73
| Waterproof ceiling down light | nos | 16
| Emergency light | nos | 2
| 13A single socket outlet | nos | 40
| 13A double socket outlet | nos | 26
| 15A single socket outlet | nos | 8
| Shaver socket outlet | nos | 16
| waterproof service socket outlet | nos | 14
| One way switch | nos | 36
| Fan regulator | nos | 8
| Ceiling Fan | nos | 8
| TV/cable outlet | nos | 8
| Data/Network outlet | nos | 8
| Distribution Board | nos | 4
Ceiling
| 6mm Thick ceiling | sq.mtr | 24.8
Metal Works
| Staircase Railing | item | 1
Roof Works
| 50x150 Timber Rafters @ 900c/c | mtr | 38.47
| 35x35 Timber battens @ 400c/c | mtr | 79.03
| 50x200 Ridge plate | mtr | 15.7
| 50x50 MS Gutter line | mtr | 15.9
| Lysaght Roof covering | sq.mtr | 16.2
| Lysaght Front Roof covering ( incl roof frame) | sq.mtr | 41.15
Fire Saety Works
| Break Glass Manual call point | item | 2
| Smoke Detector | nos | 8
| Fire Alarm Bell | nos | 2
| Portable Extinguisher(H2O) | nos | 6
| Portable Extinguisher(CO2) | nos | 6
| Junction Box | nos | 2
| Conventional Fire Alarm panel | nos | 2
| Exit Sign | nos | 2
Wood work (Balcony & Corridor)
| 100x50 timber | mtr | 28.6
| 100x50 timber | mtr | 108.68
| 100x50 thck Timber Rail | mtr | 12.6
8 | TERRACE FLOOR
8A | Concrete Works
Beam(s) B1
| Concrete | cub.mtr | 7.95
| Steel Deformed Bar 16mm | mtr | 423.3
| Steel Round Bar 6mm | mtr | 750.3
| Formwork | sq.mtr | 108
Beam(s) B3
| Concrete | cub.mtr | 1.0062
| Steel Deformed Bar 12mm | mtr | 51.6046
| Steel Round Bar 6mm | mtr | 94.8976
| Formwork | sq.mtr | 13.6422
8B | Finishing Works
Masonry & Plastering
| 150mm Thick Solid Block Exterior walls | sq.mtr | 15.75
| Plastering 15mm Thick Exterior | sq.mtr | 17.85
| Plastering 12mm Thick Interior | sq.mtr | 19.25
Floor Screed
| Flooring 65mm thick | sq.mtr | 11.46
Tiling
| 600x600 Rough Homogenous Tiles (F) | sq.mtr | 9.15
| 600x250 Ceramic Tiles on Staircase | sq.mtr | 4.82
Doors & Windows
| D2 | nos | 1
| W4 | nos | 1
Putty & Painting
| Painting on Exterior Surfaces of Wall | sq.mtr | 17.85
| Putty & Painting on interior surfaces of wall | sq.mtr | 19.25
| Putty & Painting on ceiling / sofits of slab | sq.mtr | 12.4
Electrical Works
| Electrical wiring to Lights and Fans | points | 7
| Electrcal wiring to socket outlets | points | 10
| Weatherproof light (wall mount ) | nos | 6
| Ceiling recessed Halogen light | nos | 1
| 13A double socket outlet | nos | 1
| waterproof service socket outlet | nos | 9
| One way switch | nos | 2
| Distribution Board | nos | 1
Ceiling
| 6mm Thick ceiling | sq.mtr | 12.4
Column work
| Wood Cladding | sq.mtr | 2.66
| dia75 G.I Pipe Stem | mtr | 52.8
Fire Saety Works
| Portable Extinguisher(H2O) | nos | 1
| Portable Extinguisher(CO2) | nos | 1
Roof Works
| 50x150Timber TRELLIS | mtr | 65.34
| 50x150 Timber Rafters @ 900c/c | mtr | 16.5
| 35x35 Timber battens @ 400c/c | mtr | 32.8
| 50x50 MS Gutter line | mtr | 14.46
| Lysaght Roof covering | sq.mtr | 12.4
9 | MISCELLANEOUS
| MWSC booster pump | item | 1
| Electric main panel board with meters | item | 1
10 | ADDITION & OMISSION
ADDITION
Site management
Ground work
Foundation work
Ground floor
First floor
Second floor
Third floor
Terrace floor
Miscellaneous
OMISSION
Site management
Ground work
Foundation work
Ground floor
First floor
Second floor
Third floor
Terrace floor
Miscellaneous
TOTAL COST CARRIED OUT TO SUMMARY