Contents

FORM OF AGREEMENT	1

FORM OF BID	3

APPENDIX TO TENDER/CONTRACT DATA	4

PARTICULAR CONDITIONS	6

CONDITIONS OF CONTRACT	11

# FORM OF AGREEMENT

This Agreement made the _______ day of ______________ 2015, between Government of Maldives represented by the Ministry of Housing and Infrastructure, Male’, Republic of Maldives (hereinafter called “the Employer”) of the one part and ________________________________________.(hereinafter called “the Contractor”) of the other part.

Whereas the Employer desires that the Works known as Construction of Th. Guraidhoo Revetment Project to be executed by the Contractor, and has accepted a Tender by the Contractor for the execution and completion of these Works and the remedying of any defects in accordance with the terms and conditions set forth in this Agreement for a total Contract Price of ____________________________ (in words). therein,

The Employer and the Contractor agree as follows:

- In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

- The following documents shall be deemed to form and be read and construed as part of this Agreement:

- The Letter of Acceptance dated ______________.

- The Letter of Tender _______________.

- The Addenda nos. ________.

- The Conditions of Contract;

- The Specification;

- The Drawings, and

- The completed Bill of Quantities.

- In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein, in conformity in all respects with the provisions of the Contract.

- The Employer hereby covenants to pay the Contractor, in consideration of the execution and completion of the works and the remedying of defects therein, the Contract Price at the times and in the manner prescribed by the Contract.

In Witness whereof the parties hereto have caused this Agreement to be executed the day and year first before written in accordance with their respective laws.

For and Signed on behalf of:

| Employer: …………………………………………………… | Contractor: ……………………………………………………. |
| --- | --- |
| Name: ______________________ | Name: ________________________ |
| Designation: ___________________ | Designation: _____________________ |
| Address: | Address: |

In the presence of:

| Employer: …………………………………………………… | Contractor: ……………………………………………………. |
| --- | --- |
| Name: __________________________ | Name: __________________________ |
| Designation: _____________________ | Designation: _____________________ |
| Address: | Address: |

# FORM OF BID

NAME OF CONTRACT:

___________________ Construction of Th. Guraidhoo Revetment Project

TO:

Tender Evaluation Section Ministry of Finance and Treasury, Ameenee Magu, Male’, Republic of Maldives

We have examined the Conditions of Contract, Specification, Drawings, and Bill of Quantities, the other Schedules, the attached Appendix and Addenda Nos. ________________ for the execution of the above-named Works. We offer to execute and complete the Works and remedy any defects therein in conformity with this Tender which includes all these documents, for the lump-sum fixed price excluding Goods and Services Tax (GST) of _________________________________________________ [amount in numbers & words]. The amount for Goods and Services Tax (GST) is ___________________________________ [amount in numbers & words]

or such other sum as may be determined in accordance with the Conditions of  Contract.

We accept your suggestions for the appointment of the DAB, as set out in Schedule _______________

[We have completed the Schedule by adding our suggestions for the other Member of the DAB, but these suggestions are not conditions of this offer].*

We agree to abide by this Tender until _______________ and it shall remain binding upon us and may be accepted at any time before that date. We acknowledge that the Appendix forms part of this Letter of Tender.

If this offer is accepted, we will provide the specified Performance Security, commence the Works as soon as is reasonably practicable after the Commencement Date, and complete the Works in accordance with the above-named documents within the Time for Completion.

Unless and until a formal Agreement is prepared and executed this Letter of Tender, together with your written acceptance thereof, shall constitute a binding contract between us.

We understand that you are not bound to accept the lowest or any tender you may receive.

Signature __________________________________ in the capacity of ________________________________

Duly authorized to sign tenders for and on behalf of ________________________________________________

____________________________________________________________________________________

Address

________________________________________________________________________________________________________________________________________________________________________Date: ____________________________________________________________________

*If the Tenderer does not accept, this paragraph may be deleted and replaced by:

We do not accept you suggestions for the appointment of the DAB. We have included our suggestions in the Schedule, but these suggestion are not conditions if this offer. If these suggestions are not acceptable to you, we propose that the DAB be jointly appointed in accordance with Sub-Clause 20.2 of the Conditions of Contract.

# APPENDIX TO TENDER/CONTRACT DATA

|  |  | Sub - Clause |  |  |
| --- | --- | --- | --- | --- |
| Employer’s name and address |  | 1.1.2.2 & 1.3 | Ministry of Housing and Infrastructure, Ameenee Magu, Male’ Republic of Maldives |  |
| Contractor’s name and address |  | 1.1.2.3 & 1.3 |  |  |
| Engineer’s name and address |  | 1.1.2.4 & 1.3 | Ministry of Housing and Infrastructure, Ameenee Magu, Maafannu, Male’ 20392, Republic of Maldives |  |
| Time for Completion of the Works |  | 1.1.3.3 | ____________days |  |
| Defects Notification Period |  | 1.1.3.7 | 365 days |  |
| Electronic transmission systems |  | 1.3 | Electronic Mail and Facsimile |  |
| Governing Law |  | 1.4 | Law of the Republic of Maldives |  |
| Ruling language |  | 1.4 | English |  |
| Language for communications |  | 1.4 | English |  |
| Time for access to the Site |  | 2.1 | 14 days before Commencement Date |  |
| Amount of Performance Security |  | 4.2 | 5% of the Accepted Contract Amount, in the currencies and proportions in which the Contract Price is payable. |  |
| Normal working hours |  | 6.5 | As suited for Works on site |  |
| Delay damages for the Works |  | 8.7 & 14.15(b) | The rate per day for liquidated damages shall be calculated as follows: RW ÷ CD × 0.75 Where; RW= Remaining works (i.e Total Contract Price Less Value of Certified Works) CD = Total Contract Duration |  |
| Maximum amount of delay damages |  | 8.7 | 10% of the Final Contract Price |  |
| Total advance payment |  | 14.2 | 15% of the Accepted Contract Amount |  |
| Number and timing of installments |  | 14.2 | Single installment at the Commencement. |  |
| Currencies and proportions |  | 14.2 | 100% in Maldivian Rufiyaa |  |
| Start repayment of advance payment |  | 14.2 (a) | Start repayment from the first progress payment |  |
| Repayment amortization of advance payment |  | 14.2 (b) | 15% from each progress payment |  |
| Percentage of retention |  | 14.3 | 5% |  |
| Limit of Retention Money |  | 14.3 | 5% of the Accepted Contract Amount |  |
| Plant and Materials intended for the Works, Plant and Material for payment |  | 14.5(c) | Rock Boulder / Geo Bag |  |
| Currency of Payment |  | 14.15 | Maldivian Rufiyaa |  |
| Periods for submission of insurance: - Evidence of insurance - Relevant policies |  | 18.1 18.1 | 14 days 14 days |  |
| Maximum amount of deductibles for insurance of the Employer’s risks |  | 18.2(d) | Nil |  |
| Maximum amount of third party insurance |  | 18.3 | MVR 1 Million |  |
| The Dispute Adjudication Board shall be |  | 20.2 | Ministry of Finance and Treasury Ameenee Magu, Male’ |  |
| Appointment (if not agreed) to be made by |  | 20.3 | Ministry of Finance and Treasury |  |
| Definitions of Sections: |  |  |  |  |
| Description (Sub-Clause 1.1.5.6) | Value: percentage* of Accepted Contract Amount |  | Time for Completion (Sub-Clause 1.1.3.3) | Delay Damages (Sub-Clause 8.7) |
| - These percentages shall also be applied to each half of the Retention Money under Sub-Clause 14.9 |  |  |  |  |

# PARTICULAR CONDITIONS

The Conditions of Contract comprise the “General Conditions”, which form part of the “Conditions of Contract for Construction” First Edition 1999 published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC), and the following “Particular Conditions”, which include amendments and additions to such General Conditions.

| Item | Sub-Clause | Data |
| --- | --- | --- |
| Clause 1 |  |  |
| Employer’s Representative | 1.1.2.11 | Insert Additional definition to 1.1.2 as defined “The Employer’s Representative” means the representative of the Employer appointed by the Island Council referred to in sub-clause 2.6 |
| Interpretation | 1.2 | At the end of Sub-Clause 1.2, insert: In these Conditions, provisions including the expression “Cost plus reasonable profit" require this profit to be one-twentieth (5%) of this Cost. |
| Priority of Documents | 1.5 | Delete the text in this Sub-Clause and replace with the following text: The documents forming the Contract are to be taken as mutually explanatory of one another. For the purposes of interpretation, the priority of the documents shall be in accordance with the following sequence: - the Contract Agreement (if any), - the Letter of Acceptance, - the Letter of Tender, - the Particular Conditions, - these General Conditions, - the Specification, - the Drawings, - the Bills of Quantities, and - any other documents forming part of the Contract. If an ambiguity or discrepancy is found in the documents, the Engineer shall issue any necessary clarification or instruction. |
| Details to be Confidential | 1.15 | The Contractor shall treat the details of the Contract as private and confidential, except to the extent necessary to carry out obligations under it or to comply with applicable Laws. The Contractor shall not publish, permit to be published, or disclose any particulars of the Works in any trade or technical paper or elsewhere without the previous agreement of the Employer. |
| Clause 2 |  |  |
| Employer’s Representative | 2.6 | Insert Additional sub-Clause 2.6 after Sub-Clause 2.5 The Employer’s Representative shall: - monitor the works on site daily and prepare daily sheets for the work progress - facilitate monthly site meetings with the project team - Inform the Employer of any issue to be rectified or requiring immediate attention |
| Clause 3 |  |  |
| Engineer’s Duties and Authority | 3.1 | Insert this at the end Sub-Clause 3.1 as (d): “The Engineer shall obtain the specific approval of the Employer before ordering any works involving delay or any extra payment by the Employer or to make variation of or in the Works or Contract.” |
| Management Meetings | 3.6 | Insert this new Sub-Clause 3.6 at the end of Clause 3: “The Engineer shall invite the Contractor and other relevant parties to the first Management Meeting where he shall decide upon intervals between future Management Meetings. The purpose of these Management Meetings is to coordinate the Works with the Contractor, (and other parties if deemed necessary) to record progress in relation to agreed program, and to reach and verify agreements. Minutes of each Management Meeting will be prepared by the Engineer and circulated to all parties attending the Management Meeting, prior to the next meeting, Agreements reached at the particular Management Meeting if duly recorded and confirmed at the next meeting will be considered accepted by all parties. Where such agreements require to be confirmed by Instructions from the Engineer in compliance with the Contract, the Engineer shall forthwith issue such Instructions. Agreement reached at meetings shall not be means to override the requirements to follow stipulated procedure and to submit the required quality assurance documents, method statements, shop drawings etc. |
| Clause 4 |  |  |
| Performance Security | 4.2 | At the end of the second paragraph of Sub-Clause 4.2, insert: If the Performance Security is in the form of a bank guarantee, it shall be issued either (a) by a bank located in the Country, or (b) Directly by a foreign bank acceptable to the Employer. If the Performance Security is not in the form of a bank guarantee, it shall be furnished by a financial entity registered, or licensed to do business, in the Country. |
| Subcontractors | 4.4 | Prior consent shall not be required if the value of the subcontract is less than 1% of the Accepted Contract Amount. |
| Unforeseen Physical Conditions | 4.12 | Delete the first paragraph and insert the following wordings: “In this Sub-Clause, “physical conditions” means natural physical conditions and man-made and other physical obstructions and pollutants, which the Contractor encounters at the Site when executing the Works, including hydrographic and sub-seabed conditions but excluding climatic conditions. The wind generated and swell waves that constantly approach the project site (harbor area) throughout the year shall not be considered as unforeseeable under the Clause. A day rate for removal of Hard Rock or Beach rock shall be included in the Bill of Quantities.” |
| Protection of the Environment | 4.18 | Add sub paragraph as follows; Contractor must comply with Environment Protection and Preservation Act 1993. Contractor should comply with and follow the mitigation measures proposed in the Environment Impact Assessment prepared for the project. |
| Clause 6 |  |  |
| Employment of Staff and Labour | 6.1 | Add to this Sub-Clause: The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualification and experience from sources within the Country of Works. |
| Clause 12 |  |  |
| Measurement and Evaluation | 12.1 to 12.4 | This Clause is Deleted. |
| Clause 13 |  |  |
| Variation Procedure | 13.3 | Delete the last sentence of Sub-Clause 13.3 and substitute: Upon instructing or approving a Variation, the Engineer shall proceed in accordance with Sub-Clause 3.5 to agree or determine adjustments to the Contract Price and to the schedule of payments under Sub-Clause 14.4. These adjustments shall include reasonable profit, and shall take account of the Contractor’s submissions under Sub-Clause 13.2 if applicable. |
| Clause 14 |  |  |
| The Contract Price | 14.1 | Delete sub-paragraph (a) of Sub-Clause 14.1 and substitute: - the Contract Price shall be the lump sum Accepted Contract Amount and be subject to adjustments in accordance with the Contract; Delete sub-paragraph (c) and (d) of Sub-Clause 14.1 Add the following after sub-paragraph (b) - if any part of the Works is to be paid according to works completed, Engineer shall use the rate specified in the Bill of Quantities. |
| Clause 18 |  |  |
| General Requirements for Insurances | 18.1 | Add the following at the end of Sub-Clause 18.1: Acceptable to the Employer. |
| Insurance against Damage to Property | 18.3 | Add the following sentence at the end of the Sub-Clause 18.3 Prior to commencing any excavation or using any heavy equipment in close proximity to third party properties, the Contractor shall at his own expense arrange his insurers to inspect such properties. He shall also prepare pre-operation condition reports of such properties including any photographs, as deemed appropriate, for future reference. |
| Clause 20 |  |  |
| Contractor’s Claims | 20.1 | The number days referred to in the Clause is amended as follows: 1st Paragraph: 28 days amended to 14 days 2nd Paragraph: 28 days amended to 14 days 5th Paragraph: 42 days amended to 21 days 6th Paragraph: 42 days amended to 21 days |
| Obtaining Dispute Board Decision | 20.4 | The last sentence of the 1st Paragraph is amended as follows: Such reference shall be made within 14 days on the establishment of a dispute by either Party and shall state that it is given under this Sub-Clause. The number days referred to in the Clause is amended as follows: 4th Paragraph: 84 days amended to 28 days 5th Paragraph: 84 days amended to 28 days. 28 days amended to 14 days 7th Paragraph: 28 days amended to 14 days |

# CONDITIONS OF CONTRACT

###### GENERAL CONDITIONS

The Conditions of Contract comprise the “General Conditions”, which form part of the “Conditions of Contract for Construction for Building and Engineering Works Designed by the Employer”, First Edition 1999 published by Fédération Internationale des Ingénieurs-Conseils (FIDIC), and the following “Particular Conditions”, which include amendments and additions to such General Conditions.

###### Copies of FIDIC Conditions of Contract, referred to above, may be obtained from:

###### FIDIC Secretariat

###### P.O. Box 86

###### CH 1000 Lausanne 12

###### Switzerland

###### Fax No: +41 21 653 5432

Refer to above FIDIC document which is an integral part of this Contract.