## L.Isdhoo
ISLAND | L.Isdhoo
SIZE
Bill No.1 - PRELIMINARIES
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
1.1 | Securities, Insurance, etc
1.1.1 | Provision of performance security | Item | 1
| Provision of insurance (Contractor to specify) | Item | 1
| Other security bonds, etc (Contractor to specify) | Item | 1
1.2 | Contractors Equipment, Personal and Site Facilities
1.2.1 | Mobilisation and demobilisation of Contractor's dredging equipment and construction plant | Item | 1
1.2.2 | Mobilisation and demobilisation of contractor's personal | Item | 1
1.2.3 | Time related charges for contractor personal. (Incl. food, lodging, etc) | Days
1.2.4 | Establisment and removal of the Contractor's facilities, incl. laboratory, office, workshop, etc | Item | 1
1.2.5 | Operation and maintenance of Contractor's facilities incl. laboratory, office, workshop, etc | Days
1.3 | Design and others
1.3.1 | provide as-built drawings, Quality assurance documentation, Material certificates, Technical brochures | Item | 1
1.3.2 | Provide detailed in-survey prior to commencement of physical works | Item | 1
1.3.3 | Provide detailed out-survey upon completion, prior to hand over | Item | 1
Total of bill No.1 (Carried to summary of Bills)
Bill No.2 - DREDGING, EXCAVATION & EARTHWORKS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
2.1 | Dredging and Excavation
2.1.1 | Dredging / Excavation of any material from the new harbour basin. Maximum specified depth -3m MSL | cbm
2.1.2 | Dredging / Excavation of any material from the existing harbour basin. Maximum specified depth -3m MSL | cbm
2.1.3 | Dredging / Excavation of any material for the existing harbour entrance Channel. Maximum specified depth -4m MSL | cbm
Total of bill No.2 (Carried to summary of Bills)
Bill No.3 - BREAKWATER, GROYNES AND REVETMENTS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
3.1 | Breakwaters
3.1.1 | Breakwater Type 1: Armour rocks laid to the slopes defined in drawings and to lines and levels indicated in the cross section drawings. Rate shall include levelling and placing armour rocks | m | 160
3.1.2 | Breakwater Type 2: Armour rocks laid to the slopes defined in drawings and to lines and levels indicated in the cross section drawings. Rate shall include levelling and placing armour rocks | m | 48
3.2 | Revetments
3.2.1 | Armour rocks laid to slopes with backfilled material and geotextile material as defined in the drawings | m | 98
3.3 | Beacons, Supply and Installing
3.3.1 | Supply and placing navigational aids at a minimum nominal light range of 2 nautical miles as shown on harbour layout drawing and as directed by Engineer. | No | 2
Total of bill No.3 (Carried to summary of Bills)
Bill No.4 - | QUAY WALL STRUCTURE
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
4.1 | L-Section Quay Wall (new harbour basin)
4.1.1 | Supply and install precast RC quaywall unit as per detail drawing. | m | 230
4.1.2 | Supply and install precast RC anchor blocks and fix anchor rods as per detail drawing. | m | 58
4.1.3 | Cast in-situ concrete coping in quaywall to grades, levels as indicated in the drawing | m | 230
4.1.4 | Supply and fix mooring rings in 5m intervals as per the detailed drawing | No | 46
4.1.5 | Supply and placing geotextile material to full length of the quaywall blocks covering the entire span of the quaywall length as shown in the cross section drawings | m | 230
4.2 | Mooring Blocks
4.2.1 | Construction and placing of Mooring Blocks | Nos. | 12
4.3 | Construction of Ramp (11m x 11m)
4.3.1 | Supply and placing reinforced concrete slab as per the drawing and casting and placing the required concrete blocks | sqm | 121
4.3.2 | Cope Edge Protector for protecting the concrete edge of Ramp for Landing crafts made of S355JR hot dip galvanized steel and painted to 3 layer paint systems including the cost of cast in anchor bars welded to the cope edge protectors, S355JR. Galvanized and all costs of labour, equipments etc complete all as per the details shown on drawings and specifications. | L.S | 1
4.4 | Bridge
4.4.1 | Construction of 8m Bridge | L.S | 1
4.5 | Drainage
4.5.1 | Construction of drains near the paving of harbour @ 40m Interval | LS | 1
Total of bill No.4 (Carried to summary of Bills)
Bill No.5 - BREAKWATER AND REVETMENTS | HARBOUR LIGHTS AND PAVEMENT
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
5.1 | Harbour Lights
5.1.1 | Supply and installation of two arm street lights along the quaywall line | Nos. | 12
5.2 | Construction of Interlocking pavement
5.2.1 | Surveying, compacting and levelling the harbour area grounds as specified in the drawing. | Item | 1
5.2.2 | Supply and placement of interlocking paving blocks to the length of harbours for 5m width | sqm | 1560
5.2.3 | Supply and lay Kerbs | m | 217
Total of bill No.5 (Carried to summary of Bills)
Bill No.6 - ENVIRONMENTAL CONTROL | ENVIRONMENTAL CONTROL
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
6.1 | Implement necessary mitigation measures as outlined in the technical specifications | Item | 1
6.2 | Execution of Environment Imppact Assessment | LS | 1
6.3 | Establishment of Permanent Survey Mark | LS | 1
Total of bill No.6 (Carried to summary of Bills)
Bill No.7 - PROVISIONAL SUM
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
7.1 | Sum (if any) which is specified in the contract as a provisional sum, for execution of any part of the works or for the supply of plant, materials or services | LS | 0 | 0 | 3000000
Total of bill No.7 (Carried to summary of Bills) |  |  |  |  | 3000000
Bill No.8 - ADDITIONS & OMISSIONS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
A | The accuracy of the quantities given in this Bills of Quantities is not guaranteed and the Contractor should satisfy himself as to their accuracy
B | Any adjustments that he may consider necessary should be written below and on similar continuation sheets if required, and the net amount of the adjustments is to be carried to the summary
Additions
1
2
3
4
5
6
Omissions
1
2
3
4
5
6
Total of bill No.8 (Carried to summary of Bills)
Bill No.6 - ENVIRONMENTAL CONTROL | ADDITIONS AND / OR OMISSIONS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
A | The accuracy of the quantities given in this Bills of Quantities is not guaranteed and the Contractor should satisfy himself as to their accuracy |  |  |  | 0
B | Any adjustments that he may consider necessary should be written below and on similar continuation sheets if required, and the net amount of the adjustments is to be carried to the summary
Additions
1
2
3
4
5
Omissions
1
2
3
4
5
Total of bill No.1 (Carried to summary of Bills) |  |  |  |  | 0
SUMMARY OF BILLS
Bill No. | Description |  |  |  | Amount (MVR)
1 | Preliminaries
2 | Dredging, excavation and earth work
3 | Breakwaters and revetments
4 | Quay wall structure
5 | Harbour Lights & Pavement
6 | Environmental control
7 | Provisional Sum |  |  |  | 3000000
8 | Additions and / or omissions
Goods and Services Tax
Grand total of Bills