Funadhoo Reclamation

- Sand borrow areas – are there any proposed borrow areas that need to be considered for the reclamation works.

Contractor to propose with the consultation of EPA.

- Revetment Drawings – there are two revetment drawings (DWG-CS/01/16 and RCS/01/16) which of these revetment drawings is the correct one that need to be considered

The drawings should be used as follows.

Kulhudhuffushi:

REC/01/16

RWCS/01/16

BRCS/01/16

Funadhoo:

REC/01/16

RCS/01/16

RWCS/01/16

RCS/01/16 is a correct drawing.

- The technical specification 6.1 spe

cifies that Dredging areas, dredging depths and dredging limits are specified in the drawing: REC/01/16, RWCS/01/16 – however the information cannot be seen in the drawings .

The Technical Specification 6.1: amended as follows;

6.1 Dredging areas, dredging depths and dredging limits: - Location to be proposed by the contractor from Eastern and Western side of the airport.

- Geo-textile for revetment – the drawings of revetment shows the use of geotextile, what is the specification for the geotextile to be used.

Geotextiles shall be porous, carpet‐like materials, made from synthetic fibres. Geotextiles are used as a separation layer and shall be in the form of a thin permeable membrane.

The geotextile shall be of polypropylene filter fabric and shall be resistant to air, water, chemical and bacteriological attacks. The geotextile shall fulfill the International Classification (DIN 54307) Class 4. The fabric shall be manufactured with and preserve the following mechanical properties according to DIN 54307

Description                                        Property

Weight of cloth                                    Min. 300g/m²

Tensile strength in:   a) warp:             Min 20 kN/m

b) weft:              Min 20 kN/m

Elongation at break: a) warp:             Min 50%

b) weft:              Min 50%

Penetration strength:                           Min. 3.3 kN

- BOQ item for Fill, grade & compaction for Runway, Turning Pads, Apron, Taxiway etc. .. is not included in the Funadhoo BOQ, where as it is included in the Kulhudhuffusi BOQ.

Not required for Funadhoo.

In the letter of bid and the contract data, it says that the bidders have to bid for the lump sum price. However, it is requested to amend this clause as a Measured - Price contract as the sea bed profile is unknown at this stage and therefore, it is difficult to check the quantities given in the BOQ.

Ans: Based on variation of the quantity the issue will be discussed with the Contractor upon completion of the detail survey and EIA report is approved.

- In the letter of bid and the contract data, it says that the bidders have to bid for the lump sum price. However, it is requested to amend this clause as a Measured - Price contract as the sea bed profile is unknown at this stage and therefore, it is difficult to check the quantities given in the BOQ

Ans: Based on variation of the quantity the issue will be discussed with the Contractor upon completion of the detail survey and EIA report is approved.

- In the Conditions of contract it says that Employer will carry out the design. However, in the BOQ (Bill No. 03 - General notes) says that “Design shall be checked and submitted for approval after investigation and Engineering study. Please clarify.

Ans: Based on the engineering study the issue will be discussed with the Contractor upon completion of EIA report is approved.

- Do we include the GST component in this tender? If so do we have to include it in the rates or show it as a separate component in the BOQ summary?

G.S.T. is to be included separately in the bid form.

- Funadhoo Island - Borrow locations for getting the filling material for the reclamation works are not shown in the layout drawing. Please give this detail also.

- Ans: Refer to the item 3 in Amendment 2  issued 3 May 2016.

- Funadhoo Island - What is the section between the two revetments.

- Ans: Refer to the item 2 in Amendment 2  issued 3 May 2016.