**Results Framework (RF) - Youth Development**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sector Outcome** | **Results Indicators** | **Indicator Type** | **Unit of Measure** | **Baseline** | **Targets/ Achievements** | | | | | | **Lead Agency** |
|  | **2009** | **2010** | **2011** | **2012** | **2013** |  |
| 1. Support programmes for prevention and after care of substance abuse among youth | 1. Intervention programmes to prevent substance abuse among youth, increased | Output | No. of participants | 0  (2008) | Target | 1000 | 1000 | 1200 | 1500 | 2000 | Y D /Youth Centres |
| Ach. | 742 | 951 |  |  |  |
| 1. Opportunities for isolated youth to reintegrate into society, increased | Output | No. of participants | Nil? | Target | 5000 | 5000 | 6000 | 6000 | 7000 | Y D /Youth Centres |
| Ach. | 4876 | 4908 |  |  |  |
| 1. Counseling and mentoring services for youth, increased | Output | No. of participants | 2008 | Target | 2000 | 2000 | 3000 | 4000 | 4000 | YD /Youth Centres |
| Ach. | 1749 | 1890 |  |  |  |
| 2. Promote healthy lifestyle among youth | 1. Physical and mental well-being among youth promoted | Output | No. of participants | Nil? | Target | 9000 | 9000 | 9000 | 10,000 | 10,000 | Y D /Youth Centres |
| Ach. | 6744 | 8000 |  |  |  |
| 1. Engaging youth through sports in addressing delinquency, increased | Outcome | No. of participants | Nil? | Target | 5000 | 5000 | 5000 | 6000 | 7000 | Y D /Youth Centres |
| Ach. | 3200 | 3900 |  |  |  |
| 3. Promote employment and entrepreneurship among youth | 1. Diversify youth centres functions focusing on career guidance | Outcome | No. job centres established in Youth Centres on an annual basis | Nil? | Target | NIL | 10 | 08 | 05 | 05 | NCGC/ YD/ Youth Centres |
| Ach. | NIL | 06 |  |  |  |  |
| 1. Support skills development programmes for youth | Output | No. of NGO’s working with | Nil? | Target | 30 | 40 | 40 | 50 | 50 | TIVET/YD/ Youth Centres |
| Ach. | 18 | Any achievement? |  |  |  |  |
| 1. Youth Challenge (further education and career guidance fair) | Event | No. of participants | 6000  (2008) | Target |  | 6000 | 10000 | 12000 | 15000 | YD |
| Ach. | 0 | 4300 |  |  |  |  |

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Support programmes to empower youth to be responsible, active citizens contributing to the national development | 1. Develop youth centres in all regions of the country | Output | No. of youth centres established, annually | Nil? | Target | 1 | 1 | 2 | 1 | 2 | YD |
|  |  |  |  |  | Ach. | 1 | 1 |  |  |  |  |
|  | 2. Promote volunteerism and social responsibility among youth | Output | No. of youth trained, annually | Nil? | Target | 300 | 500 | 700 | 900 | 900 | MVC/ YD |
|  |  |  |  |  | Ach. | 220 | 480 |  |  |  |  |
|  | 1. Establish Youth Councils (board) at national, provincial and island level | Output | Event | N/A | Target |  |  | (Development of a legal frame) work | Legal Framework developed and Nat. council established | 9 provincial youth council to be established |  |
|  |  |  |  |  | Ach. |  |  | Legal framework being drafted |  |  |  |
|  | 1. Conduct studies to review current youth programmes and activities | Output | Event | N/A | Target |  | Youth Mapping study conducted | Would the mapping study be used ? | Would the mapping study be used ? |  | YD |
|  |  |  |  |  | Ach. |  | Completed |  |  |  |  |
|  | 1. Re-establish Youth Parliament | Output | Event | N/A | Target |  | Conduct Youth parliament in collaboration with NGO |  |  |  | YD/NGO |
|  |  |  |  |  | Ach. |  | Completed |  |  |  |  |
|  | 1. Youth NGOs empowered and encouraged to participate in nation building | Outcome | No. of Youth NGOs affiliated | 252 (2008) | Target | 300 |  |  |  |  | YD/ Civil Society NGO’s |
|  |  |  |  |  | Ach. | 243 |  |  |  |  |  |
|  | 1. Recognise youth who make significant contributions to development | Output | Youth Awards | 61 (2008) | Target |  |  | Draft bill to be prepared | Bill drafted and submitted to parliament? |  | YD |
|  |  |  |  |  | Ach. |  |  | Bill being drafted |  |  |  |
|  | 1. Public awareness on youth issues and needs promoted | Output | Establishment of Youth Hotline Service | Nil? | Target |  |  | Programme to be launched |  |  | YD |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 1. Legislative framework for youth development, established | Output | Currently working on a Youth Act | Nil? | Target |  |  | Draft bill to be prepared | Bill Drafted and submitted to parliament? |  | YD |
|  |  |  |  |  | Ach. |  |  | Bill being drafted |  |  |  |
|  | 1. Create platforms for youth development and avenues for exposure (international and national) Create platforms for youth development and avenues for exposure (National and International Platforms | Outcome | Through invitations from affiliated international organisations | 200 Nil?8 | Target |  |  |  |  |  | YD |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
| 5. Promote culture and creativity among youth | Promote cultural activities among youth | Outcome | New programmes to be conducted | Nil? | Target |  |  |  |  |  | YD/NCA/Youth Centres |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |