Results Framework (RF) – Information, Arts and Culture

Leading Committee: MoTCA (Planning Section)

Steering Committee: MoTCA, DoH (Zakariya Hussein) , NL (Fathun), NCA (Saleem), Center of Language and History

Indicators:

- Maldivian society will be a society where each individual is able to access information and use it responsibly.

- Maldivian society will be a society where each individual will have knowledge of Maldivian culture and heritage

- Maldivian society will have knowledge and be enriched by increased engagement in arts and culture.

| Sector Outcome | Results Indicators | Indicator Type | Unit of Measure | Baseline | Targets/ Achievements |  |  |  |  |  | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2009 | 2010 | 2011 | 2012 | 2013 |  |
| - SSkills development of the artistic community developed and arts promoted to increase sector productivity and appreciation of wider public (P1) | - NNational Art Council established (P1 S1) | Output | Event | (2008) National Arts centre established | Target |  |  | Art Council Act drafted; passed and ratified |  |  | NCA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Arts Development Fund administer by the national Arts Council, established (P1 S2) | Output | Event | (2008) N/A | Target |  |  | Art Development fund established |  |  | NCA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 3. System for development of Artistic tradition and Training of Human Resources, enhanced (P1 S3) | Output | Event | (2008) no system | Target |  |  |  | Systems/ programs developed | Systems/ programs developed | NCA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 4. Public initiatives in promoting arts supported by the National Arts Centre, increased (P1 S4) | Outcome. | No |  | Target |  |  | 6 exhibitions to be held (display art of different pple/ groups\) | 6 exhibitions held (display art of different pple/ groups\) | 6 exhibitions held (display art of different pple/ groups\) | NCA |
|  |  |  |  |  | Ach. |  |  | 3 exhibitions held |  |  |  |
|  | 5. Facilitate arts and crafts practitioners to cater for tourist audiences (P1 S5) | Outcome |  |  | Target |  |  | Land obtained for Arts and Crafts Centre | Arts and crafts centre to be built | Promote the centre in tourist resorts; sell products from the centre | NCA |
|  |  |  |  |  | Ach. |  |  | Land obtained for Arts and Crafts Centre |  |  |  |
|  | 6. Formulate and host international arts and crafts festivals, and obtain opportunities from the international arena (P1 S6) | Outcome | Event |  | Target |  | Hay festival held | Hay festival held | Hay festival held; philharmonic orchestra held | Hay festival held | NCA |
|  |  |  |  |  | Ach. |  | Hay festival held |  |  |  |  |
|  | 7. Encourage and assist the public in organizing art promotion events and festivals (P1 S7) |  |  |  | Target |  |  |  |  |  | NCA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
| 2. Linguistic heritage of Maldives, conserved (P2) | - Ttext and Electronic media documentation produced on divers dialects in different regions, increased (P2 S1) | Output | No. |  | Target |  |  |  |  |  | DoH |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Ffacility for Conservation of text and electronic media produced (P2 ?”) | Output | Event |  | Target |  |  |  |  |  | DoH |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - CConduct Awareness programs and competitions on Dhivehi language (P2 S2) |  |  |  | Target |  |  |  |  |  | DoH |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - FFacilitate linguistic research and dissemination (P2 S3) |  |  |  | Target |  |  |  |  |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |

| 3. Strengthen the National Library under the Library Act, and develop and enhance library services across the country. (P3) | 1. Conduct capacity building programs for library management of the National Library. (P3 S1) | Output | No. of trainings for the staff |  | Target |  | 10 | 18 | 20 | 20 | NL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  | 6 | 11 | - | - |  |
|  | 2. Acquisition of conservation materials and archiving. (P3 S2) | Output | % |  | Target |  | N/A | 50 | 75 | 100 | MOTAC; NCHLR |
|  |  |  |  |  | Ach. |  | 0 | 2 | - | - |  |
|  | - TStaff training for conservation and preservation of physical written material | Output | No |  | Target |  |  |  | 4 | 4 |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - EEstablish a Library Board (P3 S3) | Output | Event |  | Target |  |  | Libarary board estbalished | - | - | MOTAC; NL |
|  |  |  |  |  | Ach. |  |  | Libarary board estbalished | - | - |  |
|  | - AAdopt a Library Act (P3 S4) | Output | Event |  | Target |  |  | Act drafted | Act passed and ratified | - | MOTAC; NL, AGO, LC |
|  |  |  |  |  | Ach. |  |  | Act drafted | - | - |  |
|  | - IImplement the Legal Deposit (P3 S5) Law | Output | Event | (2008) Law ratified | Target |  |  | Implementation begun; equipment for storage and access of material acquired | - | - | NL |
|  |  |  |  |  | Ach. |  |  |  | - | - |  |
|  | - IInitiate and run mobile library services(P3 S6) | Outcome | No. of mobile library activities conducted |  | Target |  | 2 | 12 | 12 | 12 | NL |
|  |  |  |  |  | Ach. |  | 4 | 3 | - | - |  |

|  | - Availability of (Acquiring materials; books CD’s, academic and research serials etc.) according to public needs increased. (Budget endorsed and through local, regional and international depositors) (P3 S7) | Output | % achieved based on the available budget |  | Target | N/A | N/A | 135,000 | 135,000 | 135,000 | NL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  | 740 | - | - |  |
|  | - NNational library upgraded with family friendly services and similar branches established; technical assistance provided to branches (P3 S8) – Alternate between urban and rural islands | Output | No |  | Target |  |  | 1 | 1 | 1 | NL |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 9. Training programs conducted for librarians in Maldives (P3 S9) | Output | No | (2008) | Target |  |  | 6 | 6 | 6 | NL |
|  |  |  |  |  | Ach. |  |  | 2 |  |  |  |
|  | 10. Separate library and adjoining park for children established (P3 S10) | Output | Event | (2008) | Target |  | Children’s librarby established and operating | Adjoining park completed |  |  | MOTAC; NL, Male' Municipality, MHTE |
|  |  |  |  |  | Ach. |  | Library opened on March 2010 |  |  |  |  |

|  | 11. A building to accommodate the National, Public and Children’s Library built (P3 S11) | Output | Event |  | Target |  |  | - | Buidling drawings completed | Building construction started | Building completed | MOTAC; NL, Male' Municipality, MHTE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  | - | Project approved by NPC for external financing. In itial requirement being prepared. |  |  |  |
|  | 12. Awareness on library use and reading increased | Impact | Event |  | Target |  |  |  | Readingcampaign conducted; monthly lectures on salinet topics conducted; publicity for new books | Readingcampaign conducted; monthly lectures on salinet topics conducted; publicity for new books | monthly lectures and activitieson salinet topics conducted; publicity for new books |  |
|  |  |  |  |  | Ach |  |  |  |  |  |  |  |
|  | 13. Library services that contribute to promotion of Islamic Faith increased | Outcome |  |  | Target |  |  |  | Obtain collection of reading material on Islamic Study | Obtain collection of reading material on Islamic Study | Provide services |  |
|  |  |  |  |  | Ach |  |  |  |  |  |  |  |
|  | 12. Public access to online and digital media increased.(P3 S12) | Output | Event |  | Target | - |  | Awareness of opensource software | Required hardware acquired, required software acquired | Material/ content created; public access granted | Material/ content created | NL |
|  |  |  |  |  | Ach. | - |  | Introduction of greenstone and koha to the library community |  |  |  |  |
| 4. Development of the cultural and archeological heritage of the Maldives enhanced (P4) | 1. Museum planning committee established (P4 S3) | Output | Event |  | Target |  |  |  |  | Committee established |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | - Inventory of cultural and heritage sites compiled (P4 S5) |  |  |  | Target |  |  |  | Training on inventory taking conducted; Inventory taking commenced | Inventory completed |  |  |
|  |  |  |  |  | Ach. |  |  |  | Training on inventory taking conducted; Inventory taking commenced |  |  |  |
|  | 1. National Centre for Historical and Linguistic Research capacities developed and affiliated to the proposed university (P4 S8) |  |  |  |  |  |  |  | NCHLR transferred |  |  |  |
|  | 2. Heritage Council and Department of Heritage to the cultural heritage, established (P4 S5 and S6) | Event |  | (2008) NIL | Target |  |  | Department of Heritage established | Heritage committee estabalished | Preparatory work for Heritage council completed | Heritage Council established |  |
|  |  |  |  |  | Ach. |  |  | Department of Heritage established | Heritage committee estabalished |  |  |  |
|  | 3. Products developed for promoting cultural tourism, increased (P4 S1) | Op | No. | (2008) – Utheemu ganduvaru | Target |  |  |  | ‘Kuruhinna tharaagandu’ (kaashidhoo) begun; ‘Kalaafaanu Ziyaarath’ (Hangnaameedhoo) begun | ‘Kuruhinna tharaagandu’ (kaashidhoo) completed; ‘Kalaafaanu Ziyaarath’ completed | N. Landhoo Maabudhuge area developed |  |
|  |  |  |  |  | Ach. |  |  |  | ‘Kuruhinna tharaagandu’ (kaashidhoo) begun; ‘Kalaafaanu Ziyaarath’ (Hangnaameedhoo) begun |  |  |  |
|  | 4. Radio/ TV programmes / print media in promoting language and history among students, increased (P4 S12) | Op | No. | (2008) | Target |  |  |  | Programme conducted on heritage day and national day; print media rn for Heritage council completedey completed000000000000000000000000000000000000000000000000000000000000000000000 | Programme conducted on heritage day and national day | Programme conducted on heritage day and national day | Centre for Language and History/ DoH |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | Hukuru Miskiy inscribed as a World Heritage Site |  |  | (2008) Included in tentative list | Target | Supplementary work ongoing |  | Supplementary work ongoing | Supplementary work ongoing | Supplementary work completed | Included in World Heritage list |  |
|  |  |  |  |  | Ach |  |  |  |  |  |  |  |
|  | 5. Revenue from visitor to cultural and heritage sites increased (P4 S10) | Imp | % | (2008) | Target |  |  |  | 5 | 5 | 5 | DoH |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
| 5. National Archive established (P5) | 1. Archival Act enacted (P5 S1) | Output | Event |  | Target |  |  |  | Archival Act drafted and subage day and national daydyion of Islamic Faithanches000000000000000000000000000000000000000000000000 | Archival Act passed and ratified |  | DoH |
|  |  |  |  |  | Ach. |  |  |  | Archival Act drafted and sub |  |  |  |
|  | 2. Archival material in custody of National Archives, increased(P5 S2) | Outcome |  | (2008) | Target |  |  |  | Vilgon Collection obtained; Acquire other materials | Vilgon Collection cataloqing completed; Acquire other materials Collection obtainedtified000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000 | Acquire other materials | DoH |
|  |  |  |  |  | Ach. |  |  |  | Vilgon Collection obtained |  |  |  |

| 6. Ensure a system of media regulation conducive to freedom of expression and diversity of media in accordance with the tenets of the constitution (P6) | - Establish an independent Media Council to regulate broadcast media (P6 S1) | Outcome | Event |  | Target | Drafting the bill | Amend BC Law | Media Council formed |  |  | MBC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  | BC law amended | Media Council formed |  |  |  |
|  | - Establish a Right to Information law in line with international standards and enable public bodies to realise their obligations in accordance with the law (P6 S2) |  | NA |  | Target | Shifted to Home min |  |  |  |  | MHA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 3. Criminal defamation to be abolished and rules on civil defamation to be revised in line with international standards (P6 S3) – ask tourism |  |  |  | Target |  |  |  |  |  | ? |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 4. System for registration of newspapers to be abolished or revised so that it is a technical registration system (P6 S3) | Output | Event |  | Target | Had talks with MTED | Had talks with MTED | Had talks with MTED |  |  | DOI/ MTED |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Cooperate with the Ministry of Economic development to prepare Intellectual Property regulations (P6 S4) | Output | Event | NA | Target |  |  | Property law amended |  |  | MTED |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
| 7. Provide for a level economic playing field and transparency of ownership within a diverse and vibrant media environment (P7) | - Establish clear and enforceable rules limiting concentration and requiring transparency of media ownership (P7 S1) |  | NA |  | Target |  | MMC law amended |  |  |  | MMC |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Establish legal framework and plan for the allocation of broadcasting license and frequencies that envisages an equitable sharing of frequencies among public, commercial and community broadcasters (P7 S2) | Output | Event |  | Target |  |  |  |  |  | MBC |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |

|  | - Broadcasting licensing system to be used to promote diversity in the airways (P7 S3) | Outcome |  |  | Target |  |  |  |  |  | MBC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Formulate and implement clear and fair rules for the allocation of public advertising (P7 S4) | Output | Event |  | Target |  |  |  |  |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
| 8. Support media as a platform for democratic discourse (P8) | 1. Through dialogue with the media community, facilitate the creation of a Media Council, possibly through a revised law that does not provide for restrictions on content, to develop professionalism and act as a self-regulatory body (P8 S1) | Output | Event | NA | Target |  | MMC Law to be amended |  |  |  |  |
|  |  |  |  |  | Ach. |  | MMC law amended |  |  |  | MMC |
|  | 2. Establish the Maldives National Broadcasting Corporation as an independent public service broadcaster (P8 S2) | Outcome | Event | NA | Target |  |  | Establish MNBC |  |  | MBC |
|  |  |  |  |  | Ach. |  |  | Established |  |  |  |
| 9. Enhance capacity building in the areas of technical and professional development to create a solid foundation for Freedom of Expression, pluralism and diversity (P9) | - IIncorporate media education and training and professional development courses into the Faculty of Arts at the College of Higher Education (P9 S1) | Outcome | Event |  | Target | Courses developed in consultation with College of Higher Educ. |  |  |  |  | DOI/ Faculty |
|  |  |  |  |  | Ach. | Courses ongoing | Courses ongoing |  |  |  |  |
|  | - PProvide training for government ministries and agencies on media relations and the Right to Information (P9 S2) |  | NA |  | Target |  |  |  |  |  | MHA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - FFacilitate an environment in which professional representative bodies can exist and function to serve journalists (P9 S3) |  | NA |  | Target |  |  |  |  |  | MMC |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |

| 10. Ensure infrastructural capacity to support media and communication, including new media and the Network Communications Environment (P10) | - IIn conjunction with relevant Ministries and agencies and the private sector, work towards the roll-out of a national ICT network that facilitates connectivity that is affordable for all communities throughout the Maldives (P10 S1) |  | NA |  | Target |  |  |  |  |  | CAM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach |  |  |  |  |  |  |
|  | - EEnsure the institutional independence of the Communications Authority and ensure transparent and accountable regulation of the ICT and mobile telephone sectors (P11 S1) |  | NA |  | Target |  |  |  |  |  | CAM |
|  |  |  |  |  | Ach |  |  |  |  |  |  |
|  | - DDevelop a national ICT strategy to facilitate e-governance and access to information for all (P12 S1) |  | NA |  | Target |  |  |  |  |  | CAM |
|  |  |  |  |  | Ach |  |  |  |  |  |  |