Format for Mid the Term Evaluation of the Achievement of Sector Outcomes of the Strategic Action Plan (2009 – 2013) of the Government of Maldives

PREVENTION OF NARCOTICS ABUSE AND TRAFICKING

- Sector Overall Progress (500 words)

{A description of the extent to which the Sector Outcomes as specified in the policy goals were realized in the period under review}

DEMAND REDUCTION - In demand reduction the sector was able to establish two detoxification centres first time in the country. That is one in Male’ and one in the south. The two centres remain at optimum capacity and always have a long listed queue of clients waiting for treatment. In partnership with NGOs three dropping centres were also put in place one in Fuah mulak and two in male’. Therefore, sector was able to increase the number of people accessing rehabilitation. Also plans have been laid out during the period under review to set a female rehab centre in vilimale and expanding the dropping centre in Fuah mulak. - Prevention activities were carried in the sector but mostly done by ministries separately (MOE, MOHF, MYHRS,MIA). Since the activities were done in isolation the impact expected was not achieved. Also resulted in duplication of resources. However, work was started to bring together all actors in prevention. A technical committee was set up to launch a pilot drug education project in schools. The committee included key people from DDPRS, MOE, MHRYS. - The sector was able to engage with NGOs and develop their capacity to deliver better services in the sector.13 NGOS have been contracted and funded by UNODC project during the period under review - DDPRS was formed to have focused interventions in the sector; the dire need for capacity building of the department is noted here. - The lack of prison-based rehabilitation was noticed and regulations were reviewed to give access to rehabilitation for those under drug use convictions SUPPLY REDUCTION - The supply reduction agencies were able to coordinate work together towards the supply of drugs brought into the country. Joint operations were carried out by MPS and MCS - MCS took initiatives to regulate the Ports to minimum requirement standards in order to increase surveillance and decrease narcotic trafficking through the ports. - Drug enforcement department set up within the MPS to have focussed intervention in supply reduction of narcotics - MCS and MPS have jointly initiated a project to bring narco dogs to Maldives under Indian assistance during the review period - MCS under UNODC funds have launched CBT at MCS for all drug enforcement officers COORDINATION - The narcotics Control Council was established at the President’s Office for better coordination of the agencies within the sector - The Drug Bill was drafted with sector wide consultation and submitted to parliament during the review period

  - Progress on Key Sector Outcomes

{For each sector outcome briefly describe the achievement made and the extent to which implementation was carried out as envisaged by the Strategies / Intervention List of the SAP. If there were any deviations what were they and the causes}

| Outcome |  | Progress | Issues |
| --- | --- | --- | --- |
| 1. | Strengthen professional treatment and rehabilitation of drug abuse | 2 detox centres established -- clients treated | - not able to reach certain areas of the country - not able to cater to the need/demand for treatment - budgetary issues for maintenance of treatment centres to run effectively |
| 2. | Prevention of substance abuse | -- programs conducted | - duplication of activities between different agencies - lack of counsellors/technical staff to work in different locations in ddprs - higher turn over of staff in remote areas |
| 3. | Enhance role of NGO, Private sector and Civil society in service provision and addressing issues | -- + 11 NGOs engaged by UNODC | - lack of monitoring - travelling costs |
| 4. | Enhance capacity and coordination among all stakeholders to address various aspects of the drug problem | --NCC meetings held regularly at President’s Office --National Survey funded by UNODC is underway |  |
| 5 | Prevention of substance abuse | Established OPS Team in Airport and seaport Established OPS Team in “Thilafushi” | - Man power - Working place - Budgetary issues to run effectively |
| 6 | Enhance capacity and coordination among all stakeholders to address various aspects of the drug problem | Intelligence sharing with neighbouring countries. Build and sustain Good relations with other law enforcement agencies Seeking assistant from DEA /US | - lack of resources - Difficulties of conviction - Insufficient rehabilitation |
| 7 | Enhance capacity and coordination among all stakeholders to address various aspects of the drug problem | Effective awareness programmes undertaken for public. | - Inappropriate or indecent detention services - Ineffective Rehabilitation |
| 8 | Enhance capacity and coordination among all stakeholders to address various aspects of the drug problem | 24 hour surveillance of the capital city by DED. Improved or strengthening intelligence. Effective investigation undertaken and special attention given to cases of drug traffickers. | - Lack of sufficient resources - Integrity issues faced to other related organization. - Financial issues. - Insufficient human resources and financial difficulties. |
| 9 | Prevention of substance abuse | Day to day briefing and progress analysis. | - Communication issues |

  - Institutional Achievements in relation to the Sector Outcomes

{Briefly describe the role of key institutions in relation to the key sector outcomes and their achievements}

| Name of Institution(s) |  | Major Responsibilities towards outcomes | Achievement |
| --- | --- | --- | --- |
| 1. | DDPRS | - Treatment and rehabilitation of users - Prevention and awareness (youth, parents, Government offices, general public) | - No of service centres increased - Community based prevention programs increased - 3 Drop-in centres established |
| 2. | Police | - Creating a safer and more secure society for all. - Reducing the Prevention of crime. (Apprehension of offenders) - Reducing the fear of crime. | - Public awareness programmes. - Forming of crime prevention committees throughout the region to tackle and prevent crime. |
| 3. | Maldives Customs Service | Border Control | Substantial progress has been made though the planned targets were not fully met |
| 4. | Dept. of Immigration | Activity of traffickers to and from the country | Do surveillance work on the activities of drug dealers at entry points into the country |
| 5. | Ministry of Human resources youth and sports | Prevention and advocacy activities among the youth | Outreach work carried out to engage at risk and vulnerable youth groups |
| 6. | Ministry of Education | Prevention and advocacy activities among students, teachers and parents | Drug education started as pilot project in 12 schools |
| 7. | Ministry of Islamic Affairs | General awareness | Friday sermons focussed on drug issue |

- Overall Assessment of Sector Performance related to key aspects

Operational Progress (300 words) {Explain the Extent to which implementation was carried out as envisaged by the Strategies / Intervention List of the SAP. If there were any deviations why was this and what where they.}

Demand Reduction - Establishment of detox centres (2 centres) - Detox Centres extended to south (1 detox in hulhumeedhoo) - Drop-in centres established in Male and South (2 in Male, one in fuvah mulah) - 2 technical staff trained in US for models of rehabilitation treatment - 2 counsellors currently under going training in counselling - Total oversees training (demand reduction) - Total local training (demand reduction) - Monitoring and Supervision of Regional service centres Supply Reduction - Special task team allocated to the Male’ International Airport - Special task team allocated to the Sea Port of Maldives. - Special task team allocated at “Thillafushi” Island for supervision - Created a more secure intelligence sharing network between 04 Atolls. - Special operation conducted at capital city Male’ and Atolls. - Overseas training for (Investigation officers and intelligence officers) - Local training for (Investigation officers and intelligence officers) - Case study and review of similar issues and information’s internationall - Ports with Strengthened access control and monitoring capacities, increased - Ports with upgraded intelligence and Risk Management mechanisms for border enforcement progressing - Some of the X-ray scan machines upgraded at the airport - Establishment of Male’ Commercial Harbor Monitoring System (CCTV) at the final stages - Airport Interdiction Room is in the process of establishment - Capacity building in terms of training, improved eg: UNODC CBT Program - More operations carried out with other enforcement agencies, than before - Process of acquiring sniffer dogs, progressing. - Advance Passenger Information System (APIS), in the process of establishment

Financial Performance (200 words) {To what extent was the budget allocation utilized and if budgetary shortfalls were encountered what were the likely causes what impact did it have in regard to pursuing the Strategies / Intervention List of the SAP}

Demand Reduction - budgets allocated for programs for one year is not sustained over for the next year therefore, effects results (eg; when the new UNDAF was signed, programs were changed) Supply Reduction - Insufficient resources and budget issues faced. - Available budget was properly utilized - Lack of adequate budget for training (for sending officers abroad or bringing an expert) - Lack of budget for acquiring tool, equipments, scanning facilities, testers, etc. - Lack of budget to acquire speedboats for monitoring and surveillance port areas

Institutional Linkages (100 words) {If any institutional linkages were expected to be developed during the implementation, to what extent were they achieved. If not what were the main causes and what was the affect on the implementation.}

Demand Reduction - Narcotics Control Council established which facilitated the much needed coordination between stakeholders especially in the area of demand reduction - For successful implementation of prevention programs more efforts have been put into to work towards one work plan amongst DDPRS, MOE and MOHRYS. Office awareness program in 2010, empowered youth program in 2010 was conducted in collaboration with MPS and MCS. - Drug education programs through life skills have been proposed. Technical committee set up by MOE to implement this activity. Supply Reduction - Improved information and intelligence sharing between other related organizations and joint investigation undertaken. - A Drug Intelligence Unit formed. - Greater effort and time given to strengthen the acquaintance between other law enforcement agencies. - Close relationship with MPS, MNDF built, in terms of information exchange, carrying out collaborative operations, and capacity building. - MOU signed between MCS and MPS for information exchange and coordinated operations

Sustainability (100 words) {To what degree could the operational aspects; including institutional linkages if any can be carried forward and describe any essential criteria required to facilitate this}

Demand Reduction - NCC meetings held regularly, which facilitated closed coordination of the key stakeholders. Dedication and commitment from policy makers necessary to sustain the coordination mechanisms - The treatment committee has been set up to facilitate the rehabilitation especially of prisoners and volunteer clients. Transparent operating procedures of the committee required for the sustainability of committee - The technical committee set up Supply Reduction - 24 hour surveillance of the capital city with intelligence led policing. - Special operations which were conducted targeting specific “Hot Spots” have shown positive results. - Targeted special operations conducted at Atolls.

3.0	Key Issues encountered

Institutional (200 words) {Discuss the Strategic position of the Lead Agency and how it affected the Implementation of Strategies/ Operational Performance}:

Demand Reduction DDPRS is the leading agency in providing treatment, rehabilitation and prevention services. There is lack of coordination between DDPRS and the other responsible agencies and also within the DDPRS itself. This lack of coordination between the stakeholders has created misleading and duplication of information, hence resulting in ineffective implementation of programs and receive less cooperation from the target audience. Supply Reduction The MCS and the MPS have been the lead agencies in the area of supply reduction. There is a strong sense Lack of coordination between the drug enforcement agencies, however there lacks coordination between MPS and some other key partners such as DPRS, the PG office, and criminal courts.

Implementation (200 words) {Matters relating to implementation finances, human resources, monitoring and oversight}

Demand Reduction - Difficulty to reach islands due to procurement complications (Maaliyyathu Qaanoon) - Bureaucracy in applying for services is too long for effective implementation - Lack of technical staff (need to fly over counsellors to other institutions when counsellors based there take leave) - Main activities of DDPRS depend of Donor funding and delay in finalising Donor activities restricts implementation of DDPRS programs Supply Reduction - Ineffective resource allocation and specialization. - Laws which subdue the effective work of the police. - lack of adequate technical training (for sending officers abroad or bringing an expert) - Lack of tool, equipments, scanning facilities, testers, etc. - Lack of speedboats for monitoring and surveillance port areas - Lack of budget to acquire the above and carry out implementation.

Environmental : (100 words) {Environmental 9including Operational aspects) aspects which were encountered and need to be addressed}

Demand Reduction - Bad weather has created delays in conducting programs at the past. Supply Reduction - Lack of proper legislation (this issue has been addressed once Maldives Customs Act has come into being)

Political (100 words) {Political considerations encountered and to be addressed}

- The anti drugs programme is the 5th pledge of the Government. Thus the work done in the sector often politicised by media. The community spirit required to implement the work of the sector often hindered by un due criticisms due to being politicised.

Socio/ Cultural (100 words) {Socio Cultural considerations encountered in respect of operation and implementation}

Demand Reduction - Restrictions from public especially parents when prevention programs are planned (after late 90’s awareness programs where drugs and drug paraphernalia were shown to the audience, this encouraged more to the habit) - Restrictions from religious scholars against establishment of MMT - Drug addiction still looked upon as a severe criminal offence and thus hinders community support required for community rehabilitation. Supply Reduction - Lack of awareness among victimized families and the conventional trends still genera public thereby demanding punitive measures to be undertaken against drug users - No differentiation between drug user and drug dealer by law - Higher expectations of public not met, every dealer caught often walks free so law enforcement and public demoralized and discouraged

Gender (100 words) {Gender related issues encountered during operation and implementation}

Demand Reduction - no separate gender specific facilities available (detox centres, rehab facilities) - few female recovering volunteers in the atolls compared to Male Supply Reduction - no separate gender specific facilities available (detention service, isolations)

Statistical and Data Collection (100 words) {All the data sources used. Other factors which surfaced in the operation and implementation}

Demand Reduction - Absence of inter-sectoral information sharing system. - No database program within DDPRS (intra-sectoral) - No data analysis done to understand trends, patterns - No data maintained to monitor relapses - No procedures for data collection Supply Reduction - Data is maintained - No analysis done on the available data - Each law enforcement body maintains its own data thus difficulty in ascertaining actual supply of drugs into and in the country - No procedures for data collection

3.0 Lessons Learnt (300 words)

{Discuss the Lessons Learnt in the process of carrying out interventions relevant to realization of the Sector Outcomes as specified in the SAP. Focus on the involved agencies and other stakeholders (including beneficiaries) and their willingness and capability to continue the interventions. If not what additional measures would need to be taken to strengthen them}

- Need to make treatment and aftercare services more accessible through out the country, to prevent relapses - 2011/R-1 Qawaaid opened doors for more people to go for treatment, but the rehabilitation centre, detox centres and aftercare systems are not equipped to cater for them, therefore need to be addressed. - Need to define the role of DDPRS more specifically and organised within DDPRS for more effective working environment

- Partnerships (200 words)

{Describe any partnerships established with a donor, private sector of civil society organization to achieve an outcome(s)}

International Partners - UNICEF (rolling work plan 2011-2012 of UNDAF) - UNODC (EC project) - UNDP (global Fund) Local partners - Journey - SWAD - Hand-in-Hand - Open Hand Treatment programs (drop-in centres, outreach programs) Supply Reduction Established partnership with UNOCD to conduct UNODC Computer-Based E-learning Program on Drug Law Enforcement at MCS. MCS is established as the National UNODC CBT Centre

- Follow-up Actions & Recommendations  (400 words)

{Recommendations for strengthening, reorienting and/or revising the implementation mechanisms and strengthening the key agencies and other stakeholders for achieving Sector Outcomes in future periods}

- The lack of coordination amongst the key agencies in demand reduction has led to duplication and in effective programme implementation therefore it is important to put in place better coordination mechanisms to foster better working environments in the demand reduction sector. It would be beneficial to work towards one work plan in the area of rehabilitation and prevention. This is recommended for not only within Government but Government and partner NGOs as well. - Capacity building of the two main partners in rehabilitation is also vital. That is in DDPRS and DPRS. Currently every Department or ministry has worked in its own territory it is important to step beyond this and share expertise and information for the success of the drug sector. Though NCC exists lack of interaction is noticed amongst key agencies especially at operation level. Regular meetings at this level would also be helpful - In supply reduction lot of operations are carried together and there is coordination amongst key law enforcement agencies. This could be further improved by formalising and putting in place procedures for regular coordination and monitoring of supply reduction activities - Can work together especially during budget process to see how resources could be most effectively sued to benefit the whole sector - Data collection and analysis needs to be streamlined to get better clearer situation reports of the drug problem - Currently data collected and reported on adhoc basis, regular intervals need to be set for this, both in demand and supply reduction.

Date: 26 June 2011

Name of Officer:  Aishath Shuweikar

Designation: Deputy Undersecretary

President’s Office