| Results Framework (RF) - Fisheries |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sector Outcome | Results Indicators | Indicator Type | Unit of Measure | Baseline | Targets/ Achievements |  |  |  |  |  | Lead Agency |
|  |  |  |  |  |  | 2009 | 2010 | 2011 | 2012 | 2013 |  |
| 1.Scope of Fisheries sector in the economy enhanced ensuring sustainability of fish and marine products (P1) | 1. Fishers trained on Long line Fishing for Yellowfin and Bigeye Tuna (P1S1) | Output | Number of fishers trained | 0 | Targ. | 30 | 75 | 130 | 60 | 60 | MOFA |
|  |  |  |  |  | Ach. | 30 | 25 |  |  |  |  |
|  | 2. SMEs including women managed / led SMEs, engaged in Skipjack industry increased. (P1-S3) | Outcome | Number of permits issued to SMEs to purchase skipjack. | 0 | Targ. | 0 (permit to issue SMEs started in yr 2010) | 16 | 10 | 10 | 10 | MOFA / MED |
|  |  |  |  |  | Ach. | 0 | 16 |  |  |  |  |
|  | 3.Long line fishing vessels of Private Sector increased (P1-S2) | Outcome | Number of operating vessels | 0 | Targ. | 0 (Long line fishing is new – undergoing training during this period – refer P1S1)) | 0 (Long line fishing is new – undergoing training during this period – refer P1S1)) | 31 | 34 | 38 | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 4. Volume of fish landed from long line fishery (P1-S1) | Output | Metric tonnes | 0 | Targ. | 0 (Long line fishing is new – undergoing training during this period – refer P1S1) | 0 (Long line fishing is new – undergoing training during this period – refer P1S1) | 8,800 | 8,500 | 10,800 | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 5. fishing vessels engaged in tuna pole and line (P1-S2) | Output | No of vessels | 1,036 | Targ | 1,061 | 1,061 | 2,000 | 2,500 | 3,000 | MOFA |
|  |  |  |  |  | Ach | 1,061 | data not available yet from the Fishers |  |  |  |  |
|  | 6. Volume of fish landed from pole and line fishery (P1-S1) | Output | Metric tonnes | 116,842.62 in 2008 | Targ | 99,885.08 | 100,885.08 | 100,985 | 101,085 | 101,185 | MOFA |
|  |  |  |  |  | Ach | 99,885.08 | data not available yet from the fishers |  |  |  |  |
|  | 7. Fishing vessels engaged in hand line fishery (P1-S2) | Output | No of vessels | 386 | Targ | 425 | 425 |  |  |  | MOFA |
|  |  |  |  |  | Ach |  | data not available yet from the fishers |  |  |  |  |
|  | 8. Volume of fish landed from hand line fishery (P1-S2) | Output | Metric tones | 7,737.29 in 2008 | Targ | 10,326.03 | 11,236 | 12,236 | 13,236 | 14,236 | MOFA |
|  |  |  |  |  | Ach | 10,326.03 | data not available yet from the fishers |  |  |  |  |
| 2. Regulate the market to ensure that changes in the buying price of fish in international markets are passed through to local fishermen. (P2) | 1. Floor price revised weekly (P2-S1) | Output | Event | A floor pricing mechanism is established. Needs annual revision based on surveys and international market data. | Targ. | Revision periodically (100%) | Revision periodically (100%) | Revision periodically | Revision periodically | Revision periodically | MOFA |
|  |  |  |  |  | Ach. | Revised (100%) | Revised (100%) |  |  |  |  |
| 3. Expansion of Business development, trade and export promotion in fisheries. (P3) | 1. MSC Certification for skipjack fishery to promote marketing of fish and fishery related products from pole and line fishery. (P3-S4) | Outcome | Event | Pre-assessment process started (2008) | Targ. | Report on completion of pre-assessment | Report on completion of Full assessment | Certification and implementation |  |  | MOFA |
|  |  |  |  |  | Ach. | Report on pre-assessment | Report on full assessment |  |  |  |  |
|  | 2. Operate a dedicated FAD center for the construction and installation of FADs. (P3-S7) | Output | Number of FADs | 13 | Targ. | 20 | 20 | 20 | 20 | 20 | MOFA |
|  |  |  |  |  | Ach. | 22 | 23 |  |  |  |  |
|  | 3.Extension of repayment of loan period for Fishing vessels and Engines to Fishers from 6 to 10 years (P3-S8) | Output | Number of agreements | 0 | Targ. | 9 | 8 | Extend individuals who apply |  |  | Bank of Maldives / MOFA |
|  |  |  |  |  | Ach. | 9 | 8 |  |  |  |  |
|  | 4.Develop and finance acquisition of low cost Refrigerated Sea Water systems for local fishing crafts (P3-S1 & S2) | Output | Number | 6 loans issued for 6 RSW/vessels | Targ. | 6 | 6 | 6 | 6 | 6 | MOFA |
|  |  |  |  |  | Ach. | 0 (No application for the loan) | 0 (No application for the loan) |  |  |  |  |
|  | 5.Participation in fish trade fairs / events (P3-S5) | Output | Number of events | INFOFISH tuna fair every second year and Brussels Seafood EXPO every year. | Targ. | 1 | 2 | 1 | 2 | 1 | MOFA |
|  |  |  |  |  | Ach. | 1 | 2 |  |  |  |  |
|  | 6. Establish a “Maldives Fish” Brand in compliance with international standards. (P3-S6) | Output | Event | 0 | Targ | Project started | Project to be finalized | Project to be started in last quarter of 2011. s |  |  | MOFA |
|  |  |  |  |  | Ach | 0% | 0% |  |  |  |  |
|  | 8.Provide soft loans to assist in upgrading fish processing facilities established by fishing communities (P3-S9) | Output | No of loans | 0 | Targ. | 0 | 0 | Started to issue in 2011 |  |  | MED |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 9. Provide training for the production of high quality fishery products (P3-S10) | Output | Number of trainings | 1 | Targ. | 10 | 8 | 6 | 5 | 5 | MOFA |
|  |  |  |  |  | Ach. | 6 | 8 |  |  |  |  |
|  | 10. Financial Assistance schemes to develop ice plants (P3-S10) | Output | Number of loan | 0 | Targ. | 0 | 4 | 4 (Revised) | 0 | 0 | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 | 1 sanctioned to date | 0 | 0 |  |
| e4. Sector Capacity Building and Training, enhanced (P4) | 1. Establishment of Maldives Fisheries Training Centre (P4-S4) | Output | Event | 0 | Targ. | 1 Center |  |  |  |  | MOFA |
|  |  |  |  |  | Ach. | 1 Center established |  |  |  |  |  |
|  | 2. Conduct a National campaign to promote fishing industry among the nation’s youth including young women (P4-S2) | Output | No of schools in Malé and outer atolls | 1 | Targ. | 0 | 0 | 0 (funds not available | 2 | 2 | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 3. Provide career guidance to promote fishing industry among the nation’s youth including young women (P4-S3) | Output | No of schools | 4 | Targ. | 13 | 1 | 3 | 8 | 10 | MOFA |
|  |  |  |  |  | Ach. | 13 | 1 | No budget allocated |  |  |  |
|  | 4. Fishing industry (Harvesting sector) share of the local workforce. (P4-S2) | Output | No. of local workforce | No of Fisherman in harvesting sector in 2008 = 14,066 | Targ. | 14,423 | 14,000 | 14,000 | 14,000 | 14,000 | MOFA |
|  |  |  |  |  | Ach. | 14,423 | Data not available |  |  |  |  |
| 5.Enhanced Research in fisheries and fish breeding and productivity introduced (P5) | 1.Marine research centre’s research mandate streamlined (P5-S1) | Output | % | 0 | Targ. | 50% | 50% | 50 (Revised) | 50 (Revised) |  | MOFA |
|  |  |  |  |  | Ach. | 0% | 0% |  |  |  |  |
|  | 2.Fisheries research facility established at Maniyafushi (P5-S2) | Output | % | 5% (Moved equipment and staff from Bodumoharaa to Maniyafushi) | Targ. | 30% | 30% | 35% (Revised) | 20% (Revised) | 20% (Revised) | MOFA |
|  |  |  |  |  | Ach. | 20% | 0% |  |  |  |  |
|  | 3.Establishment of a mariculture Development corporation (Under-consideration) (P5-S4) | Output | Event | 0 | Targ. | Bodumohora RFP |  |  |  |  | MOFA |
|  |  |  |  |  | Ach. | 0 (luxury villa) |  |  |  |  |  |
|  | 4.New bait harvesting methods studied and adopted for national use (P5-S3) | Outcome | Number | 2 studies | Targ. | 0 | 1 | 2 (Revised) | 1 | 0 | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 5.Establish an improved fisheries vessels and catch data collection system (P5-S7) | Output | % | Log books already designed. | Targ. | 50% | 30% | 10% | 10% |  | MOFA |
|  |  |  |  |  | Ach. | 20% | 40% |  |  |  |  |
|  | 6. Identify and lease potential islands, lagoons and water bodies for mariculture development (P5-S5) | Outcome | Number of lagoons/islands | 2 lagoons was awarded from public announced 6 lagoons in 2008 | Targ. | 0 | 4 | 4 (Revised) |  |  | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 |  |  |  |  |
|  | 7. Facilitate research centers / outposts on collaboration with foreign universities and research organizations (P5-S6) | Outcome | No of centers/outposts | 0 | Targ. | 0 | 0 | 1 | 1 |  | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 | 1 |  |  |  |
| 6. Fisheries infrastructure modernized to meet planned and emerging developments (P6) | 1. Conduct a technical study for the identification and development of fisheries support services. Identify specifically the support required for women in the sector (P6-S1) | Outcome | Event | 0 | Targ. | 0 | Report on technical study |  |  |  | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 (Funds not allocated) |  |  |  |  |
|  | 2.Undertake a study for the potential of developing a seafood hub in the Maldives (P6-S3) | Outcome | Event | Concept of a seafood hub was developed | Targ. | 0 | Report on study |  |  |  | MOFA |
|  |  |  |  |  | Ach. | 0 | 0 (Funds not allocated) |  |  |  |  |
|  | 3. Fisheries harbor infrastructure modernized including facilities for fisheries support services (P6-S1) | Outcome | Event | Fish land site to be established in Hulhumale | Targ. | To conduct a study for development and management of Hulhumale fish landing site and to design the harbour | To seek a potential project development partner to complete the site | To seek a potential project development partner to complete the site | Fish landing to be utilized |  | MOFA |
|  |  |  |  |  | Ach. | Completed | Major delays due to limited number of interested parties |  |  |  |  |
| 7.Regulatory framework established for sustained development and management of fishery sector (P7) | 1.Fisheries Law revised to meet planned and emerging developments in a gender and inclusive sensitive manner (P7-S1) | Output | Event | New Fisheries Law drafted | Targ. |  |  | Law completed and submit to Majlis | Law adopted |  | MOFA |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 2. Fisheries Regulations Revised (P7-S2) | Output | Event | Compilation of Fisheries Regulations available | Targ |  |  | Regulations to be completed | Regulations adopted |  | MOFA |
|  |  |  |  |  | Ach |  |  |  |  |  |  |
|  | 2. Mechanism to phase out foreign fishing in EEZ established (P7-S4) | Output | Event | Target achieved in 2010. | Targ. |  | Completed (100%) |  |  |  | MOFA |
|  |  |  |  |  | Ach. |  | 100% |  |  |  |  |
|  | 3. Establish management plans for key species harvested. (P7-S3) | Output | Event | Data collection began for key species | Targ. |  | shark management plan | Grouper and Turtle Management plan | Sea-cucumber management plan, tuna management plan | Tuna management plans | MOFA |
|  |  |  |  |  | Ach. |  | 85% completed. Need stakeholder consultations |  |  |  |  |
|  | 4. Establish a MCS system to stop IUU fishing. (P7-S6) | Output | Event | Equipment needed for MCS system procured. | Targ. |  | Analysis of MCS requirements for Maldives | Procure Equipment and installation | Implementation |  | MOFA |
|  |  |  |  |  | Ach. |  | 100% |  |  |  |  |
|  | 5.Develop a boat building code with stakeholder participation (P7-S7) | Outcome | Event | 0 | Targ. | Formulation | Formulation | Implementation |  |  | Ministry of transport & Communication, Transport Authority, MOFA, Maldives Marine Police/ MNDF Coast Guard |
|  |  |  |  |  | Ach. | 0 | 100% |  |  |  |  |

Lead Agency:

Agriculture Division / Ministry of Fisheries and Agriculture,

Steering Committee:

- MOFA,

- MED,

- BoM,

- Ministry of Transport and Communication,

- Transport Authority,

- Marine Police,

- MNDF; Cost Guard,

- HDC

Result impact indicators

1. Export quality and value added fishery products

-Increase the number of export fishery products

2. Increase mariculture and aquaculture farming in Maldives

- Increase the employment rate in the sector and economic benefits associated with it.

-Reduce imported fishery products eg: shrimp, prawn

Revised – as the result indicator was not targeted for year 2012 and 2013.

Marine Stewardship Council-UK

Phase 1: Initiating Maniyafushi; Research Facility Using Equipment Moved from Bodumohara and Existing Buildings on Maniyafushi - 35% of total project. Achieved 5% in 2008 and 20% in 2009. 10% still need to be achieved.

Phase 2: Expanding Maniyafushi Research Facility - 65% of total project, which still remains to be achieved as funds become available.

No budget allocation for 2010

Targeted activities: catching oceanic species (Initially 2010, now 2012), economizing livebait use (2011) and holding livebait for multi-day use (2012).