Results Framework (RF) - Land Reform

| Sector Outcome | Results Indicators | Indicator Type (Event/Op/ Oc./Imp) | Unit of Measure | Baseline | Targets/ Achievements |  |  |  |  |  | Lead Agency | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2009 | 2010 | 2011 | 2012 | 2013 |  |  |
| 1. Land Tenure system modernized through Land Reforms(P1) | 1. Legislation relating to land tenure revised and necessary regulations relating to the Act, developed (S1,2) | Output | Event |  | Target | Revision of Land Law | Revision of Land Law | Draft Land Law submitted to AG office |  |  |  | Submitted to AG Office |
|  |  |  |  |  | Ach. | Stakeholder consultation | Stakeholder consultations | Submitted to AG office |  |  |  |  |
|  | 2. Land Authority Established to regulate issues relating to Land and Land Tax scheme introduced (S4,6) | Output | Event | Land Authority not existing | Target |  | Preliminary work for establishing Land Authority | Establish Land Authority |  |  |  | Paper submitted for approval and action |
|  |  |  |  |  | Ach. |  | Cabinet Paper submitted to resident’s Office |  |  |  |  |  |
|  | 3. Tenancy deposit and Land tax mechanism, introduced (S3) | Output | Event |  | Target |  |  | Land Tax and tenancy deposit mechanism established |  |  |  | Land tax component included in the draft land bill |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | 4. Develop a Tenancy Act (S3) | Outcome | % |  | Target |  |  |  |  |  |  | Sent to AG |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |

- Need to re-word the indicators as written in the SAP document

| 2. Enhanced investments in Land and Property Development(P2) | 1. Land Bank and Land Tribunal established (S2,3) | Output | Event | Land Bank Tribunal not existing. | Target |  |  | Preliminary work for establishing Land Bank and Tribunal completed | Land Tribunal and Land Bank established |  |  | After establishment of a Land Authority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | 2. Land ownership by individuals(S1) | Outcome | % |  | Target | × | × | × | × | × |  | Establish the baseline |
|  |  |  |  |  | Ach. | Incl. in Land Law | Incl. in Land Law | Incl. in Land Law | Incl. in Land Law | Incl. in Land Law |  |  |
|  | 3. Establishment of a land Market S1,2,3) | Outcome | % |  | Target |  |  |  |  |  |  | Preliminary works |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |

| Sector Outcome | Results Indicators | Indicator Type (Event/Op/ Oc./Imp) | Unit of Measure | Baseline | Targets/ Achievements |  |  |  |  |  |  | Lead Agency | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2009 |  | 2010 | 2011 | 2012 | 2013 |  | Currently, there is no master plan. Budget not approved for physical development master plan |
| 3. Sustainable land management practices implemented with decentralized Land Administration and Management(P3,4) | 1. A physical planning act, regulations and national physical development master plan developed(S1,2) | Output | Event | Draft Planning Act developed | Target | Prepare draft Act | Finalize draft Act |  | Submit Draft Act to AG office | Planning Act implemented |  |  |  |
|  |  |  |  |  | Ach. | Draft Act prepared | Translated to Dhivehi |  |  |  |  |  |  |
|  | 2. Local and Regional Land use plans developed aligned with the National Master P lan, increased(S3) | Output | No. |  | Target |  |  |  | Prepare National Master Plan | National Master Plan completed And Submitted to Parliament | Local and Regional Land use Plans developed in Line with the National Master Plan |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |  |
|  | 3. Ensure that Land Use plans are integrated to the development plans at authority level and development programs implemented through approved land use policies and plans(S6) | Output | % |  | Target |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |  |
|  | - IIntegrating climate change risks into resilient island planning (S4) | Output |  |  | Target |  |  |  | Ammend Planning regs |  |  |  |  |
|  |  |  |  |  | Ach. |  |  |  | On going |  |  |  |  |

| 4. Efficiency in Land Management enhanced with strengthened institutional capacity in management and administration(P5,6&7) | 1. National Land cadastre and Land Management database operationalized P5(S1,2) | Output | Event |  | Target |  |  | Prepare National Land Cadastre and Land Management Database | National Land Cadastre and Land Management Database operational |  |  | Preliminary works for Preparing Land Management Database conducted in 2008, but no additional work in 2009 & 2010 as Budget was not allocated for this activity |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | 2. Specialized institutions for surveying, land registration, valuation and town and country planning established and made operational (P6-S1,2,3) | Output | Event |  | Target |  |  |  |  |  |  | Refer to comment 1.2 |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |
|  | 3. An inter Ministerial committee established to review issues and provide policy level directions (P7-S1) | Output | Event |  | Target |  | Establish Inter Ministerial committee |  |  |  |  | Committee in place |
|  |  |  |  |  | Ach. |  | Inter Ministerial committee formed and approved by President’s office |  |  |  |  |  |
|  | 4. Planning Councils at different administrative levels to which technical inputs on land related issues are provided, increased (P7-S2) | Output | No. |  | Target |  |  |  | Establish Planning Council / Body in 7 National offices |  |  |  |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |  |