Results Framework (RF) - Regional Development and Decentralization

| Sector Outcome | Results Indicators | Indicator Type (Event/Op/ Oc./Imp) | Unit of Measure | Baseline | Targets/ Achievements |  |  |  |  |  | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2009 | 2010 | 2011 | 2012 | 2013 |  |
| - IIslands, Atolls, and City Councils engaged in planning and implementing development policies in accordance with needs of communities and the decentralized administrative system established through 7 Regions , 188 island councils, 19 atoll councils, 2 city councils. (P1) | - Decentralization Law, Local Government Election Law enacted (P1,S1) and other related laws | Output | Event | Community consultations on local councils. 000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000 | Target | Consultations on preparing the bill | Draft of 2 bills prepared; 2 Acts passed; ratified | Laws that will define financial and natural resource allocation to local councils drafted; | Laws that will define financial and natural resource allocation to local councils passed and ratified; Supporting laws and regulations drafted and passed (as required) | Other supporting laws and regulations drafted and passed (as required) | LGA |
|  |  |  |  |  | Ach. | Consultations on preparing the bill | Draft of 2 bills prepared; 2 Acts passed and ratified |  |  |  |  |
|  | 2-Regulatory Frameworks for local governance established (P1,S3) | Output | Event | N/A (2008) | Target | N/A | Drafted and shared with ministries for comments | Adopt by 95 island and 8 atoll and 2 city councils | Adopt in remaining islands and atolls | Revision and review of framework | LGA |
|  |  |  |  |  | Ach. | N/A | Amendments made as per feedback | 25 Islands adopted |  |  |  |
|  | 3-Women and other disadvantaged groups consulted in governance and development ( decision making, formulating of policies) formulation/ revision of relevant laws. | Output | Event | N/A (2008) | Target | N/A | N/A | 25% women participating in consultative meetings. Participatory developed at all levels. | 35% women participating in consultative meetings | 50% women participating in consultative meetings | LGA for council MOHA for national offices |
|  |  |  |  |  | Ach. | N/A | N/A |  |  |  |  |

Lead agency: policy and supervision section/ Home affairs – Political appointee: Shafeeq, Mohamed Faroug / Civil service: Shareef Nafees, Rifa,

Steering Committee: PO, LGA, MoHA, DNP, MED

|  | 4-Local Government Rules of Procedure (‘Hinga Gavaidhu'), of elected councils, developed and adopted (P1,S4, P1S2) | Output | Event | N/A (2008) | Target | N/A | Prepare Rule of Procedures documents for LGA, city, atoll and island councils | Adopted by, 188 islands, 19 atolls and 2 city councils; revision of Local Government Rules of Procedure (to incorporate the concepts of wards in some cities) | Revise rules of procedure (where required) | Revise rules of procedure (where required) | LGA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. | N/A | All drafted and shared with ministries for comments | Adopted by 188 councils, 19 atolls and city councils |  |  |  |
|  | 5-Standard Operating Procedures (SOP) for local councils, developed and adopted (Functions included in the SOP to address gender and other inclusion issues) (P1,S4, P1S2) | Output | Event | N/A (2008) | Target | N/A | N/A | SOP drafted | 2 city council, 120 island council 10 atoll councils. | Remaining islands & atoll councils | LGA |
|  |  |  |  |  | Ach. | N/A | N/A |  |  |  | LGA |

|  | 6-Councils having Service Charters to serve their communities efficiently (P1,S3, P1S5, P1S6) | Outcome | No. of councils | N/A (2008) | Target | N/A |  | N/A | Begin drafting Service charters |  | Service charters adopted; and begin implementing | All councils implementing service charters | LGA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. | N/A |  | N/A |  |  |  |  |  |
|  | 7- Local councils generating their own funds to supplement government funding provisions, increased (P1S6) | Outcome | Income generation increased | N/A (2008) | Target | N/A |  | N/A | Complete demarcation boundaries for islands & atolls |  | Regulations to allocate resources drafted and passed (refer P1S1) | Regulation implemented | LGA |
|  |  |  |  |  | Ach. | N/A |  | N/A |  |  |  |  |  |
|  | 8-Increased representation of women and people from vulnerable groups in local bodies created by local councils | Output | % | N/A (2008) | Target | N/A |  | N/A | 15% |  | 20% | 35% |  |
|  |  |  |  |  | Ach. | N/A |  | N/A |  |  |  |  |  |
|  | 9- Increased capacity of local councils, local government officials and respective administrative staff in planning and implementing development policies | Outcome | Event | N/A(2008) | Target | N/A |  | N/A | Orientation of local councillors; seminar on local governance conducted; planning and budgeting workshops, quarterly round tables conducted |  | 4 skills workshops conducted for local councils & national offices/ Training manual | 4 skills workshops conducted for local councils and national offices | LGA for local council, MoHA for national offices |
|  |  |  |  |  | Ach. | N/A |  | N/A | Orientation of local councillors done; seminar on local governance conducted; First quarterly round tables conducted |  |  |  |  |
| 2. Provincial Administration and Commercial Centers setup to provide social and economic opportunities that create a competitive environment (P2) | - Regions with National Offices (‘Gaumee Idhaaraa’), established (P2S1) | Output | Event | N/A (2008) | Target | Establishment of 7 province offices | Province offices in operation |  |  | Establishment of Atoll National Offices | Establish atoll units for national offices | Further develp national offices and units | MoHA |
|  |  |  |  |  | Ach. | Establishment of 7 province offices | Province offices in operation |  |  | 7 National Offices in operation |  |  |  |

|  | - Development of commercial centers, increased (P2S1, P2S2) | Output | No. | Kulhudhufushi/ Addu International Port | Target | Decentralization of Port Activities, change the management to private limited company owned : Kulhudhushi port | Maamigili Aiport/ Thimarafushi Aiport/ Fuamulah Aiport / Daranvandhoo Aiport / Felivaru Airport | Distribution centres in Vilufushi and Thinadhoo/ Collection Centres; harbours to be developed |  |  | MED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | - Mechanisms and Frameworks established for development planning at the regional level (P2S5) | Output | Event | N/A (2008) | Target | N/A | N/A | DNP, LGA and MoFT together to form Decenttralized Planning and Budgeting Manual; Councils to apply the manual for planning and budgeting process | Improve the regional planning and budgeting process through capacity development and process improvement | Improve the regional planning and budgeting process through capacity development and process improvement | MoHA |
|  |  |  |  |  | Ach. | N/A | N/A |  |  |  |  |
|  | 4. Line Ministries which have decentralized services at the provincial level, increased (P2S6; P2S4) | Outcome | % | hospitals , vocational training (2008) | Target | DNR (ID card and passport), ferry system, public health | Tertiary Education, Public Health. | Islami affairs,MED services, | Other ministries | Other ministries | MoHA |
|  |  |  |  |  | Ach. | Achieved | Achieved |  |  |  |  |
|  | 5. Relevant professional and skilled workers engaged in their vocations in regions increased (P2S3) | Impact | % | N/A (2008) | Target | N/A | N/A | Developing a monitoring mechanism with line ministries involvement | 35% | 50% | MoHA for national offices/ LGA for councils |
|  |  |  |  |  | Ach. | N/A | N/A |  |  |  |  |

| 4. Increased participation of Civil Society and Private Sector at the Local Government level in social and economic activities (P3) | 1. Coordination between Local Councils, Civil Society organizations and Private Sector increased. (P3S1) | Outcome | No. | No legal status for island development committees, community based organizations (2008) | Target | N/A | Legal status to WDC; | Establish 188 island WDC and 2 city WDC; MOUs signed between local councils and civil society organization and private sector in service provision; 2 participatory meetings ( for 3 sectors) in development issues in each island | MOUs signed between local councils and civil society organization and private sector in service provision; participatory meeting in development planning and formulating development policies | MOUs signed between local councils and civil society organization and private sector in service provision; participatory meeting | LGA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Ach. | N/A | Legal authority to WDC |  |  |  |  |
|  | - Create a conductive environment for civil society growth and mobilization. (P3S2) | Output | Event | Associations Law (2008) | Target | Financial support for NGO’s from Gov/ NGO’s support project/ | Financial support for NGO’s from Gov/NGO forum; signing of civiv engagement project; civic engagement project finalised | model for public policy forum established, situation analysis of civil society; NGO forum; public image campaign for NGOs; Redrafting of Association Act; NGO directry established | Association Act ratified; Training for NGOs; Training Government officials in working with civil society; Public Policy Forums; | NGO building | MoHA |
|  |  |  |  |  | Ach. | Financial support for NGO’s from Gov/ NGO’s support project/ | NGO forum |  |  |  |  |
| 5. Links between local level functionaries and national authorities strengthened to coordinate and facilitate implementation of national programmes (P5) | 1. System for Intra Government coordination between central and local government institutions established (P4S1) | Output | Event | e- government / structure/ legal plat form for government | Target | N/A | N/A | Established in 7 National Offices | 30 Island Councils, 5 Atoll Councils | Additional 20 Island Councils and 5 Atoll Councils | LGA for local councils; MoHA for national offices |
|  |  |  |  |  | Ach. |  |  |  |  |  |  |
|  | 2. Develop a participatory monitoring and evaluation mechanism for national offices and local councils (P3S2) | Output | No. | N/A | Target | N/A | N/A | Incorporate M&E tool in the decentralized planning and budgeting manual; 15% of women and other vulnerable groups / Preparing guideline for gender mainstreaming/ M&E tool to measure physical contribution of women | Utilize the planning and budgeting forms of councils for monitoring progress; 20% of women and other vulnerable groups | Strengthen the M&E of national offices and councils through feedback from 2012; 35% of women and other vulnerable groups | LGA for local councils; MoHA for national offices |
|  |  |  |  |  | Ach. | N/A | N/A |  |  |  |  |

Three national level indicators

- Establishing a mechanism for participatory decision making in planning and implementing initiatives.

- Developing of policies and legislations in place of effective implementation of decentralized administrative system.

- Relevant professional and skilled workers engaged in their vacations in regions increased. ( already an indicator v important)