## Table 1
L. ISDHOO - DHAN'BIDHOO CAUSEWAY
SUMMARY OF BILLS
Bill No. | Description | Amount (MVR)
1 | Preliminaries
2 | Causeway
3 | Road Works
4 | Environmental control
5 | Additions and/or Omissions
Sub Total of Bills
Goods and Service taxes
Grand Total of Bills

## Sheet1
Bill No. 1 - PRELIMINARIES
Item | Description | Unit | Quantity | Rate(MVR) | Amount (MVR)
1.1 | Securities, Insurance, etc
1.1.1 | Provision of performance security. | Item | 1
1.1.2 | Provision of insurance ( Contractor to specify). | Item | 1
1.1.3 | Other security bonds, etc (Contractor to specify). | Item | 1
1.2 | Contractors Equipment, Personal and Site Facilities
1.2.1 | Mobilization and demobilization of Contractor's dredging equipment and construction plant | Item | 1
1.2.2 | Mobilization and demobilization of Contractor's personal | Item | 1
1.2.3 | Time related charges for contractor personal. (Incl. food, lodging, etc.) | Days
1.2.4 | Establishment and removal of the Contractor's facilities, incl. laboratory, office, workshop, etc | Item | 1
1.2.5 | Operation and maintenance of the Contractor's facilities incl. laboratory, office, workshop, etc | Days
1.3 | Design and Others
1.3.1 | Provide as - Built drawings, Quality assurance documentation, Material certificates, Technical brochures. | Item | 1
1.3.2 | Provide detailed in-survey prior to commencement of physical works | Item | 1
1.3.3 | Provide detailed out-survey upon completion prior to hand over. | Item | 1
Total of bill No.1 (Carried to summary of Bills)
Bill No. 2 - CAUSEWAY
Item | Description | Unit | Qty | Rate(MVR) | Amount (MVR)
2.1 | Sand fill to as per the drawi ng provided to MSL+1.3m | cbm | 20974.8
2.2 | Construction and installation of concrete culvart (width- 9m, length-15m, with wing walls) | nos | 8
2.3 | Cast and installation of L-Kerbs | m | 840
2.4 | Rockboulder revetment on both sides of the causeway | m | 840
Total of bill No.2 (Carried to summary of Bills) 22,191,007.00
Bill No. 3 - ROAD WORKS
Item | Description | Unit | Qty | Rate(MVR) | Amount (MVR)
3.1 | Cut, fill, shape the subgrade and compact ti get the specified cross elevation and CBR 60% for the carriageways | sqm | 8640
3.2 | Supply, place compact aggregate base course (100mm thick) | sqm | 8640
3.3 | Supply, lay & compact 40mm thick asphalt seal for all the roads including prime coat and tack coat, rate to include any activity & material required to connect the new road to existing road | sqm | 8640
3.5 | Road Signages, rate to include excavation, foundation work and any other works to established the sign boards | nos | 3
3.6 | Supply installation of Single arm street lights | nos | 42
3.7 | Road marking continuous line, 100mm wide with thermoplastic material | m | 960
Total of bill No.3 (Carried to summary of Bills) 22,191,007.00
Bill No. 4 - Environmental Control
Item | Description | Unit | Qty | Rate(MVR) | Amount (MVR)
4.1 | Implement necessary mitigation measures as outlined in the technical specifications | Item | 1
4.2 | Carryout Environmental Impact Assesment | Item | 1
Total of bill No.4 (Carried to summary of Bills)
Bill No. 5 - Additions and/or Omissions
Item | Description | Unit | Qty | Rate(MVR) | Amount (MVR)
A | The accuracy of the quantities given in this Bills of Quantities is not guaranteed and the Contractor should satisfy himself as to their accuracy
B | Any adjustments that he may consider necessary should be written below and on similar continuation sheets if required, and the net amount of the adjustments is to be carried to the Summary
Additions
1
2
3
4
5
Omissions
1
2
3
4
5
Total of bill No.5 (Carried to summary of Bills) |  |  |  |  | -