## Summary
SUMMARY OF BILLS
Bill No. | Description |  | Amount MVR
1 | Preliminaries
2 | Dredging, excavation & earthwork
3 | Breakwaters and revetments
4 | Quay wall structure
5 | Harbour pavement
6 | Environmental control
7 | Additions and/or Omissions
| Goods and Services Tax | 6% | 0
Grand Total of Bills |  |  | 0

## Bills
.L.FONADHOO HARBOUR PROJECT - BOQ -
BILL NO. 1 - PRELIMINARIES |  |  | ORIGINAL CONTRACT
Item | Description | Unit | Qty | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
1.1 Securities, Insurance, etc
1.1.1 | Provision of performance security. | Item | 1 | 65000 | 65000 | 1
1.1.2 | Provision of insurance ( Contractor to specify). | Item | 1 | 187500 | 187500 | 1
1.1.3 | Other security bonds, etc (Contractor to specify). | Item | 1 | 135000 | 135000 | 1
1.2 Contractors Equipment, Personal and Site Facilities
1.2.1 | Mobilization and demobilization of Contractor's dredging equipment and construction plant | Item | 1 | 190000 | 190000 | 1
1.2.2 | Mobilization and demobilization of Contractor's personal | Item | 1 | 85000 | 85000 | 1
1.2.3 | Time related charges for contractor personal. (Incl. food, lodging, etc.) | Days | 210 | 2450 | 514500 | 210
1.2.4 | Establishment and removal of the Contractor's facilities, incl. laboratory, office, workshop, etc | Item | 1 | 47000 | 47000 | 1
1.2.5 | Operation and maintenance of the Contractor's facilities incl. laboratory, office, workshop, etc | Days | 210 | 1750 | 367500 | 210
1.3 Design and Others
1.3.1 | Provide as - Built drawings, Quality assurance documentation, Material certificates, Technical brochures. | Item | 1 | 43000 | 43000 | 1
1.3.2 | Provide detailed in-survey prior to commencement of physical works | Item | 1 | 50000 | 50000 | 1
1.3.3 | Provide detailed out-survey upon completion prior to hand over. | Item | 1 | 120000 | 120000 | 1
Total of bill No.1 (Carried to summary of Bills) |  |  |  |  | 1804500
BILL NO. 2 - DREDGING, EXCAVATION & EARTHWORKS
Item | Description | Unit | Qty | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
2.1 Dredging & Excavation
2.1.3 | Maintenance Dredging / Excavation of any material for the existing channel, with width 25m. Maximum specified depth -3m MSL | m3 | 12768 | 105 | 1340640 | 1800
2.1.4 | Maintenance Dredging / Excavation of any material in the existing basin. Maximum specified depth -3m MSL | m3 | 1552 | 135 | 209520 | 1552
Total of bill No.2 (Carried to summary of Bills) |  |  |  |  | 1550160
BILL NO. 3 - BREAKWATER AND REVETMENTS
Item | Description | Unit | Qty | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
3.2 Revetment
3.2.1 | Armour rocks laid to the slopes with backfilled material and geotextile material as defined in drawings | m | 67 | 24000 | 1608000 | 21
3.3 Beacons, Supply and Installing
3.3.1 | Supply and placing navigational aids as shown on harbour layout drawing and as directed by Engineer. | No | 2 | 22500 | 45000 | 2
Total of bill No.3 (Carried to summary of Bills) |  |  |  |  | 1653000
BILL NO. 4 - QUAY WALL STRUCTURE
Item | Description | Unit | No | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
4.1 L-Section Quay Wall
4.1.1 | Supply and install precast RC quay wall unit as per detail drawing. | m | 162 | 30500 | 4941000 | 166
4.1.2 | Supply and install precast RC anchor blocks and fix anchor rods as per detail drawing . | m | 162 | 2650 | 429300 | 166
4.1.3 | Cast in-situ concrete coping in quaywall to grades, levels, as indicated in the drawing | m | 162 | 8800 | 1425600 | 166
4.1.4 | Supply and fix mooring hooks in 4m intervals as per the detail drawing | No | 40.5 | 1100 | 44550 | 42.5
4.1.5 | Supply and placing geotextile material to the full length of the quawall blocks covering the entire span of the quawall length as shown in the cross section drawing | m | 162 | 575 | 93150 | 166
4.1.6 | Demolision of insitu concrete capping | m | - | - | - | 166
4.2 Construction of a Ramp
4.2.1 | Supply and placing reinforced concrete slab as per drawing | m2 |  |  |  | 144
4.2.2 | Supply and placing concrete blocks as per the drawing | Item |  |  |  | 2
Total of bill No.4 (Carried to summary of Bills) |  |  |  |  | 6933600
BILL NO. 5 - Harbour Pavement
Item | Description | Unit | No | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
5.1 Construction of interlocking pavement
5.1.1 | Surveying, compacting and levelling the harbour area grounds as specified in the drawing | Item | 1 | 229000 | 229000 | 1
5.1.2 | Supply and placement of Interlocking blocks in the area given in the harbour layout drawing, 5m wide from capping slab to full quaywall length | m2 | 1145 | 690 | 790050 | 830
5.1.3 | Installation of harbour lights | Item | 11.45 | 22500 | 257625 | 6
Total of bill No.5 (Carried to summary of Bills) |  |  |  |  | 1276675
BILL NO. 6 - Environmental Control
Item | Description | Unit | No | Rate(MVR) | Amount(MVR) | Qty | Rate(MVR) | Amount(MVR)
6.1 | Implement necessary mitigation measures as outlined in the technical specifications | Item | 1 | 150000 | 150000 | 1
Total of bill No.6 (Carried to summary of Bills) |  |  |  |  | 150000