## MAIN SUMMARY
SUMMARY OF BILLS OF QUANTITIES
704 PAX MOSQUE AT S.meedhoo
|  | DESCRIPTION | AMOUNT | %
BILL NO.
| 01.0.00 | 01 PRAYER HALL & ABLUTION
| 02.0.00 | 02 MINARET
|  | TOTAL AMOUNT |  | MRF
|  | GST 6% |  | MRF
|  | CONTRACT VALUE |  | MRF

## MOSQUE Summary
SUMMARY OF BILLS OF QUANTITIES
ESTIMATE OF SINGLE STOREY MOSQUE (700 PAX)
SINGLE STOREY BUILDING
CLIENT: MINISTRY OF ISLAMIC AFFAIRS |  |  | SMU-67-BOQv3
Bill No |  | Description | Amount
1 |  | PRELIMINARIES
2 |  | GROUND WORKS
3 |  | CONCRETE
4 |  | MASONRY AND PLASTERING
5 |  | METAL WORKS
6 |  | CEILING
7 |  | DOORS AND WINDOWS
8 |  | FINISHES
9 |  | HYDRAULICS & DRAINAGE
10 |  | PAINTING
11 |  | FURNITURE
12 |  | ELECTRICAL INSTALLATION
13 |  | WOODWORK
14 |  | ROOFING
15 |  | FIRE FIGHTING SYSTEM
16 |  | EXTERIOR BOUNDARY AND PAVEMENT
17 |  | ADDITIONS & OMISSIONS
TOTAL
GST 6.00 %
GRAND TOTAL
NOTE :
Duration :

## MOSQUE BOQ
BILLS OF QUANTITIES
OF SINGLE STOREY MOSQUE (700 PAX)
Item | Description | Qty | Unit | Rate | Total Amount
BILL No: 01
PRELIMINARIES
Proposed Single Storey Mosque (700 pax)
1.1 | GENERAL NOTES
1 | Abbreviations
m - metre
Nos - numbers
m³ - cubic metre
m² - square metre
lm - Linear metre
kg - Kilograms
incl. - including
mm - millimetre
SS - Stainless Steel
GI - Galvanised steel
1.2 | SITE MANAGEMENT COSTS
1 | Allow for all on and off site management cost including costs of foreman and assistants | 1 | item
1.3 | SAFETY ON SITE
1 | Providing & maintaining adequate safety measure on site for all workers & all authorized visitors on site & protecting adjoining properties & people against falling objects or other with regard to the construction works | 1 | item
1.4 | PLANTS & MACHINERY
1 | Provision & maintenance of all necessary temporary plants, machineries & scaffolding that is required for the completion of the project | 1 | item
1.5 | SERVICES & FACILITIES
1 | Provision & maintenance of services & facilities such as water, power supply, lighting & fuel required for the project. | 1 | item
1.6 | SIGN BOARD
1 | Allow for sign board (1500 mm x 900 mm)Design should be approved by client. | 1 | item
1.7 | TEMPORARY FENCING & HOARDING
1 | Supply, erect & maintenance of a fence through out the construction period & hoarding all along the perimeter of the site | 1 | item
1.8 | Insurance
1 | Insurance as stated in the general conditions | 1 | item
BILL No: 01 PRELIMINARIES
TOTAL OF BILL No: 01 - Carried over to summary
BILL No: 02
GROUND WORKS
2.1 | GENERAL
Note: Rates shall include for: levelling, grading, trimming, compacting to faces of excavation, keep sides plumb, backfilling, consolidating and disposing surplus soil
Building footrpint area (712sqm)
2.2 | SITE CLEARING
1 | Clearing site including trees less than 1m girth complete with stumps and roots (38m x 38m plot) and demolition of existing builidng | 1451 | m²
| Demolition of existing buidling and disposal to allocated land within the island | 394 | m²
Removal of Trees
Removal of Shrubs and Bushes
Large rocks removal
Removal of other debris
Disposal to allocated land within the island
2.3 | EXCAVATION
Note: Excavation quantities are measured to the faces of concrete members. Rates shall include for all additional excavation required to place the formwork/shuttering and dewatering the trenches for the required days.
1 | Excavation for foundation
| Excavation for foundation pads | 128.07 | m³
| Excavation for foundation beams | 82.62 | m³
2.4 | FILLING
Notes: Rates shall include for: levelling, grading, trimming and compacting
1 | Sand blinding layer to receive damp proof membrane | 76.84 | m²
2 | Earth filling in ground floor (300mm above ground level) | 30.74 | m³
2.5 | WATER PROOFING
Note: Rates shall include for: dressing around and sealing to avoid all penetrations
1 | Apply 2 coats of Brush Bond or similar on foundation rafts,strip beams & tie beams, steps and under ground masonry & concrete walls in accordance with manufacturer's instructions | 1 | item
2.6 | Damp Proof Membrane
(a) Rates shall include for: dressing around and sealing to all penetrations.
| Heavy duty polyethylene sheet damp proof membrane (1000 gauge) laid on blinding layer. | 322 | m²
BILL No: 02 - GROUND WORKS
TOTAL OF BILL No: 02 - Carried over to summary
BILL No: 03
CONCRETE
3.1 | GENERAL
(a) Rates shall include for: provision to place in position; casting of all required items and finishing after removal of formwork and additional concrete required to conform to structural and excavated tolerances
(b) Rates shall include supply of all formwork item including form oil, timber, plywood, nails etc.
(c) Mix ratio for reinforced concrete shall be 1:2:3 and lean concrete shall be 1:3:6 by volume
1 | Allow for concrete testing. | 1 | LS
3.2 | LEAN CONCRETE
Note: Quantity is measured with additional 0.1m to the edges of concrete foundation members. Rates shall be inclusive for any additional concrete required to place the formwork.
1 | 50mm thick lean concrete to bottom of raft foundation or strip footing and beams
| Concrete Volume | 11.53 | m³
Cement
River sand
Coarse aggregate
3.3 | REINFORCED CONCRETE
(a) Rates shall include for: cleaning, fabrication, placing, the provision for all necessary temporary fixings and supports including tie wire and chair supports, laps and wastage
(b) All reinforcing bars except 6mm dia bars shall be high strength deformed bars
(c) The exact length inclusive of laps are given. The rates shall take into account any wastage.
In-situ reinforced concrete to:
3.3.1 | Foundation
1 | Foundation Pad F1 (1900 x 1900 x 400mm)
| Concrete Volume | 8.66 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 39.9 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.84 | m³
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (T12@100) | 1.11 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
2 | Foundation Pad F2 (1200 x 1200 x 400mm)
| Concrete Volume | 23.04 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 134.4 | m²
12mm thick plywood
| 50mm x 50mm timber | 2.82 | m³
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. high tensile steel bar (T10@150) | 3.83 | t
3 | Foundation Pad F3 (1400 x 1400 x 400mm)
| Concrete Volume | 4.7 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 21.36 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.48 | m³
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. high tensile steel bar (T10@150) | 0.19 | t
4 | Foundation Pad F4 (1200 x 2500 x 400mm)
| Concrete Volume | 2.4 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 15.6 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.36 | m³
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (T12@100) | 0.26 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
6 | Foundation Beam FB
| Concrete Volume | 26.62 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 53.23 | m²
12mm thick plywood
| 50mm x 50mm timber | 1.14 | m³
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (4T12) | 1.38 | t
| 6mm. dia, ring bar (R6@100) | 0.26 | t
7 | Foundation Beam TB1
| Concrete Volume | 26.85 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 53.71 | m²
12mm thick plywood
| 50mm x 50mm timber | 1.14 | m³
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (2T12) | 1.21 | t
| 6mm. dia, ring bar (R6@100) | 0.3 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
8 | Foundation Beam TB2
| Concrete Volume | 12.94 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 25.87 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.54 | m³
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar (12T16) | 1.5 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.5 | t
| 6mm. dia, ring bar (R6@100) | 0.99 | t
3.3.2 | Columns
1 | Columns C1 (circular)
| Concrete Volume | 3.57 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 35.67 | m²
12mm thick 400mm dia metal frame
Mould oil
Reinforcement. ( Upto bar length 6m)
| 12mm. dia, 6m. high tensile steel bar (8T12) | 0.15 | t
| 06mm. dia, 6m. Ring bars (R6@150 with HOOK) | 0.07 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
2 | Columns C2
| Concrete Volume | 21.6 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 288 | m²
12mm thick plywood
| 50mm x 50mm timber | 6 | m³
Nails
Mould oil
Reinforcement. ( Upto bar length 6m)
| 12mm. dia, 6m. high tensile steel bar (4T12) | 0.85 | t
| 6mm. dia, 6m. Ring bars (2R6@150 with HOOK) | 0.66 | t
3 | Columns C3
| Concrete Volume | 2.4 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 38.4 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.84 | m³
Nails
Mould oil
Reinforcement. ( Upto bar length 6m)
| 12mm. dia, 6m. high tensile steel bar (4T12) | 0.14 | t
| 6mm. dia, 6m. high tensile steel bar (R6@150) | 0.11 | t
4 | Columns C4
| Concrete Volume | 0.77 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 5.36 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.12 | m³
Nails
Mould oil
Reinforcement. ( Upto bar length 6m)
| 12mm. dia, 6m. high tensile steel bar (4T12) | 0.03 | t
| 6mm. dia, 6m. high tensile steel bar (R6@150) | 0.03 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
5 | Columns (well)
| Concrete Volume | 2.14 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 3.96 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.12 | m³
Nails
Mould oil
3.3.3 | Beams
1 | First Floor Beams B1
| Concrete Volume | 1.2 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 9.91 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.24 | m³
Nails
Mould oil
Reinforcement.
| 20mm. dia, 6m. high tensile steel bar (6T20) | 0.17 | t
| 16mm. dia, 6m. high tensile steel bar (2T16) | 0.04 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.02 | t
| 6mm. dia, ring bar (R6@100) | 0.03 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
2 | First Floor Beams B2
| Concrete Volume | 3.42 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 30.96 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.66 | m³
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar 82T16) | 0.45 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.11 | t
| 6mm. dia, ring bar (R6@150) | 0.07 | t
3 | First Floor Beams B3
| Concrete Volume | 20.75 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 187.82 | m²
12mm thick plywood
| 50mm x 50mm timber | 3.96 | m³
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar (4T16) | 1.38 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.69 | t
| 6mm. dia, ring bar (R6@150) | 0.64 | t
3 | First Floor Beams B4
| Concrete Volume | 3.64 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 32.99 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.72 | m³
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar (4T16) | 0.24 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.12 | t
| 6mm. dia, ring bar (R6@150) | 0.11 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
5 | First Floor Beams B5
| Concrete Volume | 2.02 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 18.82 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.42 | m³
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar (6T16) | 0.24 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.05 | t
| 6mm. dia, ring bar (R6@150) | 0.05 | t
6 | First Floor Beams B6
| Concrete Volume | 6.05 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 40.99 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 25mm. dia, 6m. high tensile steel bar (12T25) | 1.44 | t
| 16mm. dia, 6m. high tensile steel bar (2T16) | 0.11 | t
| 6mm. dia, ring bar (2R6@100) | 0.19 | t
7 | First Floor Beams B7
| Concrete Volume | 3.19 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 21.5 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 25mm. dia, 6m. high tensile steel bar (8T25) | 0.64 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.07 | t
| 6mm. dia, ring bar (R6@150) | 0.06 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
8 | First Floor Beams B8
| Concrete Volume | 3.19 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 28.9 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 25mm. dia, 6m. high tensile steel bar (4T25) | 0.48 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.11 | t
| 6mm. dia, ring bar (R6@150) | 0.09 | t
9 | Roof beams RB (above main entrance)
| Concrete Volume | 0.42 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 4.83 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. Ring bars (T10@100 H&V) | 0.03 | t
| 10mm. dia, 6m. Ring bars (T10@100 H&V) | 0.07 | t
10 | Roof beams RB (above window and hall entrance)
| Concrete Volume | 0.59 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 11.27 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. Ring bars (T10@100 H&V) | 0.03 | t
| 10mm. dia, 6m. Ring bars (T10@100 H&V) | 0.11 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
11 | Lintel Beams (LB)
| Concrete Volume | 1.15 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 12.46 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (8T12) | 0.09 | t
| 12mm. dia, 6m. Cross bars (T12@150) | 0.04 | t
| 06mm. dia, 6m. Ring bars (R6@150) | 0.01 | t
3.3.4 | Slabs
1 | Ground Concrete Slab (100mm thickness)
| Concrete Volume | 68.97 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 620.76 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. high tensile steel bar (T10@200) Top Reinf. | 1.53 | t
2 | Roof Concrete Slab (150mm thickness)
| Concrete Volume | 59.7 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 413.28 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar (T16@50) Distribution Steel | 1.96 | t
| 10mm. dia, 6m. high tensile steel bar (T10@150) Top Reinf. | 2.07 | t
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
3 | Roof Concrete Slab (150mm thickness)
| Concrete Volume | 12.38 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 85.73 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. high tensile steel bar (T10@150) Top Reinf. | 0.21 | t
4 | Roof Concrete Slab (200mm thickness)
| Concrete Volume | 9.03 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 62.5 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 10mm. dia, 6m. high tensile steel bar (T10@150) Top Reinf. | 1.4457 | t
5 | Ramp slab
| Concrete Volume | 1.05 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 7.29 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 6mm. dia, 6m. high tensile steel bar (R6@250) Bottom Reinf. | 0.02 | t
BILL No: 03 - CONCRETE
TOTAL OF BILL No: 03 - Carried over to summary
BILL No: 04
MASONRY AND PLASTERING
4.1 | GENERAL
Note: Rates shall include for: cleaning out cavities, forming rebated reveals and pointing and cleaning down to reveals where necessary; fractional size blocks, all necessary machine cutting, cutting or forming chases or edges of floor slabs, cutting or leaving holes and openings as recesses for and building in pipes, conduits, sleeves and similar as required for all trades; leaving surfaces rough or raking out joints for plastering and flashing, bedding frames or plates, building in joists, bearers or similar, temporary supports to openings, templates, reinforcement in walls and for all necessary making good. Providing approved quality mesh at joints between structaral members and masonry in the exterior walls
4.2 | SOLID BLOCK WORK
150 x 150 x 300mm solid block wall, blocks laid common bond
1 | Masonry below raised ground floor level
| Masonry area | 40.95 | m2
Bricks
Cement for block placing
River Sand
2 | Raised Ground floor
| Masonry area | 398.23 | m2
Bricks
Cement for block placing
River Sand
4.3 | PLASTERING
12mm thick interior cement plastering and 20mm thick exterior cement plastering as specified on
1 | Masonry below +150
a | Exterior
| Plastering area (Exterior) | 81.9 | m2
Cement for plastering
River sand for plastering
2 | Raised Ground floor
a | Exterior
| Plastering area (Exterior) | 398.23 | m2
Cement for plastering
River sand for plastering
b | Interior
| Plastering area (Interior) | 398.23 | m2
Cement for plastering
River sand for plastering
BILL No: 04 - Carried forward
BILL No: 04 - Brought forward
4.4 | FLOORING
Cement sand screeding on the floor as specified on.
1 | Ground floor
50 mm thick screed in the floor
| Cement sand screed Area | 518.9 | m2
Cement
River sand
2 | Corridors
50 mm thick screed in the floor
| Cement sand screed Area | 133.2 | m2
Cement
River sand
3 | Toilets and Ablution Area
50 mm thick screed in the floor
| Cement sand screed Area | 50.4 | m2
Cement
River sand
4 | Ramp
50 mm thick screed in the floor
| Cement sand screed Area | 7.29 | m2
Cement
River sand
BILL No: 04 - MASONRY & PLASTERING
TOTAL OF BILL No: 04 - Carried over to summary
BILL No: 05
METAL WORKS
5.1 | GENERAL
Note: (a) Rates shall include for: all fabrication work, welding, marking, drilling for bolts including those securing timbers, steel plates, bolts, nuts and any type of washer, riveted work, counter sinking and tapping for bolts or machine screws.
(b) Rates shall include for all painting and finishing as specified
(c) Rates shall include for fabrication and erection and temporary supports and fixing into position
(c) The contractor shall submit the detail of the Garbage chute and get the approval from the Consultant before fixing it in position
5.2 | RAILING ON RAMP ACCESS
5.2.1 | SS pipe Railing for Ramps and Ground floor Stairs
1 | 1200mm high handrail with ø50mm SS pipe horizontally top and ø25mm SS pipes veritically and 3x ø25mm SS horizontally with 18mm welded base plates as shown in the drawing | 3 | item
BILL No: 05 - METAL WORKS
TOTAL OF BILL No: 05 - Carried over to summary
BILL No: 06
CEILINGS
6.1 | SUSPENDED CEILING
Boral concealed suspended ceiling with concealed grid system or similar including framing, beading, nails and screws. Rate shall include for the painting and finishing.
1 | Ground floor
| Ceiling Area | 518.9 | m2
9mm thick Tongue and Groove for Ceiling
50mm x 50mm Timber frame work
Nails
2 | Corridors
| Ceiling Area | 135.6 | m2
3mm thick Plywoodfor Ceiling
50mm x 50mm Timber frame work
Nails
3 | Toilets and Ablution Areas
| Ceiling Area | 50.2 | m2
3mm thick Plywoodfor Ceiling
50mm x 50mm Timber frame work
Nails
BILL No: 06 - CEILING
TOTAL OF BILL No: 06 - Carried over to summary
BILL N0: 07
DOORS AND WINDOWS
7.1 | GENERAL
Notes: (a) Rates shall include for locks, latches, closures, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware and these materials should brass and of superior quality.
(b) Rates shall include for door frames, mullions, transoms, trims, glazing, tinting, timber panels, boarding, framing, lining, fastenings and all fixings
(c) Rates shall include for all painting
7.2 | TIMBER DOORS, ALUMINIUM DOORS AND WINDOWS
1 | D1 (2850 x 1700) + top curved | 10 | Nos
2 | D2 (2150 x 1000) | 4 | Nos
3 | D3 (2150 x 900) | 2 | Nos
4 | D4 (2150 x 800) | 3 | Nos
5 | D5 (2150 x 700) | 6 | Nos
1 | W1 (3000 x 1800) dome shape | 22 | Nos
2 | W2 (2850 x 1600) dome shape | 6 | Nos
3 | W3 (600 x 600) diamond | 5 | Nos
BILL N0: 07 -DOORS AND WINDOWS
TOTAL OF BILL No: 07 - Carried over to summary
BILL N0: 08
FINISHES
8.1 | GENERAL
Note: Rates shall include for: fixing, bedding, grouting, pointing, finishing and any other similar works to ensure the required finish. All tiles shall be Whitehorse or equiv.
8.2 | FLOOR TILES
8.2.1 | Ground floor
1 | 600x600mm Polished Ceramic floor tiles
| 600mm x 600mm tiling area | 495.9 | m2
Tiles
Cement for tiling
8.2.2 | Corridors
1 | 600x600mm Polished Ceramic floor tiles
| 600mm x 600mm tiling area | 135.6 | m2
Tiles
Cement for tiling
8.2.3 | Toilets and Ablution Areas
1 | 600x600mm Polished Ceramic floor tiles
| 600mm x 600mm tiling area | 51.2 | m2
Tiles
Cement for tiling
8.2.4 | Ramps
1 | 200x200mm Skid proof Rough Concrete Finish
| 200mm x 200mm tiling area | 18 | m2
Tiles
Cement for tiling
8.2.5 | Steps
1 | 200x200mm Skid proof ceramic floor tiles
| 200mm x 200mm tiling area | 13.32 | m2
Tiles
Cement for tiling
8.3 | WALL TILES
8.3.1 | Ground floor
1 | 300x200mm Ceramic wall tiles
| 300mm x 200mm tiling area | 121.5 | m2
Tiles
Cement for tiling
8.3.2 | Toilets and Ablution Areas
1 | 300x200mm Ceramic wall tiles
| 300mm x 200mm tiling area | 40.2 | m2
Tiles
Cement for tiling
BILL N0: 08 - FINISHES
TOTAL OF BILL No: 08 - Carried over to summary
BILL N0: 09
HYDRAULICS & DRAINAGE
9.1. | Internal Plumbing
| Internal plumbing in toilets, pantries, Kitchens and laundries incl. Supply and laying of pipes | 8 | item
9.2. | External plumbing
1 | Direct Municipality Water connection pipe work for ground floor to first floor with separate water meters incl. supply and laying of pipes. | 1 | item
2 | Where Municipality water connection available provision for water meter connection | 1 | Nos
4 | Waste water and sewage connection from all the toilets, to the municipality sewer line with Catch pits and Manhole. Also the well water over flow to the Municipality Drain incl. Supply and laying of pipes. | 1 | item
9.3. | Sanitary Fixtures & Accessories
Sanitary fixtures complete including brackets. All sanitary fittings shall be of superior quality Cotto or equiv. Taps, Hand shower, Head shower, Bidet shower, TP Hoder and Soap trays should be Stainless steel
9.3.1 | Toilets
1 | WC suites incl. Flush tank and fittings with fresh water connection | 8 | Nos
2 | Wash basin | 2 | Nos
3 | Muslim Shower with water connection | 8 | Nos
4 | Mirror | 2 | Nos
5 | Soap tray | 10 | Nos
6 | Toilet paper holder | 8 | Nos
7 | Floor drain | 8 | Nos
8 | Accessibility Bars | 4 | Nos
9 | Ablution taps | 19 | Nos
10 | Floor drain | 9 | Nos
9.3.2 | Pumps
1 | Supply and installation of appropriate capacity Water pump 'Davey' or equivalent, complete including pump stand, connecting to pipe work and electricity as specified | 1 | Nos
BILL No: 09 - Carried forward
BILL No: 09 - Brought forward
9.2 | DRAINAGE
9.2.1 | Preamble notes
| (a) Rates shall include for excavation, maintaining faces of drain pipe trenches and pits, backfilling, disposal of surplus soil, bends, junctions, reducers, expansion joints and all joints, gutters, end caps and other incidental materials. | 1 | item
(b) All pipework shall be UPVC
9.2.2 | Rainwater discharge pipe
| ø 75mm PVC Rainwater down pipe from Roof (including false canopy roof) to the drainage. | 1 | item
BILL No:09 - HYDRAULIC AND DRAINAGE
TOTAL OF BILL No:09 - Carried over to summary
BILL No:10
PAINTING
10.1 | GENERAL
Note: (a) Rates shall include for: the provision, erection and removal of scaffolding, preparation, rubbing down between coats and similar work, the protection and/or masking floors, fittings and similar work, removing and replacing door window furniture
(b) All painting work shall be carried in accordance with the Specifications
(c) Emulsion paint finish after grinding the area and applying putty.
10.2 | WALLS
Emulsion paint finish (Nippon or equiv.) after grinding the area and applying putty and exterior walls should be applied with weather proof textured paint
10.2.1 | Ground floor
1 | Exterior
| Painting area | 398.23 | m2
Wall sealer
Emulsion paint (textured)
2 | Interior
| Painting area | 398.23 | m2
Wall sealer
Emulsion paint
Putty
10.2.2 | Toilets and Ablution Areas
1 | Exterior
| Painting area | 42.3 | m2
Wall sealer
Emulsion paint (textured)
2 | Interior
| Painting area | 78.4 | m2
Wall sealer
Emulsion paint
Putty
10.3 | CEILING
Emulsion paint finish after grinding the area and applying putty. Both Slab soffit and false ceiling
1 | Ground floor
| Painting area | 495.9 | m2
Wall sealer
Emulsion paint
Putty
2 | Corridors
| Painting area | 135.6 | m2
Wall sealer
Emulsion paint
Putty
3 | Toilets and Ablution Areas
| Painting area | 51.2 | m2
Wall sealer
Emulsion paint
Putty
BILL No: 10 - Carried forward
BILL No: 10 - Brought forward
10.4 | WATER PROOFING
Suitable water proofing material to be used
1 | Toilets | 51.2 | m²
2 | Roof Slab | 599.28 | m²
BILL No: 10 - PAINTING
TOTAL OF BILL No: 10 - Carried over to summary
BILL No: 11
FURNITURE
11.1 | GENERAL
Rates shall include for supply & installation.
11.2 | Mimbaru
| Stand for Khuthuba with Steps and Cushion (Design should be approved from the client) | 1 | m
11.3 | Mus'haf Cupboard
| Mus'haf Cupboard 2m L x 600mm H x 300mm D | 6 | m
11.4 | Sound Cupboard
| Sound Cupboard 1.2m H x 600mm L x 450mm D | 1 | m
BILL No: 11 -FURNITURE
TOTAL OF BILL No: 11 - Carried over to summary
BILL No: 12
ELECTRICAL INSTALLATIONS
12.1 | GENERAL
(a) Rates shall include for: screws, nails, bolts, nuts, standard cable fixing or supporting clips, brackets, straps, rivets, plugs and all incidental accessories
(b) Rates for work in trench shall include for: excavation, maintaining faces of excavations, backfilling, compaction, appropriate cable covers, warning tape and disposal of surplus spoil
(c) Rates for electrical conduits, fittings, equipment and similar items shall include for: all fixings to various building surfaces
(d) Light end and switch end of wiring together measured as one point
(e) A point wiring for power points is measured as one point for each socket outlet; other end of wire is not included in the quantity.
(f) Rates shall include for supply and complete installation
(g) Rates shall include special electrical works, lift and air conditioning system
(h) Three phase power supply
12.2 | ELECTRICAL BOARDS
1 | Complete installation, including for all connections, earthing, painting, testing and similar of:
| Single phase main panel board with connections from the mains including meters, cut-off fuse and other accessories to be located in the panel room at ground floor to electrical engineers specification | 1 | Item
2 | Panel Board | 1 | Nos
12.3 | ELECTRICAL WIRING
| Electrical wiring with copper conductor cable in conduits in walls and concrete as per government regulations including necessary D-boards at each level. | 1 | item
12.4 | ELECTRICAL FIXTURES
| Distribution board | 1 | nos
| Sub-Distribution board | 8 | nos
| Ceiling Fan 56' (KDK or equiv.) | 22 | nos
| Airconditioner Units Cassette Type 48, 000 BTU complete with outdoor units | 12 | nos
| Ceiling Mount Lamp LED 54W 5100lm 94 lm/W | 54 | nos
| Wall Mount 2x LED 3W 252lm 84lm/W | 13 | nos
| Ceiling Mount LED Track Lamp 8.5W 808lm 45lm/W | 42 | nos
| Solar Outdoor LED Waterproof Fencegate Décor | 12 | nos
| Ceiling Mount Fluorescent Lamp 2x tubular 54W 4450lm 41lm/W | 18 | nos
| Wallmount LED Unilamp 2W 240lm 120lm/W | 6 | nos
| Halide Lamp 70W 6500lm 63lm/W | 12 | nos
| Spotlight Unilamp 12W 1620lm 135lm/W | 12 | nos
BILL No: 12 - Carried forward
BILL No: 12 - Brought forward
| Telephone Socket Outlet | 2 | nos
| Network Socket Outlet | 2 | nos
| Switch Socket Outlet 13AMP | 22 | nos
| Switch Socket Outlet 15AMP 1-gang | 12 | nos
| Switch Socket Outlet Weatherproof | 2 | nos
| Ceiling Fan Regulator | 22 | nos
| One way Switch Outlet 1-gang | 10 | nos
| Two way Switch 1-gang | 18 | nos
| Three Phase Isolators | 4 | nos
12.6 | SOLAR PANELS
Solar Panels fixed on Roof Slab with Batteries including installation and connection
| Solar Panels PV | 32 | nos
| Battery Store (19.6 kWh@25ºC (77ºF), 6.6KW, 7kW for 10 sec.) | 2 | nos
BACKLIT NAME BOARD
| Masjid Name Board with cout out Letter and Backlighting (Design and suply) | 1 | nos
BILL No: 12 - ELECTRICAL INSTALLATION
TOTAL OF BILL No: 12 - Carried over to summary
BILL No: 13
WOODWORK
13.1 | General
(a) Rates shall include for: all labour in framing, notching and fitting around projections, pipes, light fittings, hatches, grilles and similar and complete with cleats, packers, wedges and similar and all nails and screws.
13.2 | Calligraphy
1 | Calligraphy Board 2m x 4m (Design and suply) | 1 | m
2 | Calligraphy Board 1.5m x 4m ( (Design and suply) | 2 | m
BILL No: 13 - WOODWORK
TOTAL OF BILL No: 13 - Carried over to summary
BILL N0: 14
ROOFING
14.1 | General
14.1.1 | GENERAL
Rates shall include for: fair edges, dressing over angel fillets, turning into grooves, all other labours, circular edges, nails, screws and other fixings and laps
14.2 | MAIN MOSQUE DOME
1 | Pre Fabrcated Dome
| 6000mm radius 4000m height with SS Gold plated Crescent (850mm dia.) placed over roof slab fixed to withstand Windspeed 65 knots | 1 | item
2 | Roof Screed
Fiberglass covering on Roof
Roof Area
| Fiberglass mat (225gsm) | 599.28 | m2
Resin (200litre barrel)
BILL N0: 14 - ROOFING
TOTAL OF BILL No: 14 - Carried over to summary
BILL No: 15
FIRE FIGHTING SYSTEM
15.1 | GENERAL
(a) Rates shall include for sockets, running joints, backnuts and similar; incidential fittings, clips, saddles, brackets, straps, hangers, screws, nails and fastenings complete, incl. cutting and forming holes; excavating laying pipes and backfilling trenches.
(b) Shop drawings of the system should be submitted to the consultant for approval.and it should be acceptable and comply to the regulation of the MNDF Fire and Rescue Service Department
(c) All items used in fire fighting system should be acceptable and comply to regulations of the MNDF Fire and Rescue Service Department.
15.2 | FIRE APPLIANCES
15.2.1 | Ground Floor
1 | Fire extinguisher | 2 | No
BILL No: 15 - FIRE FIGHTING SYSTEM
TOTAL OF BILL No: 15 - Carried over to summary
BILL No: 16
EXTERIOR BOUNDARY AND PAVEMENT
16.1 | GENERAL
Price should include levelling and laying pre-cast blocks, including price of blocks and workmanship
16.2 | Excavation for boundary | 16 | m³
16.3 | Boundary Foundation Beam FB1
| Concrete Volume | 6.4 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 12.8 | m²
12mm thick plywood
| 50mm x 50mm timber | 0.3 | m³
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (4T12) | 0.45 | t
| 6mm. dia, ring bar (R6@100) | 0.25 | t
]
16.4 | Columns C4 (Boundary)
| Concrete Volume | 3.42 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 39.6 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement. ( Upto bar length 1.2m)
| 12mm. dia, 6m. high tensile steel bar (4T12) | 0.23 | t
| 10mm. dia, 6m. Ring bars (4R10@200 with HOOK) | 0.18 | t
16.5 | PRE-CAST BOUNDARY BLOCKS
Pre-cast blocks for Boundary Walls
1 | Boundary Wall
| Prefabricated Boundary area | 153.36 | m2
Prefabricated concrete blocks 1200 x 1200
Cement for block placing
River Sand
BILL No: 16 - Carried forward
BILL No: 16 - Brought forward
16.6 | PAINTING
Emulsion paint finish after grinding the area and applied with weather proof textured paint
1 | Boundary wall
| Painting area | 291.12 | m2
Wall sealer
Emulsion paint
Putty
16.7 | Pavement blocks
Levelling and laying concrete blocks
| Interlocking blocks 100 x 200 (thickness 50mm) Pavement area | 84 | m2
| Pre-fab Slabs 400 x 600 (thickness 50mm) Pavement area | 44 | m2
| Pre-fab Slabs 1300 x 1300 (thickness 50mm) Pavement area | 3.38 | m2
| Pre-fab Slabs 1300 x 1800 (thickness 50mm) Pavement area | 16.38 | m2
| Pre-fab Slabs 1300 x 2800 (thickness 50mm) Pavement area | 26.88 | m2
BILL No: 16 - EXTERIOR BOUNDARY AND PAVEMENT
TOTAL OF BILL No: 16 - Carried over to summary
BILL No: 17
ADDITIONS & OMISSIONS
BILL No: 16 - ADDISSION & OMISSION
TOTAL OF BILL No: 16 - Carried over to summary
SUMMARY
1 | PRELIMINARIES
2 | GROUND WORKS
3 | CONCRETE
4 | MASONRY AND PLASTERING
5 | METAL WORKS
6 | CEILINGS
7 | DOORS AND WINDOWS
8 | FINISHES
9 | HYDRAULICS & DRAINAGE
10 | PAINTING
11 | FURNITURE
12 | ELECTRICAL INSTALLATIONS
13 | WOODWORK
14 | ROOFING
15 | FIRE FIGHTING SYSTEM
16 | EXTERIOR BOUNDARY AND PAVEMENT
17 | ADDITIONS & OMISSIONS
GRAND TOTAL

## MINARET SUMMARY
SUMMARY OF BILLS OF QUANTITIES
ESTIMATE OF SINGLE STOREY MOSQUE MINARET(700 PAX)
CLIENT: MINISTRY OF ISLAMIC AFFAIRS
Bill No |  | Description | Amount
1 |  | GROUND WORKS
2 |  | CONCRETE
3 |  | MASONRY AND PLASTERING
4 |  | METAL WORKS
5 |  | DOORS AND WINDOWS
6 |  | FINISHES
7 |  | PAINTING
8 |  | ELECTRICAL INSTALLATIONS
9 |  | ADDITIONS & OMISSIONS
TOTAL
GST 6.00 %
GRAND TOTAL
NOTE : |  | 1) Masonry, plastering & Screeding works quoted with Manufactured sand.
Duration :

## MINARET BOQ
BILLS OF QUANTITIES
OF SINGLE STOREY MOSQUE MINARET(700 PAX)
Item | Description | Qty | Unit | Rate | Total Amount
BILL No: 01
GROUND WORKS
1.1 | GENERAL
Note: Rates shall include for: levelling, grading, trimming, compacting to faces of excavation, keep sides plumb, backfilling, consolidating and disposing surplus soil
| Building footrpint area | 25 | m²
1.2 | EXCAVATION
Note: Excavation quantities are measured to the faces of concrete members. Rates shall include for all additional excavation required to place the formwork/shuttering and dewatering the trenches for the required days.
1 | Excavation for foundation
| Excavation for Minaret Foundation | 82.5 | m³
1.3 | FILLING
Notes: Rates shall include for: levelling, grading, trimming and compacting
1 | Sand blinding layer to receive damp proof membrane | 49.5 | m²
2 | Earth filling in ground floor (300mm above ground level) | 19.8 | m³
1.4 | WATER PROOFING
Note: Rates shall include for: dressing around and sealing to avoid all penetrations
1 | Apply 2 coats of Brush Bond or similar on foundation rafts,strip beams & tie beams, steps and under ground masonry & concrete walls in accordance with manufacturer's instructions | 1 | item
1.5 | Damp Proof Membrane
(a) Rates shall include for: dressing around and sealing to all penetrations.
| Heavy duty polyethylene sheet damp proof membrane (1000 gauge) laid on blinding layer. | 62 | m²
BILL No: 01 - GROUND WORKS
TOTAL OF BILL No: 01 - Carried over to summary
BILL No: 02
CONCRETE
2.1 | GENERAL
(a) Rates shall include for: provision to place in position; casting of all required items and finishing after removal of formwork and additional concrete required to conform to structural and excavated tolerances
(b) Rates shall include supply of all formwork item including form oil, timber, plywood, nails etc.
(c) Mix ratio for reinforced concrete shall be 1:2:3 and lean concrete shall be 1:3:6 by volume
1 | Allow for concrete testing. | 1 | LS
2.2 | LEAN CONCRETE
Note: Quantity is measured with additional 0.1m to the edges of concrete foundation members. Rates shall be inclusive for any additional concrete required to place the formwork.
1 | 50mm thick lean concrete to bottom of raft foundation or strip footing and beams
| Concrete Volume | 2.5 | m³
Cement
River sand
Coarse aggregate
2.3 | REINFORCED CONCRETE
(a) Rates shall include for: cleaning, fabrication, placing, the provision for all necessary temporary fixings and supports including tie wire and chair supports, laps and wastage
(b) All reinforcing bars except 6mm dia bars shall be high strength deformed bars
(c) The exact length inclusive of laps are given. The rates shall take into account any wastage.
In-situ reinforced concrete to:
2.3.1 | Foundation
1 | Foundation Pad Minaret (5000 x 5000 x 2700mm)
| Concrete Volume | 74.25 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 79 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 12mm. dia, 6m. high tensile steel bar (T12@150 BW TB) | 0.3 | t
| 10mm. dia, 6m. high tensile steel bar (T12@150 BW B) | 0.15 | t
1.6mm. dia, 90mm Steel ties
BILL No: 02 - Carried forward
BILL No: 02 - Brought forward
2.3.2 | Columns
1 | Columns C2 (Minaret)
| Concrete Volume | 6.09 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 95.7 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement. ( Upto bar length 8m)
| 16mm. dia, 6m. high tensile steel bar (4T16) | 0.55 | t
| 6mm. dia, 6m. Ring bars (R6@150 with HOOK) | 0.24 | t
1.6mm. dia, 90mm Steel ties
2 | Minaret top concrete structure
| Concrete Volume | 2.3 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. | 160.93 | m²
9mm thick Resin
50mm x 50mm timber
Nails
Mould oil
Reinforcement. ( Upto bar length 6m)
| 10mm. dia, 6m. high tensile steel bar (10@100 bw) | 0.03 | t
1.6mm. dia, 90mm Steel ties
BILL No: 02 - Carried forward
BILL No: 02 - Brought forward
2.3.3 | Beams
1 | Minaret Beams B1
| Concrete Volume | 0.67 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 5.52 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 20mm. dia, 6m. high tensile steel bar (6T20) | 0.1 | t
| 16mm. dia, 6m. high tensile steel bar (2T16) | 0.03 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.02 | t
6mm. dia, ring bar (R6@100)
1.6mm. dia, 90mm Steel ties
2 | Minaret Beams B2
| Concrete Volume | 2.37 | m³
Cement
River sand
Coarse aggregate
Concrete chemical Rheomix 141
Water proofing material
| Formwork. (Sides upto slab level) | 21.47 | m²
12mm thick plywood
50mm x 50mm timber
Nails
Mould oil
Reinforcement.
| 16mm. dia, 6m. high tensile steel bar 82T16) | 0.32 | t
| 12mm. dia, 6m. high tensile steel bar (2T12) | 0.08 | t
6mm. dia, ring bar (R6@150)
1.6mm. dia, 90mm Steel ties
BILL No: 02 - CONCRETE
TOTAL OF BILL No: 02 - Carried over to summary
BILL No: 03
MASONRY AND PLASTERING
3.1 | GENERAL
Note: Rates shall include for: cleaning out cavities, forming rebated reveals and pointing and cleaning down to reveals where necessary; fractional size blocks, all necessary machine cutting, cutting or forming chases or edges of floor slabs, cutting or leaving holes and openings as recesses for and building in pipes, conduits, sleeves and similar as required for all trades; leaving surfaces rough or raking out joints for plastering and flashing, bedding frames or plates, building in joists, bearers or similar, temporary supports to openings, templates, reinforcement in walls and for all necessary making good. Providing approved quality mesh at joints between structaral members and masonry in the exterior walls
3.2 | SOLID BLOCK WORK
150 x 150 x 300mm solid block wall, blocks laid common bond
2 | Raised Ground floor
| Masonry area | 81.12 | m2
Bricks
Cement for block placing
River Sand
4.3 | PLASTERING
12mm thick interior cement plastering and 20mm thick exterior cement plastering as specified on
2 | Raised Ground floor
a | Exterior
| Plastering area (Exterior) | 81.12 | m2
Cement for plastering
River sand for plastering
b | Interior
| Plastering area (Interior) | 81.12 | m2
Cement for plastering
River sand for plastering
BILL No: 03 - Carried forward
BILL No: 03 - Brought forward
3.4 | FLOORING
Cement sand screeding on the floor as specified on.
1 | Ground floor
50 mm thick screed in the floor
| Cement sand screed Area | 115.2 | m2
Cement
River sand
BILL No: 03 - MASONRY & PLASTERING
TOTAL OF BILL No: 03 - Carried over to summary
BILL No: 04
METAL WORKS
4.1 | GENERAL
Note: (a) Rates shall include for: all fabrication work, welding, marking, drilling for bolts including those securing timbers, steel plates, bolts, nuts and any type of washer, riveted work, counter sinking and tapping for bolts or machine screws.
(b) Rates shall include for all painting and finishing as specified
(c) Rates shall include for fabrication and erection and temporary supports and fixing into position
(c) The contractor shall submit the detail of the Garbage chute and get the approval from the Consultant before fixing it in position
4.2 | RAILING ON RAMP ACCESS
4.2.1 | GI Ladder and safety covering
1 | GI Ladder with Enamel Coating fixed to interrior of the Minaret for acces to top level of minaret for maintenance. | 4 | item
1 | Pre Fabrcated Dome
| 2200mm radius 2500m height placed over roof slab fixed to withstand Windspeed 65 knots | 1 | item
BILL No: 04 - METAL WORKS
TOTAL OF BILL No: 04 - Carried over to summary
BILL No: 05
DOORS AND WINDOWS
5.1 | GENERAL
Notes: (a) Rates shall include for locks, latches, closures, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware and these materials should brass and of superior quality.
(b) Rates shall include for door frames, mullions, transoms, trims, glazing, tinting, timber panels, boarding, framing, lining, fastenings and all fixings
(c) Rates shall include for all painting
5.2 | TIMBER DOORS, ALUMINIUM DOORS AND WINDOWS
2 | D1 (2150 x 700) as shown in drawing | 1 | Nos
BILL N0: 05 -DOORS AND WINDOWS
TOTAL OF BILL No: 05 - Carried over to summary
BILL N0: 06
FINISHES
6.1 | GENERAL
Note: Rates shall include for: fixing, bedding, grouting, pointing, finishing and any other similar works to ensure the required finish.
6.2 | FLOOR TILES
6.2.1 | Ground floor
1 | 600x600mm Ceramic floor tiles
| 600mm x 600mm tiling area | 92.16 | m2
Tiles
Cement for tiling
(b) All pipework and fittings shall be high pressure UPVC
(c) Rate shall include for supply and fixing of all pipes
BILL N0: 06 - FINISHES
TOTAL OF BILL No: 06 - Carried over to summary
BILL N0: 07
PAINTING
7.1 | GENERAL
Note: (a) Rates shall include for: the provision, erection and removal of scaffolding, preparation, rubbing down between coats and similar work, the protection and/or masking floors, fittings and similar work, removing and replacing door window furniture
(b) All painting work shall be carried in accordance with the Specifications
(c) Emulsion paint finish after grinding the area and applying putty.
7.2 | WALLS
Emulsion paint finish after grinding the area and applying putty and exterior walls should be applied with textured paint
7.2.1 | Ground floor
1 | Exterior
| Painting area | 81.12 | m2
Wall sealer
Emulsion paint
2 | Interior
| Painting area | 81.12 | m2
Wall sealer
Emulsion paint
Putty
7.3 | CEILING
Emulsion paint finish after grinding the area and applying putty. Both Slab soffit and false ceiling
1 | Level 1 to 4
| Painting area | 103.5 | m2
Wall sealer
Emulsion paint
Putty
7.4 | WATER PROOFING
Suitable water proofing material to be used
1 | Minaret | 15.12 | m²
BILL No: 7 - PAINTING
TOTAL OF BILL No: 7 - Carried over to summary
BILL No: 08
ELECTRICAL INSTALLATIONS
8.1 | GENERAL
(a) Rates shall include for: screws, nails, bolts, nuts, standard cable fixing or supporting clips, brackets, straps, rivets, plugs and all incidental accessories
(b) Rates for work in trench shall include for: excavation, maintaining faces of excavations, backfilling, compaction, appropriate cable covers, warning tape and disposal of surplus spoil
(c) Rates for electrical conduits, fittings, equipment and similar items shall include for: all fixings to various building surfaces
(d) Light end and switch end of wiring together measured as one point
(e) A point wiring for power points is measured as one point for each socket outlet; other end of wire is not included in the quantity.
(f) Rates shall include for supply and complete installation
(g) Rates shall include special electrical works, lift and air conditioning system
(h) Three phase power supply
8.2 | ELECTRICAL BOARDS
1 | Complete installation, including for all connections, earthing, painting, testing and similar of:
| Single phase main panel board with connections from the mains including meters, cut-off fuse and other accessories to be located in the panel room at ground floor to electrical engineers specification | 1 | Item
8.3 | ELECTRICAL WIRING
| Electrical wiring with copper conductor cable in conduits in walls and concrete as per government regulations including necessary D-boards at each level. | 1 | item
ELECTRICAL FIXTURES
| Floor light Low IP65 striplight LED with Heat dissipating Aluminum bars 12mm W x 5mm H x 50m length rolls | 2 | nos
| Ceiling Mount Fluorescent Lamp 2x tubular 54W 4450lm 41lm/W | 2 | nos
| Spotlight adjustable 12W 1620lm 135lm/W | 4 | nos
| One way Switch 1-gang | 1 | nos
8.5 | SOUND SYSTEM
| (1) Horn Loudspeaker 75W (TOA or equiv) | 4 | nos
| (2) Speakers 30W wall fixed shall be "JBL", "Bose" or equivalent (White color) | 12 | nos
| (3) Amplifier 360w, 100v (Line 6, or YAMAHA or equiv) | 2 | nos
| (4) Audio Mixer (8 Channel), phantom power shall be "YAMAHA", "Sound Craft" or Equivalent | 1 | nos
| (5) Wireless Headworn mic shall be "Sennheiser", "SHURE" or Equivalent | 1 | nos
| (6) Cable Mic shall be "Bose" or "JTS" or equivalent | 1 | nos
| (7) Goose neck mic with shock mount shall be "SHURE" OR "Sennheiser" OR equivalent | 1 | nos
| (8) Adjustable mic stand with round Base | 1 | nos
| (9) Microphone Cable with Connection Jacks and Extension | 1 | nos
BILL No: 8 - ELECTRICAL INSTALLATION
TOTAL OF BILL No: 8 - Carried over to summary
BILL No: 09
ADDITIONS & OMISSIONS
BILL No: 09 - ADDISSION & OMISSION
TOTAL OF BILL No: 09 - Carried over to summary
SUMMARY
1 | GROUND WORKS
2 | CONCRETE
3 | MASONRY AND PLASTERING
4 | METAL WORKS
5 | DOORS AND WINDOWS
6 | FINISHES
7 | PAINTING
8 | ELECTRICAL INSTALLATIONS
9 | ADDITIONS & OMISSIONS
GRAND TOTAL
(a) Rates shall include for sockets, running joints, connectors, elbows, junctions, valves, reducers, expansion joints, backnuts and similar, incidental fittings, clips saddles, brackets, straps, hangers, screws, nails and fixing complete, including cutting and forming holes, excavating, laying pipes and backfilling trenches.