## Cover
BILL OF QUANTITIES
CLASSROOM BLOCK at TH.BURUNEE SCHOOL
CLIENT : MINISTRY OF EDUCATION, GOVERNEMNT OF MALDIVES

## BOQ Summary
SUMMARY OF BILLS OF QUANTITIES
CLASSROOM BLOCK at TH.BURUNEE SCHOOL
| DESCRIPTION | AMOUNT | %
Bill №: 01 - PRELIMINARIES
Bill №: 02 - EXCAVATION AND FILLING
Bill №: 03 - INSITU CONCRETE WORKS
Bill №: 04 - MASONRY
Bill №: 05 - STRUCTURAL METAL WORKS
Bill №: 06 - ROOFING
Bill №: 07 - WINDOWS, SCREENS & LIGHTS
Bill №: 08 - DOORS, SHUTTERS & HATCHES
Bill №: 09 - FLOOR, WALL, CEILING, AND ROOF FINISHINGS
Bill №: 10 - SUSPENDED CEILING
Bill №: 11 - PAINTING & DECORATIONS
Bill №: 12 - STAIRS, WALKWAYS AND BALUSTRADES
Bill №: 13 - MECHANICAL & ELECTRICAL SERVICES
Bill №: 14 - PLUMBING
Bill №: 15 - INSULATION, FIRE STOPPING & FIRE PROTECTION
Bill №: 16- ADDITIONS AND OMMISIONS
TOTAL AMOUNT

## BOQ for tender
0
CLASSROOM BLOCK at TH.BURUNEE SCHOOL
Male', Republic of Maldives
BILL OF QUANTITIES
ITEM |  |  |  | DESCRIPTION | UNIT | QTY | MATERIAL RATE | LABOUR RATE | AMOUNT
1.0.00 |  |  |  | Bill №: 01 - PRELIMINARIES
1.1.00 | GENERAL NOTES
Abbreviations
|  |  | m | - metre
|  |  | nr | - numbers
|  |  | m3 | - cubic metres
|  |  | m2 | - square metres
|  |  | m | - linear metre
|  |  | t | - tons
|  |  | inc. | - including
|  |  | mm | - millimetre
|  |  | SS | - stainless steel
|  |  | GI | - galvanized iron
1.2.00 | SITE MANAGEMENT COSTS
|  |  |  | Allow for all on and off site management cost including costs of foreman and assistants, temporary services, telephone, fax, hoardings & similar. | item | 1
1.3.00 | SIGN BOARD
|  |  |  | Allow for sign board. | nr | 1
1.4.00 | CLEAN-UP
|  |  |  | Allow for clean-up upon completion of works. | item | 1
1.5.00 | INSURANCE, BONDS, GUARANTEES AND WARRANTIES
|  |  |  | Insurance as stated in the general conditions. | item | 1
1.6.00 | TOTAL OF BILL №: 01 - Carried Over To Summary
2.0.00 |  |  |  | Bill №: 02 - EXCAVATION AND FILLING
2.1.00 | GENERAL
|  |  | (a) | Rates shall include for: leveling, grading, trimming, compacting to faces of excavation, keep sides plumb, backfilling, consolidating, and disposing surplus soil.
2.2.00 | SITE CLEARING
2.2.01 |  |  |  | Clear the area of site from rubbish and vegetable matters, stumps, roots. Rates shall include for removal of trees and tree stumps | m2 | 346.95
2.3.00 | EXCAVATION
Excavation quantities are measured to the faces of concrete members. Rates shall include for all the additional excavation required to place the formwork. Rates shall include for backfilling.
2.3.01 |  |  |  | Excavation for Foundation pads | m3 | 65.742
2.3.02 |  |  |  | Excavation for Foundation beams | m3 | 27.2518
2.4.00 | FILLING
Rate shall include for: levelling, grading, trimming, compacting and similar
2.4.01 |  |  |  | Compacted earth filling under ground slab | m2 | 342.72
2.4.02 |  |  |  | 150mm thick coarse aggregate layer under foundation | m2 | 342.72
2.5.00 | DAMP-PROOF MEMBRANE
Rate shall include for: dressing around and sealing to all penetrations.
2.5.01 |  |  |  | Polythene damp proof membrane (500 gauge) | m2 | 342.72
2.6.00 | DE-WATERING
2.6.01 |  |  |  | De-watering the excavation until completion of concrete work as required | item | 1
2.7.00 | TOTAL OF BILL №: 02 - Carried Over To Summary
3.0.00 |  |  |  | Bill №: 03 - INSITU CONCRETE WORKS
3.1.00 | GENERAL
|  |  | (a) | Rates shall include for: placing in position, making good after removal of formwork, mortar touch up to all concrete and casting in all required items; additional concrete required to conform to structural and excavated tolerances
|  |  | (b) | Mix ratio for reinforced concrete shall be 1:2:3 and lean concrete shall be 1:2:6.
|  |  | (c) | All structural concrete shall be GRADE M25 and lean concrete shall be GRADE M15
|  |  | (d) | Rates shall include for: concrete, formwork, reinforcement, cleaning, fabrication, placing, the provision for all necessary temporary fixings and supports including tie wires and chair supports, laps, distribution bars and wastage.
|  |  | (e) | Rates shall include for: all necessary boarding, supports, erecting, framing, temporary cambering, cutting, perforations for reinforcing bars, bolts, straps, ties, hangers, pipes and removal of formwork.
|  |  | (f) | Rates shall include for: cleaning, fabrication, placing the provision for all necessary temporary fixings and supports including tie wires and chair supports, laps, distribution bars and wastage.
|  |  | (g) | All reinforcing bars shall be high strength bars.
|  |  | (h) | Slab soffits to be finished fairfaced, use plasteciser and formwork with reducing agent.
|  |  | (i) | All exposed & external concrete members shall be casted with masterpel 777 or equivalent water proofing chemical.
|  |  | (j) | Rate shall include for applying 2 coats of waterproofing chemical to substructure.(Below ground level).
3.1.01 |  |  |  | Allow for Concrete Testing. | item | 1
3.2.00 | MASS CONCRETE
Quantity is measured to the edges of concrete foundation members. Rates shall be inclusive for any additional concrete required to place the formwork.
3.2.01 |  |  | 50 | mm Lean Concrete (Foundations) | m3 | 4.35
3.3.00 | REINFORCED INSITU CONCRETE
SUB-STRUCTURE
FOUNDATION PADS
3.3.01 | 1800 | x | 1800 | x 300mm Foundation pads, F1 | m3 | 2.916
3.3.02 | 1600 | x | 1600 | x 300mm Foundation pads, F2 | m3 | 0.768
3.3.03 | 1400 | x | 1400 | x 300mm Foundation pads, F3 | m3 | 5.292
3.3.04 | 1200 | x | 1200 | x 300mm Foundation pads, F4 | m3 | 4.32
3.3.05 | 1100 | x | 1100 | x 300mm Foundation pads, F5 | m3 | 1.452
3.3.06 | 750 | x | 750 | x 300mm Foundation pads, F6 | m3 | 1.6875
FOUNDATION BEAMS
3.3.07 | 450 | x | 200 | mm Foundation beam, TB | m3 | 13.6259
STAIR STARTER
3.3.08 | 200 | x | 1275 | mm Concrete stair starter | m3 | 0.54
COLUMNS
3.3.09 | 200 | x | 350 | mm Concrete columns C1 | m3 | 0.1365
3.3.10 | 200 | x | 350 | mm Concrete columns C2 | m3 | 0.1365
3.3.11 | 200 | x | 300 | mm Concrete columns C3 | m3 | 0.819
3.3.12 | 200 | x | 200 | mm Concrete columns C4 | m3 | 0.26
3.3.13 | 150 | x | 150 | mm Concrete columns SC | m3 | 0.08775
3.4.00 | GROUND FLOOR
COLUMNS
3.4.01 | 200 | x | 350 | mm Concrete columns C1 | m3 | 0.609
3.4.02 | 200 | x | 350 | mm Concrete columns C2 | m3 | 0.609
3.4.03 | 200 | x | 300 | mm Concrete columns C3 | m3 | 3.654
3.4.04 | 200 | x | 200 | mm Concrete columns C4 | m3 | 1.16
3.4.05 | 150 | x | 150 | mm Concrete columns SC | m3 | 0.3915
SLABS
3.4.06 |  |  | 100 | mm thk Concrete Slab on ground | m3 | 30.877
3.4.07 |  |  | 100 | mm thk Concrete Slab on ramp | m3 | 0.57
3.5.08 |  |  | 150 | mm thk Concrete Slab on half landing level | m3 | 1.98
STAIRCASE
3.4.09 |  |  |  | Concrete staircase GF to FFL -400 | m3 | 0.39328
3.4.10 |  |  |  | Concrete staircase GF to 1st FL | m3 | 1.4064
HALF LANDING BEAMS
3.4.11 | 400 | x | 200 | mm Beam B2 | m3 | 0.716
3.4.12 | 400 | x | 200 | mm Beam B3 | m3 | 0.456
3.5.00 | FIRST FLOOR
COLUMNS
3.5.01 | 200 | x | 350 | mm Concrete columns C1 | m3 | 0.6531
3.5.02 | 200 | x | 350 | mm Concrete columns C2 | m3 | 0.6531
3.5.03 | 200 | x | 300 | mm Concrete columns C3 | m3 | 3.9186
3.5.04 | 200 | x | 200 | mm Concrete columns C4 | m3 | 1.244
3.5.05 | 150 | x | 150 | mm Concrete columns SC | m3 | 0.41985
SLABS
3.5.06 |  |  | 180 | mm thk Concrete Slab on first floor | m3 | 32.8475
3.5.07 |  |  | 135 | mm thk Concrete Slab on first floor | m3 | 16.1177
BEAMS
3.5.08 | 475 | x | 200 | mm Beam B1 | m3 | 2.3797
3.5.09 | 400 | x | 200 | mm Beam B2 | m3 | 6.494
3.5.10 | 400 | x | 200 | mm Beam B3 | m3 | 2.2819
3.5.11 | 400 | x | 200 | mm Beam B4 | m3 | 2.2819
3.5.12 | 175 | x | 350 | mm Beam HB | m3 | 1.1637
RC WALL
3.5.13 |  |  |  | 100mm thk 100mm high RC walls | m3 | 0.28524
3.6.00 | ROOF LEVEL - 01
BEAMS
3.6.01 | 300 | x | 200 | mm Beam RB | m3 | 2.8364
3.7.00 | ROOF LEVEL - 02
BEAMS
3.7.01 | 300 | x | 200 | mm Beam RB | m3 | 6.5819
3.8.00 | OTHER WORKS
Lintel and Sill beams
3.8.01 | 150 | x | 150 | mm Beam LT1 | item | 1
3.8.02 | 300 | x | 150 | mm Beam LT2 | item | 1
SHADING
3.8.03 |  |  | 150 | mm thk Concrete shading @ 1st slab level | item | 1
3.8.04 |  |  | 150 | mm thk Concrete shading @ roof beam level | item | 1
FIN
3.8.05 | 100 | X | 150 | mm thk Concrete fin GF | item | 1
3.8.06 | 100 | X | 150 | mm thk Concrete fin 1ST | item | 1
RC bench
3.8.07 |  |  | 75 | mm thk Concrete Slab for vanity at toilet | item | 1
3.9.00 |  |  |  | TOTAL OF BILL №: 03 - Carried Over To Summary
4.0.00 |  |  |  | Bill №: 04 - MASONRY
4.1.00 | GENERAL
|  |  | (a) | Rates shall include for: cleaning out cavities, forming rebated reveals and pointing and cleaning down to reveals where necessary; fractional size blocks, all necessary machine cutting, cutting or forming chases or edges of floor slabs, cutting or leavingholes and openings as recesses for and building in pipes, conduits, sleeves and similar as required for all trades; leaving surfaces rough or raking out joints for plastering and flashing, bedding frames or plates, building in joists, bearers or similar, temporary supports to openings, templates, reinforcement in walls and for all necessary making good.
4.2.00 | BLOCK WORK
Cement block wall, bricks laid to form alternate courses of headers and stretchers, laid on and inc. mortar (EXTERNAL WALLS).
|  |  | 150 | mm thk full height
4.2.01 |  |  |  | BELOW GROUND LEVEL | m2 | 13.5
|  |  | 150 | mm thk full height
4.2.02 |  |  |  | GROUND FLOOR | m2 | 212.77
4.2.03 |  |  |  | FIRST FLOOR | m2 | 172.06
Cement block wall, bricks laid to form alternate courses of headers and stretchers, laid on and inc. mortar (INTERNAL WALLS).
|  |  | 150 | mm thk full height
4.2.04 |  |  |  | GROUND FLOOR | m2 | 141.19
4.2.05 |  |  |  | FIRST FLOOR | m2 | 79.95
|  |  | 100 | mm thk 2.4m height
4.2.06 |  |  |  | GROUND FLOOR | m2 | 24.23
4.2.07 |  |  |  | FIRST FLOOR | m2 | 24.4
|  |  | 100 | mm thk full height
4.2.08 |  |  |  | GROUND FLOOR | m2 | 16.14
4.2.09 |  |  |  | FIRST FLOOR | m2 | 18.34
4.3.00 |  |  |  | TOTAL OF BILL №: 04 - Carried Over To Summary
5.0.00 |  |  |  | Bill №: 05 - STRUCTURAL METAL WORKS
5.1.00 | GENERAL
|  |  | (a) | Rates shall include for: all fabrication work, welding, marking, drilling for bolts incl. those securing timbers, steel plates, bolts, nuts and any type of washer, riveted work, counter sinking and tapping for bolts or machine screws.
|  |  | (b) | Rates shall include for fabrication and erection and temporary supports and fixing into position.
|  |  | (c) | “Welding” is deemed to be in accordance with the specification and for the material to which it is to be used. Gusset plates, shoe plates, ends, caps, cleats, brackets, stiffeners, bolts, etc.,are required to be included to the rate of the associated steel work in which they occur.
|  |  | (d) | For the description of materials and workmanship refer to the Specification of works, pricing Preambles and Drawings.
|  |  | (e) | Contractor shall submit shop drawings for approval prior to fabrication.
|  |  | (f) | Unless specified otherwise, rate shall include for: All shop fabrication work, marking, delivery, unloading, hoisting, erecting and fixing as per detail drawings, All welds & allowance for rolling margin, the weight of weld metal in welded constructions, members of any length, cutting to size and shape and joints in the running length, grinding to a smooth finish, unless otherwise required, Machine drilled bolt, holes, bolts, nuts and washers, cleats, shoe and gusset plates and all other connections, Wire brushing to clean all the steel surfaces (except stainless steel) after fabrication and spray painting with two coats of quick drying metal primer zinc phosphate & two coats of matt anti corrosive paint with final paint, all necessary accessories and preparation and submission of Shop Drawings and As Built Drawings as specified.
5.2.00 | STEEL TRUSS
TRUSS TR1
5.2.01 |  |  |  | Steel truss 11.525m span with 60.3mm dia x 3.2mm thick CHS pipe top and bottom chord and 42.4mm dia. x 2.0mm thick CHS pipe web members | no | 10
STEEL FRAMING
5.2.02 |  |  |  | 60.3mm dia x 3.2mm thick GI bracing beam | m | 28.5
5.2.03 | 50 | x | 100 | x 2.5mm 'C' Purlins at 900 c/c | m | 412.5
5.3.00 |  |  |  | TOTAL OF BILL №: 05 - Carried Over To Summary
6.0.00 |  |  |  | Bill №: 06 - ROOFING
6.1.00 | GENERAL
|  |  | (a) | Rates shall include for: fair edges, dressing over angel fillets, roof sealant, turning into grooves, all other labours, circular edges, nails, screws and other fixings and laps.
6.2.00 | MAIN ROOF COVERING
6.2.01 |  |  |  | Lysaght roofing sheet to specification | m² | 359.55
6.2.02 |  |  |  | 50mm mineral wool insulation with reflective layers on both installed as per suppliers specifications with recommended lap length and air gap tape. Rate shall include for BRC mesh over purlins to support insulation layer. | m² | 359.55
6.3.00 | CAPPING
6.3.01 |  |  |  | Lysaght ridge cap as per roofing sheet suppliers assembly | m | 29.4
6.4.00 | GUTTER
6.4.01 | 200 | x | 200 | mm Zinc Aluminium gutter | m | 57
6.5.00 | DOWN PIPE
6.5.01 |  |  | 82 | mm dia rain water pipe | item | 1
6.5.02 |  |  | 50 | mm dia rain water pipe | item | 1
6.6.00 | FASCIA
6.6.01 | 50 | x | 200 | mm fascia board | m | 80.98
6.7.00 |  |  |  | TOTAL OF BILL №: 06 - Carried Over To Summary
7.0.00 |  |  |  | Bill №: 07 - WINDOWS, SCREENS & LIGHTS
7.1.00 | GENERAL
|  |  | (a) | Rates shall include for locks, latches, closers, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware.
|  |  | (b) | Rates shall include for door frames, mullions, transoms, trims, glazing, tinting, timber panels, boardings, framing, lining, fastenings and all fixings.
|  |  | (c) | Sizes are given overall outside dimensions of actual doors and windows.
|  |  | (d) | Thickness and sizes of glass panels are shown on the Drawings and doors and windows schedule
|  |  | (e) | Rates shall include for all painting as specified
|  |  | (f) | Rates shall include all items specified in the door schedule and specification.
|  |  | (g) | Frames and sashes to be 25-60 micron black powder coated aluminium other wise specified.
7.2.00 | WINDOWS
GROUND FLOOR
7.2.01 | 1525 | x | 1300 | W1 - Aluminium sliding window with clear glass panel on aluminium frame | nr | 6
7.2.02 | 2450 | x | 1500 | W2 - Aluminium side/top hung window with reflective glass panel on aluminium frame | nr | 6
7.2.03 | 650 | x | 750 | W3 - Aluminium window with aluminium louvers on aluminium frame | nr | 4
7.2.04 | 3000 | x | 600 | V1 - Aluminium window with aluminium louvers on aluminium frame | nr | 7
7.2.05 | 2550 | x | 600 | V2 - Aluminium window with aluminium louvers on aluminium frame | nr | 1
7.2.06 | 1875 | x | 600 | V3 - Aluminium window with aluminium louvers on aluminium frame | nr | 2
7.2.07 | 2550 | x | 600 | V4 - Aluminium window with aluminium louvers on aluminium frame | nr | 1
FIRST FLOOR
7.2.08 | 1525 | x | 1300 | W1 - Aluminium sliding window with clear glass panel on aluminium frame | nr | 6
7.2.09 | 2450 | x | 1500 | W2 - Aluminium side/top hung window with reflective glass panel on aluminium frame | nr | 6
7.2.10 | 650 | x | 750 | W3 - Aluminium window with aluminium louvers on aluminium frame | nr | 2
7.2.11 | 1200 | x | 1500 | W4 - Aluminium side/top hung window with reflective glass panel on aluminium frame | nr | 1
7.2.12 | 3000 | x | 600 | V1 - Aluminium window with aluminium louvers on aluminium frame | nr | 7
7.2.13 | 2550 | x | 600 | V2 - Aluminium window with aluminium louvers on aluminium frame | nr | 1
7.2.14 | 2550 | x | 600 | V4 - Aluminium window with aluminium louvers on aluminium frame | nr | 1
7.3.00 |  |  |  | TOTAL OF BILL №: 07 - Carried Over To Summary
8.0.00 |  |  |  | Bill №: 08 - DOORS, SHUTTERS & HATCHES
8.1.00 | GENERAL
|  |  | (a) | Rates shall include for locks, latches, closers, push plates, pull handles, bolts, kick plates, hinges and all door & window hardware.
|  |  | (b) | Rates shall include for door frames, mullions, transoms, trims, glazing, tinting, timber panels, boardings, framing, lining, fastenings and all fixings.
|  |  | (c) | Sizes are given overall outside dimensions of actual doors and windows.
|  |  | (d) | Thickness and sizes of glass panels are shown on the Drawings and doors and windows schedule.
|  |  | (e) | Rates shall include for all painting as specified
|  |  | (f) | Rates shall include all items specified in the door schedule and specification.
|  |  | (g) | Frames and sashes to be 25-60 micron black powder coated aluminium other wise specified.
8.2.00 | DOORS
GROUND FLOOR
8.2.01 | 1000 | x | 2300 | D1 - Aluminium panel door on Aluminium frame with 6mm thk clear glass | nr | 5
8.2.02 | 1000 | x | 2300 | D2 - Aluminium panel door on Aluminium frame with aluminium louvers | nr | 3
8.2.03 | 900 | x | 2200 | D3 - PVC panel door on PVC frame (single swing) | nr | 2
8.2.04 | 700 | x | 2000 | D4 - PVC panel door on PVC frame (single swing) | nr | 3
8.2.05 | 1000 | x | 2300 | D5 - Aluminium panel door on Aluminium frame | nr | 1
FIRST FLOOR
8.2.06 | 1000 | x | 2300 | D1 - Aluminium panel door on Aluminium frame (single swing) | nr | 7
8.2.07 | 1000 | x | 2300 | D2 - Aluminium panel door on Aluminium frame (single swing) | nr | 2
8.2.08 | 900 | x | 2200 | D3 - PVC panel door on PVC frame (single swing) | nr | 2
8.2.09 | 700 | x | 2000 | D4 - PVC panel door on PVC frame (single swing) | nr | 6
8.3.00 |  |  |  | TOTAL OF BILL №: 08 - Carried Over To Summary
9.0.00 |  |  |  | Bill №: 09 - FLOOR, WALL, CEILING, AND ROOF FINISHINGS
9.1.00 | GENERAL
|  |  | (a) | Rates shall include for: fixing, bedding, grouting, and pointing materials; making good around pipes, sanitary fixtures, and similar; cleaning down and polishing.
9.2.00 | PLASTERING
|  |  | 20 | mm thk cement plaster on external surface as specified on the drawing. Waterproofed with Sika product or equivalent.
9.2.01 |  |  |  | GROUND FLOOR | m2 | 212.77
9.2.02 |  |  |  | FIRST FLOOR | m2 | 172.06
|  |  | 16 | mm thk cement plaster on internal surface as specified on the drawing
9.2.03 |  |  |  | GROUND FLOOR | m2 | 559.75
9.2.04 |  |  |  | FIRST FLOOR | m2 | 399.1
9.3.00 | CEMENT SCREED
|  |  | 50 | mm thk cement screed
9.3.01 |  |  |  | GROUND FLOOR | m2 | 207.55
9.3.02 |  |  |  | FIRST FLOOR | m2 | 203.04
|  |  | 35 | mm thk cement screed with 2.5mm self levelling screed
9.3.03 |  |  |  | GROUND FLOOR | m2 | 73.144
9.3.04 |  |  |  | FIRST FLOOR | m2 | 59.23
|  |  | 25 | mm thk cement screed waterproofed with masterpel 777 or equivalent
9.3.05 |  |  |  | GROUND FLOOR | m2 | 26.3
9.3.06 |  |  |  | FIRST FLOOR | m2 | 31.23
9.4.00 | FLOOR TILING
| 600 | x | 600 | mm Homogenous Non-slip tiles
9.4.01 |  |  |  | GROUND FLOOR | m2 | 207.55
9.4.02 |  |  |  | FIRST FLOOR | m2 | 203.04
| 300 | x | 300 | mm Homogenous Non-slip tiles
9.4.03 |  |  |  | GROUND FLOOR | m2 | 26.3
9.4.04 |  |  |  | FIRST FLOOR | m2 | 31.23
9.5.00 | FLOOR PAINTING
Epoxy floor paint
9.5.01 |  |  |  | GROUND FLOOR | m2 | 73.14
9.5.02 |  |  |  | FIRST FLOOR | m2 | 59.23
9.6.00 | WALL TILING
| 300 | x | 600 | mm Homogenous tiles
9.6.01 |  |  |  | GROUND FLOOR | m2 | 77.8152
9.6.02 |  |  |  | FIRST FLOOR | m2 | 68.3552
9.7.00 |  |  |  | TOTAL OF BILL №: 09 - Carried Over To Summary
10.0.00 |  |  |  | Bill №: 10 - SUSPENDED CEILING
10.1.00 | GENERAL
|  |  | (a) | Rates shall include for: all labour in framing, notching and fitting around projections, pipes, light fittings, hatches, grilles and similar and complete with cleats, packers, wedges and similar and all nails and screws.
10.2.00 | PLASTERBOARD CEILING
Fixed "Boral" or equivalent plasterboard ceiling system with timber framing
10.2.01 |  |  |  | FIRST FLOOR | m2 | 168.31
6mm Cement board ceiling on roof eave / gable ceiling / toilet area
10.2.02 |  |  |  | GROUND FLOOR | m2 | 26.3
10.2.03 |  |  |  | FIRST FLOOR | m2 | 174.68
10.3.00 |  |  |  | TOTAL OF BILL №: 10 - Carried Over To Summary
11.0.00 |  |  |  | Bill №: 11 - PAINTING & DECORATIONS
11.1.00 | GENERAL
|  |  | (a) | Rates shall include for: the provision, erection and removal of scaffolding, preparation, wall putty application, rubbing down between coats and similar work, the protection and/or masking floors, fittings and similar work, removing and replacing door & window furniture.
|  |  | (b) | All painting work shall be carried in accordance with the Specifications.
11.2.00 | WALL PAINTING
Weatherbound paint finish as specified (EXTERNAL SURFACES)
11.2.01 |  |  |  | GROUND FLOOR | m2 | 247.0285
11.2.02 |  |  |  | FIRST FLOOR | m2 | 207.6325
Emulsion paint finish including putty application on brick walls as specified (INTERNAL SURFACES)
11.2.03 |  |  |  | GROUND FLOOR | m2 | 559.75
11.2.04 |  |  |  | FIRST FLOOR | m2 | 399.1
11.3.00 | CEILING PAINTING
Weatherbound paint finish as specified (SLAB SOFFIT)
11.3.01 |  |  |  | GROUND FLOOR | m2 | 314.63
Emulsion paint finish including putty application on ceiling as specified (CEILING)
11.3.02 |  |  |  | GROUND FLOOR | m2 | 28.11
11.3.03 |  |  |  | FIRST FLOOR | m2 | 342.99
11.4.00 |  |  |  | TOTAL OF BILL №: 11 - Carried Over To Summary
12.0.00 |  |  |  | Bill №: 12 - STAIRS, WALKWAYS AND BALUSTRADES
12.1.00 | GENERAL
|  |  | (a) | Rates shall include for: all fabrication work, welding, marking, drilling for bolts incl. those securing timbers, steel plates, bolts, nuts and any type of washer, riveted work, counter sinking and tapping for bolts or machine screws.
|  |  | (b) | Rates shall include for fabrication and erection and temporary supports and fixing into position.
12.2.00 | RAMP RAILING
25mm dia SS hollow pipe handrail at 900mm height as per drawing
12.2.01 |  |  |  | RAMP | m | 9.8
12.3.00 | STAIRCASE RAILING
50-25mm dia GI powder coated handrail at 900mm height as per drawing
12.3.01 |  |  |  | GROUND - 1ST FLOOR | m | 6.4
12.4.00 | WALKWAY RAILING
50-25mm dia SS hollow pipe handrail at 1100mm height as per drawing
12.4.01 |  |  |  | FIRST FLOOR | m | 28.12
12.5.00 |  |  |  | TOTAL OF BILL №: 12 - Carried Over To Summary
13.0.00 |  |  |  | Bill №: 13 - MECHANICAL & ELECTRICAL SERVICES
13.1.00 | GENERAL
|  |  | (a) | Design, provide and install electrical network for the entire building complete in accordance to standards set by the local governing body STELCO/FENAKA
|  |  | (b) | The following items and description and the drawings are given as a guidance as to the nature of the information required to be returned by the contractor. Should they not be appropriate the contractor should provide a similar BOQ using the Additions/Ommisions sheets provided at the back of this BOQ.
|  |  | (c) | The cost shall include for: screws, nails, bolts, nuts, standard cable fixing or supporting clips, brackets, straps, rivets, plugs and all incidental accessories.
|  |  | (d) | Rate shall include for necessary chasings, trenching, conduits, cables, cable trays, fittings and clips, cutting holes and chases in brick work/ block work/ concrete work complete with all necessary accessories such as sockets, connections, cable glands and boxes, hardware clips, soldering and jointing materials etc., for proper installing and laying of cables.
|  |  | (e) | Rates for electrical isolators, conduits, fittings, equipment and similar items shall include for: all fixings to various building surfaces.
|  |  | (f) | A light fixture is measured as one point; switch end of wire is not included in the quantity.
|  |  | (g) | A point wiring for power points is measured (regardless of 1 gang, 2 gang etc) as one point for each socket outlet; other end of wire is not included in the quantity.
|  |  | (h) | All under ground cables directly buried in ground/run in trenches to be properly laid and covered with cable tiles/trench covers. Rate for under ground cables shall include for all necessary excavation, sand layers, concrete tiles, warning strips and back filling with approved quality earth properly compacted, hot dipped galvenized brackets for trenches, accessories, etc as applicable.
|  |  | (i) | The contractors are requested to refer Conditions of Contract, Special Conditions of Contract, Drawings and Specification and other relevant documents related to this tender prior to pricing of the following items
|  |  | (j) | The contractor shall provide a schedule of all builder's work in connection with details of such items as necessary, along with the tender.
|  |  | (k) | Rates for materials/ plants/ equipments not approved for duty free facilities to be quoted on duty paid basis.
|  |  | (l) | All equipments shall be guaranteed for a period of 12 months from the date of commissioning or date of practical completion of the project which ever later
|  |  | (m) | The rate shall include for insurance during handling, rehandling, transport, storage until ready for installation, delivery of equipments up to the point of installation and until handing over.
|  |  | (n) | The rates shall include for comprehensive maintenance during defects liability period of 12 months from the date of handing over
|  |  | (o) | The tenderer shall submit the following information on the items/equipments quoted for together with the tender.
a. make
b. model No.
c. technical data
d. country of manufacture
e. delivery period
f. lead time for manufacturing.
g. port of shipping
h. CIF value of each item in foreign currency.
j. Optional items and their additional cost. (additional cost
to be submitted separately)
k. Schedule of items to be carried out by others connected to
installation of generators/transformers/Electrical panels
such as some builders work and electrical connection.
l. Details of all special features
m. schedule attached to specification.
|  |  | (p) | Rate for all electrical panels shall include for supply and installation of all necessary MCCBs, MCBS, EFRs, ELCBs, auxiliary contacts, Voltmeters, ammeters, Digital analyser,kWh meters, indicator lamps, selector switches, copper bus bars, inter locks, aligning and grounding of the panel, inter connectors, internal wiring connections to switch gear,steel channels and necessary hardware fixing insulating materials,all in fully enclosed metal clad panels and distribution boards completed as shown in drawing. They shall comply with the specifications andI.E.E.regulations and be complete to working order to the approval of local authorities.
|  |  | (q) | Rate shall include for supply, installation, maintaining, testing and commissioning of the system for power and lighting according to drawings and specifications to working order.
|  |  | (r) | All materials, equipment wiring shall confirm to local codes, specifications, standards/latest I.E.E. regulations ( BS 7671 ).
13.2.00 | MAIN DISTRIBUTION, SUB DISTRIBUTION AND DISTRIBUTION SYSTEM
Distribution Boards ( DB )
Electrical and internet distribution Panel for each floor as shown on the drawing, complete with all incoming and outgoing MCBs, RCCBs, etc any other item required to working order, wall mounted wall mount steel powder coated, IP44 enclouser with neutral link, earth bar and required accessories, all complete as per the specifications & drawings.
13.2.01 |  |  |  | Distribution Boards | nr | 6
13.2.02 |  |  |  | Internet switch board | nr | 1
MAIN / SUB CABLING
All under ground cables directly buried in ground/ in the trenches as appilcable, to be laid properly and covered with cable tiles, protection tapes, etc for mechanical protection, PVC sleeves may use if required. Rate shall include for all necessary works/accessories such as excavation, sand layers, cable tiles, warning strips and back filling with approved quality earth,properly compacted, to the satisfication of the Engineer.
All above ground cables shall be laid on cable tray/ trucnking /conduits as appilcable and covered by tray covers, etc. for mechanical protection. PVC sleeves may use if required. Rate shall include for all necessary works/ accessories such as galvernized brackets, supporting materials, fittings, nails, cable ties, earthing, etc, trays shall be of required sizes, GI powder coated, and shotted, to the satisfication of Engineer
CABLING UP TO MDB
13.2.03 |  |  |  | Cabling from main Electrical source to DB | item | 1
13.2.03 |  |  |  | Cabling from main Internet source to Internet switchboard | item | 1
13.3.00 | GENERAL EARTHING
13.3.01 |  |  |  | Allow for the total earthing system inclusive of the necessary cables from all the DBs | item | 1
13.4.00 | POINT WIRING AND FITTINGS
Rate shall include for supply & installation of cable, conduits for point wiring in concealed installations including lights,switches, power outlet,data points,isolators, etc, all as specified
13.4.01 |  |  |  | Supply and Installation of 2 x 1C 1.5mm2 PVC/PVC/Cu + 2.5mm2 PVC/Cu earth cable c/w uPVC conduit, junction boxes etc. for lights and switches point wiring | nr | 238
13.4.02 |  |  |  | Supply and Installation of 2 x 1C 2.5mm2 PVC/PVC/Cu + 2.5mm2 PVC/Cu earth cable c/w uPVC conduit, junction boxes,ethernet cables, RJ45 Connectors, VGA cables etc. for the Socket outlets point wiring | nr | 130
13.5.00 | LIGHTS,SWITCHES AND SOCKETS
Rate shall include supply and installation of following lighting fixtures, socket outlets as specified and detailed, fixed in position including all fixing accessories, supports and connect to power, under following conditions
1. All bathrooms, out door light fixtures shall be IP65
2. All switches & sockets shall be ABB or equivalent brand.
LIGHTS AND SWITCHES
13.5.01 |  |  |  | Outdoor wall light 40W (IP65) | nr | 33
13.5.02 |  |  |  | Mirror light (7W LED light) | nr | 7
13.5.03 |  |  |  | Recessed Down light 12W LED | nr | 18
13.5.04 |  |  |  | Ceiling light 18W LED | nr | 4
13.5.05 |  |  |  | 2 x 4' tube light with weather proof opal casing | nr | 5
13.5.06 |  |  |  | 2 x 4' fluorescent light with opal casing | nr | 51
13.5.07 |  |  |  | Ceiling fan (52" - 54") | nr | 24
13.5.08 |  |  |  | Light switch (1 G) | nr | 20
13.5.09 |  |  |  | Light switch (2 G) | nr | 18
13.5.10 |  |  |  | Light switch (3 G) | nr | 1
13.5.11 |  |  |  | Light switch (4 G) | nr | 18
13.5.12 |  |  |  | Light switch (5 G) | nr | 3
13.5.13 |  |  |  | Exhaust fan | nr | 4
13.5.14 |  |  |  | Emergency Lights | nr | 14
13.5.15 |  |  |  | Exit lights | nr | 18
SOCKETS
13.5.16 |  |  | 13 | A twin sockets | nr | 62
13.5.17 |  |  | 13 | A sockets | nr | 26
13.5.18 |  |  |  | Twin computer network outlet | nr | 6
13.5.19 |  |  |  | Data points | nr | 6
13.5.20 |  |  |  | HDMI,VGA & RAC AV Sockets | nr | 6
13.5.21 |  |  |  | HDMI,VGA & RAC AV Twin Sockets | nr | 6
13.5.22 |  |  |  | Speakers with volume controller and paging mic | nr | 12
13.5.23 |  |  |  | Two gang TV/SAT socket outlet | nr | 6
13.6.00 |  |  |  | TOTAL OF BILL №: 13 - Carried Over To Summary
14.0.00 |  |  |  | Bill №: 14 - PLUMBING
14.1.00 | GENERAL
|  |  | (a) | Rates shall include for sockets, running joints, connectors, elbows, junctions, valves, reducers, expansion joints, backnuts and similar, incidental fitting, clips saddles, brackets, straps, hangers, screws, nails and fixing complete, including cutting and forming holes, excavating, laying pipes and backfilling trenches.
|  |  | (b) | All pipe work and fittings shall be high pressure PVC.
|  |  | (c) | Rates shall include for supply and fixing of all pipes.
|  |  | (d) | All sanitary fixtures used shall be of superior quality and approved by the architect/consultant on submission of samples.
14.2.00 | WATER SUPPLY
Provide and fix UPVC high pressure pipes including piping, connections, fittings, valves, excavations, ducting, fixing with brackets and leak testing.
INTERNAL PLUMBING - FRESH WATER SUPPLY PIPE
14.2.01 |  |  |  | Note: Internal plumbing to all toilets and kitchen including supply and laying of pipes. | item | 1
EXTERNAL PLUMBING
14.2.02 |  |  |  | Connection to MWSC/FENAKA water meters. | item | 1
14.2.03 |  |  |  | All pipe works under groundfloor screed/slab to be laid for Waste water, sewage, fresh water and well water connection. | item | 1
14.2.04 |  |  |  | Waste water and sewage connection from all the toilets including the necessary catch pits and manholes as necessary. Rates shall include for supply and laying of pipes including clean-outs as necessary. | item | 1
14.2.05 |  |  |  | Water connection to all toilets. Rate shall include for supply and laying of pipes. | item | 1
14.3.00 | DISCHARGE WORK
14.3.01 |  |  |  | Provide and fix UPVC pipes including vent pipes, vent cowls, cleaning eye, connections, fittings, valves, excavations, ducting, fixing with brackets, connecting to mainsewer line and leak testing. | item | 1
14.4.00 | FIXTURES
Complete installation, cleaning and testing of:
14.4.01 |  |  |  | Wash basin | nr | 11
14.4.02 |  |  |  | Wash basin tap | nr | 11
14.4.03 |  |  |  | Muslim shower with stop valve | nr | 9
14.4.04 |  |  |  | Soap holder | nr | 9
14.4.05 |  |  |  | Floor Drain | nr | 4
14.4.06 |  |  |  | Floor Gully | nr | 9
14.4.07 | 510 | x | 1110 | Face Mirror | nr | 7
14.4.08 |  |  |  | Water Closet | nr | 9
14.4.09 | 1000 | x | 600 | Counter top with tile finish | nr | 1
14.4.10 | 1875 | x | 600 | Counter top with tile finish | nr | 3
14.4.11 |  |  |  | Water booster pump | nr | 1
14.4.12 |  |  |  | Water dispencer | set | 2
DISABLED TOILET
14.4.13 |  |  |  | Wash basin | nr | 1
14.4.14 |  |  |  | Wash basin tap | nr | 1
14.4.15 |  |  |  | Muslim shower with stop valve | nr | 1
14.4.16 |  |  |  | Soap holder | nr | 1
14.4.17 | 510 | x | 1110 | Face Mirror | nr | 1
14.4.18 |  |  |  | Water Closet | nr | 1
14.4.19 |  |  |  | Railings | set | 1
14.5.00 |  |  |  | TOTAL OF BILL №: 14 - Carried Over To Summary
15.0.00 |  |  |  | Bill №: 15 - INSULATION, FIRE STOPPING & FIRE PROTECTION
15.1.00 | GENERAL
|  |  | (a) | Rates shall include for: cabinet,screws, nails, bolts, nuts, standard cable fixing or supporting clips, brackets, straps, rivets, plugs and all incidental accessories
|  |  | (b) | Rates shall include for cable conduits, fittings, equipment and similar items shall include for: all fixings to various building surfaces
|  |  | (c) | Rates shall include for all necessary electrical wiring and accessories required for completion
15.2.00 | FIRE EXTINGUISHERS (Confirming to BS EN 3-10)
15.2.01 |  |  |  | Supply and installation of 2Kg CO2 Extinguishers | nr | 3
15.2.02 |  |  |  | Supply and installation of 9 Lt. water Extinguishers. | nr | 3
15.3.00 |  |  |  | TOTAL OF BILL №: 15 - Carried Over To Summary
16.0.00 |  |  |  | Bill №: 16- ADDITIONS AND OMMISIONS
16.1.00 | ADDITIONS
16.1.01 |  |  |  | Bill №: 01 - PRELIMINARIES
16.1.02 |  |  |  | Bill №: 02 - EXCAVATION AND FILLING
16.1.03 |  |  |  | Bill №: 03 - INSITU CONCRETE WORKS
16.1.04 |  |  |  | Bill №: 04 - MASONRY
16.1.05 |  |  |  | Bill №: 05 - STRUCTURAL METAL WORKS
16.1.06 |  |  |  | Bill №: 06 - ROOFING
16.1.07 |  |  |  | Bill №: 07 - WINDOWS, SCREENS & LIGHTS
16.1.08 |  |  |  | Bill №: 08 - DOORS, SHUTTERS & HATCHES
16.1.09 |  |  |  | Bill №: 09 - FLOOR, WALL, CEILING, AND ROOF FINISHINGS
16.1.10 |  |  |  | Bill №: 10 - SUSPENDED CEILING
16.1.11 |  |  |  | Bill №: 11 - PAINTING & DECORATIONS
16.1.12 |  |  |  | Bill №: 12 - STAIRS, WALKWAYS AND BALUSTRADES
16.1.13 |  |  |  | Bill №: 13 - MECHANICAL & ELECTRICAL SERVICES
16.1.14 |  |  |  | Bill №: 14 - PLUMBING
16.1.15 |  |  |  | Bill №: 15 - INSULATION, FIRE STOPPING & FIRE PROTECTION
TOTAL
16.2.00 | OMISSIONS
16.2.01 |  |  |  | Bill №: 01 - PRELIMINARIES
16.2.02 |  |  |  | Bill №: 02 - EXCAVATION AND FILLING
16.2.03 |  |  |  | Bill №: 03 - INSITU CONCRETE WORKS
16.2.04 |  |  |  | Bill №: 04 - MASONRY
16.2.05 |  |  |  | Bill №: 05 - STRUCTURAL METAL WORKS
16.2.06 |  |  |  | Bill №: 06 - ROOFING
16.2.07 |  |  |  | Bill №: 07 - WINDOWS, SCREENS & LIGHTS
16.2.08 |  |  |  | Bill №: 08 - DOORS, SHUTTERS & HATCHES
16.2.09 |  |  |  | Bill №: 09 - FLOOR, WALL, CEILING, AND ROOF FINISHINGS
16.2.10 |  |  |  | Bill №: 10 - SUSPENDED CEILING
16.2.11 |  |  |  | Bill №: 11 - PAINTING & DECORATIONS
16.2.12 |  |  |  | Bill №: 12 - STAIRS, WALKWAYS AND BALUSTRADES
16.2.13 |  |  |  | Bill №: 13 - MECHANICAL & ELECTRICAL SERVICES
16.2.14 |  |  |  | Bill №: 14 - PLUMBING
16.2.15 |  |  |  | Bill №: 15 - INSULATION, FIRE STOPPING & FIRE PROTECTION
TOTAL
16.3.00 |  |  |  | TOTAL OF BILL №: 16 - Carried Over To Summary