## Summary
K.THULUSDHOO SHORE PROTECTION
SUMMARY OF BILLS
Bill Section | Description | Amount (MVR)
Bill No.01 | Preliminaries | 0
Bill No.02 | Dredging and filling | 0
Bill No.03 | Revetment construction | 0
Bill No.04 | Groyne construction | 0
Bill No.05 | Additions & Omissions | 0
Sub total
GST
TOTAL

## Prelimimaries
BILL NO. 01 - PRELIMINARIES
Item No | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
1.1 | SITE ESTABLISHMENT COST Allow for mobilization & demobilization of contractor's plant, equipment & labour | Item | 1
1.2 | SECURITIES & INSURANCE
1.2.1 | Provision of performance security | Item | 1
1.2.2 | Provision of insurance | Item | 1
1.2.3 | Other security bonds, etc. | Item | 1
1.3 | SITE MANAGEMENT Allow for all on and off site management costs including costs of foreman and assistants, temporary services, telephone, fax, hoardings, fences and similar items. | Days
1.4 | SIGN BOARD Provide sign board as per clients' requirements | Item | 1
1.5 | SAFETY ON SITE Establishing and maintaining safety measures on site | Item | 1
1.6 | ENVIRONMENTAL MONITORING
1.6.1 | Allow for environmental monitoring and submission of reports as per EIA requirements | Item | 1
1.6.2 | Environmental Monitoring | Item | 1
1.7 | SURVEY WORKS
1.7.1 | Provide detailed in-survey prior to commencement of works | Item | 1
1.7.2 | Provide detailed out-survey upon completion | Item | 1
1.8 | AS-BUILT DRAWINGS | Item | 1
TOTAL OF BILL NO. 01

## Dredging & filling
BILL NO. 02 - DREDGING AND FILLING
Item No. | Description | Unit | Qty | Rate (MRF) | Amount (MRF)
2 | DREDGING AND FILLING
| Allow for dredging, transport ang filling as per the lines and levels indicated in the drawings | m³ | 6500
TOTAL OF BILL NO. 02

## Revetment Construction
BILL NO. 03 - REVETMENT CONSTRUCTION
Item No. | Description | Unit | Qty | Rate (MRF) | Amount (MRF)
3 | GENERAL
Revetment construction inclusive of all materials and workmanship as shown in the drawings
3.1 | REVETMENT CONSTRUCTION (TYPE 1)
3.1.1 | Laying of geotextile on prepared slopes. Rate shall include for proper overlaps as per manufacturers instruction, anchors etc complete. | m² | 3078
3.1.2 | Installation of rock filter and armour layer to the slopes and levels indicated in the drawing | m | 342
3.1.3 | Construction of concrete curb and screed; allow for levelling and compaction | m | 0
TOTAL OF BILL NO. 03

## Groyne Construction
BILL NO. 04 - REVETMENT CONSTRUCTION
Item No. | Description | Unit | Qty | Rate (MRF) | Amount (MRF)
4 | GENERAL
Revetment construction inclusive of all materials and workmanship as shown in the drawings
4.1 | CONSTRUCTION OF ROCK BOULDER GROYNE
4.1.1 | Installation of rock filter and armour layer to the slopes and levels indicated in the drawing | m | 80
4.2 | CONSTRUCTION OF ROCK BOULDER BREAKWATERS
4.2.1 | Installation of rock filter and armour layer to the slopes and levels indicated in the drawing | m | 420
TOTAL OF BILL NO. 04

## Additions-Omissions
BILL NO. 05 - ADDITIONS & OMISSIONS
Item No. | Description | Unit | Qty | Rate (MRF) | Amount (MRF)
5 | GENERAL
5.1 | Contractor should satisfy himself as to the accuracy of the quantities given in the Bills of Quantities
5.2 | Any adjustments that he may consider necessary should be written below and on similar continuation sheets if required and the net amount of the adjustments is to be carried to the summary
Additions
1
2
3
4
5
Omissions
1
2
3
4
5
| TOTAL OF BILL NO. 05 |  |  |  | 0