Greater Male’ Environmental Improvement and Waste Management Project

Project No: 51077-002,

Bidding Document – Volume 1

Invitation for Bids No.: CW/03

Procurement of

Construction of Island Waste Management Centers - Retender

Seven Lots

| Lot 2 | K. Maafushi & K. Guraidhoo |
| --- | --- |
| Lot 3 | V. Thinadhoo & V. Felidhoo |
| Lot 4 | V. Keyodhoo & V. Rakeedhoo |
| Lot 5 | AD. Mahibadhoo & AD. Hangnamedhoo |
| Lot 6 | AA. Himandhoo & AA. Feridhoo |
| Lot 7 | AA. Thoddoo |
| Lot 8 | K. Kaashidhoo |

Issued on: 08th May 2023

Issued By: National Tender, Ministry of Finance

Preface

This Bidding Document for the Procurement of Works has been prepared by the Ministry of Environment of the Government of the Maldives and is based on the Standard Bidding Document for the Procurement of Works–Small Contracts (SBD Works-Small) issued by the Asian Development Bank dated December 2016

ADB’s SBD Works-Small has the structure and the provisions of the Master Procurement Document entitled “Bidding Documents for the Procurement of Works–Small Contracts”, prepared by multilateral development banks and other public international financial institutions except where ADB-specific considerations have required a change.

Table of Contents

PART 1	BIDDING PROCEDURES

Part 1

Sections 1, 2, 3, 4, & 5

Bidding Procedures

Section 1 – Instruction to Bidders 	                                                                    1-1

Section 2 - Bid Data Sheet 	                                                                    2-1

Section 3 - Evaluation and Qualification Criteria	                                              3-1

Section 4- Bidding Forms	                                                                               4-1

Section 5 - Eligible Countries	                                                                    5-1

PART 2	REQUIREMENTS

Part 2

Section 6

Employer’s Requirements

- Specifications

- Drawings

- Supplementary Information Regarding Works to Be Procured

- Personnel Requirements

- Equipment Requirements

1. Specifications 	                                                        6-1

PART 3	CONDITIONS OF CONTRACT AND CONTRACT FORMS

Part 3

Section 7, 8 and 9

Contract Data

Section 7 - General Conditions of Contract	                                             7-1

Section 8 - Particular Conditions of Contract	                                              8-1

Section 9 - Contract Forms	                                                                              9-1

Part 1

Sections 1, 2, 3, 4, & 5

Bidding Procedures

Section 1 – Instruction to Bidders

Section 1 Instructions to Bidders

| - General |  |  |
| --- | --- | --- |
| - Scope of Bid | 1.1 | In connection with the Invitation for Bids (IFB) indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this Bidding Document for the procurement of the Works as specified in Section 6 (Employer’s Requirements). The name, identification, and number of contracts of this bidding are provided in the BDS. |  |
|  | 1.2 | Throughout this Bidding Document, - the term “in writing” means communicated in written form and delivered against receipt; - except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and - “day” means calendar day. |  |
| - Source of Funds | 2.1 | The Borrower or Recipient (hereinafter called “Borrower”) indicated in the BDS has applied for or received financing (hereinafter called “funds”) from the Asian Development Bank (hereinafter called “ADB”) toward the cost of the project named in the BDS. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this Bidding Document is issued. |  |
|  | 2.2 | Payments by ADB will be made only at the request of the Borrower and upon approval by ADB in accordance with the terms and conditions of the Financing Agreement between the Borrower and ADB (hereinafter called “Financing Agreement”), and will be subject in all respects to the terms and conditions of that Financing Agreement. No party other than the Borrower shall derive any rights from the Financing Agreement or have any claim to the funds. |  |
| - Fraud and Corruption | 3.1 | ADB’s Anticorruption Policy requires Borrowers (including beneficiaries of ADB-financed activity), as well as Bidders, Suppliers, and Contractors under ADB-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, ADB - defines, for the purposes of this provision, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; - “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation. - “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; - “collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party; - “obstructive practice” means (a) deliberately destroying, falsifying, altering, or concealing of evidence material to an ADB investigation; (b) making false statements to investigators in order to materially impede an ADB investigation; (c) failing to comply with requests to provide information, documents, or records in connection with an Office of Anticorruption and Integrity (OAI) investigation; (d) threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or (e) materially impeding ADBʼs contractual rights of audit or access to information; and - “integrity violation" is any act which violates ADB’s Anticorruption Policy, including (i) to (v) above and the following: abuse, conflict of interest, violations of ADB sanctions, retaliation against whistleblowers or witnesses, and other violations of ADB's Anticorruption Policy, including failure to adhere to the highest ethical standard. - will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations in competing for the Contract; - will cancel the portion of the financing allocated to a contract if it determines at any time that representatives of the Borrower or of a beneficiary of ADB financing engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations during the procurement or the execution of that contract, without the Borrower having taken timely and appropriate action satisfactory to ADB to remedy the situation; - will impose remedial actions on a firm or an individual, at any time, in accordance with ADB’s Anticorruption Policy and Integrity Principles and Guidelines (both as amended from time to time), including declaring ineligible, either indefinitely or for a stated period of time, to participate in ADB-financed, -administered, or -supported activities or to benefit from an ADB-financed, -administered, or -supported contract, financially or otherwise, if it at any time determines that the firm or individual has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations; and |  |
|  |  | - will have the right to require that a provision be included in bidding documents and in contracts financed by ADB, requiring Bidders, suppliers, and contractors to permit ADB or its representative to inspect their accounts and records and other documents relating to the bid submission and contract performance and to have them audited by auditors appointed by ADB. |
|  | 3.2 | Furthermore, Bidders shall be aware of the provisions of GCC 28.3 and 73.2 (i). |
| - Eligible Bidders | 4.1 | A Bidder may be a natural person, private entity, or government-owned enterprises subject to ITB 4.5 - or any combination of them with a formal intent to enter into an agreement or under an existing agreement in the form of a Joint Venture. In the case of a Joint Venture: - all partners shall be jointly and severally liable; and - the Joint Venture shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the Joint Venture during the bidding process and, in the event the Joint Venture is awarded the Contract, during contract execution. |
|  | 4.2 | A Bidder, and all parties constituting the Bidder, shall have the nationality of an eligible country, in accordance with Section 5 (Eligible Countries). A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract including related services. |
|  | 4.3 | A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to be in a conflict of interest with one or more parties in this bidding process if any of, including but not limited to, the following apply: - they have controlling partners in common; or - they receive or have received any direct or indirect subsidy from any of them; or - they have the same legal representative for purposes of this bid; or - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to material information about or improperly influence the Bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or - a Bidder participates in more than one bid in this bidding process, either individually or as a partner in a joint venture, except for alternative offers permitted under ITB 13 of the Bidding Document. This will result in the disqualification of all Bids in which it is involved. However, subject to any finding of a conflict of interest in terms of ITB 4.3 (a)–(d) above, this does not limit the participation of a Bidder as a Subcontractor in another Bid or of a firm as a Subcontractor in more than one Bid; or - Bidder or any affiliated entity, participated as a Consultant in the preparation of the design or technical specifications of the works that are the subject of the Bid; or - a Bidder was affiliated with a firm or entity that has been hired (or is proposed to be hired) by the Employer or Borrower as Engineer for the Contract. |
|  | 4.4 | A firm shall not be eligible to participate in any procurement activities under an ADB-financed, -administered, or -supported project while under temporary suspension or debarment by ADB pursuant to its Anticorruption Policy (see ITB 3), whether such debarment was directly imposed by ADB, or enforced by ADB pursuant to the Agreement for Mutual Enforcement of Debarment Decisions. A bid from a temporary suspended or debarred firm will be rejected. |
|  | 4.5 | Government-owned enterprises in the Borrower’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) are not a dependent agency of the Borrower. |
|  | 4.6 | Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. |
|  | 4.7 | Firms shall be excluded if by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s country prohibits any import of goods or contracting of works or services from that country or any payments to persons or entities in that country. |
|  | 4.8 | In case a prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. |
| - Eligible Materials, Equipment, and Services | 5.1 | The materials, equipment, and services to be supplied under the Contract shall have their origin in eligible source countries as defined in ITB 4.2 above and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment, and services. |
|  | 5.2 | For purposes of ITB 5.1 above, “origin” means the place where the materials and equipment are mined, grown, produced, or manufactured, and from which the services are provided. Materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that differs substantially in its basic characteristics or in purpose or utility from its components. |
| - Contents of Bidding Document |  |  |
| - Sections of Bidding Document | 6.1 | The Bidding Document consist of Parts I, II, and III, which include all the sections indicated below, and should be read in conjunction with any addenda issued in accordance with ITB 8. PART I Bidding Procedures Section 1 - Instructions to Bidders (ITB) Section 2 - Bid Data Sheet (BDS) Section 3 - Evaluation and Qualification Criteria (EQC) Section 4 - Bidding Forms (BDF) Section 5 - Eligible Countries (ELC) PART II Requirements Section 6 – Employer’s Requirements (ERQ) PART III Conditions of Contract and Contract Forms Section 7 - General Conditions of Contract (GCC) Section 8 - Particular Conditions of Contract (PCC) Section 9 - Contract Forms (COF) |
|  | 6.2 | The IFB issued by the Employer is not part of the Bidding Document. |
|  | 6.3 | The Employer is not responsible for the completeness of the Bidding Document and their addenda, if they were not obtained directly from the source stated by the Employer in the IFB. |
|  | 6.4 | The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the bid. |
| - Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | 7.1 | A prospective Bidder requiring any clarification on the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise his inquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer will respond in writing to any request for clarification, provided that such request is received prior to the deadline for submission of bids, within a period given in the BDS. The Employer shall forward copies of its response to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 22.2. |
|  | 7.2 | The Bidder is advised to visit and examine the Site of Works and its surroundings and obtain for itself, on its own risk and responsibility, all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense. |
|  | 7.3 | The Bidder and any of its personnel or agents will be granted permission by the Employer to enter its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | 7.4 | The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | 7.5 | The Bidder is requested to submit any questions in writing, to reach the Employer not later than 1 week before the meeting. |
|  | 7.6 | Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. |
|  | 7.7 | Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| - Amendment of Bidding Document | 8.1 | At any time prior to the deadline for submission of Bids, the Employer may amend the Bidding Document by issuing addenda. |
|  | 8.2 | Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. |
|  | 8.3 | To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Employer may, at its discretion, extend the deadline for the submission of Bids, pursuant to ITB 22.2. |
| - Preparation of Bids |  |  |
| - Cost of Bidding | 9.1 | The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| - Language of Bid | 10.1 | The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| - Documents Comprising the Bid | 11.1 11.2 | The Bid shall comprise the following: - Letter of Bid; - completed Schedules, in accordance with ITB 12 and ITB 14, or as stipulated in the BDS; - Bid Security or Bid-Securing Declaration, in accordance with ITB 19; - alternative Bids, at Bidder’s option and if permissible, in accordance with ITB 13; - written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 20.2; - documentary evidence in accordance with ITB 17, establishing the Bidder’s qualifications to perform the contract; - Technical Proposal in accordance with ITB 16; - Any other document required in the BDS. In addition to the requirements under ITB 11.1, Bids submitted by a Joint Venture shall include a copy of the Joint Venture Agreement entered into by all partners. Alternatively, a Letter of Intent to execute a Joint Venture Agreement in the event of a successful Bid shall be signed by all partners and submitted with the Bid, together with a copy of the proposed agreement. |
| - Letter of Bid and Schedules | 12.1 | The Letter of Bid, Schedules, and all documents listed under Clause 11, shall be prepared using the relevant forms in Section 4 (Bidding Forms), if so provided. The forms must be completed without any alterations to the text, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested and as required in the BDS. |
| - Alternative Bids | 13.1 | Unless otherwise indicated in the BDS, alternative Bids shall not be considered. |
|  | 13.2 | When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different times for completion. |
|  | 13.3 | When specified in the BDS pursuant to ITB 13.1, and subject to ITB 13.4 below, Bidders wishing to offer technical alternatives to the requirements of the Bidding Document must first price the Employer’s design as described in the Bidding Document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. |
|  | 13.4 | When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the Works. Such parts will be identified in the BDS and described in Section 6 (Employer’s Requirements). The method for their evaluation will be stipulated in Section 3 (Evaluation and Qualification Criteria). |
| - Bid Prices and Discounts | 14.1 | The prices and discounts quoted by the Bidder in the Letter of Bid and in the Schedules shall conform to the requirements specified below. |
|  | 14.2 | The Bidder shall submit a bid for the whole of the works described in ITB 1.1 by filling in prices for all items of the Works, as identified in Section 4 (Bidding Forms). In case of admeasurement contracts, the Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities. Items against which no rate or price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bill of Quantities. |
|  | 14.3 | The price to be quoted in the Letter of Bid shall be the total price of the Bid, excluding any discounts offered. Absence of the total bid price in the Letter of Bid may result in the rejection of the Bid. |
|  | 14.4 | The Bidder shall quote any discounts and the methodology for their application in the Letter of Bid, in accordance with ITB 12.1. |
|  | 14.5 | Unless otherwise provided in the BDS and the Conditions of Contract, the prices quoted by the Bidder shall be fixed. If the prices quoted by the Bidder are subject to adjustment during the performance of the Contract in accordance with the provisions of the Conditions of Contract, the Bidder shall furnish the indexes and weightings for the price adjustment formulas in the Table(s) of Adjustment Data in Section 4 (Bidding Forms) and the Employer may require the Bidder to justify its proposed indexes and weightings. |
|  | 14.6 | If so indicated in ITB 1.1, bids are invited for individual contracts or for any combination of contracts (packages). Bidders wishing to offer any price reduction for the award of more than one Contract shall specify in their bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package. Price reductions or discounts shall be submitted in accordance with ITB 14.4, provided the Bids for all contracts are submitted and opened at the same time. |
|  | 14.7 | All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of bids, shall be included in the rates and prices and the total bid price submitted by the Bidder. |
| - Currencies of Bid and Payment | 15.1 | The currency(ies) of the Bid and payment shall be as specified in the BDS. |
|  | 15.2 | Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the prices shown in the appropriate form(s) of Section 4, in which case a detailed breakdown of the foreign currency requirements shall be provided by Bidders. |
| - Documents Comprising the Technical Proposal | 16.1 | The Bidder shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule, and any other information as stipulated in Section 4 (Bidding Forms), in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. |
| - Documents Establishing the Qualifications of the Bidder | 17.1 | To establish its qualifications to perform the Contract in accordance with Section 3 (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding information sheets included in Section 4 (Bidding Forms). |
|  | 17.2 | Domestic Bidders, individually or in joint ventures, applying for eligibility for domestic preference shall supply all information required to satisfy the criteria for eligibility as described in ITB 33. |
| - Period of Validity of Bids | 18.1 | Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as nonresponsive. |
|  | 18.2 | In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 19, it shall also be extended 28 days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its Bid. |
| - Bid Security/Bid-Securing Declaration | 19.1 | Unless otherwise specified in the BDS, the Bidder shall furnish as part of its Bid, in original form, either a Bid-Securing Declaration or a bid security as specified in the BDS. In the case of a bid security, the amount and currency shall be as specified in the BDS. |
|  | 19.2 | If a Bid-Securing Declaration is required pursuant to ITB 19.1, it shall use the form included in Section 4 (Bidding Forms). The Employer will declare a Bidder ineligible to be awarded a Contract for a specified period of time, as indicated in the BDS, if the Bid-Securing Declaration is executed |
|  | 19.3 | If a bid security is specified pursuant to ITB 19.1, the bid security shall be, at the Bidder’s option, in any of the following forms: - an unconditional bank guarantee, - an irrevocable letter of credit, or - a cashier’s or certified check, all from a reputable source from an eligible country as described in Section 5 (Eligible Countries). In the case of a bank guarantee, the bid security shall be submitted either using the Bid Security Form included in Section 4 (Bidding Forms) or another form acceptable to the Employer. The form must include the complete name of the Bidder. The bid security shall be valid for 28 days beyond the original validity period of the bid, or beyond any period of extension if requested under ITB 18.2. |
|  | 19.4 | Unless otherwise specified in the BDS, any Bid not accompanied by a substantially compliant bid security or Bid-Securing Declaration, if one is required in accordance with ITB 19.1, shall be rejected by the Employer as nonresponsive. |
|  | 19.5 | If a bid security is specified pursuant to ITB 19.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the performance security pursuant to ITB 41. |
|  | 19.6 | If a bid security is specified pursuant to ITB 19.1, the bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | 19.7 | The bid security may be forfeited or the Bid-Securing Declaration executed, - if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid, except as provided in ITB 18.2; or - if the successful Bidder fails to - sign the Contract in accordance with ITB 40; - furnish a performance security in accordance with ITB 41; - accept arithmetical corrections in accordance with ITB 31; or - furnish a domestic preference security, if applicable, in accordance with ITB 41. |
|  | 19.8 | The bid security or the Bid-Securing Declaration of a Joint Venture shall be in the name of the Joint Venture that submits the Bid. If the Joint Venture has not been legally constituted at the time of bidding, the bid security or the Bid-Securing Declaration shall be in the names of all future partners as named in the letter of intent mentioned in ITB 4.1. |
| - Format and Signing of Bid | 20.1 | The Bidder shall prepare one original set of the documents comprising the Bid as described in ITB 11 and clearly mark it “ORIGINAL.” Alternative Bids, if permitted in accordance with ITB 13, shall be clearly marked “ALTERNATIVE.” In addition, the Bidder shall submit copies of the Bid in the number specified in the BDS, and clearly mark each of them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
|  | 20.2 | The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid, except for unamended printed literature, shall be signed or initialed by the person signing the bid. If a Bidder submits a deficient authorization, the Bid shall not be rejected in the first instance. The Employer shall request the Bidder to submit an acceptable authorization within the number of days as specified in the BDS. Failure to provide an acceptable authorization within the prescribed period of receiving such a request shall cause the rejection of the Bid. |
|  | 20.3 | Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. |
| - Submission and Opening of Bids |  |  |
| - Sealing and Marking of Bids | 21.1 | Bidders may always submit their Bids by mail or by hand. When so specified in the BDS, Bidders shall have the option of submitting their Bids electronically. Procedures for submission, sealing, and marking are as follows: - Bidders submitting Bids by mail or by hand shall enclose the original and each copy of the Bid, including alternative Bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “ORIGINAL,” “ALTERNATIVE,” and “COPY.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. The rest of the procedure shall be in accordance with ITB 21.2 and ITB 21.3. - Bidders submitting Bids electronically shall follow the electronic bid submission procedures specified in the BDS. |
|  | 21.2 | The inner and outer envelopes shall - bear the name and address of the Bidder; - be addressed to the Employer as provided in BDS 22.1; - bear the specific identification of this bidding process indicated in BDS 1.1; and - bear a warning not to open before the time and date for bid opening. |
|  | 21.3 | If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the Bid. |
| - Deadline for Submission of Bids | 22.1 | Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. |
|  | 22.2 | The Employer may, at its discretion, extend the deadline for the submission of Bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| - Late Bids | 23.1 | The Employer shall not consider any Bid that arrives after the deadline for submission of bids, in accordance with ITB 22. Any Bid received by the Employer after the deadline for submission of Bids shall be declared late, rejected, and returned unopened to the Bidder. |
| - Withdrawal, Substitution, and Modification of Bids | 24.1 | A Bidder may withdraw, substitute, or modify its Bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 20.2, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the Bid must accompany the respective written notice. All notices must be - prepared and submitted in accordance with ITB 20 and ITB 21 (except that withdrawal notices do not require copies), and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL,” “SUBSTITUTION,” “MODIFICATION;” and - received by the Employer prior to the deadline prescribed for submission of Bids, in accordance with ITB 22. |
|  | 24.2 | Bids requested to be withdrawn in accordance with ITB 24.1 shall be returned unopened to the Bidders. |
|  | 24.3 | No Bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of Bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |
| - Bid Opening | 25.1 | The Employer shall open the Bids in public at the address, on the date, and time specified in the BDS in the presence of Bidders` designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 21.1, shall be as specified in the BDS. |
|  | 25.2 | First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding Bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “SUBSTITUTION” shall be opened and read out and exchanged with the corresponding Bid being substituted, and the substituted Bid shall not be opened, but returned to the Bidder. No bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at bid opening. Envelopes marked “MODIFICATION” shall be opened and read out with the corresponding Bid. No bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at bid opening. Only envelopes that are opened and read out at bid opening shall be considered further. |
|  | 25.3 | All other envelopes shall be opened one at a time, reading out the name of the Bidder; the Bid Price(s), including any discounts and alternative bids and indicating whether there is a modification; the presence of a bid security or Bid-Securing Declaration, if required; and any other details as the Employer may consider appropriate. Only discounts and alternative offers read out at bid opening shall be considered for evaluation. Unless otherwise specified in the BDS, all pages of the Letter of Bid and Schedules are to be initialed by at least three representatives of the Employer attending the bid opening. No Bid shall be rejected at bid opening except for late Bids, in accordance with ITB 23.1. |
|  | 25.4 | The Employer shall prepare a record of the bid opening that shall include, as a minimum, the name of the Bidder and whether there is a withdrawal, substitution, or modification; the Bid Price, per contract if applicable, including any discounts and alternative offers; and the presence or absence of a bid security or a Bid-Securing Declaration, if one was required. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders who submitted Bids on time, and posted online when electronic bidding is permitted. |
| - Evaluation and Comparison of Bids |  |  |
| - Confidentiality | 26.1 | Information relating to the examination, evaluation, comparison, and post qualification of Bids and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders. |
|  | 26.2 | Any attempt by a Bidder to influence the Employer in the evaluation of the Bids or Contract award decisions may result in the rejection of its Bid. |
|  | 26.3 | Notwithstanding ITB 26.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it may do so in writing. |
| - Clarification of Bids | 27.1 | To assist in the examination, evaluation, and comparison of the bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the prices or substance of the Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Bids, in accordance with ITB 31. |
|  | 27.2 | If a Bidder does not provide clarifications of its Bid by the date and time set in the Employer’s request for clarification, its Bid may be rejected. |
| - Deviations, Reservations, and Omissions | 28.1 | During the evaluation of Bids, the following definitions apply: - “Deviation” is a departure from the requirements specified in the Bidding Document; - “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and - “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| - Determination of Responsiveness | 29.1 | The Employer’s determination of a Bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11. |
|  | 29.2 | A substantially responsive Bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - if accepted, would: - affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or - limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. |
|  | 29.3 | The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 16, Technical Proposal, in particular, to confirm that all requirements of Section 6 (Employer’s Requirements) have been met without any material deviation, reservation, or omission. |
|  | 29.4 | If a Bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| - Nonmaterial Nonconformities | 30.1 | Provided that a Bid is substantially responsive, the Employer may waive any nonconformities in the Bid that do not constitute a material deviation, reservation, or omission. |
|  | 30.2 | Provided that a Bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. |
|  | 30.3 | Provided that a Bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. The adjustment shall be made using the methods indicated in Section 3 (Evaluation and Qualification Criteria). |
| - Correction of Arithmetical Errors | 31.1 | Provided that the Bid is substantially responsive, the Employer shall correct arithmetical errors on the following basis: - Only for unit price contracts, if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected. - If there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected. - If there is a discrepancy between the bid price in the Summary of Bill of Quantities and the bid amount in item (c) of the Letter of Bid, the bid price in the Summary of Bill of Quantities will prevail and the bid amount in item (c) of the Letter of Bid will be corrected. - If there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a), (b) and (c) above. |
|  | 31.2 | If the Bidder that submitted the lowest evaluated bid does not accept the correction of errors, its bid shall be disqualified and its bid security may be forfeited or its Bid-Securing Declaration executed. |
| - Conversion to Single Currency | 32.1 | For evaluation and comparison purposes, the currency(ies) of the Bid shall be converted into a single currency as specified in the BDS. |
| - Margin of Preference | 33.1 | Unless otherwise specified in the BDS, a margin of preference shall not apply. |
| - Evaluation of Bids | 34.1 | The Employer shall use the criteria and methodologies listed in this Clause. No other evaluation criteria or methodologies shall be permitted. |
|  | 34.2 | To evaluate a Bid, the Employer shall consider the following: - the bid price, excluding Provisional Sums and the provision, if any, for contingencies in the Summary Bill of Quantities for admeasurement contracts, or Schedule of Prices for lump sum contracts, but including Daywork items, where priced competitively. - price adjustment for correction of arithmetic errors in accordance with ITB 31.1; - price adjustment due to discounts offered in accordance with ITB 14.4; - converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 32; - adjustment for nonconformities in accordance with ITB 30.3; and - application of all the evaluation factors indicated in Section 3 (Evaluation and Qualification Criteria). |
|  | 34.3 | The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. |
|  | 34.4 | If this Bidding Document allows Bidders to quote separate prices for different contracts, and to award multiple contracts to a single Bidder, the methodology to determine the lowest evaluated price of the contract combinations, including any discounts offered in the Letter of Bid, is specified in Section 3 (Evaluation and Qualification Criteria). |
|  | 34.5 | If the Bid for an admeasurement contract, which results in the lowest Evaluated Bid Price, is seriously unbalanced, front loaded or substantially below updated estimates in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, taking into consideration the schedule of estimated Contract payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. |
| - Comparison of Bids | 35.1 | The Employer shall compare all substantially responsive Bids to determine the lowest evaluated Bid, in accordance with ITB 34.2. |
| - Qualification of the Bidder | 36.1 | The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive Bid meets the qualifying criteria specified in Section 3 (Evaluation and Qualification Criteria). |
|  | 36.2 | The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 17.1. |
|  | 36.3 | An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the Bid, in which event the Employer shall proceed to the next lowest evaluated bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. |
| - Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | 37.1 | The Employer reserves the right to accept or reject any Bid, and to annul the bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all Bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
| F. Award of Contract |  |  |
| - Award Criteria | 38.1 | The Employer shall award the Contract to the Bidder whose offer has been determined to be the lowest evaluated Bid and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be qualified to perform the Contract satisfactorily. |
| - Notification of Award | 39.1 | Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, that its Bid has been accepted. |
|  | 39.2 | At the same time, the Employer shall also notify all other Bidders of the results of the bidding. The Employer will publish in an English language newspaper or well-known freely accessible website the results identifying the bid and lot numbers and the following information: (i) name of each Bidder who submitted a Bid; (ii) bid prices as read out at bid opening; (iii) name and evaluated prices of each Bid that was evaluated; (iv) name of bidders whose bids were rejected and the reasons for their rejection; and (v) name of the winning Bidder, and the price it offered, as well as the duration and summary scope of the contract awarded. After publication of the award, unsuccessful Bidders may request in writing to the Employer for a debriefing seeking explanations on the grounds on which their Bids were not selected. The Employer shall promptly respond in writing to any unsuccessful Bidder who, after publication of contract award, requests a debriefing. |
|  | 39.3 | Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. |
| - Signing of Contract | 40.1 | Promptly after notification, the Employer shall send the successful Bidder the Contract Agreement. |
|  | 40.2 | Within 28 days of receipt of the Contract Agreement, the successful Bidder shall sign, date, and return it to the Employer. |
| - Performance Security | 41.1 | Within 28 days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the performance security in accordance with the Conditions of Contract, subject to ITB 34.5, using for that purpose the Performance Security Form included in Section 9 (Contract Forms), or another form acceptable to the Employer. |
|  | 41.2 | Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security or execution of the Bid-Securing Declaration. In that event, the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |
|  | 41.3 | The above provision shall also apply to the furnishing of a domestic preference security, if so required. |

Section 2 - Bid Data Sheet

This section consists of provisions that are specific to each procurement and supplement the information or requirements included in Section 1 – Instructions to Bidders.

| A. GENERAL |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids (IFB) is: (IUL)13-K/13/2023/171 |
| ITB 1.1 | The Employer is: Ministry of Environment, Climate Change and Technology, Republic of the Maldives |
| ITB 1.1 | The name of the bidding process is: National Competitive Bidding (NCB) Construction of Island Waste Management Centers - Retender Lot 2: K. Maafushi & K. Guraidhoo Lot 3: V. Thinadhoo & V. Felidhoo Lot 4: V. Keyodhoo & V. Rakeedhoo Lot 5: AD. Mahibadhoo & AD. Hangnameedhoo Lot 6: AA. Himandhoo & AA. Feridhoo Lot 7: AA. Thoddoo Lot 8: K. Kaashidhoo The identification number of the bidding process is: TES/2022/W-058-R01 The number and identification of lots comprising this bidding process is: 07 lots Bidders have the option of participating in any Lot or combination of 2 Lots |
| ITB 2.1 | The Borrower is: Republic of Maldives |
| ITB 2.1 | The name of the Project is: Greater Male Environmental Improvement & Waste Management Project https://www.adb.org/projects/51077-002/main |

| B. Contents of Bidding Documents |  |
| --- | --- |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: Clarifications are to be in writing only. No phone calls will be accepted Attention:; Ms. Fathimath Rishfa Ahmed. Chief Procurement Executive. Address:; National Tender. Ministry of Finance, Ameenee Magu. City:; Male’. ZIP Code:; 20379. Country:; Maldives Email:; mohamed.mafaaz@finance.gov.mv. Cc to:; tender@finance.gov.mv.. Requests for clarification should be received by the Employer no later than: 07 days before deadline of submission |
| ITB 7.4 | A pre-bid meeting will be held online, details of which will be provided to all registered Bidders as well as Bidders who submit by email their interest to attend the meeting before 1400 hours on 18th May 2023. A site visit conducted by the Employer will not be organized. Bidders may visit to the site at their own cost. |

| C. Preparation of Bids |  |  |
| --- | --- | --- |
| ITB 10.1 |  | The language of the Bid is: English |
| ITB 11.1 (b) |  | In accordance with ITB 12 and ITB 14, the following schedules shall be submitted with the bid, including the priced Bill of Quantities for admeasurement contracts, key personnel and subcontractors, and data on financial resources for meeting the required financial resources requirement that must be submitted with the Bid together with the price schedules. |
| ITB 11.1 (h) |  | The Bidder shall submit with its Bid the following additional documents: 1. Tax Registration Certificate International foreign companies who are already engaged in any work in Maldives, or have re-registered their entity in the Maldives, or have incorporated a company in Maldives shall be eligible to pay local taxes under tax regulations of the Maldives. For more information please visit: https://www.mira.gov.mv/ Winning bidder shall be eligible to pay local taxes under tax regulations of the Maldives. 2. Business Incorporation / Registration Certificate. Registration is not required for International bidders at this stage. However, international bidders shall be responsible to ensure that they confirm with required registration under Foreign Investment Registration and Foreign Direct Investment Policy requirements of Maldives prior to bid submission. For more information please visit: http://www.trade.gov.mv/ 3. Bid Security as prescribed in the bidding document 4. Power of Attorney or Authorization to sign. 5. National Contractors Registry Certificate. All contractors should adhere to National Contractors Registry and all relevant guidelines and shall sought any permits, if required, applicable at the time of submission of the tender. Registration is not required for International bidders at this stage; however, international bidders shall submit the documents as per clause 13 of ‘Construction Industry Contractor’s Regulation’ at the time of submission. For more information please visit: http://www.planning.gov.mv/ The Employer may request submission of additional documents after the bid opening. |
| ITB 12.1 |  | The units and rates in figures entered the Bill of Quantities and Daywork Schedule should be typewritten or if written by hand, must be in print form. Bill of Quantities and Daywork Schedule not presented accordingly may be considered nonresponsive. |
| ITB 13.1 |  | Alternative bids shall not be permitted. |
| ITB 13.2 |  | Alternative times for completion shall not be permitted. |
| ITB 13.4 |  | Not Applicable |
| ITB 14.5 |  | The prices quoted by the Bidder shall be fixed. |
| ITB 15.1 |  | The prices shall be quoted by the bidder and shall be paid in: Maldivian Rufiyaa |
| ITB 16.1 | Technical Proposal shall also include a Health and Safety COVID-19 Plan (HS-C19 Plan), in accordance with the relevant government regulations and guidelines on COVID-19 prevention and control, or in the absence thereof, to international good practice guidelines, such as World Health Organization. 2020. Considerations for public health and social measures in the workplace in the context of COVID-19. Geneva. Available here: https://www.who.int/publications-detail/considerations-for-public-health-and-social-measures-in-the-workplace-in-the-context-of-covid-19 The bidder may also refer to the COVID-19 health and safety guidance given in the IEE report attached to this bidding document. If a Bidder submits a HS-C19 Plan that does not provide sufficient information in accordance to the required submission information listed in the bidding document by the Employer, the Employer shall issue a clarification to request for further information from the Bidder. The Bidder must submit the requested information within 5 working days of receiving such a request. Furthermore, non-submission of HS-C19 plan is not grounds for disqualification but the bidder if awarded would need to submit the document and get approval from the employer before contract award. |
| ITB 18.1 |  | The bid validity period shall be 120 days. |
| ITB 19.1 |  | The bidder shall furnish a Bid security as follows: Lot 2: K. Maafushi & K. Guraidhoo - MVR 50,000.00 Lot 3: V. Thinadhoo & V. Felidhoo - MVR 40,000.00 Lot 4: V. Keyodhoo & V. Rakeedhoo – MVR 40,000.00 Lot 5: AD. Mahibadhoo & AD. Hangnameedhoo - MVR 60,000.00 Lot 6: AA. Himandhoo & AA. Feridhoo - MVR 55,000.00 Lot 7: AA. Thoddoo - MVR 30,000.00 Lot 8: K. Kaashidhoo - MVR 30,000.00 The validity of the bid security shall be: 28 Days beyond the validity of the Bid. Bid Security shall be submitted separately for each Lot. Please Note! that a SWIFT message in the form of MT760 will not be accepted as bid security. |
| ITB 19.2 |  | Not Applicable |
| ITB 19.4 |  | Subject to the succeeding sentences, any bid not accompanied by an irrevocable and callable bid security shall be rejected by the Employer as nonresponsive. If a Bidder submits a bid security that (i) deviates in form, amount, and/or period of validity, or (ii) does not provide sufficient identification of the Bidder (including, without limitation, failure to indicate the name of the Joint Venture or, where the Joint Venture has not yet been constituted, the names of all future Joint Venture Partners), the Employer shall request the Bidder to submit a compliant bid security within 14 days of receiving such a request. Failure to provide a compliant bid security within the prescribed period of receiving such a request shall cause the rejection of the Bid. |
| ITB 20.1 |  | In addition to the Original Tender, the number of copies required is: 1 Authentic Hard Copy (stamped), 1 Authentic Soft copy (stamped & scanned) |
| ITB 20.2 |  | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: An organizational document, board resolution or its equivalent, or power of attorney specifying the representative’s authority to sign the Bid on behalf of, and to legally bind, the Bidder. If the Bidder is an intended or an existing joint venture, the power of attorney should be signed by all partners and specify the authority of the named representative of the Joint Venture to sign on behalf of, and legally bind, the intended or existing Joint Venture. If the Joint Venture has not yet been formed, also include evidence from all proposed Joint Venture partners of their intent to enter into a Joint Venture in the event of a contract award in accordance with ITB 11.2. |
| ITB 20.2 |  | The Bidder shall submit an acceptable authorization within 14 days. |

| Submission and Opening of Bids |  |
| --- | --- |
| ITB 21.1 | Bidders shall not have the option of submitting their Bids electronically. |
| ITB 21.1 (b) | If bidders shall have the option of submitting their Bids electronically, the electronic bidding submission procedures shall be: Not Acceptable |
| ITB 22.1 | For Tender submission purposes only, the Employer’s address is: Attention: Ms. Fathimath Rishfa Ahmed, Chief Procurement Executive Address: National Tender, Ministry of Finance Ameenee Magu, City: Male’ZIP Code: 20379 Country: Republic of Maldives The deadline for Tender submission is: Date: 08th JUNE 2023 Time: 1100 Hours Maldivian Time |
| ITB 25.1 | The bid opening shall take place at: Address: National Tender, Ministry of Finance Ameenee Magu, City: Male’ ZIP Code: 20379 Country: Republic of Maldives Date: Same as ITB 22.1 Time: Immediately after the deadline for Tender Submission |
| ITB 25.1 | If electronic bid submission is permitted in accordance with ITB 21.1, the specific bid opening procedures shall be: Not Applicable |
| ITB 25.3 | The Letter of Bid and Schedules shall be initialed by 02 two representatives of the Employer attending the Bid opening. |

| Evaluation and Comparison of Bids |  |
| --- | --- |
| ITB 32.1 | Not applicable. |
| ITB 33.1 | A margin of preference shall not apply. |

| F. Award of Contract |  |
| --- | --- |
| ITB 39.2 | The procedures for Bidding-Related Complaints. The Bidder should submit its complaint following these procedures, in writing, to: For the attention: Ms. Fathimath Rishfa Title/position: Chief Procurement Executive Employer: Ministry of Finance, Republic of Maldives E-mail address: mohamed.mafaaz@finance.gov.mv Cc to: tender@finance.gov.mv |  |

Section 3 - Evaluation and Qualification Criteria

This section contains all the criteria that the Employer shall use to evaluate Bids and qualify Bidders if the Bidding was not preceded by a prequalification exercise and post qualification is applied. In accordance with ITB 34 and ITB 36, no other methods, criteria and factors shall be used. The Bidder shall provide all the information requested in the forms included in Section 4 (Bidding Forms).

## Table of Criteria

# 1.	Evaluation	3-3

# 1.1 Adequacy of Technical Proposal	3-3

# 1.2 Completion Time	3-3

# 1.3 Technical Alternatives	3-4

# 1.4 Quantifiable Nonconformities and Omissions	3-4

# 1.5 personnel …………………………………………………………………...……………………..……..3-4

# 1.6 Equipment ………………………………………………………………………………………………….…..3-4

# 1.7 Margin of Preference 	3-5

# 1.8 Multiple Contracts 	3-5

# 1.9 Health and Safety COVID -19 Plan (HS-C19)…………………………………………………..…..  3-5

# 1.10 Plan outlines …………………………………………………………………………….……..………3-62.	Qualification	3-7

# 2.1 Eligibility	3-7

2.1.1 Nationality	3-7

2.1.2 Conflict of Interest	3-7

# 2.1.3 ADB Eligibility	3-7

2.1.4 Government-Owned Enterprise	3-7

# 2.1.5 United Nations Eligibility	3-7

# 2.2 Historical Contract Nonperformance	3-8

2.2.1   History of Nonperforming Contracts	3-8

2.2.2   Pending Litigation and Arbitration	3-8

# 2.3 Financial Situation	3-9

# 2.3.1 Historical Financial Performance	3-9

# 2.3.2 Average Annual Construction Turnover	3-9

2.3.3 Financial Resources	3-10

# 2.4 Construction Experience	3-12

# 2.4.1 Contracts of Similar Size and Nature	3-12

2.4.2 Construction Experience in Key Activities	3-12

Evaluation and Qualification Criteria

Evaluation

In addition to the criteria listed in ITB 34.2 (a)–(e), other relevant factors are as follows:

- Tax clearance of all bidders shall be checked prior to contract award.

# 1.1	Adequacy of Technical Proposal

Evaluation of the Bidder’s Technical Proposal will include an assessment of the Bidder’s technical capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section 6 (Employer’s Requirements).

Noncompliance with equipment and personnel requirements described in Section 6 (Employer’s Requirements) shall not normally be a ground for bid rejection, and such noncompliance will be subject to clarification during bid evaluation and rectification prior to contract award.

1.2	Completion Time

An alternative Completion Time is not allowed. The following durations apply per lot. In case of more than 1 lot or multiple lots, the works are expected to be taken out simultaneously not consecutively and this must be considered in your planning, mobilization and scheduling of works:

| Lot No. | Description | Duration (Days) |
| --- | --- | --- |
| Lot 2 | Construction of Waste Management Centers at K. Maafushi & K. Guraidhoo | 120 Days |
| Lot 3 | Construction of Waste Management Centers at V. Thinadhoo & V. Felidhoo | 120 Days |
| Lot 4 | Construction of Waste Management Centers at V. Keyodhoo & V. Rakeedhoo | 120 Days |
| Lot 5 | Construction of Waste Management Centers at AD. Mahibadhoo & AD. Hangnamedhoo | 150 Days |
| Lot 6 | Construction of Waste Management Centers at AA. Himandhoo & AA. Feridhoo | 150 Days |
| Lot 7 | Construction of Waste Management Centers at AA. Thoddoo | 150 Days |
| Lot 8 | Construction of Waste Management Centers at K. Kaashidhoo | 150 Days |

# 1.3	Technical Alternatives

Technical alternatives, if permitted under ITB 13.4, will be evaluated as follows:

Not applicable

# 1.4	Quantifiable Nonconformities and Omissions

Subject to ITB 14.2 and ITB 34.2, the evaluated cost of quantifiable nonconformities including omissions, is determined as follows:

Pursuant to ITB 30.3, the cost of all quantifiable nonmaterial nonconformities shall be evaluated, including omissions in Daywork where competitively priced but excluding omission of prices in the Bill of Quantities. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of bids.”]

# 1.5	Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

| No | Position | No | Professional Qualification/Work Experience (years) | In Similar Works Experience (years) |
| --- | --- | --- | --- | --- |
| 1 | Construction Manager | 1 per Lot | Min. Diploma or equivalent in Civil Engineering, Construction Management or related field | 5 |
| 2 | Construction Supervisor | 1 per Lot | Suitable qualification (professional certificate) or equivalent experience | 3 |
| 3 | Skilled workers | 3 per Lot | Experience in masonry, structural steel works, electrical works | 3 |
| 4 | Unskilled labour | 5 per Lot |  | 3 |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section IV, Bidding Forms.

# 1.6	Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required per Site |
| --- | --- | --- |
| 1 | Concrete Mixer | 2 |
| 2 | Vibrator / Plate Compactor | 2 |
| 3 | Welding Genset / Welding transformer | 2 |
| 4 | - |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV.

# 1.7	Margin of Preference

Not applicable

# 1.8	Multiple Contracts

Works are grouped in multiple contracts and pursuant to ITB 34.4, the Employer shall evaluate and compare Bids on the basis of a contract, or a combination of contracts, or as a total of contracts in order to arrive at the least-cost combination for the Employer by taking into account discounts offered by Bidders in case of award of multiple contracts.

If a Bidder submits several successful (lowest evaluated substantially responsive) bids, the evaluation will also include an assessment of the Bidder’s capacity to meet the following aggregated requirements as presented in the bid:

Average annual construction turnover,

Financial resources,

Equipment to be allocated, and

Personnel to be fielded.

- If the bidder has been awarded any contracts in the first round of announcement the assessment will include the aggregated requirements as presented in the bid and requirements mentioned below of awarded lots:

| Evaluation criteria | Lot 1 |
| --- | --- |
| Average annual construction turnover | MVR 4.9 million |
| Financial resources | MVR 1.5 million |
| Equipment to be allocated | As mentioned under Section 3 - 1.5 and 1.6 above for both lots |
| Personnel to be fielded |  |

Maximum of 2 lots will be awarded to one firm / bidder.

# 1.9	Health and Safety COVID -19 Plan (HS-C19)

# The Employer will take into account the quality of the draft Health and Safety COVID -19 Plan (HS-C19 Plan) attached to the Technical Proposal in its evaluation of the Adequacy of the Technical Proposal.

The bidder should demonstrate in the HS-C19 Plan the health and safety measures they will put in place on site in relation to COVID-19 prevention and controls, including but not limited to, PPE requirements, site set up, training, induction and mobilization of new personnel, equipment and plants cleaning and other hazard management measures while undertaking site work activities, site visitor’s health and safety protocols, as well as the approach to the monitoring and reporting of the HS-C19 Plan. The HS-C19 Plan should be fit for purpose for the particular construction works of this contract and be aligned with any relevant government regulations and guidelines on COVID-19 prevention and controls, as well as workplace safety requirements, or in the absence thereof, to international good practice guidelines such as World Health Organization. 2020. Considerations for public health and social measures in the workplace in the context of COVID-19. Geneva. Available here:

(https://www.who.int/publications/i/item/considerations-for-public-health-and-social-measures-in-the-workplace-in-the-context-of-covid-19). The bidder may also refer to the COVID-19 health and safety guidance given in the IEE report attached to this bidding document.

# 1.10	Plan Outlines

The requirement for the following plan outlines are listed in Section 4:

Quality Plan Outline

Health & Safety Plan Outline

Contractors Environmental Management Plan

Qualification

It is the legal entity or entities comprising the Bidder, and not the Bidder’s parent companies, subsidiaries, or affiliates, that must satisfy the qualification criteria described below.

Eligibility

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

Nationality

| Nationality in accordance with ITB Subclause 4.2. | must meet requirement | must meet requirement | must meet requirement | not applicable | Forms ELI – 1; ELI – 2 with attachments |
| --- | --- | --- | --- | --- | --- |

Conflict of Interest

| No conflicts of interest in accordance with ITB Subclause 4.3. | must meet requirement | must meet requirement | must meet requirement | not applicable | Letter of Bid |
| --- | --- | --- | --- | --- | --- |

ADB Eligibility

| Not having been declared ineligible by ADB, as described in ITB Subclause 4.4. | must meet requirement | must meet requirement | must meet requirement | not applicable | Letter of Bid |
| --- | --- | --- | --- | --- | --- |

Government-Owned Enterprise

| Bidder required to meet conditions of ITB Subclause 4.5. | must meet requirement | must meet requirement | must meet requirement | not applicable | Forms ELI - 1, ELI - 2 with attachments |
| --- | --- | --- | --- | --- | --- |

United Nations Eligibility

| Not having been excluded by an act of compliance with a United Nations Security Council resolution in accordance with ITB Subclause 4.7. | must meet requirement | must meet requirement | must meet requirement | not applicable | Letter of Bid |
| --- | --- | --- | --- | --- | --- |

Historical Contract Nonperformance

    - 2.2.1	History of Nonperforming Contracts

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

| Nonperformance of a contracta did not occur as a result of contractor default since 1 January 2020 | Must meet requirement | Must meet requirement | Must meet requirementb | Not Applicable | Form CON-1 |
| --- | --- | --- | --- | --- | --- |

a  Nonperformance, as decided by the Employer, shall include all contracts where (a) nonperformance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Nonperformance shall not include contracts where Employers decision was overruled by the dispute resolution mechanism. Nonperformance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted.

b This requirement also applies to contracts executed by the Bidder as Joint Venture partner.

2.2.2	Pending Litigation and Arbitation

    - Not Applicable.

Financial Situation

- 2.3.1	Historical Financial Performance

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |
| Submission of audited financial statements or, if not required by the law of the Bidder’s country, other financial statements acceptable to the Employer, for the last 03 (Three) years (2019 – 2021 or if available 2020-2022) to demonstrate the current soundness of the Bidder’s financial position. As a minimum, the Bidder's net worth for the last year, calculated as the difference between total assets and total liabilities should be positive. | must meet requirement | not applicable | must meet requirement | not applicable | Form FIN - 1 with attachments |

- 2.3.2	Average Annual Construction Turnover

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |
| Minimum Average Annual Construction turnover of MVR. Lot 2: 2.54 Million MVR Lot 3: 2.11 Million MVR Lot 4: 2.12 million MVR Lot 5: 3.00 Million MVR Lot 6: 2.75 Million MVR Lot 7: 1.75 Million MVR Lot 8: 1.65 Million MVR calculated as total certified payments received for contracts in progress or completed, within the last 3 (Three) years. | must meet requirement | must meet requirement | must meet 25% of the requirement | must meet 40% of the requirement | Form FIN - 2 |

- 2.3.3	Financial Resources

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |
| For Single Entities: The Bidder must demonstrate that its financial resources defined in FIN - 3, less its financial obligations for its current contract commitments defined in FIN - 4, meet or exceed the total requirement for the Subject Contract of Lot 2: 761,000 MVR Lot 3: 632,000 MVR Lot 4: 635,000 MVR Lot 5: 902,000 MVR Lot 6: 830,000 MVR Lot 7: 525,000 MVR Lot 8: 500,000 MVR | must meet requirement | not applicable | not applicable | not applicable | Form FIN – 3 and Form FIN – 4 |
| For Joint Ventures: - One partner must demonstrate that its financial resources defined in FIN - 3, less its financial obligations for its own current contract commitments defined in FIN - 4, meet or exceed its required share of 40% from the total requirement for the Subject Contract. AND | not applicable | not applicable | not applicable | must meet requirement | Form FIN – 3 and Form FIN – 4 |
| - Each partner must demonstrate that its financial resources defined in FIN - 3, less its financial obligations for its own current contract commitments defined in FIN - 4, meet or exceed its required share of 25% from the total requirement for the Subject Contract. AND | not applicable | not applicable | must meet requirement | not applicable | Form FIN – 3 and Form FIN – 4 |
| - (The joint venture must demonstrate that the combined financial resources of all partners defined in FIN - 3, less all the partners’ total financial obligations for the current contract commitments defined in FIN - 4, meet or exceed the total requirement for the Subject Contract of Lot 2: 761,000 MVR Lot 3: 632,000 MVR Lot 4: 635,000 MVR Lot 5: 902,000 MVR Lot 6: 830,000 MVR Lot 7: 525,000 MVR Lot 8: 500,000 MVR | not applicable | must meet requirement | not applicable | not applicable | Form FIN – 3 and Form FIN – 4 |

Construction Experience

# 2.4.1	Contracts of Similar Size and Nature

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |
| Participation in at least one contract that has been successfully or substantially completed within the last 5 (Five) years and that is similar to the proposed works, where the value of the Bidder’s participation exceeds $ Lot 2: 1.77 Million MVR Lot 3: 1.47 Million MVR Lot 4: 1.50 million MVR Lot 5: 2.11 Million MVR Lot 6: 1.95 Million MVR Lot 7: 1.21 Million MVR Lot 8: 1.16 Million MVR The similarity of the Bidder’s participation shall be based on the physical size, nature of works, complexity, methods, technology or other characteristics as described in Section 6 (Employer’s Requirements). | must meet requirement | not applicable | not applicable | must meet requirement | Form EXP - 1 |

# 2.4.2	Construction Experience in Key Activities

(May be complied with by specialist subcontractors. The employer shall require evidence of the subcontracting agreement from the bidder. A specialist subcontractor is a specialist enterprise engaged for highly specialized processes, which the main contractor cannot provide.)

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |
| For the above or other contracts executed during the period stipulated in 2.4.1 above, a minimum construction experience in the following key activities: | must meet requirements | must meet requirements a | not applicable | not applicable | Form EXP - 2 |
| Earthworks (levelling, cut and filling) |  |  |  |  |  |
| Pavement and carriageways (pavement, concrete pavement) |  |  |  |  |  |
| Civil works (small buildings 1-2 story, single housing) |  |  |  |  |  |
| Structural steel work (Shed constructions) |  |  |  |  |  |
| Utilities (electricity, water supply, sewerage) |  |  |  |  |  |

a In the case of a joint venture bidder, at least one of the partners must have the experience in the key activity if the     bidder itself (not its subcontractor) will carry out the relevant activity.

- Section 4- Bidding Forms

      - Letter of Bid	 4-2

      - Schedules	4-5

      - Bill of Quantities	4-7

      - Form of Bid Security (Bank Guarantee)	4-8

      - Technical Proposal	4-8

        - Form PER-1 Personnel	4-9

        - Error! Reference source not found.	4-11

      - Bidder’s Qualification	 4-12

  - Form ELI – 1: Bidder’s Information Sheet	4-13

  - Form ELI – 1: Bidder’s Information Sheet				4-14

  - Form CON -1 Bidders Historical Performance				4-15

  - Form LIT - 1: Pending Litigation and Arbitration				4-16

  - Form FIN - 1: Historical Financial Performance				4-17

  - Form FIN - 2: Average Annual Construction Turnover			4-18

  - Form FIN - 3:  Availability of Financial Resources			4-19

  - Form FIN - 4:  Financial Resources Requirement			4-20

  - Form FIN - 5: Self-Assessment Tool for Bidder’s Compliance		4-21

to Financial Resources (Criterion 2.3.3 of Section 3)

  - Form EXP - 1:  Contracts of Similar Size and Nature			4-22

  - Form EXP - 2:  Construction Experience in Key Activities		4-23

BID SUBMISSION CHECKLIST

Failure to include requested documentation may result in disqualification of your bid

(Check here that you have included everything asked for!!)

| Is the Letter of Bid signed by an Authorised Person, supported by a Power of Attorney |  |
| --- | --- |
| Is your Letter of Bid signed in ink by the authorised representative and the Letter of bid is an ORIGINAL and NOT a photocopy/scan copy/ certified true copy. A Photocopied/scan/certified true copy Letter of Bid or a digital signature will result in DISQUALIFICATION OF YOUR BID |  |
| Have you considered all Addendums to Bid, Minutes of Pre-Bid Meeting and Clarifications issued, in the preparation of YOUR BID? |  |
| Have you answered Items, b), c), d), e), g), h) i) j) k) l) in Section 4, Letter of Bid |  |
| Have you included the “Power of Attorney” authorising the representative to sign? Section 2, ITB 20.2 |  |
| Have you provided the correct number of days (120 days) for BID VALIDITY? Section 2, ITB 19.1 |  |
| Have you included an ORIGINAL, SIGNED Bid Security per Section 2 ITB 19.1. You may not submit a SWIFT message as a Bid Security. Note that Bid Security must be valid for 28 days beyond Bid Validity |  |
| Have you included your COVID-19 Health Plan, HS-C19 as per ITB 16.1. |  |
| For technical proposal have you included information on: - Site organization - Method statement - Mobilization schedule - Construction Schedule - Health & safety covid 19 plan |  |
| Form PER1 -1 Personnel: As stated under Section 3, 1.5 Personnel for each lot |  |
| Form PER -2 Resume of proposed personnel. |  |
| Form EQU – Equipment: As stated under Section 3, 1.6 Equipment for each lot |  |
| Are all Price Schedules/BOQ filled, |  |
| Are all of the Bidding Forms in YOUR BID supported with documentary Evidence as requested? ## IT IS NOT ENOUGH TO JUST FILL IN THE FORMS – YOU MUST PROVIDE PROOF |  |
| # Form ELI – 1: Bidder’s Information Sheet: If forming a JV – an MOU or Letter of Intenet to be provided, Articles of Incorporation and othe requirements per GoM |  |
| # Form ELI - 2: Joint Venture Information Sheet: Full Name and numbers of JV members and As Above |  |
| # Form CON - 1: History contract Non-performance: To fill by each JV member indicating any non-performance of a contract. |  |
| # Form EXP - 1: Similar Contractual Experience: Copies of Previous similar projects including completeion certificates or commission certificates |  |
| # Form EXP - 2: Experience ein Key activities; Supporting evidence of claims made on earthworks, pavement and carriageways, civil works, structure steel work and utilities. |  |
| Form Fin-1: Financial Statements Provide Independently Audited End of Year Taxation /Financial Statements for the years ending 2019 – 2021 or if available 2020-2022. |  |
| Form Fin-2: Average Annual Turnover: This information is usually assessed from the Financial Statements provided in Fin-1. |  |
| Form Fin-3: Financial Resources. All members of the JV or single entities must provide information relating to available cash assets, Lines of Credit (Bank Proof to be provided) |  |
| Form Fin-4: Current Contract Commitments: Bidders (or each Joint Venture partner) should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion |  |
| As per ITB 11.1 (h). The Bidder shall submit with its Bid the following additional documents: - Tax Registration Certificate |  |
| - Business Incorporation/ registration certificate |  |
| - Bid security |  |
| - Power of Attorney authorizing to sign the bid. |  |
| - Contract agreements for the past and ongoing contracts that are similar in nature. For completed contracts, local purchase orders, submit Acceptance Certificates, Completion Certificates or Taking Over certificates or equivalents for foreign firms |  |
| - National Contractors Registry Certificate |  |
| - The audited financial statements for the last 3 years (2019, 2020, 2021 or if available 2020,2021 and 2022) |  |

Letter of Bid

-Note-

The bidder must accomplish the Letter of Bid on its letterhead clearly showing the bidder’s complete name and address.

Date:

ICB/NCB No.:

Invitation for Bid No.:

To: [. . . insert complete name of the employer . . .]

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) Clause 8.

- We offer to execute in conformity with the Bidding Documents the following Works: [. . . insert narrative . . .]

- The total price of our Bid, excluding any discounts offered in item (d) below is:

- The total bid price from the Summary of Bill of Quantities for admeasurement contracts or Activity Schedule for lump sum contracts should be entered by the bidder inside this box. Absence of the total bid price in the Letter of Bid may result in the rejection of the bid.

| Lot No. | Description | Bidding Price In (MVR) | GST 8% | Total Bidding Price In (MVR) |
| --- | --- | --- | --- | --- |
| Lot 2 | Construction of Waste Management Centers at K. Maafushi & K. Guraidhoo |  |  |  |
| Lot 3 | Construction of Waste Management Centers at V. Thinadhoo & V. Felidhoo |  |  |  |
| Lot 4 | Construction of Waste Management Centers at V. Keyodhoo & V. Rakeedhoo |  |  |  |
| Lot 5 | Construction of Waste Management Centers at ADh.Mahibadhoo & ADh.Hangnamedhoo |  |  |  |
| Lot 6 | Construction of Waste Management Centers at AA. Himandhoo & AA. Feridhoo |  |  |  |
| Lot 7 | Construction of Waste Management Centers at AA. Thoddoo |  |  |  |
| Lot 8 | Construction of Waste Management Centers at K. Kaashidhoo |  |  |  |

- The discounts offered and the methodology for their application are as follows: [. . . insert discounts and methodology for their application if any . . .]

- Our bid shall be valid for a period of ……….[insert bid validity period as specified in ITB 18.1 of the BDS .] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- If our bid is accepted, we commit to obtain a performance security in accordance with the Bidding Document.

- Our firm, including any Subcontractors or Suppliers for any part of the Contract, have nationalities from eligible countries in accordance with ITB 4.2.

- We, including any Subcontractors or Suppliers for any part of the contract, do not have any conflict of interest in accordance with ITB 4.3.

- We are not participating, as a Bidder in more than one Bid in this bidding process in accordance with ITB 4.3(e), other than alternative offers submitted in accordance with ITB 13.

- Our firm, its affiliates or subsidiaries, including any Subcontractors or Suppliers for any part of the contract, has not been declared ineligible by ADB, under the Employer’s country laws or official regulations or by an act of compliance with a decision of the United Nations Security Council.

- [We are not a government-owned enterprise] / [We are a government-owned enterprise but meet the requirements of ITB 4.5].

- We have paid, or will pay the following commissions, gratuities, or fees with respect to the bidding process or execution of the Contract:

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |
| ……………………….. | ……………………. | ……………………… | ………….. |
| ……………………….. | ……………………. | ……………………… | ………….. |

- We understand that this Bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We agree to permit ADB or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by ADB.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section 6 (Employer’s Requirements) and our technical proposal, or as otherwise agreed with the Employer.

Name                             …………………………………………….. (Complete Name of person signing)

In the capacity of            ……………………………………………(Legal capacity of person signing)

Signed                         ………………………………………………(Signature of Authorized person)

Duly authorized to sign the

Bid for and on behalf of   ……………………………………………(Complete Name of Bidder)

Date                          ……………… day of ……………………… (DD/MM/YYYY)

Schedules

Schedule of Payment Currencies

For  ...........................insert name of Section of the Works

Separate tables may be required if the various sections of the Works (or of the Bill of Quantities) will have substantially different foreign and local currency requirements. In such a case, the Employer should prepare separate tables for each Section of the Works.

|  | A | B | C | D |
| --- | --- | --- | --- | --- |
| Name of Payment Currency | Amount of Currency | Rate of Exchange to Local Currency | Local Currency Equivalent C = A x B | Percentage of Net Bid Price (NBP) 100xC NBP |
| Local Currency ……………………….. |  | 1.00 |  |  |
| Foreign Currency #1 ……………………….. |  |  |  |  |
| Foreign Currency #2 ……………………….. |  |  |  |  |
| Foreign Currency #3 ……………………….. |  |  |  |  |
| Net Bid Price |  |  |  | 100.00 |
| Provisional Sums Expressed in Local Currency |  | 1.00 |  |  |
| BID PRICE |  |  |  |  |

-- Note --

The rates of exchange shall be the selling rates 28 days prior to the deadline for submission of bids published by the source specified in BDS 15.

Bill of Quantities

[Admeasurement Contract]

See separate excel files

Units of Measurement

The following units of measurement and abbreviations are recommended for use unless other national units are mandatory in the country of the Employer.

| Unit | Abbreviation | Unit | Abbreviation |
| --- | --- | --- | --- |
| cubic meter hectare hour kilogram lump sum meter metric ton (1,000 kg) | m3 or cum ha h kg ls m t | millimeter month number square meter square millimeter week | mm mon no. m2 or sqm mm2 or sqmm wk |

Form of Bid Security (Bank Guarantee)

Bank’s name, and address of issuing branch or office

Beneficiary: 	name and address of the employer

Date:

Bid Security No.:

We have been informed that . . . . . name of the bidder. . . . .  (hereinafter called “the Bidder”) has submitted to you its bid dated . . . . . . . . . (hereinafter called “the Bid”) for the execution of . . . . . . . . name of contract . . . . . . . under Invitation for Bids No. . . . . . . . . . (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we  . . . . . name of bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . . . . . .amount in words . . . .  . . . . .  (. . . . . . .amount in figures . . . . . . .  ) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder

(a)	has withdrawn its Bid during the period of bid validity specified by the Bidder in the Letter of Bid; or

(b)	does not accept the correction of errors in accordance with the Instructions to Bidders (hereinafter “the ITB”); or

(c)	having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Agreement, or (ii) fails or refuses to furnish the performance security, in accordance with the ITB, or (iii) fails or refuses to furnish the domestic preference security, if required.

This guarantee will expire (a) if the Bidder is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Bidder and the Performance Security issued to you upon the instruction of the Bidder; and (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy your notification to the Bidder of the name of the successful Bidder, or (ii) 28 days after the expiration of the Bidder’s bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

. . . . . . . . . . . .Authorized signature(s) and bank’s seal (where appropriate). . . . . . . . . .

-- Note --

In case of a joint venture, the bid security must be in the name of all partners to the joint venture that submits the bid.

Technical Proposal

Personnel

Equipment

Site Organization

Method Statement

Mobilization Schedule

Construction Schedule

Health & Safety COVID-19 Plan

Others

Form PER-1 Personnel

Form PER – 1: Proposed Personnel

Bidder should provide the details of the proposed personnel and their experience record in the relevant Information Forms below for each candidate:

| 1. | Title of position* |
| --- | --- |
|  | Name |
| 2. | Title of position* |
|  | Name |
| 3. | Title of position* |
|  | Name |
| 4. | Title of position* |
|  | Name |
| 5. | Title of position* |
|  | Name |
| etc. | Title of position* |
|  | Name |

-- Note --

*As listed in Section 6 (Employer’s Requirements).

Form PER – 2: Resume of Proposed Personnel

The Bidder shall provide all the information requested below. Use one form for each position as requested in Section 6 of the Bidding Documents

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| ### From | ### To | ### Company, Project, Position and Relevant Technical & Management Experience |
| --- | --- | --- |

Form EQU-1 Equipment

The Bidder shall provide adequate information and details to demonstrate clearly that it has the capability to meet the equipment requirements indicated in Section 6 (Employer’s Requirements), using the Forms below. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Type of Equipment |  |  |
| --- | --- | --- |
| Equipment Information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current Status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially Manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Bidder’s Qualification

To establish its qualifications to perform the contract in accordance with Section 3 (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder.

Form ELI – 1: Bidder’s Information Sheet

| Bidder’s Information |  |  |
| --- | --- | --- |
| 111 | Bidder’s legal name |  |
| 2 | In case of a Joint Venture, legal name of each partner |  |
| 3 | Bidder’s country of constitution |  |
| 4 | Bidder’s year of constitution |  |
| 5 | Bidder’s legal address in country of constitution |  |
| 6 | Bidder’s authorized representative (name, address, telephone number(s), fax number(s), e-mail address) |  |
|  | Attached are copies of the following documents. - 1. In case of a single entity, articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2. - 2. Authorization to represent the firm or Joint Venture named above, in accordance with ITB 20.2. - 3. In case of a Joint Venture, a letter of intent to form a Joint Venture or Joint Venture agreement, in accordance with ITB 4.1. - 4. In case of a government-owned enterprise, any additional documents not covered under 1 above required to comply with ITB 4.5. |  |

Form ELI - 2: Joint Venture Information Sheet

Each member of the Joint Venture and Specialist Subcontractor must fill out this form separately.

| Joint Venture / Specialist Subcontractor Information |  |
| --- | --- |
| Bidder’s legal name |  |
| Joint Venture Partner’s or Specialist Subcontractor’s legal name |  |
| Joint Venture Partner’s or Specialist Subcontractor’s country of constitution |  |
| Joint Venture Partner’s or Specialist Subcontractor’s year of constitution |  |
| Joint Venture Partner’s or Specialist Subcontractor’s legal address in country of constitution |  |
| Joint Venture Partner’s or Specialist Subcontractor’s authorized representative information (name, address, telephone number(s), fax number(s), e-mail address) |  |
| Attached are copies of the following documents. - 1. Articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2. - 2. Authorization to represent the firm named above, in accordance with ITB 20.2. - 3. In the case of a government-owned enterprise, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB 4.5. |  |

Form CON – 1: Historical Contract Non-Performance

Each Bidder must fill out this form in accordance with Criteria 2.2.1 of Section 3 (Evaluation and Qualification Criteria) to describe any history of non-performing contracts.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name below:

Joint Venture Partner: ___________________

| Table 1: History of Non-Performing Contracts |  |  |  |
| --- | --- | --- | --- |
| Choose one of the following: No non-performing contracts. Below is a description of non-performing contracts involving the Bidder (or each Joint Venture member if Bidder is a Joint Venture). |  |  |  |
| Year | Description | Amount of non-performed portion of contract ($ equivalent) | Total Contract Amount ($ equivalent) |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Purchaser: [insert full name] Address of Purchaser: [insert street/city/country] Reason(s) for nonperformance: [indicate main reason(s)] | [insert amount] | [insert amount] |

Form FIN - 1: Historical Financial Performance

Each Bidder must fill out this form.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name below:

Joint Venture Partner: ………………………..

| Financial Information | Financial Data for Previous 3 Years [MVR Equivalent] |  |  |
| --- | --- | --- | --- |
|  | Year 1: | Year 2: | Year 3: |

Information from Balance Sheet

| Total Assets (TA) |  |  |  |
| --- | --- | --- | --- |
| Total Liabilities (TL) |  |  |  |
| Net Worth = TA – TL |  |  |  |
| Current Assets (CA) |  |  |  |
| Current Liabilities (CL) |  |  |  |
| Working Capital = CA - CL |  |  |  |

| Most Recent Working Capital |  | To be obtained for most recent year and carried forward to FIN - 3 Line 1; in case of Joint Ventures, to the corresponding Joint Venture Partner’s FIN - 3. |
| --- | --- | --- |

Information from Income Statement

| Total Revenues |  |  |  |
| --- | --- | --- | --- |
| Profits Before Taxes |  |  |  |
| Profits After Taxes |  |  |  |
| - Attached are copies of financial statements (balance sheets including all related notes, and income statements) for the last _____ years, as indicated above, complying with the following conditions. - Unless otherwise required by Section 3 of the Bidding Document, all such documents reflect the financial situation of the legal entity or entities comprising the Bidder and not the Bidder’s parent companies, subsidiaries, or affiliates. - Historical financial statements must be audited by a certified accountant. - Historical financial statements must be complete, including all notes to the financial statements. - Historical financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted). |  |  |  |

Form FIN - 2: Average Annual Construction Turnover

Each Bidder must fill out this form.

The information supplied should be the Annual Turnover of the Bidder or each member of a Joint Venture in terms of the amounts billed to clients for each year for work in progress or completed, converted to US dollars at the rate of exchange at the end of the period reported.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name below:

Joint Venture Partner: ……………………..

| Annual Turnover Data for the Last 3 Years (Construction only) |  |  |  |
| --- | --- | --- | --- |
| Year | Amount Currency | Exchange Rate | MVR Equivalent |
| 2021 |  |  |  |
| 2020 |  |  |  |
| 2019 |  |  |  |
| Average Annual Construction Turnover |  |  |  |

Form FIN – 3:  Availability of Financial Resources

Bidder must demonstrate sufficient financial resources, usually comprising of Working Capital supplemented by credit line statements or overdraft facilities and others to meet the Bidder’s financial requirements for

- its current contract commitments, and

- the subject contract.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name below:

Joint Venture Partner: ……………………………….

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (MVR equivalent) |
| 1 | Working Capital (to be taken from FIN - 1) |  |
| 2 | Credit Linea |  |
| 3 | Other Financial Resources |  |
|  | Total Available Financial Resources |  |

a	To be substantiated by a letter from the bank issuing the line of credit.

Form FIN- 4:  Financial Resources Requirement

Bidders (or each Joint Venture partner) should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name below:

Joint Venture Partner: ………………………………….

|  | ### Name of Contract | ### Employer’s Contact (Address, Tel, Fax) | Contract Completion Date | Outstanding Contract Value (X) a | Remaining Contract Period in months (Y) b | Monthly Financial Resources Requirement (X / Y) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| Total Monthly Financial Requirements for Current Contract Commitments |  |  |  |  |  | MVR …………………. |

a	Remaining outstanding contract values to be calculated from 28 days prior to the bid submission deadline (MVR equivalent based on the foreign exchange rate as of the same date).

b	Remaining contract period to be calculated from 28 days prior to bid submission deadline.

Form FIN - 5: Self-Assessment Tool for Bidder’s Compliance to Financial Resources

This form requires the same information submitted in Forms FIN - 3 and FIN - 4. All conditions of “Available Financial Resources Net of CCC ≥ Requirement for the Subject Contract” must be satisfied to qualify.

Form FIN - 5A: For Single Entities

| For Single Entities: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| ……………….. (Name of Bidder) |  |  |  | . . . . . . . . . . ._ |  |

Form FIN - 5B: For Joint Ventures

| For Joint Ventures: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| One Partner: |  |  |  |  |  |
| ……………….. (Name of Partner) |  |  |  | . . . . . . . . . . . |  |
| Each Partner: |  |  |  |  |  |
| ……………….. (Name of Partner 1) |  |  |  | . . . . . . . . . . . |  |
| ……………….. (Name of Partner 2) |  |  |  | . . . . . . . . . . . |  |
| ……………….. (Name of Partner 3) |  |  |  | . . . . . . . . . . . |  |
| All partners combined | ∑ D = Sum of available financial resources net of current contract commitments for all partners |  | ∑ D = _______ | . . . . . . . . . . . |  |

- Note -

Form FIN – 5 is made available for use by the bidder as a self-assessment tool, and by the employer as an evaluation work sheet, to determine compliance with the financial resources requirement as stated in 2.3.3. Failure to submit Form FIN - 5 by the Bidder shall not lead to bid rejection.

Form EXP – 1:  Contracts of Similar Size and Nature

Fill up one (1) form per contract.

| Contract of Similar Size and Nature |  |  |
| --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |
| Award Date |  | Completion Date |
| Total Contract Amount | MVR |  |
| If partner in a Joint Venture or subcontractor, specify participation of total contract amount | Percent of Total | Amount |
| Employer’s Name Address Telephone/Fax Number E-mail |  |  |
| Description of the Similarity in Accordance with Criterion 2.4.1 of Section 3 (Evaluation and Qualification Criteria) |  |  |
| Participation in at least one contract that has been successfully or substantially completed within the last 5 (Five) years and that is similar to the proposed works, where the value of the Bidder’s participation exceeds $ Lot 2: 1.77 Million MVR Lot 3: 1.47 Million MVR Lot 4: 1.50 million MVR Lot 5: 2.11 Million MVR Lot 6: 1.95 Million MVR Lot 7: 1.21 Million MVR Lot 8: 1.16 Million MVR The similarity of the Bidder’s participation shall be based on the physical size, nature of works, complexity, methods, technology or other characteristics as described in Section 6 (Employer’s Requirements). |  |  |

** Reference Letters or completion certificates from the clients should be attached with the forms.
Form EXP - 2:  Construction Experience in Key Activities

Fill up one (1) form per contract.

| Contract with Similar Key Activities |  |  |
| --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |
| Award Date |  | Completion Date |
| Total Contract Amount | MVR |  |
| If partner in a Joint Venture or subcontractor, specify participation of total contract amount | Percent of Total | Amount |
| Employer’s Name Address Telephone Number Fax Number E-mail |  |  |
| Description of the Key Activities in Accordance with Criterion 2.4.2 of Section 3 (Evaluation and Qualification Criteria) |  |  |
| For the above or other contracts executed during the period stipulated in 2.4.1 above, a minimum construction experience in the following key activities: - Earthworks (levelling, cut and filling) - Pavement and carriageways (pavement, concrete pavement) - Civil works (small buildings 1-2 story, single housing) - Structural steel work (Shed constructions) - Utilities (electricity, water supply, sewerage) |  |  |

Section 5 - Eligible Countries

This section contains the list of eligible countries.

| 1 | Afghanistan | 35 | Philippines |
| --- | --- | --- | --- |
| 2 | Armenia | 36 | Samoa |
| 3 | Australia | 37 | Singapore |
| 4 | Azerbaijan | 38 | Solomon Islands |
| 5 | Bangladesh | 39 | Sri Lanka |
| 6 | Bhutan | 40 | Taipei, China |
| 7 | Brunei Darussalam | 41 | Tajikistan |
| 8 | Cambodia | 42 | Thailand |
| 9 | China, People's Republic of | 43 | Timor-Leste |
| 10 | Cook Islands | 44 | Tonga |
| 11 | Fiji | 45 | Turkmenistan |
| 12 | Georgia | 46 | Tuvalu |
| 13 | Hong Kong, China | 47 | Uzbekistan |
| 14 | India | 48 | Vanuatu |
| 15 | Indonesia | 49 | Viet Nam |
| 16 | Japan | 50 | Austria |
| 17 | Kazakhstan | 51 | Belgium |
| 18 | Kiribati | 52 | Canada |
| 19 | Korea, Republic of | 53 | Denmark |
| 20 | Kyrgyz Republic | 54 | Finland |
| 21 | Lao People's Democratic Republic | 55 | France |
| 22 | Malaysia | 56 | Germany |
| 23 | Maldives | 57 | Ireland |
| 24 | Marshall Islands | 58 | Italy |
| 25 | Micronesia, Federated States of | 59 | Luxembourg |
| 26 | Mongolia | 60 | The Netherlands |
| 27 | Myanmar | 61 | Norway |
| 28 | Nauru | 62 | Portugal |
| 29 | Nepal | 63 | Spain |
| 30 | New Zealand | 64 | Sweden |
| 31 | Niue | 65 | Switzerland |
| 32 | Pakistan | 66 | Turkey |
| 33 | Palau | 67 | United Kingdom |
| 34 | Papua New Guinea | 68 | United States |

Part 2

Section 6

Employer’s Requirements

- Specifications

- Drawings

- Supplementary Information Regarding Works to Be Procured

- Personnel Requirements

- Equipment Requirements

1. Specifications

Table of Contents

- Error! Reference source not found. & Background

- Purpose of the Works

- Error! Reference source not found. of Works

- Error! Reference source not found.

- Technical Specifications

  - Preliminaries

  - Site works

  - Concrete works

  - Steel Reinforcement

  - Masonry

  - Error! Reference source not found.

  - Carpentry & joinery

  - Ceiling

  - Aluminium doors & windows

  - Roofing

  - Finishes

  - Plumbing

  - Painting

  - Electrical installations

  - Fencing

  - Water Tank

- Contractor’s Documents

- Site delineation, use, access, and possession details

- Site Organization

- Health & Safety Plan

- Reporting and progress monitoring

- Testing and inspection requirements during construction

- Commissioning

List of abbreviations and acronyms

| ADB | Asian Development Bank |
| --- | --- |
| EPA | Environmental Protection Agency |
| ERQ | Employer’s Requirements |
| ER | Project Manager |
| ESHS | Environmental, Social, Health and Safety |
| GoM | Government of Maldives |
| HVAC | Heating, Ventilation and Air Conditioning |
| ISWMC | Island waste management Center |
| LRA | Labour Relations Authority |
| MoE | Ministry of Environment (The “Employer”) |
| MSW | Municipal Solid Waste |
| MWSC | Maldives Water and Sewerage Company |
| SWM | Solid Waste Management |

- Introduction and Background

| ## Introduction | The Government of Maldives (GoM) is committed to improve the environmental conditions and strengthen the solid waste management system in the Maldives. As part of the National Waste Management Policy and the Saafu Raajje (the “Clean Maldives” campaign) adopted and initiated in 2015, GoM has taken an initiative to implement the “Greater Malé Environmental Improvement and Waste Management Project” for improving solid waste management (SWM) throughout the country and particularly in the project area with financial support from the Asian Development Bank (hereinafter ADB) and other financial institutions. |
| --- | --- |
| ## Background | As part of its national strategy to achieve efficient public spending on economic and social services, the GoM targeted 70% of its total population to reside in Greater Malé. The plan seeks to create spatial agglomeration and generate economic opportunities for faster growth and poverty reduction. Tourism accounts for 30% of gross domestic product and is expected to expand, particularly in the project area that encompasses Zone 3 (the Maldives is divided into seven zones. The projected doubling of Malé’s population will significantly increase pressure on already stressed solid waste management services. Improving SWM in the Greater Malé region is a top priority of the government. The National Waste Management Policy (2015) outlines key principles to improve environmental quality, and the planned Solid Waste Management Act will establish a new legal and institutional framework for the sector. On behalf of GoM, the Ministry of Environment (MoE) launched the Saafu Raajje (“Clean Maldives”) initiative in 2015, a national campaign promoting public awareness of good waste management practices, and in November 2015 a green tax was passed to levy fees on tourist resorts and guesthouses to raise funds for environmental programs. In 2016 and in 2017 respectively, MoE commissioned a consultancy company to conduct a feasibility study for a Regional Waste Management Center (RWMC) on the island of Thilafushi that is located approx. 7 km east of Malé and to outline a concept design for the future waste transfer system in the project area. The objective of the project is to establish a sustainable regional SWM system in the Greater Malé region and its inhabited outer islands by: - Improving collection, transfer, disposal, treatment, recycling, and rehabilitating the existing dumpsite. - Strengthening institutional capacities for solid waste services delivery and environmental monitoring; and - Improving public awareness in reduce-reuse-recycle (“3R”). |

Purpose of the Works

| General | The purpose of the works is presented in the following: |  |
| --- | --- | --- |
| Lot | Islands | Purpose of the work |
| Lot 2 | K. Maafushi & K. Guraidhoo | Construction of new ISWMC facility |
| Lot 3 | V. Thinadhoo & V. Felidhoo | Construction of new ISWMC facility |
| Lot 4 | V. Keyodhoo & V. Rakeedhoo | Construction of new ISWMC facility |
| Lot 5 | AD. Mahibadhoo & AD. Hangnamedhoo | Construction of new ISWMC facility |
| Lot 6 | AA. Himandhoo & AA. Feridhoo | Construction of new ISWMC facility |
| Lot 7 | AA. Thoddoo | Construction of new ISWMC facility |
| Lot 8 | K. Kaashidhoo | Construction of new ISWMC facility |

Scope of the works

| ## Scope of the works | - Site clearance from vegetation, topsoil, existing buildings, waste and other debris (if needed) - Site levelling, grading, compacting - Earthworks (cutting, backfilling, compacting) for the preparation of foundations, supply and surface water drainage works - Fencing, supply, and installation of gates - Steel works: Building of steel sheds for coverage of waste processing areas - Civil works: Construction of a Guardroom (if needed), an Office building including all connections to site utilities (Alternatively: Procurement, installation, and connection of prefabricated buildings) - Construction of site infrastructure: Lighting, rainwater drainage, water supply facilities, sewerage water, electrical provision, distribution, and connections - Landscaping works & sign boards |
| --- | --- |
| ## Construction Activities | The Contractor’s responsibilities during the works shall include but are not limited to the following: - Mobilize all Contractor’s Personnel and sub-contractors and erect temporary facilities (if possible and needed). - Prepare the Site for construction and manage all construction works on the Site. - Ensuring timely delivery of all Materials and Goods to the Site. - Integrate Works to ensure safety of personnel, assets, and environment. - Connect Site infrastructure to utilities (water, sewerage, power, and telecommunication). |
| ## Commissioning Activities | The Contractor’s commissioning activities shall, without limitation, consist of: - Prepare and submit relevant Contractor’s Documents including commissioning plan and as-built drawings; |

Site Data

| ## General | This section lists the relevant site data to be considered by the Contractor when designing and building the Works. |  |
| --- | --- | --- |
| ## Site location | See Drawings |  |
| ## Site conditions | The Site conditions are the following |  |
| Lot | Islands | Site conditions |
| Lot 2 | K. Maafushi & K. Guraidhoo | Existing municipal dumpsite, site clearance from waste and debris is needed, site infrastructure is closed by |
| Lot 3 | V. Thinadhoo & V. Felidhoo | Existing municipal dumpsite, site clearance from waste and debris is needed, site infrastructure is closed by |
| Lot 4 | V. Keyodhoo & V. Rakeedhoo | Existing municipal dumpsite, site clearance from waste and debris is needed, site infrastructure is closed by |
| Lot 5 | AD. Mahibadhoo & AD. Hangnamedhoo | Existing municipal dumpsite, site clearance from waste and debris is needed, site infrastructure is closed by |
| Lot 6 | AA. Himandhoo & AA. Feridhoo | Site provided by Island council, infrastructure (electricity, water, sewerage) nearby |
| Lot 7 | AA. Thoddoo | Site provided by Island council, infrastructure (electricity, water, sewerage) nearby |
| Lot 8 | K. Kaashidhoo | Existing municipal dumpsite, site clearance from waste and debris is needed, no site infrastructure (electricity, water, sewerage) close to the site |

Technical Specification

| - Preliminaries |  |
| --- | --- |
| ## General | The Contractor shall for all Works, - Meet the objectives of the Contract with respect to content, time, and costs. - Protect health and safety of the public, third parties, the Employer’s Personnel, and the Contractor’s Personnel during the entire works - Maximize the protection of the environment and minimize any adverse environmental impacts caused by the Works to the Site, its surroundings and to air, water and soil. - Ensure that the Works are fit for purpose and meet the requirements of a fully functional, durable and easy and safe to maintain waste facility complying with or exceeding these Employer’s Requirements. Provide evidence of meeting the requirements by carrying out the commissioning in due course as per agreed scheduling and phasing requirements. |
| ## Standard & Codes |  |
|  | The Contractor shall, perform the Works in compliance with all regulations, standard specifications or statutes of the Government of Maldives unless otherwise conform to this specification. |
|  | Wherever current British Standard Specifications and Codes of Practice are defined hereinafter it shall be understood that either the British version or any other internationally recognized standards and codes of practice shall apply to and form part of these specifications unless otherwise specified in respect of all materials and works to which they have application. |
| ## Drawings and Specifications |  |
|  | Drawings and Specifications are intended to complement each other, so that if anything is shown on the Drawings, but not mentioned in the specifications or vice versa, it is to be furnished and built as though specifically set forth in all three. If any discrepancies, errors, ambiguities or omissions occur in the Drawings or Specifications, the same shall be referred to the Project manager before proceeding with the Works, and the Project manager decision on such discrepancies, errors, ambiguities or omissions shall be final. |
|  | In addition to the Drawings and Specifications attached hereto, the Project manager will during the progress of the Works furnish additional Drawings, Specifications, and instructions as may be necessary, in the opinion of the Project manager for the purpose of the proper and adequate execution and maintenance of the Works, and the Contractor shall make his work conform. Such drawings and instructions shall be deemed to be part of the Contract Documents. |
| ## Transportation to the Site |  |
|  | The Contractor shall provide all necessary transport, handling and storage of all materials, components, and the like to their points of installation on site including transport to and from storage. The Contractor shall provide all necessary transport of labour to and from the site. |
| ## Schedule and Execution Plan |  |
|  | The Contractor shall prepare and submit to the Project manager for approval the construction schedule and an execution plan of temporary facilities, stock yards, etc., before the start of the Works. |
| ## Repairing and Correction |  |
|  | Any breakage(s) or defect(s) of existing buildings, roads utilities, or part(s) of them caused by the Works including transportation for the works shall be repaired or corrected by the Contractor with his responsibility. |
| ## Workmanship and Materials |  |
|  | All workmanship shall be of the best standard. All goods and materials to be incorporated in the Works must be new, unused, of the most recent or current models and incorporate all recent improvements in design and materials unless provided otherwise in the contract. |
| ## Obvious Work |  |
|  | Where an item of work is obviously required for the type of work being undertaken then it shall be deemed to have been included even though the item is not specifically mentioned or shown in the Drawings or Specifications. |
| ## Protection |  |
|  | The Contractor shall have the Works and adjoining properties protected from inclement weather. Any loss or damage caused by weather, carelessness or lack of skill of workers, accident or otherwise shall be of such property that are affected. |
|  | The work shall be suspended for such time as may be directed and/or approve by the Project manager if the specified quality of work is difficult to maintain during inclement weather. |
| ## Scaffolding |  |
|  | The Contractor shall provide all scaffolding necessary for the proper execution of the Works. |
|  | The scaffolds shall be erected safely and convenient for the execution and supervision of the Works and maintained and inspected periodically for safety. |
| ## Construction Machine |  |
|  | All necessary construction machines shall be provided and maintained by the Contractor and shall be approved by the Project manager. |
| - Site works |  |
| ## Site Clearing |  |
|  | The Site shall be cleared of all vegetation, rock, boulders, etc. and surface soil shall be removed as directed by the Project manager. The trees which are to be retained shall be protected from damage. |
|  | Spreading, leveling, and consolidating on site where required, shall be made with suitable surplus excavated material obtained from the Site. Other soils used for filling shall be approved by the Project manager. |
|  | The Contractor shall dispose all unsuitable and surplus excavated material. |
|  | The Contractor shall always tidy up and leave the Site in a clean and sanitary condition during the execution of the Works. |
| ## Excavation |  |
|  | Excavation shall be performed to the required depth as shown in the Drawings. |
|  | Excavation area shall be protected from any water flowing in. Sides of excavations shall be shored or inclined to retain excavation unless otherwise specified. |
|  | Excavation near adjoining structures shall be executed with care so as not to damage those structures. |
|  | Excavated material shall be deposited within specified areas as directed unless otherwise specified. |
|  | The Contractor is deemed to have inspected the site and to leave ascertained for himself as to the nature of the soil, etc. and also the areas where to collect and stack the materials for which necessary site clearance shall have to be made at his own cost. |
|  | Stacking or excavated materials shall be done at places approved by the Project manager and the original ground levels of such places shall have been recorded by him jointly with the Contractor before commencement of stacking operation. |
|  | Extra excavation and allied lead/lift required specifically for providing working space to workmen or shuttering to walls of basement etc. shall be measured for payment, no extra claim being allowed for such work incidental to development and executions of allied jobs. Only authorized excavation approved by the Project Manager shall be paid for. |
|  | Sufficient clear working space shall be left all around excavated area. The disposal of waste/unserviceable materials may be in filling and/or in embankment according to nature of place of disposal. The appropriate specifications for filling and/or embankment shall apply. |
|  | All foundation trenches shall be excavated to the full widths and depths shown on the drawings or to such greater or smaller depths as may be found necessary in the opinion of the Project manager and so ordered by his representative. |
|  | Should any excavation be taken down below the specified levels, the Contractor shall fill in such excavation at his own cost with cement concrete specified for foundations, well rammed in position until it is brought up to the level. |
|  | All foundation pits shall be refilled to the original surface of the ground with approved materials, which shall be well consolidated as directed by the Project manager. |
|  | The Contractor shall erect temporary barricades around the excavations and if necessary, make provisions of red lamps. |
|  | The Contractor shall remove/maintain/restore all service lines like telephone, water supply, electricity etc. without any extra charges. |
| ## Backfill |  |
|  | All earth used for filling shall unless otherwise stated, be selected hard dry material from the excavation. |
|  | The backfill of excavations shall be placed in horizontal layers not exceeding 300 mm in thickness. Each layer shall be compacted by hand or other mechanical means to the required density before the next layer is added. |
|  | If required, the Contractor shall dewater the excavations and maintain them dry for stability and especially at the time of concreting. |
|  | Bailing, pumping out or otherwise removing all water which may accumulate in the excavation from all causes. |
|  | Provision of adequate barriers, lighting, gangways across open trenches, etc. for protection of workmen and public. |
| - Concrete works |  |
| ## General |  |
|  | Materials used in the Works shall be new, of the qualities and kinds specified herein and equal to approved samples. Delivery shall be made sufficiently in advance to enable further samples to be taken and tested if required. No materials shall be used until approved and materials not approved shall be immediately removed from the Works. |
|  | Materials shall be transported, handled and stored on the site or elsewhere in such a manner to prevent damage, deterioration or contamination. |

| ## Cement |  |
| --- | --- |
|  | Cement shall be Ordinary Portland Cement. |
|  | Cement shall conform to the appropriate Speciation listed below: |
|  | Portland cement - BS 12 (British standard) |
|  | Other kinds of cement shall not be used unless otherwise approved by the Project manager. |
| ## Aggregate |  |
|  | Fine aggregate shall be imported river sand or Manufactured Sand, free from silt. Coarse aggregate shall be clean well-graded imported granite chips ranging in average size from 5mm to 25mm. Coarse aggregate shall be unloaded and kept in a manner not to cause segregation of small and large particles. Aggregate to be stored in piles shall be in a location where good drainage is provided. |
|  | Aggregate shall not contain injurious amount of rubbish, dirt, organic impurities and other foreign matters. |
|  | Strength of aggregate shall be more than that of hardened concrete paste. |
|  | In case of using fine aggregate of 0.01% or more water soluble chloride content, the necessary measures for corrosion inhibiting of reinforcement shall be instructed by the Project manager. |

| ## Water |  |
| --- | --- |
|  | Water shall not contain injurious amount of impurities which may adversely affect concrete and reinforcement. |
|  | Ground water shall not be used for concrete works. |
|  | Water shall be obtained from a public supply where possible, and shall be taken from any other sources only if approved by the Project manager. Only water of approved quality shall be used for washing out formwork, curing concrete and similar surfaces. |
| ## Handling and Storage of Material |  |
|  | Cement |
|  | Cement shall be stored in a manner to prevent weathering. |
|  | Bagged cement shall be piled no more than 10 bags so as to permit easy inspection |
|  | Cement caked even to the slightest extent shall not be used. Such cement and rejected cement shall be immediately separated from other bags of cement so that they shall not be mistaken for others. |
|  | Aggregate |
|  | Aggregate shall be stored in a manner effectively separating coarse and fine aggregate according to type and shall be prevented from inclusion of dirt, rubbish and other undesirable foreign matters. |
|  | Coarse aggregate shall be unloaded and piled in a manner not to cause segregation of small and large particles. Aggregate to be stored in piles shall be in mounds of moderate height and at a location where good drainage is provided. |
| ## Mix Proportion & Strength |  |
|  | Mix ratio for lean concrete shall be in the proportion 1:2:6 (cement: fine aggregate: coarse aggregate) by dry volume. |
|  | The water to cement ratio (w/c) in any mixing used to produce reinforced concrete shall not be more than 0.4 by weight. |
|  | The minimum characteristics strength of concrete at an age 28 days shall not be less than 30 N/mm² |
|  | If no admixture is added to increase the workability, the slump of fresh concrete in any mix shall not be more than 100 mm. |
|  | Design mix proportion shall be to obtain required workability, consistency, and durability. |
| ## Production of Concrete |  |
|  | Mixing shall be done in a mechanical mixer. The mixer drum shall be free of hardened mortar adhering to its inner surface. Before mixing commences the drum shall be primed by washing with rich cement grout. A measured quantity of dry course aggregate shall be first placed in the hopper. This shall be followed with the measured quantity of sand and then cement. The skip shall be raised and the dry material slipped into the drum. |
|  | Measuring |
|  | All materials shall be measure by volume for each batch and water may be measured volumetrically. |
|  | Cement shall be measured by number of bags unless automatic cement weight measure is in use. |
|  | Mixing Control |
|  | Concrete mixture shall be constantly controlled to obtain required workability and mixed strength. Mixing time for each batch shall be not less than 3 minutes or the dry materials shall be mixed for at least four turns of the drum after which the correct quantity of water shall be added gradually while the drum is in motion, to ensure even distribution of the materials. |
|  | Quality Control |
|  | The Contractor shall conduct tests for quality control toward insuring that concrete of the required quality is constantly produced. |
|  | The Contractor shall have all quality control test report ready for submission as required by the Project manager. |
| ## Transporting and Placing |  |
|  | General |
|  | Concrete shall be transported in a manner to minimize segregation, spill, age and other changes in quality thereof. |
|  | Concrete shall be placed and consolidated in a manner to insure uniformity and optimum density. |
|  | In case of rain or other conditions which may affect the quality of concrete during concreting, the Contractor shall take necessary measures as instructed by the Project manager. |
|  | Time Limit |
|  | The time limit from start of mixing to completion of placing of a batch as rule, shall be 30 minutes. |
|  | Preparation Prior to Placing. |
|  | The place where concrete is to be deposited shall be cleaned and sheathing shall be sprinkled with water. Subsequently, water accumulated in the form shall be removed. |
|  | Construction Joint |
|  | Joint surfaces shall be cleaned, made free of laitance and other foreign matters, and wetted prior to concreting. Joint surface shall be roughened if directed by the Project manager. |
|  | The locations of shapes of construction joints shall be consulted and approved by the Project manager. |
|  | Concrete Placing |
|  | Concrete placing shall be proceeded to keep the surface of placed concrete as horizontal as possible. |
|  | Concrete shall be continuously poured to compact around reinforcing bars and corners of formwork. |
|  | The maximum time interval between placement of continuous concreting shall not exceed 0.5 hours. However, when special measure are taken this time limit may be changed according to instruction or approval of the Project manager. |
|  | Consolidation |
|  | Vibrating of concrete and tapping of formwork shall be performed to wall, column and other places difficult for concrete to proceed. Proper number of workers for placing and compacting concrete shall be arranged. |
|  | Vibrator shall be operated for concrete called for water tightness, difficult portion for concrete to proceed and other cases directed by the Project manager. However, vibrator shall not be touched reinforcing bars and shall not be operated more than 30 seconds at same spot. |
|  | Concrete shall be placed 300 - 600 mm thickness at once in case vibrator is performing. In case flexible-insert-vibrator is called for, concrete shall not be placed thicker than the length of the insert or vibrator at one pouring. |
|  | Placing Speed |
|  | Concrete shall be placed at the speed suited for the workability of the concrete and condition of the place of placement, which insures proper consolidation of concrete. |
| ## Concrete Curing |  |
|  | Curing Method |
|  | After concrete has been placed, the concrete surface shall be kept moist by sprayed with water or by other appropriate methods and shall be protected from direct sunlight and rapid drying. This curing period shall be for not less than 14 days. |
|  | As a rule, no foot traffic nor loads shall be permitted on concrete for at least 24 hours after placement. |
| ## Test |  |
|  | General |
|  | The contractor shall be required to conduct all tests according to British standard method and procedure when the Project manager determines. |
|  | Test, as a rule, shall be conducted at the locations directed or at the testing institutions approved by the Project manager. |
|  | In case of failure in test, measure shall be taken as instructed by the Project manager. |
|  | The Contractor shall keep test records during the work and for 2 years after completion of the contracted work. |
|  | Material |
|  | Cement Test (1) Setting test. (2) Soundness test. (3) Compressive strength test. Note: Item (1) shall be conducted once in every manufacturer. Item (2) & (3) shall be conducted once in every 2,000 bags. |
|  | Aggregate test: Grading and fineness modules. |
| ## Concrete |  |
|  | Fresh concrete Slump test, shall be conducted at any time during concrete mixing on the request Project manager. |
|  | Compressive strength test of concrete Test for estimation on strength of concrete in structure: |
|  | In order to check the strength of concrete, compressive strength test, samples shall be taken from the mix and tested on the 7th day and 28th day. 150 x 150 x 150 mm cube molds shall be used for sampling and testing. The number of test cubes to be used in a test shall be not less than 3 for each test. 7th day and the 28th day unless otherwise instructed by the Project Manager. |
|  | Test sample cubes shall be made in accordance with British Standards, and sampling shall be taken as near as possible at the point of placement. |
|  | Test sample cubes shall be stored without being disturbed and shall be covered during the first 24 hours, and carefully transported specimens to the testing laboratory. Test pieces shall be cured in water after demolding. The temperature of test pieces shall be kept as close as possible to the temperature of the concrete in structure until the time of testing. |
|  | The test results shall be expressed in the average value by calculating the average compressive strength of all test pieces. The average value must be equal to or greater than the specified strength. |
| ## Defective Concrete and Finishes |  |
|  | Honeycombed surfaces shall be made good or on the instruction of the Project manager be cut out by the Contractor and by using approved concrete repair mortar Conmix Recon GP (or similar). |
|  | Concealed concrete faces shall left as from the formwork except honeycombed surfaces shall be made good. Faces of concrete intended to be rendered shall be roughened by approved means to form a key. Faces of concrete that are to have finished other than those specified shall be prepared in an approved manner as instructed by the Project manager. |
| ## Structure and Material |  |
|  | Structure |
|  | Formwork shall be performed to obtain accurate concrete in accordance with the designated drawings. |
|  | Formwork shall be firmed and secured to bear the force of concreting and tightened to avoid cement paste seeping. |
|  | Materials |
|  | Sheathing for formwork shall be waterproof plywood of not less than 12 mm thick. Joint of sheathing shall be butt joint and firmly assembled. In case of using wood board for sheathing, boards shall be 15 mm thick and applied planer. Joint shall be tongued and grooved unless otherwise approved by the Project manager. |
|  | Form liners shall be sound and suitable materials to cast the in-situ concrete structure accurately and safely as shown on the Drawings. |
|  | Timber form boards for sheathing where used for fair-faced concrete shall be of such new materials as not to cause any defects to the surface of the concrete. Special care shall be taken in fabrication, storage, and protection of these boards. |
|  | Other Material |
|  | Fastening hardware to be used shall be those with allowable tensile strength guaranteed by manufacturer through strength tests. |
|  | Form oil shall not have injurious effects on quality of concrete nor to bonding of surface finishing materials and shall be subject to approval of the Project manager. |
| ## Performance |  |
|  | Design of formwork |
|  | Formwork shall be designed to withstand construction leads during concreting, lateral pressure of fresh concrete, shock and vibrators due to concrete placing. |
|  | Formwork shall be free of injurious leakage of water, easy to remove, and shall not damage concrete at removal. |
|  | Supports shall be provided with the adequate horizontal and diagonal bracing and/or stays to prevent collapsing, heaving and twisting of formwork due to horizontal loads working during concrete placing. |
|  | Tolerance |
|  | The dimensional tolerances in location and cross section of concrete member used for designing and construction of formwork shall conform to the following table |

|  | Fabrication and Erection |
| --- | --- |
|  | Erection of formwork, and transportation and storage of materials thereof shall be started only after previously placed concrete has reached an age which acceptance of these loads will not have any adverse effect on the concrete. |
|  | Sheathing shall be fabricated and installed accurately to match the locations, shapes and dimensions of members called for in the Drawings. |
|  | Sheathing shall be installed tightly so as not to permit cement paste or mortar to escape from joints. |
|  | Pipes, boxes and other embedded hardware shall be properly secured to sheathing or others so that they will not move during concrete placing. |
|  | Supports shall be erected plumb. Supports at any two vertically consecutive floors shall be erected as near as possible to identical locations on a common plane. |
|  | Shoring shall be erected paying special attention to safety. |
|  | If sheathing is reused, the surface in contact with the concrete shall be thoroughly cleaned off and sufficiently repaired before reuse. In case of using for fair-faced concrete, the same sheathings shall be used twice after approval of the Project manager. |
|  | Striking of forms |
|  | The minimum period for keeping the forms in position and for watering after laying the concrete shall be as per the following table, except otherwise specified in RCC drawings. Forms shall be removed in such a manner as to ensure the complete safety of the structure, so that there is no shock or vibration as would damage the reinforced concrete. The responsibility for the safety of the concrete shall rest entirely with the Contractor and the Contractor shall be held liable for any damage done and shall have to make good the same at his own expenses. |
|  | The minimum time for formwork to remain in place shall be as per the following table. |

| Vertical sides of beams, slabs and columns | 48 hours |
| --- | --- |
| Soffits of slab | 21days |
| Soffits of beams | 21 days |
| Cantilevers | 28 days |

|  | Relocation of Support |
| --- | --- |
|  | Supports under concrete shall be not relocated |
|  | Removal of formwork |
|  | Formwork shall be removed gently and inspection by the Project manager shall be obtained immediately after the removal of sheathing and defects shall be immediately remedied according to instruction of the Project manager |
|  | After shoring’s have been removed, members shall be carefully observed for cracking and defection, when found, they shall be reported immediately to the Project manager for his instruction. |
| - Steel Reinforcement |  |
| ## Material |  |
|  | Reinforcing steel shall be of the dimensions given in the Drawings. |
|  | Reinforcing bars shall comply with the requirement of B.S.4449. And welded wire fabric, square bar fabric and expanded metal shall comply with appropriate part of B.S.4483. |
|  | Dia. 6mm reinforcing steel shall be a round mild steel bar, and 12mm and 16mm shall be deformed high strength bars. |
|  | Any other non-specified reinforcing steel shall be used only with the approval of the Project manager. |
|  | All reinforcing steel and binding wire shall be stored under cover and shall be at least 250mm above the ground. |
| ## Cleaning |  |
|  | Reinforcing shall be cleaned before use so that it is free from rust, oil, dirt or other coatings that reduce bond. |
| ## Bending and Laps |  |
|  | The reinforcement shall be bent cold in an approved bar bending machine. Preferably bars of full length shall be used. Lapping of bars where necessary shall conform to the following table, otherwise conforming to BS1487 ‘Bending Dimensions of Bars of Concrete reinforcement.’ |
| ## Reinforcement Cover |  |
|  | Concrete cover for reinforcement shall not be less than 45mm for substructure and shall not be less than 40mm for super-structure concrete. |
| ## Placing |  |
|  | Reinforcement intended for contact when passing each other shall be securely tied together with binding wire. |
|  | Binders and stirrups shall tightly embrace the longitudinal reinforcement to which they shall be security bound or spot-welded |
|  | Binding wire shall be turned in from the formwork and shall not project beyond reinforcing bars. |
|  | All reinforcement shall be inspected by the Project manager and approved before concrete is placed in the forms. |
| - Structural Steel |  |
| ## Scope | This section shall apply to the work involved with structural steels. All incidental items of structural steel shall be stated in the particular specification. |
| ## Materials |  |
|  | Steel |
|  | Shape of steel shall be precise and straight and free of injurious scratches and rust. |
|  | All steel sections shall be of strength class 43 A. |
|  | Dimensions of steel section and tolerance of dimension shall conform to standard dimension of steel regulated in BS standard. |
|  | Bolt |
|  | Shape of bolt, nut, and washer shall be in accordance with requirement of BS 4190 & BS 3692. |
|  | Quality of bolt shall be SC 43 A. |
|  | Welding Rod |
|  | Arc welding rod shall conform to materials to be welded, and position |
|  | Material Test |
|  | Material test may be omitted with the approval of the Project manager for standard materials with mill certificates |
|  | Tension and flexure tests shall be conducted on materials exceed the above |
|  | Number of steel materials to be tested shall be one in every different section. Number shall be increased by one in every 20-ton or a fraction of it |
| ## Fabrication |  |
|  | Main fabrication shall be done in workshop unless otherwise specified or approved by the Project manager |
|  | Full scale drawing of each section shall be drawn prior to fabrication and checked by the Project manager |
|  | Section of each material shall be cut perpendicular to axis unless otherwise specified in the drawing |
|  | Saw and angle cutter shall be used for cutting, and cut section shall be free of any noticeable defect. |
|  | Deformation caused by cutting shall be corrected |
|  | Bending process shall be done by normal temperature or hot drawn process. Steel shall be red heat in hot drawn process |
|  | Those directed in the drawing shall be chiseled finish and completely attached |
|  | Materials shall be checked for bend, distortion, warp, etc. before fabrication |
| ## Bolt |  |
|  | Bolt Hole |
|  | Spacing of bolt holes shall be as directed in the following table |

| Diameter of Bolt mm | Standard Pitch mm | Minimum Pitch mm | End Distance mm | Edge Distance mm |
| --- | --- | --- | --- | --- |
| 12 | 50 | 30 | 30 | 25 |
| 16 | 50 | 40 | 40 | 30 |

|  | Minimum pitch and end distance for lightweight steel shape shall be more than 3 times and 2.5 times a Bolt diameter respectively |
| --- | --- |
|  | Diameter of hole shall not be over 0.5 mm larger than bolt diameter. However, for anchor bolt 5mm clearance shall be allowed between bolt diameter and diameter of hole unless otherwise specified |
|  | Bolt hole shall either be drilled open or reamed after sub punching. Punching can only be permitted for a material thickness less than 13 mm |
|  | Rolled edge around a hole shall be removed |
|  | Position of a bolt hole shall be precise so that the center of all holes aligns |
|  | Protection against loosing of Nuts |
|  | Nuts shall be protected against loosing by concrete covering, double nuts or other proper means |
|  | Shear Bolt |
|  | Shear bolt shall be provided with washers to keep the nut outside of grip |
| ## Welding |  |
|  | Welding |
|  | Welder shall be an experienced or have an authorized qualification in Maldives. |
|  | Welding Machine |
|  | Arc welding machine shall be alternate or direct current type which provides sufficient and adequate current. |
|  | The field arc welding machine shall be provided with remote control for easy control of current. |
|  | Preparation |
|  | Welding shall be done as much downward as possible using a jig such as Rotary frame |
|  | Welding rod shall be always kept in a dry area and if necessary, dried by drying equipment. |
|  | Welding surface shall be free of water, scale or others injurious to welding work. Slag appeared on the created surface in the middle of welding shall be cleaned before starting again. |
|  | Fabrication |
|  | Welding edge shall be smoothed by automatic gas cutting or other proper finishes |
|  | Built - up |
|  | Jig shall be used to keep mutual position of materials in assembly |
|  | Temporary bolt hole for assembly shall be bored with approval of the Project manager |
|  | Proper amount of construction, predistortion or restraint shall be added to welding parts to attain precise finish dimensions and shape |
|  | Welding materials shall be properly met in fillet welds |
|  | Tack |
|  | Short bead shall be avoided for tack welding. The minimum length of tack welding shall be as follows. Plate thickness under 3.2 mm Bead length over 30 mm, from 3.2 to 25 mm- 40 mm |
|  | The end of joint, corner angle, beginning and ending point of final welding shall be avoided for tack welding |
|  | Tack welding as a part of final welding shall be perfectly done |
|  | Work |
|  | Type of welding rod, rod diameter, current, voltage and welding speed shall be selected in accordance with type of welding work |
|  | Order of welding and movement of rod shall be determined so as that there shall be no deformation after welds |
|  | Welding shall be carefully done in concealment in raining and strong wind |
|  | Finishes |
|  | Surface of welds shall be as smooth as possible and size and length of welds shall not be less than designed dimensions |
|  | Reinforcement of weld shall not exceed 0.1s + 1 mm (s: Designated size) in fillet welds |
|  | Welded parts shall be free of undercut, overlap, crack, blow hole, lack of welds, lack of weld settlement, rolled up slag or other defects |
|  | Crater at the end of bead shall be carefully heaped up and slag, sputter, etc. shall be completely removed after welds |
|  | Safety |
|  | Safe scaffoldings shall be provided for the field welds work |
|  | Welding facilities shall be such that there shall be no electric leakage of electric shock. There also shall be sufficient protection for fire |
|  | Electric shock protection device shall be used and also care shall be taken not to get suffocated or intoxicated by gas when welding in small area |
|  | Inspection |
|  | Welding parts shall be inspected before, during after welding in accordance with work schedule |
|  | Correction |
|  | Welding parts having injurious defects shall be removed and rewelded |
|  | When deposited metal gets cracked, at least 50 mm from the edge of crack shall be cut off and rewelded |
|  | When base metal gets cracked, it shall be replaced |
|  | Under cut parts shell be corrected by attaching deposited metal |
|  | Injurious deformation left on welding material shall be correct or reinforced |
| ## Transportation |  |
|  | Materials shall be marked for easy fabrication |
|  | Small items such as gusset plates, bolts, etc. shall be packed in adequate size, and the contents shall be identified |
|  | Material list shall be made before transporting so that material number, quantity, etc. shall be easily identified |
|  | While transporting materials, care shall be taken for preventing from defect |
| ## Erection |  |
|  | Erection |
|  | Erection procedure shall be prepared by the contractor and be approved by the Project manager prior to the erection |
|  | Material shall be stored on flat surface in order not to get distortion, twist or other defects. Correction shall be made to those distortion or twisted before erection |
|  | Horizontal reinforcement and bracing shall be placed and bolts are temporary tightened as trusses are put up |
|  | Connection of materials by bolts, etc. shall be made after distortion on plumb is thoroughly corrected |
|  | Temporary bracing or other reinforcement shall be placed to resist wind pressure or other loads erection |
|  | When heavy objects are placed on a horizontal element in the course of erection, they shall be reinforced with prior approval of the Project manager |
|  | Care shall be taken on all facilities so that there is no accident |
| - Masonry |  |
| ## Materials |  |
|  | Material used for masonry and plastering work, shall conform to Section 3 - CONCRETE WORKS. |
|  | Masonry work shall be done with cement bricks or blocks of approved quality unless specified otherwise |
|  | The blocks shall be free from excessive amounts of salt or other impurities and shall be inspected and approved by the Project manager |
| ## General |  |
|  | Execution Drawing Work shall be complied with this specification unless otherwise stated on particular Specification or Drawings. Any work not specified shall be discussed and directed by the Project manager. Execution drawing of block or brick alignment (inclusive of indication for hanging bolt, wood plug and conduit pipe), detail reinforcement, window opening, and another requirement shall be prepared and submitted for the Project manager |
|  | Stake-Board Stake-board shall be provided at each 5m in length and shall be inspected by the Project manager for the accuracy, firmness, and secureness. However, suitable ruler, plumb-bob and leveler shall be provided for minor performance of cement block and bricks. |
|  | Transportation and storing Care shall be taken for damage during transportation of materials and any defect of natural finished concrete blocks or bricks shall be rejected. Different size of material shall be stored separately and projected from dirt and other impurities |
|  | Curing Any shock or load shall not be applied until concrete mortar or other fills hardened. Corner, projection and top of cement block or brick work shall be protected from rain, dryness, cold, damage and stain by covering. Void between blocks or bricks shall not be intruded by rainwater |
| ## Cement Blocks / Bricks |  |
|  | Material Cement block shall be of acceptable quality low permeability blocks with no defects and sample shall be submitted for approval of the Project manager |
|  | Horizontal reinforcement for concrete block wall |
|  | Horizontal reinforcement shall be provided at end of wall adjoining to concrete column. Reinforcing bar shall be anchored into end block and column |
|  | Horizontal reinforcing bar for block wall shall be 6 dia. @ 600 mm and reinforcing bar for opening shall be 2 - 9 dia. with stirrup of 6 dia. @200 mm unless otherwise specified |
|  | Placing Blocks & Bricks |
|  | Cement blocks shall be saturated with water and joint shall be cleaned |
|  | Bonding mortar shall be used immediately after mix, and mixed mortar left for more than one hour shall be rejected |
|  | Vertical and horizontal joint of blocks shall be filled completely and suitable with mortar online shall not be moved or rearranged. Joint and surface of block of exposed finished block wall shall be cleaned immediately after joint is filled |
|  | In case concrete block wall is attached to structural concrete, block wall shall be placed before concreting structure |
|  | Mortar for joint shall be touched with steel trowel before hardened and exposed joint shall be finished with uniform width and planned without roughness or cavity |
|  | Height for placing block per day shall be maximum 1.2 m unless otherwise specified |
|  | Blocks shall be placed with cavity side under |
|  | Joints |
|  | The thickness of joints shall not exceed 10 mm and the joints shall be rated (13 mm dup.) when the mortar is still floor, so as to provide for proper bond for the plaster. Any mortar which falls on the floor from these joints or removed due to raking of joints shall not be reused. |
|  | Lintel |
|  | Lintel shall be reinforced concrete as approved or directed by the Project manager |
|  | Main reinforcing bar shall be anchored more than 40D (40 x diameter of the bar) at both end |
|  | In case lintel is prefabricated, shop drawing shall be submitted for approval of the Project manager |
|  | Frame of Opening |
|  | In case frame is temporarily installed before placing of blocks, frame shall be firmly placed, and joiner shall be bonded with mortar as placing each block at side and top of frame |
|  | In case frame is installed after placing of blocks, joiner shall be bonded with additional mortar at space or every two blocks or more |
|  | Back of frame shall be filled and compacted with mortar by providing shuttering board. |
|  | Wood plug and anchor bolt shall be covered with mortar or concrete |
|  | Piping |
|  | Principally, piping shall not be placed in block wall unless piping block is in use |
|  | In case electric conduit pipe is placed in cavity of concrete blocks, care shall be taken not to obstruct reinforcing bar, and cavity shall be completely filled |
|  | In case chipping and piping on face of blocks is unavoidable, performance shall be conforming to instruction of the Project manager |
|  | Joiner and supporter for exposed piping shall be buried at joint which back is filled or otherwise approved by the Project manager |

| Use | Cement | Slaked Lime | Sand | Joint Width |
| --- | --- | --- | --- | --- |
| Ordinary Brick and Blocks | 1 | 0.2 | 2.8 | 10 |
| Exposed Bricks and Blocks | 1 |  | 2 |  |
| Exposed Cavitied Blocks | 1 |  | 1 |  |
| Furnace and smokes stack | 1 | 0.5 | 3 |  |

|  | Placing |
| --- | --- |
|  | Brick shall be cleaned and suitably saturated in water before use |
|  | Binding mortar shall be placed sufficiently compacted |
|  | Bricks shall be placed in such a way as to form alternate courses of headers and stretchers. Maximum height of placement shall not exceed 1.2 m per day. |
|  | All perpends shall be kept strictly true and square |
|  | Lintel |
|  | Lintel shall be reinforced concrete or precast concrete as shown on the Drawing, unless otherwise specified, or approved or directed by the Project manager |
|  | Main reinforcing bar shall be anchored more than 40D (40 x diameter of the bar) at both end |
|  | In case lintel is prefabricated, shop drawing shall be submitted for approval of the Project manager |
|  | Frame of Opening |
|  | In case frame is temporarily installed before placing of bricks, frame shall be firmly placed and joiner shall be bonded with mortar as placing each brick at side and top of frame. |
|  | In case frame is installed after placing of bricks, joiner shall be bounded with additional mortar at space of every two blocks or more |
|  | Back of frame shall be filled and compacted with mortar by providing shuttering board. |
|  | Wood plug and anchor bolt shall be covered with mortar or concrete |
| - Plastering |  |
| ## General |  |
|  | All masonry walls shall have smooth finished cement plaster on both sides with a surface setting coat of neat cement applied within an hour of the completion of rendering |
|  | Cement rendering to floor shall be same as above |
|  | Conmix Megaflow MP (or similar) must be used in all interior and exterior plaster works |
| ## Materials & Storage |  |
|  | Plaster materials which are affected by moisture such as plaster and cement shall be stored properly |
|  | Materials used for plastering shall conform to those of Section 3 - Concrete Works. Grading of sand, however, shall be as in table below |

| Grading of sand | Mortar plastering | Plastering |
| --- | --- | --- |
| 5mm sifting thorough 100% 0.15mm sifting less than 10% | for first coat for finish coat | for first coat and dubbing out |
| 2.5mm sifting through 100% 0.15mm sifting less than 10% | for finish coat | for second coat |

|  | White cement or filler or similar shall confirm to the requirements of Portland cement, BS.12 |
| --- | --- |
|  | Conmix Megaflow MP or similar (approved by the Project manager) shall be used as a admixture for all internal and external plastering. The amount of admixture shall be such that it affects mortar strength very little |
| ## Mixing ratio |  |
|  | Mixing volume ratio of mortar shall be as in table below: |

| Base | Area of application | first coat cement: sand | Dabbing out cement: sand | Finish coat cement: sand |
| --- | --- | --- | --- | --- |
| Masonry | Floor | - | - | 1:2 |
| blocks | Interior wall | 1:2 | 1:3 | 1:3 |
|  | Exterior wall | 1:2 | 1:3 | 1:3 |

| ## Thickness of Coating | The standard thickness of the coatings shall be as in the table below unless otherwise indicated on the Drawings or instructed by the Project Manger |
| --- | --- |

Standard thickness of coating (mm)

| Base | Area of application | First coat | Dubbing out | Second coat | Finish coat | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Masonry | Floor | - | - | - | 25 | 25 |
| block | Interior wall | 10 | - | 10 | 5 | 25 |
|  | Exterior wall | 10 | - | 10 | 5 | 25 |

| ## Finish |  |
| --- | --- |
|  | Type of finish and work schedule |

| Type | Work Schedule | Notes |
| --- | --- | --- |
| 1.Trowel finish | Shall be applied flat by metal trowel Shall be finished by pressing with t trowel. | Before applying second coat, h corner and edge shall be screed well. |
| 2. Wood trowel finish | Shall be applied and finished flat with wood trowel |  |
| 3. Brush finish | Shall be applied flat by wood trowel. Shall be blushed | Care shall be taken not to wet brushes. |
| 4.Spray finish | Cracks in base shall be fixed. Shall be sprayed more than twice. | Mixing for spraying on exterior wall cement: (Plaster & pigment ≤ 1) spray shall be applied perpendicular to the surface. |
| 5. Cement wash | Opening and projections in base shall be fixed Cement water solution shall be applied with brush |  |
| 6. Coloured mortar finish | Shall be applied and finished with mortar of specified colour on base | Mixing colour mortar shall comply with that of spray finish |
| 7. Scratch Surface finish | Mortar with rough finish materials shall be applied Shall be scratched by metal comb after checking dryness. | Mixing shall be cement ≥ (plaster + pigment) |
| 8. Floor plastering | Cement paste shall be smoothed. Hard mortar shall be applied with trowel. | Dry mortar shall be hammered and screeded after checking dryness. |
| 9. Floor concrete polish finish | Concrete shall be plate hammered smoothed by vibrator. Shall be polish-finished by wood trowel or steel trowel | Agent of hardening and colouring shall be applied according to schedule and direction of the Project manager. |

| ## Preparation of setting bed |  |
| --- | --- |
|  | Deformation, unevenness on the wall or floor of concrete or concrete block shall be corrected |
|  | Concrete surface which is too smooth to plaster shall be roughened with chisel, etc. |
|  | Dry backing of concrete or block or dry base coat of cement mortar or plaster shall be properly wetted. Backing and base coat shall be cleaned before plaster |
|  | Looseness on backing or plastering face shall be immediately corrected |
|  | Joints and corners where cracks are likely to occur must be properly dealt with and approved by the Project manager |
| - Carpentry & joinery |  |
| ## Materials |  |
|  | Timber shall be in accordance with the requirements of BS 1186 ‘Quantity of Timber and Workmanship in Joinery’, Part 1, ‘Quality of Timber’ |
|  | Timber and timber products shall be subject to the inspection and approval of the Project manager |
|  | Timber shall be seasoned to stable moisture content compatible with the finished use, straight and true and free from wind, warp and distortion and in lengths suitable for the members required |
|  | All timber shall be in long lengths and laps, scars or splices shall be over a bearing surface. Where obtainable, finishing timber exposed to view shall be in single lengths |
| ## Preservation of Timber |  |
|  | Where preservative treatment is specified, the timber is to be of the correct moisture content and free from surface moisture content and dirt. |
|  | All rafters, purlins, framing scribe pieces, wall plates, trusses etc. shall be treated with approved timber preservative oil. No extra payment shall be made for such coating and will be considered inclusive in the rate of the respective item in the BOQ |
|  | Treatment shall be carried out after all cutting and shaping is completed |
| ## Hardware |  |
|  | Hardware shall be standard quality and samples shall be submitted to the Project manager for approval |
|  | All hinges shall be stainless steel or brass and shall be approved by the Project manager |
|  | The dimensions and quality of hardware shall meet the requirements and shall not be rested, deformed or defective |
| ## Dimensions and Finish |  |
|  | All dimensions of timber given are finished dimensions |
|  | All elements and others of structural nature which are exposed must be machine planed to a smooth finish |
|  | All unexposed timber shall be machine planed to a rough finish |
|  | All joinery work shall be dressed on all four sides and hand dressed where necessary and sanded to all exposed surfaces. All arises in any way accessible shall be sanded and smoothed off |
| ## Workmanship |  |
|  | All connections whether nailed, screwed, glued, morticed or dove-tailed shall be accurately made and properly executed to provide sound, satisfactory connections for the class of work required |
|  | Timbers containing defects or distortions shall not be used |
|  | All joinery shall be manufactured by skilled tradesman with accurate tolerances and set out and with tools, jigs, machines, and equipment appropriate for the work |
|  | Assembly of the joinery units and joinery frames, etc. shall be by means of glued connections appropriate to the work - mortice and tenon, housing and doweling, etc. where practicable including the use of glued blocks wherever required. Nailing, screwing shall only be used with prior approval of the Project manager; corrugated fasteners shall not be used for effecting connections |
| - Ceiling |  |
| ## General Requirements |  |
|  | Contractor shall examine all other sections of the specifications for requirements which affects work of this section whether or not such work is specifically mentioned in this section |
|  | Contractor shall coordinate work with that of all other trades affecting, or affected by work of this section. Contractor shall check electrical, air conditioning drawings to ensure proper integration and fitting of light fittings, ceiling difference and other openings in the ceilings for access panels of Heating & Air Conditioning system |
| ## Scope |  |
|  | Contractor shall provide all labour, equipment, services and transportation required to complete all acoustical ceiling work as shown on drawing, as specified herein, or both and see Drawings and schedules for details location |
| ## Specifications and Standards |  |
|  | The ceiling system shall conform to British Standard Specifications 476: Part 5, Part 6 and Part 7 |
| ## Samples |  |
|  | Representative samples of ceilings tiles / sheets shall be submitted for Project manager’s approval before materials are purchased. Submit samples of suspension system parts showing materials, finish, and methods of connection along with tiles. Materials delivered to the job site shall conform to the approved samples |
| ## Manufactures |  |
|  | Suspension system shall be the products of reputable manufacturer and the suspension system shall fit to the specified acoustic tiles |
| ## Workmanship |  |
|  | Acoustical units shall be delivered in manufacturer’s original, labeled, unopened cartons, suitably stored within the building and protected from damage until ready for installation |
|  | Installation of acoustical ceiling shall be done by approved or experience ceiling tile Contractor |
|  | Before commencing acoustical ceiling work, inspect all surfaces and structural element to receive work of this section to assure that conditions are suitable for installation of the work |
|  | The building shall be glazed and have a relative humidity not exceeding 70% before units are delivered to the site of work is begun |
|  | Acoustical ceiling work shall be coordinated with that of related trades. Acoustical ceilings shall be suspended from structural elements only, completely independent of all mechanical and electrical system and their suspension |
|  | Suspension system shall be manufactured by or approved by ceiling materials manufacturer. Manufacturer’s standard recommended clips shall be used for attachment to structural framings. Power driven eye pins will be permitted in concrete, but each pin shall be tested after installation for 150 pounds load (weight of one workman) |
| - Aluminium doors & windows |  |
| ## Aluminum Doors & Windows |  |
|  | Aluminum Doors and Windows shall generally conform to relevant British Standard Specifications |
|  | The sashes and frames shall be assembled from extruded profiles made of Aluminum alloy conforming to British Standard and distinguished for their out-standing anti-corrosive features and durability |
|  | The auxiliary components in sashes as locks, pivots, sliding gear etc. shall comprise of stainless steel or resisting materials |
|  | The tolerance are to be as follows: a) Inside width of frame 3mm Maximum b) Inside height of frame 3mm Maximum c) Depth of frame 2mm Maximum d) Opposite side, Inside distance 2mm Maximum |
|  | The performance - associated requirements are 1) Strength (resistance to wind pressure and other forces applied in use) 2) Air tightness or ability to cut out drafts. 3) Water - tightness against rain or dew. 4) Sound arresting effect to (shut off noise from outside as well as inside). |
|  | All surfaces shall have an anodized protective surface layer of minimum 25 Micron thickness. |
|  | Glazing shall be done as specified by the Project manager. Glass shall be tinted, clear or wired as specified in the drawings. Thickness shall be according to the size of panels as given hereunder |

| Not exceeding 1 sq. ft. | 2mm |
| --- | --- |
| Exceeding 1 sq. ft. but not exceeding 2 sq. ft. | 3mm |
| Exceeding 2 sq. ft. but not exceeding 4 sq. ft | 4mm |
| Exceeding 4 sq. ft. but not exceeding 6 sq. ft | 5mm |
| Exceeding 6 sq. ft. | 6mm |

|  | Prior to import and / or purchase of the Aluminum Doors and Windows, the relevant specification of the manufacturer’s perfectly along with samples to be submitted to the Project manager for approval. This clause shall not be contravened on any account |
| --- | --- |
|  | The fitting shall be done with utmost care not to spoil the finishes given by the manufactures, and any cleaning done shall be done with cleaners etc. as specified by the Manufactures |
|  | The Contractor shall provide all items, articles, materials, operations, mentioned, or scheduled on the drawings, including all the labour materials, including fixing devices, equipment and incidentals necessary as required for their completion |
|  | The Contractor shall submit shop drawings and/or samples of each type of doors, windows, railings and other items of metal work to the Project manager for approval. The shop drawings shall show full size sections of doors and windows etc. thickness of metal, details of construction hardware as well as connection of windows, doors and other metal work to adjacent work |
|  | Aluminum doors and shutters shall be manufactured by an approved manufacturer and shall be of sections, sizes combination and details shown on the drawings. The frame member shall be one piece, corners shall be electrically welded, ground smooth and true and glazing bare shall be threaded or interlocked as approved by the Project manager |
|  | Glazing for doors and windows shall be of specified thickness and of approved quality and shall conform to specification of glazing. Fixing for glazing shall be done with aluminum Snap-On beading as per detail drawing and instructions. Necessary continuous rubber gaskets of approved make shall be provided |
|  | Colour for doors and windows shall be approved by the Project manager |
| ## Aluminum louvers |  |
|  | Samples shall be submitted for approval |
|  | All metal louvres shall be installed according to manufacturer’s instructions |
|  | All units shall be installed plum, well fitted and securely attached to supporting frames |
| - Roofing |  |
| ## Roofing Material |  |
|  | Steel roofing shall be Lysaght trim deck Roofing sheet or equivalent roofing sheets, of standard thickness fixed to supports with approved fasteners as per manufacturers recommendations or as shown on the Drawings. Sheets shall have approved side laps with the top sheet laps facing away from the prevailing weather. |
|  | Roof sheeting shall project a minimum of 50mm into gutters with the maximum projection into gutters leaving access for cleaning. Flashing are to be manufactured from like or compatible materials and shall cover the sheets a minimum of 100mm. Attachments and joints are to be made with mechanical fasteners and sealant approved by the sheet manufacturer |
|  | Packs of sheets shall be kept dry in transit and on site to prevent water and/or condensation being trapped between adjacent surfaces. Packs of sheets standing on site shall be stored clear of the ground. Sheets shall be handled using clean dry gloves |
|  | The roof and gutters shall be swept clean of all debris using a soft broom at least at the end of each day’s work and particularly on the completion of fixing |
|  | The job shall be left clean and, in a weather, tight condition |
|  | All sheeting shall be fixed in a workmanlike manner and in accordance with the manufacturer’s recommendations |
|  | Contractor must submit a sample of roofing sheet for approval or supply manufacturer’s warranty to verify the quality if the product |
|  | Color of the roofing sheets has to be approved by the Project manager |
| - Finishes |  |
| ## General |  |
|  | Ceramic Tile shall comply with British Standard specification No. 1281 and shall be approved sizes as shown on Drawings and the product of a reputable manufacturers approved by the Project manager |
| ## Ceramic and Vitreous Tile Materials |  |
|  | Ceramic and Vitreous clay Wall Tiles |
|  | All tiles for wall installation shall have cushion edge, impervious porcelain, and highly glazed surface. Colours shall be as selected by the Project manager and shall include trimmers, corner pieces, bullnose and all other special shapes indicated or required. All this shall be free from flaws, cracks, and crazing |
|  | The contractor shall submit samples of the selected type of tile or when at the request of the Project manager |
|  | Color and design of the tile will be approved by the Project manager |
|  | Floor Ceramic and Vitreous Tiles |
|  | Non-slip ceramic tile for shall be used on all floor locations. Floor tiles shall be specially prepared for floor use but shall have all the qualities of ceramic tiles listed above for wall use. |
| ## Mortar Materials |  |
|  | Standard brand of light gray or white Portland Cement as specified in drawings, conforming to current British Standard specifications shall be used |
|  | Sand: shall be clean, sharp, river sand, conforming to British Standard Specifications and graded fine to coarse within the following limits: 100% passing 8 sieve, 90% to 100% passing 16 sieve, 60% to 90% passing 30 sieve, 25% to 55% passing 50 sieve and 0% to 15% passing 100 sieve. |
| ## Cement Colour |  |
|  | Dry cement colour, chemically inert, non-fading, alkali fast, mineral pigment, as approved shall be used wherever refinished |
| ## Waterproofing |  |
|  | Floors and walls of toilet areas, corridors and planter boxes shall be treated with Conmix Moyaproof HF water proofing coating or similar. The waterproofing material / compound shall be approved by the Project manager prior to application |
| ## Installation Requirements |  |
|  | As far as possible, tile lay out work should be in such a way that no tile less than half size occurs. Align joints in wall tile vertically and horizontally except where other patterns are shown or specified, align joints in floor tiles at right angles to each other straight with walls to conform to the patterns selected. Verify locations of accessories before installing tiles. Work shall be coordinated with plumbing and other trades before starting of tile work |
|  | Installation of ceramic and vitreous tile shall be in accordance with manufacturer’s instructions |
| ## Floor Tile Installation |  |
|  | All ceramic and vitreous clay tile floors shall be laid by using Conmix C-500 Tile Adhesive or equivalent. Concrete surfaces shall be cleaned and surface of concrete shall be wetted prior to placing of setting mortar |
|  | When mixed with water, the mortar mix shall be of such consistency and workability as to produce maximum density. Determine consistency by stroking the mortar surface with a trowel. Whereof correct consistency, the trawled surface readily assumes a smoothed, slickened appearance |
|  | Spread setting bed mortar and screed to provide smooth, dense beds with true planes pitched to drains. The thickness of bed shall be such that the floor tile will finish flush with adjacent finished flooring, but bedding shall have average thickness of 38mm |
|  | After bed has set sufficiently to be worked over, trowel or brush a thin layer, 3mm in thickness, of neat Portland cement paste over the surface of the back of tile. Do not prepare larger setting bed than can be covered with tile before the mortar sets |
|  | Press tile firmly into the bed tapping with wood blocks to obtain firm bedding of total tile area and a smooth top surface. All tile shall be properly aligned with straight joints in even widths. Joints width shall be determined by spacers on ceramic tiles. Tamping shall be completed within one (1) hour after placing tile. Adjust work out of line within this period |
|  | Tiles shall be fitted closely around pipes running through walls and floors. Pitch floors to drains |
| ## Wall Tile Installation |  |
|  | All wall tiles shall be laid by using an approved Conmix C-500 adhesive or equivalent compound. Concrete surfaces shall be cleaned, and surface of concrete shall be wetted prior to placing of setting mortar |
|  | Setting bed of tiles shall be done with cement slurry. The thickness of slurry bed shall be 3mm thick minimum for setting tiles and walls |
|  | Installation of tiles shall be in accordance with standards and applicable requirements previously specified for floor tile |
|  | Tiles shall be installed in perfect vertical plumb and as per the pattern and joints as shown on drawings |
| ## Grouting |  |
|  | Grouting shall not commence for at least 24 hours after placing of tiles |
|  | Grout for floor and wall ceramic and vitreous tiles shall be waterproof, tile grout approved and added as directed by the Project manager |
|  | Grout mixed to a creamy consistency in accordance with manufacturer’s directions shall be used for joint filling. Maximum width of joints shall be 3mm |
|  | Force maximum grout into the joints with trowel. Before grout sets, strike or tool joints to base of cushion and fill all skips and gaps. Do not permit setting bed materials to show through grouted joints. Cure grout joints by maintaining damp condition for three (3) days by sponging down, or other methods approved by the Project manager. Allow floors to set 48 hours before permitting ordinary foot traffic |
| ## Defects in Tiles and Tile Laying |  |
|  | The surface of all tiled floors shall be perfectly in level and shall be executed by experienced workers in the field of tile laying. A sample panel of laid tiles of each type shall be approved by the Project manager before commencement of tile laying. Chipped or damaged tiles installed by the Contractor shall be rejected and shall have to be replaced by the Contractor at his own cost and risk |
| ## Guarantees |  |
|  | Manufacturer shall be providing his standard guarantees for work under this section. However, such guarantees shall be in addition to not in lieu of all other liabilities which manufacturers and Contractor may have by other provisions of the Contract Documents |
| - Plumbing |  |
| ## General |  |
|  | The materials used and workmanship shall be of highest quality and grade unless otherwise specified shall conform to the latest specifications of British Standards and Codes of Practice “Water Supply “Sanitary. Pipe Work “Building Drainage “Surface Water and Sub- Soil Drainage” or similar and applicable to details and work indicated on the Drawing and Bill of Quantities. In case of any discrepancy / ambiguity the decision of the Project managers shall be final, and the contractor will act and perform accordingly |
|  | The work shall be executed strictly in accordance with the rules and regulations set by the relevant local authority of the Maldives |
|  | The Contractor shall be responsible for obtaining the necessary approvals and test certificates from the concerned departments of Maldives |
|  | Plumbing work shall be carried out by licensed plumbers and shall produce the copy of the license along with the tenders, or approved by the Project manager |
|  | Any damage done by the Contractor to any existing work during the course of execution of his work, shall be made good by him at his own cost. Failing which it shall be get done by the Project managers at Contractor’s risk and cost |
|  | The Contractor shall be responsible to connect the drainage and water supply to the mains and to obtain the necessary approvals and certificates from the relevant authorities of the Maldives |
|  | All connections to mains and meter installation shall be arranged by the Contractor and payment of fees thereof, if any, shall also be made by him |
|  | The Contractor shall be responsible for the watch and ward of all fittings until the Works is fully completed and handed over to the owner |
|  | The levels, measurements and other information concerning the existing site as shown on the drawings or as described as are supposed to be correct. The Contractor shall, however, verify them by himself and no extra claim whatsoever shall be entertained on account of the errors or omissions in such matters or on account of the descriptions turning out to be different from what was excepted. |
|  | The Project manager shall instruct the Contractor to purchase and use such materials of particular make or from particular source as may in his opinion be necessary for proper and reasonable compliance with the specification and execution of the Works |
|  | After all plumbing fixtures and equipment have been set ready for use, and before the Contractor leaves the job, he shall thoroughly clean all fixtures installed by him, removing all plaster, stickers, rust stains and other foreign matter of discolouration on fixtures, leaving every part in acceptable condition and ready for use to the satisfaction of the Project managers |
| ## Drawings and Information Required |  |
|  | The Contractor shall submit shop drawing for the entire installation including installation details for all items required or asked for approval of the Project manager |
|  | Approved by the Project manager of shop drawing for any material, apparatus, devices and layout, shall not relieve the Contractor from the responsibility of furnishing same of proper dimension, size, quantity and all performance characteristic to efficiently perform the requirements and intent of the Contract Documents. Such approval shall not relieve the Contractor from responsibility for errors of any sort in the shop drawing. |
|  | If the shop drawings deviate from the contract Documents the Contractor shall advise the Project managers of the deviations in writing accompanying the shop drawings including the reasons for the deviations. At the start of the Project the Contractor shall periodically and thereafter submit to the Project managers list of all shop drawings which will be submitted in the course of the project. The list shall show the disposition of each item including date of submission approval etc. The list shall be kept up to date through the entire course of construction |
| ## As-Built Drawings |  |
|  | During Construction, the Contractor shall keep an accurate record of all deviations between the work as shown on the Contract Drawings and that which is actually installed |
|  | The Contractor shall secure from the Project managers after approval of his Shop Drawing a complete set of drawing and note changes thereon in ink |
|  | The Contractor shall make a complete record of all changes and revisions in the original design which exist in the completed work |
|  | The cost of furnishing above prints and preparing these for record “shall be deemed to be include in the tendered cost and its effects spread over other items of work, and as such item shall not be a subject to payment”. When all revisions showing the work as finally installed the corrected Original Transparencies shall be submitted to the Project managers before final payment for the completed work will be made. |
| ## Operating and Maintenance Instructions |  |
|  | Three sets of operating and maintenance instruction covering completely the operation and maintenance of all plumbing equipment, controls, heaters, pumps and the like shall be furnished to the Owner, by the Contractor |
| ## Tests |  |
|  | The entire system of drains, waste and vent piping inside and outside the building shall be tested by the Contractor under a water test, which shall include the entire system from the lowest point to the highest pipes above the roof |
|  | The water test shall be made in accordance with all local requirement. Every portion of the system shall be tested to a hydrostatic pressure equaling to latest 15 feet head of water. After filling, the Contractor shall shut off water supply and shall allow it to stand 2 hours under test during which time there shall be no loss or leakage |
|  | The Contractor shall furnish and pay for device, material supplies, labour and power require for all tests. All tests shall be made in the presence and to the satisfaction of Project manager |
|  | Defects disclosed by the test shall be repaired or if required by the Project manager defective work shall be replaced with new work without any extra charge to the Owner. Test shall be operated as directed until the work is proved satisfactory |
|  | Fixture shall be tested for soundness, stability of support and satisfactory operation |
|  | The Contractor shall notify the Project manager at least one week in advance of making the required test, so that arrangements may be made for their presence to witness the test |
|  | Equipment shall be tested in service and the Contractor shall demonstrate that the equipment performs the work intended for it and that it complies with the requirement of these specification for such equipment, to the satisfaction of Project managers |
|  | The rates shall include for all costs associated with tests |
|  | Timely notice shall be given by the Contractor to the Project manager of the hour of tests |
| ## Work in Common Piping |  |
|  | Material |
|  | Piping and fitting material shall be P.V.C, Hard Impact P.V.C. or High Temperature P.V.C & shall comply with requirements of Maldives Water & sewerage Company (MWSC) and relevant authorities. |
|  | Materials for the piping and service requirements shall basically conform to the service pressures encountered |
|  | Providing Drawings and Manuals |
|  | The Contractor shall submit one set of originals and further two copies of layout drawings to the Project manager after completion of the Works. These drawings must give the following information: (a) Run of all piping and diameter on all floors and the vertical stacks. (b) Location and sizes of all control valves, access panels and other equipment. (c) IL of all manholes including IL at our files. |
|  | No completion certificate will be issued until the drawings are submitted. The Contractor shall submit to the Project manager for approval, samples, shop drawings, manufacturer’s drawings, equipment characteristics and capacity data etc. of all equipment, accessories devices etc. that he proposes to use in the installation |
|  | Samples |
|  | The Contractor shall provide samples of all sanitary fittings, pipes and specials, man- hole cover and frames, gratings and water supply pipes and fittings etc., and shall be deposited with the Project manager (which will be returned to the Contractor at the completion of the Works) and shall obtain approval from the Project manager before using in the Works. Any material rejected by the Project manager shall be removed from the site within 24 hours of rejection. |
|  | Existing pipes |
|  | The site shall be examined for field drains and those, when found, shall be either entirely removed or diverted, trenches filled with dry earth in 200mm to 300mm layers and consolidated as directed by the Project manager |
|  | Spare Parts |
|  | Necessary spare parts of the plumbing equipment for the one (1) year operation shall be supplied by the Contractor |
|  | Excavation |
|  | All excavations shall be timbered to the satisfaction of the Project manager and the type of timber shall be suitable to the kind of earth encountered. Fixing of timber and removal after completion of work shall be done as directed by the Project manager |
|  | Should any water accumulated in the trenches, headings or other excavation, the Contractor shall do such work as may be necessary to drain away the accumulated water and shall install pumps as may be required to keep the excavation and trenches dry. The Contractor shall ensure that the flow water in trenches or excavation does not injure or remove cement or aggregate of any concrete that has not set. No subsoil water shall be discharged into open drains or sewer at the site |
|  | In refilling trenches after excavation this should be done in layers of 150mm after consolidating each layer. Special care shall be to see that the earth is packed uniformly and no injury to the pipe |
|  | Rates for excavation should include for backfilling in consolidated layers where necessary and as directed by the Project manager |
|  | Piping |
|  | The Contractor shall, as soon as possible after the award of the contract, prepare and submit to the Project manager for approval, working drawings showing exact locations and pipe runs for all pipework, the layout and setting up of equipment and the connection of piping to the equipment. Such drawings shall include details and methods of supports, anchors and sleeves etc. |
|  | Pipe runs shown in the drawings are approximate and intended to indicate the general run and locations only. The exact locations of all pipework shall be determined on Site. |
|  | All pipes, fittings etc. shall be kept closed against moisture and foreign matters when stored at site and during installation |
|  | All pipes shall be fixed clear of one another and be so arranged as to provide easy access for maintenance and repair |
|  | All plumbing work shall be carried out by suitably qualified plumbers in accordance with the British Code of Practice and Regulations and requirements of related Authorities |
|  | Materials for the piping and service requirements shall basically conform to the service pressures encountered |
|  | Each part of the installation of the plumbing work shall be completed in all details as shown in the drawings or as specified and provided with all necessary control valves, etc. that will be necessary for their satisfactory operation |
|  | All piping shall be run plumb, and straight and parallel to walls, except drain line which shall pitch 6mm per 300mm in the direction of flow |
|  | Pockets, unnecessary traps, turns and off-sets shall be avoided. When traps or pockets are unavoidable, they shall be valved drains |
|  | Piping installed on the concrete slab shall be firmly fixed or anchored to the floor with packing to prevent damage to pipes. Pipes shall not be bent with bender where cross with another pipe or change to upward |
|  | Where pipes are to be laid directly in the ground, bed shall be sufficiently compacted, necessary protection for piping shall be taken |
|  | Backfill shall be done after the approval of the Project manager in such a manner not to damage the pipeline and shall be restored to the original stage |
|  | Where pipes penetrate through waterproof part or fire partition or fire wall, pipe sleeves shall be provided and clearance between pipe sleeve and pipe shall be filled with caulking material approved by the Project manager |
|  | Pipes, fittings, valves and accessories shall be thoroughly cleaned, both internally and externally before installation and shall be cleaned before putting into service |
|  | Plumbing work shall be completed in accordance with the details shown on the Drawings or as specified and provided with all necessary control valves, etc. that will be necessary for their satisfactory operation |
|  | All pipes shall be cut square and true to the pipe axis by means of suitable tools without reducing pipe diameter and cut ends shall be finished smooth. Before making connections, chips, dirt and other foreign matter shall be removed from inside interior of each pipe. Fixing of hangars and embedding of pipe sleeves shall be carried out without delay along with the progress of the work where required |
|  | Pipe connections for the water supply system shall be by union type for pipes of 50mm diameter and less and for pipework above 50mm diameter, connections shall be made by means of appropriate socket fitting etc. Jointing shall be generally by means of solvent cement according to manufacturer’s instructions |
|  | Vertical pipe shall be braced at more than 2 point in every story |
| ## Water Supply Work |  |
|  | Materials |
|  | Pipes, joints and fittings for water supply work shall be high pressure P.V.C. |
|  | Materials and workmanship shall comply with the local water supply authority requirements |
|  | Spacing of supports |
|  | Support spacing for P.V.C pipes shall be as follows |

| Nominal Dia. | up to 40 | more than 50 |
| --- | --- | --- |
| Space (m) | 1.2 | 1.5 |

| ## Drainage Work |  |
| --- | --- |
|  | General |
|  | High Pressure P.V.C pipe and fittings shall be used for all drainage work including vent pipes |
|  | Joints shall be made by the cold-jointing method, and the pipe interior shall have not offset at the joint interfering with the flow. Joint adhesive shall be good quality and shall not be affected by heat and shock |
|  | Where horizontal drain branch joints the main, such branch shall be connected to the main in a substantially horizontal position and at an acute angle of not more than 45 degree to the main in all cases |
|  | Vent stack pipes |
|  | Vent pipe shall be vertically branched out upward from a horizontal drain branch pipe or other appropriate point. Horizontal branching of the vent pipe shall be done on approval of the Project manager |
|  | Where vent pipes on each floor are to be connected to the vent stack, all connections shall be made at least 150mm above the respective overflow edges of fixture on that floor. |
|  | The provision of the preceding item shall also apply to the connection of vent stack vent pipe. |
|  | Vent stack shall be connected to the waste stack or soil stack at the lowest part to stack pipe |
|  | Where vent pipe is to be connected to the horizontal drainpipe, such angle shall be more than 45 degree to upward |
|  | Vent stack shall be extended 600 mm from the top of the roof or lead to the wall and top of pipe shall be covered with vent cap |
|  | Spacing of Support |
|  | Spacing for support shall conform to the section of Water Supply Work item of spacing. |
| ## Laying of Pipes | A detailed piping layout drawing for the drainage works, based on the existing site conditions shall be prepared by the contractor and approved by the Project Manager prior to any pipe laying works. |
|  | The pipes shall be laid in accordance with the lines and levels in the drawings approved by the Project Manager. |
| ## Laying of sewer water Mains |  |
|  | All mains shall be laid on a good solid, bottom to prevent subsidence and consequent fracture |
|  | Mains running under buildings, if unavoidable, shall be completely surrounded by 150 mm of concrete |
|  | In case of mains passing through a well, the weight of the latter shall be carried by a lintel or a suitable relieving arch |
|  | All rising mains shall be properly plugged to all wall brackets at regular intervals as given in the drawings |
|  | All mains shall be concealed inside wall as far as possible except for vertical sewer mains, cleaning doors shall be provided in the walls whenever necessary and as directed by the Project manager |
| ## Sewers |  |
|  | After completion of the pipe laying and connection works, the pipe shall be tested in length between manholes in the following manner:- |
|  | In the lowest manhole/intercepting trap as the case may be, a plug shall be inserted in the pipe. The disc in the pipe at the upper manhole shall be fitted with a filling pipe with a right-angle bend and an air cook. The pipeline shall then be filled with water by means of the pipe connection on the upper disc. The air cock on the upper disc shall be kept open white the pipeline is being filled to permit the escape of air. When the pipes are filled with water and air excluded, the air cock shall be shut and the water shall be poured into conical filler, attached to the filling pipe until the water remains in the filter. The filling pipe shall then be raised and fastened so that the height of surface of the water in the filler above the invert of the pipe is 1828 mm which will be usual test pressure for S.W pipes. If the water level does not fall more than 16mm (12mm) in a length of 91.4 meter the test may be considered satisfactory. The Contractor shall rectify any defective works at his own expense. |
| ## P.V.C Pipes |  |
|  | Manufacturer’s instruction should be followed for all PVC piping works. Pipes to be used for water mains shall where specified have integral rubber ring joints when solvent cement joints are specified, a sufficient number of expansion/contraction joints shall be incorporated in the length of mains to allow for variation of temperature to the recommendation of the pipe manufacturers. |
|  | These pipes shall be effectively protected from the direct rays of sun immediately after they are laid and until permission is given for the trenches to be refilled by the Project manager. Subject to such permission being obtained, trenches shall be refilled without delay. Final connection at a fixed point shall be deemed unto the majority of the length of the pipeline has been covered by backfill in order to reduce the effect of expansion and contraction caused by temperature variations. |
| ## Bends & other Specials |  |
|  | In fixing bends care shall be taken to see that the axis of the bend is truly vertical or horizontal as the case may be and the spigot of the bend is well in the socket of the pipe with which a joint has to be formed. The Contractor shall be called on to replace any faulty work at his own expense. |
| ## Flanged Joints |  |
|  | All flanged joints shall be made by painting the faces of the flanged with red lead freely and bolting the flanges evenly on all sides. A thin fiber of lead wool may be used in making the joints watertight when facing of the flanges is not true. Rubber insertions may be used with approval. Sewage resistant rubber insertion to be used for sewer lines |
| ## Support for P.V.C Pipes |  |
|  | When P.V.C pipelines incorporate metal valves or other heavy fittings, it is essential to support the valves directly rather than allowing their weight to be carried by the P.V.C pipe and support shall be placed on either side of the fittings mentioned above. Molded plastic fitting also should be supported. |
|  | Maximum allowable horizontal support distance for P.V.C are given below |

| Nominal before | 12 mm (1/2”) | 18 mm (3/8”) | 25 mm (1”) | 32 mm (1¼”) | 38 mm (1½”) | 50 mm (2”) |
| --- | --- | --- | --- | --- | --- | --- |
| Support distance | 533 mm (1’9”) | 616 mm (2’0”) | 686 mm (2’3”) | 764mm (2’6”) | 840 mm (2’9”) | 915 mm (3’0”) |
| Nominal bore | 75 mm (3”) | 100 mm (4”) |  |  |  |  |
| Support distance | 1220 mm (4’0”) | 1290 mm (4’6”) |  |  |  |  |

|  | For vertical installation supports, distances shall be doubled |
| --- | --- |
| ## Sewer Pipe Specials | All ‘P’, ‘S’, ‘I’ junctions bends etc. required shall be furnished and set without extra charge and shall confirm to the pipe specifications as to quality. |
| ## Air Valves | These valves to be fitted as per drawings and Bill of Quantities shall be tested and accompanied by a certifying their efficiency. The floating ball in the valve shall be suitable metal or vulcanite or rubber specially manufactured for tropical conditions. |
| ## Scour Washout Valve | These shall be provided at portions shown in place and shall contain in one unit a flanged scour valve with short connection pieces, cast iron bend and T pieces for connection to main pipe. The rate shall also provide for short length of straight pipe to a convenient as per details complete with covers and surface boxes. |
| ## Reflux Valve | The Reflux valves shall be of approved manufacture and the body and door shall be of cast iron and the facing shall be gun metal. |
| ## Foot valves and Strainers | Foot valve and strainers should be of reputable manufacture approved by the Project manager and shall be fitted with flushing lever attachment where specified. |
| ## Pressure Reducers | Pressure reducing valves shall be of the equilibrium type of approved manufacture and capable of reducing the pressure to the valve required as per plan and Bill of Quantities. |
| ## Water Meter | This shall be provided if required by local authority as per their specification and approval. |
| ## Equilibrium Ball Valves | These should be of reputable manufacture approved by the Project manager and be of the angle pattern with gun metal valve seats guide bush, copper float with wrought iron lever and links with bronze pins. |
| ## Fittings |  |
|  | All sanitary pipes, gullies, water closets/bidets, squatting basins, sinks bath tubs etc. to be of approved design and to be obtained from approved Manufacture and to be of the best stoneware glazed inside and outside, with burnt hard and sound, free from flaws, blisters, cracks and other imperfections and best quality commonly called ‘Firsts’. Rates should include for all bends, junctions, traps, specials, cleaning, painting, fixing clear of wall etc. complete as specified as per Bill of Quantities. |
|  | All pipes, fittings, flushing cisterns, valves, stop cocks, taps, tanks, surface boxes etc. to be of the best of their kinds and in addition to complying with previous clauses to be from approved Manufacturers and all taps, cocks, valves etc. to be screwed down pipe. Taps to be of brass/nickel coated and valves to be of gun metal as specified in Bill of Quantities. All tanks to be made fly-proof and to the complete satisfaction of the Project manager. All lavatory basins, sinks etc. must be fixed at least 12mm, the latter method of fixing is preferable. Rates should include for all cutting and waste, bends, taps junctures, cleaning eyes, tees. |
|  | Contractor shall submit pipes, fittings, flushing cisterns, valves, stop cocks, taps, tanks, surface boxes etc. to be approved by the Project manager |
| ## Manholes and Manhole covers and Frames |  |
|  | Concrete cover slabs or top rings of manholes shall provide a suitable seating for a rectangular cover and frame having a clear opening 0.61m x 0.457m or alternatively a circular or double triangular cover and frame having a clear opening of 550m dia. depending on the type of C.I manhole cover to be used, and the rate for manholes shall allow for such provision. |
|  | Where the supply of C.I manhole cover and frames is payable separately the cost of setting, surrounding, painting and materials for same shall be allowed for in the rate for manholes |
|  | Suitable lifting rings, hooks or brackets shall be provided in the precast manhole sections. Box holes shall be separately grouted with 1:2 cement mortar. |
|  | The Contractor shall supply two manhole keys for each pattern of cover without additional charge over the rate for covers (or manholes). |
|  | Heavy duty (grade A) cast iron manhole cover and frames shall be of the double triangular type to B.S and having a clear opening of 550mm dia. |
|  | Medium duty (grade B) cast iron manhole covers and frames shall be of the circular type having a clear opening of 550m dia or the rectangular type having a clear opening of 0.457m x 0.61m and confirm to BS. They shall be of the single seal type, the weight of cover frame being approximately 127.00 kgs. |
|  | Light duty (grade C) cast iron manhole cover and frames shall be of the doubles seal flat type having a clear opening of 0.457m x 0.61m conforming to B.S.S. weight of cover and frame approximately 50.75kgs. |
|  | All manhole covers and frames shall be supplied, coated with a black bituminous composition, and be given two coats of bituminous paint after bedding |
|  | No extra rate is payable for drop and/or junction manholes but piping in and surrounds of drop lines are payable at that relevant rates for S.W piping and manholes |
|  | In drop manholes where the difference in level between the incoming drains and the sewer does not exceed 0.610m in 75mm and there is sufficient room in the manhole, the connecting pipe may be brought directly through the manhole wall, and the fall accommodated by constructing a ramp in the benching of the manhole. The ramp shall be of concrete and finished equal to that of the benches. No extra rate is payable. |
| ## Interceptor Manhole |  |
|  | All SWG gravity sewer lines should be, connected through an intercepting manhole before connecting to the main sewer line, and the dimensions of the manhole and trap to be in conformity with the drawings given. |
|  | Step iron shall be of galvanized malleable cast overall length per step 0.61m protected with 4 coats of anti-corrosive paint. |
| ## Fixtures and Accessories |  |
|  | Maker, class and colour shall conform to the Drawings and particular specifications or the instructions of the Project manager. |
|  | Sanitary fixtures shall be as follows: |

| Fixture | Type/model/catalogue No. | Color/Remarks |
| --- | --- | --- |
| Water Closet | American standard or equivalent | White |
| Basin | American standard or equivalent | White |
| Muslim shower | Water Tec or equivalent | White |
| Mirror Unit | Plastic or Wooden type with higher quality finish |  |
| Kitchen Sink | Not required |  |

|  | Flush Valves Flush valve for water closet shall be made of chrome-plated bronze and able to flush 15 litre of water within 10 seconds under 1.0kg/cm² supply pressure. |
| --- | --- |
|  | Faucet and Tap Faucet and tap shall be made of chrome-plated bronze. Flush valve and faucet shall pass the pressure test of 17.5 kg/cm². |
|  | Traps All traps shall be made of Vitrified of P.V.C. |

| Fixture | Dia. (mm) | Seal depth |
| --- | --- | --- |
| Water Closet (W.C.) | 100 | 50 or more |
| Wash Basin | 32 | 50 or more |
| Kitchen Sink | 38 | 50 or more |

|  | Miscellaneous |
| --- | --- |
|  | Metal accessories which is exposed-to-view shall be chrome-plated |
|  | Screw used to fix the fixture or accessories shall be brass made and shall be made chrome-plated where exposed-t-view |
|  | Anchor bolts or expansion bolts shall be used where the fixtures are to be installed on the concrete, block or brick wall and wooden block, if used, shall be treated with preservative and firmly embedded in the wall. |
|  | In case wood block is used for anchor purpose, such wood shall be treated with anti- corrosive paint. |
|  | Where fixture is anchored to the slab, necessary anchor hole and pipe sleeve shall be provided at the construction of such slab |
|  | Clearance between the fixture and wall shall be filled with white cement or sealing compound. |
|  | Position of faucet or tap shall be determined with due consideration given to convenience according to the surrounding situation, and securely installed |
| ## Height of Fixture Installation |  |
|  | Height of fixture shall be as follows unless otherwise specified on the Drawings |

| Fixture |  | Height (mm) |
| --- | --- | --- |
| Wash Basin | Floor finish to front top edge - Male Floor finish to top of mirror - Male - Female | 700 1675 1660 |
| Lavatory | Floor finish to front top edge | 760 |
| Shelf | Floor finish to top of shelf - Male - Female | 1005 990 |
| Drinking fountain | Floor to front top edge | 765 |
| Flush valve, WC | Floor to center of valve | 600 |
| Paper holder | Floor to center of holder - Japanese type | 400 |
|  | - Western type | 750 |
| Faucets | Sink floor to top of faucet | 300 |
| Sink |  |  |
| Lavatory | Lav. Top to top of faucet | 150 |
| Bath | Bathtub top to top of faucet | 150 |
| Bathroom | Floor finish to top faucet | 300 |

| - Painting |  |
| --- | --- |
| ## Material |  |
|  | All paints shall be approved by the Project manager for colour, quality and type. All painting work shall be carried out in accordance with the paint manufacturer’s specifications unless otherwise directed by the Project manager |
|  | Paint shall be ready mixed and all paints, varnishes, enamels, lacquer stains, paste fillers and similar materials shall be delivered to the site in the original containers with the seals unbroken and labels intact. Each container shall give the manufacturer’s name, type of paint, colour of paint and instructions for reducing. Thinning shall be done only in accordance with the manufacturer’s directions. |
|  | Use of product by the same manufacturer shall be a general rule in each stage of work in this Specification. |
|  | Colour, luster, colour scheme, finish shall be decided by the Project manager after checking sample paint test. |
|  | The painting shall be performed by experienced and competent painter |
|  | Where walls are specified to be painted, all columns arises, groove, rough surfaces, reveals, soffits and returns, etc. shall be included and no extra shall be payable |
| ## Definition of Terminology | Surface Sealing: Surface to be painted shall be sealed to have uniform suction and prevent lye from oozing out. Spot Puttying: All cracks and depressions shall be filled flush with putty. Spot painting: Spot puttied area shall be touched up by paint Touch-up: Any damaged area after the prime coat has been applied shall be touched up Drying hour: The drying time of double coated paint shall be measured at the temperature of 20°C and humidity of 70%. Amount of paint: The amount shall be standard amount of paint itself not including thinner. It shall increase or decrease depending on shape and surface condition in the process of painting. |
| ## Paint Finish Symbols | OP Synthetic resin mix paint finish VP Solvent-polyvinyl chloride resin paint finish EP Polyvinyl acetate resin emulsion paint finish AEP Synthetic resin emulsion paint finish CL Clear lacquer finish EXP Epoxy resin paint finish Stipple (OP) Stippled finish (oil mix paint finish) Stipple (EP) Stippled finish (polyvinyl acetate resin emulsion paint finish |
| ## Painting in General |  |
|  | Preparation of Paint (a) Mixing: Paint content with pigment shall be thoroughly stirred to make a uniform consistency. (b) Thinning: Portable water shall be used for thinning of emulsion paint and water-soluble paint. Proper thinner, product of the same manufacturer as paint, as a rule, shall be used for other types of painting. Percentage of thinning and viscosity shall be conducted with direction of manufacturer or catalogue as they vary with the method of paint, temperature, type of material to be painted. (c) Allowable period of Use: Paint mixed with more than 2 types shall be used with direction of a manufacturer or catalogue as allowable period of use, mixing ratio and mixing method vary. The paint which has passed allowable period of use shall not be used. |
|  | Conditions of Painting (a) Work shall not be executed in the following situations - When humidity is above 85% - When raining or it is forecast - When dusts are present - When temperature of surface is high under hot weather and bubbles are likely to develop on the painted surface. (b) Conditions of Surface to be painted: Work shall not be executed, or proper means shall be taken in the following situations. - When surface is damp and wet - When condensation is likely to develop on the surface. - All nail holes on veneer, board. etc., shall be covered with proper rust-proof paint before the subsequent painting is applied in accordance with this specification. |
|  | Performance Paint shall be evenly and uniformed applied on the surface. Areas of difficult application such as pointed part, internal angle, welded part, etc. shall be thoroughly painted and double coated as necessary to deep uniform coating thickness. Painting shall be properly done by carefully selecting the painting method by the shape of surface and types of paint. |
|  | Protection Dangerous material such as paint, thinner, etc., excluding emulsion paint and water-soluble paint shall be kept in accordance with regulations concerned. |
| ## Procedure of Painting |  |
|  | Exterior - Surface of Mortar, Plaster, Concrete and Slate AEP- Synthetic resin emulsion paint. |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Dry, clean and free from impurities |  |  |
| 2. Surface sealing | 1 | Sealer for emulsion paint | longer than 4 hours |  |
| 3. Puttying |  | Conmix Conputty (or similar) |  |  |
| 4. Grinding |  | Grind with proper grinding tool |  |  |
| 5. Spot painting |  | Synthetic resin emulsion paint |  |  |
| 6. Second coating | 1 | Synthetic resin emulsion paint | longer than 4 hours | 0.10-0.13 |
| 7. Finish coating | 2 | Synthetic resin emulsion paint | longer than 4 hours | 0.10-0.13 |

Notes:

      - Degree of dryness on the surface to be painted shall be kept under 6% in water content and below PH 9.5

      - Puttying and sanding process shall allow to omit depending on the conditions of the surface.

      - Drying time of putty shall be long enough for sanding to proceed.

      - Amount of sealer for surface sealing shall be adjusted with direction of the Project manager as it varies with the surface conditions.

|  | Exterior - Iron Products in General OP - Synthetic resin mix paint |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Completely remove rust, moisture, oil and other impurities by sander, cleaner and surface. |  |  |
| 2. First Coating 24 hours | 1 | Rust proof oil paint | longer than 24 hours | 0.13-0.15 |
| 3. Touch-up |  | Touch-up rustproof oil paint |  |  |
| 4. First Coating | 1 | Rustproof oil paint | longer than 24 hrs. | 0.13-0.15 |
| 5. Second coating | 1 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.15 |
| 6. Finish coating | 1 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.15 |

Note:

Paint for touch-up painting shall be the same as used for first coat in process No. 2

|  | Exterior - Wood OP - Synthetic resin mix paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Clean and sand to plane surface |  |  |
| 2. Knot treatment | 1-2 | Lacquer varnish | longer than 24 hours |  |
| 3. First coating | 1 | First coat paint of oil mix paint | longer than 24 hrs. | 0.13-0.15 |
| 4. Second Coating | 1 | Oil mix paint | longer than 24 hrs. | 0.11-0.13 |
| 5. Finish coating | 1 | Oil mix paint | longer than 24 hrs. | 0.11-0.13 |

Note:

Puttying and sanding shall be done after process No.2 when there are cracks, etc. on the surface putty shall be oil-putty, but drying time shall vary depending on conditions.

|  | Interior - Mortar, board, etc. Stipple (EP) - Polyvinyl acetate resin emulsion paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Dry, clean and free from impurities |  |  |
| 2. Surface sealing | 1 | Sealer for emulsion paint | longer than 4 hours |  |
| 3. Puttying |  | Conmix Conputty (or similar) |  |  |
| 4. Grinding |  | Grind with proper grinding tool |  |  |
| 5. Spot painting |  | Second coating paint of polyvinyl acetate resin emulsion paint |  |  |
| 6. Second Coating | 2 | Polyvinyl acetate resin emulsion paint | longer than 4 hrs. | 1.11-0.13 |
| 7. Finish Coating | 1 | Polyvinyl acetate resin emulsion paint for stipple-finish | longer than 4 hrs. | 0.25-0.35 |

Notes:

- Degree of dryness on the surface to be painted shall be kept under 6% in water content and below PH 9.5

- Puttying and sanding process shall allow to omit depending on the conditions of the surface.

- Drying time of putty shall be long enough for sanding to proceed.

- Amount of sealer for surface sealing shall be adjusted with direction of the Project manager as it varies with the surface conditions

|  | Interior - Mortar, plaster, concrete, etc. VP Solvent - Polyvinyl chloride resin paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Dry, clean and free from impurities |  |  |
| 2. Surface sealing | 1 | Sealer for emulsion paint | longer than 2 hours |  |
| 3. Puttying |  | Conmix ConPutty for polyvinyl chloride resin paint (or similar) |  |  |
| 4. Grinding |  | Grind with proper grinding tool |  |  |
| 5. Spot painting |  | Solvent-polyvinyl chloride resin enamel emulsion paint |  |  |
| 6. Second Coating | 1 | Solvent-polyvinyl chloride resin enamel emulsion paint | longer than 4 hrs. | 0.11-0.14 |
| 7. Finish Coating | 2 | Solvent-polyvinyl chloride resin enamel emulsion paint | longer than 4 hrs. | 0.11-0.14 |

Notes:

- Degree of dryness on the surface to be painted shall be kept under 6% in water content and below PH 9.5

- Puttying and sanding process shall allow to omit depending on the conditions of the surface.

- Drying time of putty shall be long enough for sanding to proceed.

- Amount of sealer for surface sealing shall be adjusted with direction of the Project manager as it varies with the surface conditions.

|  | Interior - Mortar, plaster, concrete, etc. EP Polyvinyl acetate resin emulsion paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Dry, clean and free from impurities |  |  |
| 2. Surface sealing | 1 | Sealer for emulsion paint | longer than 4 hrs. |  |
| 3. Puttying |  | Conmix ConPutty for emulsion paint (or similar) |  |  |
| 4. Grinding |  | Grind with proper grinding tool |  |  |
| 5. Spot painting |  | Polyvinyl acetate resin emulsion paint |  |  |
| 6. Second Coating | 1 | Polyvinyl acetate resin emulsion paint | longer than 4 hrs. | 0.11-0.13 |
| 7. Finish Coating | 1 | Polyvinyl acetate resin emulsion paint | longer than 4 hrs. | 0.11-0.13 |

Notes:

- Degree of dryness on the surface to be painted shall be kept under 6% in water content and below PH 9.5

- Puttying and sanding process shall allow to omit depending on the conditions of the surface.

- Drying time of putty shall be long enough for sanding to proceed.

- Amount of sealer for surface sealing shall be adjusted with direction of the Project manager as it varies with the surface conditions.

|  | Interior - Iron products, steel. OP - Synthetic resin mix paint |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Completely remove rust, moisture, oil and other impurities by sander, cleaner and surface |  |  |
| 2. First Coating | 1 | Synthetic resin rust-proof. Red lead-type, lead compound- type | longer than 24 hrs. | 0.18-0.22 0.13-0.15 |
| 3. Touch-up |  | Touch-up rust proof paint |  |  |
| 4. First Coating | 1 | Synthetic resin rust-proof paint. Red lead-type, Lead compound- type | Longer than 24 hrs. | 0.18-0.22 0.13-0.15 |
| 5. Second Coating | 1 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.13 |
| 6. Finish Coating | 1 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.13 |

Notes:

- Paint for touch-up painting shall be the same as used for first coat in process No.2

- When oil rust-proof paint is used instead of synthetic resin rust proof, its specification shall conform to No. 5 and No.6.

|  | Interior - Wood Products in Clear Finish. Cl - Clear Lacquer Finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface preparation |  | Clean and sand to plane surface |  |  |
| 2. Colouring | 1-2 | N.G.R Stain | longer than 2 hrs. |  |
| 3. Colouring sealer | 1 | Wood-sealer | longer than 2 hrs. | 0.08-0.10 |
| 4. Grain treatment | 1-2 | Oil sealer | Longer than 12 hrs. |  |
| 5. Second Coating | 2 | Sanding sealer | longer than 4 hrs. | 0.10-0.13 |
| 6. Grinding |  | Grinding with proper grinding tool |  |  |
| 7. Finish Coating | 2 | Clear lacquer |  | 0.06-0.08 |
| 8. Grinding |  | Sanding with water |  |  |
| 9. Finish Coating | 1 | Clear lacquer | Longer than 24 hrs. | 0.06-0.08 |
| 10. Polishing |  | Polish with polishing compound |  |  |

Notes:

- Grain treating process shall be allowed to omit for certain trees approved by the Project manager.

- Process (2) through (4) shall be allowed to omit by the use of colouring and grain treating agents.

- Number of coats for processed 5 and 6 and processes 7 and 8 shall indicate the repetition of process.

|  | Interior - Wood Products OP - Synthetic resin mix paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Clean and sand to plane surface |  |  |
| 2. Knot treatment | 1-2 | Lacquer varnish | longer than 2 hrs. |  |
| 3. First coating | 1 | First coating paint for synthetic resin mix paint | Longer than 2 hrs. | 0.13-0.15 |
| 4. Grinding |  | Grind with proper grinding tool |  |  |
| 5. Finish Coating | 2 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.13 |

Notes:

    - Puttying and sanding shall be done after process No.2 when there are Cracks, etc. on the surface. Putty shall be oil putty, but the drying time shall vary depending on conditions.

|  | Interior - Wood Products AEP, EP - Synthetic resin emulsion paint or vinyl acetate resin emulsion paint finish Steel Sash OP - Synthetic resin mix paint finish. |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Clean and sand to plane surface |  |  |
| 2. Knot treatment | 1-2 | Lacquer varnish | longer than 2 hrs. |  |
| 3. First coating | 1 | First coating paint for synthetic resin emulsion, first coat paint for vinyl acetate resin emulsion | Longer than 24 hrs. | 0.10-0.13 |
| 4. Finish Coating | 2 | Synthetic resin emulsion paint Vinyl acetate resin emulsion paint | longer than 24 hrs. | 0.10-0.12 0.11-0.13 |

Notes:

    - Puttying and sanding shall be done after process No.2 when there are Cracks, etc. on the surface. Putty shall be oil putty, but drying time shall vary depending on conditions.

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Phosphoric acid chemical coat treatment by metal surface treating agent |  |  |
| 2. Priming | 1 | Wash-primer | between 2-8 hrs. | 0.06-0.08 |
| 3. First coating | 1 | Primer for sash | Longer than 10 hrs. | 0.10-0.16 |
| 4. Touch-up |  | Touch-up primer |  |  |
| 5. First coating | 1 | Primer for sash | Longer than 10 hrs. | 0.13-0.16 |
| 6. Second Coating | 1 | Synthetic resin mix paint | Longer than 15 hrs. | 0.11-0.13 |
| 7. Finish Coating | 2 | Synthetic resin mix paint | longer than 15 hrs. | 0.11-0.13 |

Notes:

- Wash primer shall be omitted when surface is treated by phosphoric acid in process No.1.

- Paint for processes up to No.4 and No.5 shall be similar paint used for first coat in process No.3 or that recommended by a manufacturer.

|  | Steel Sash, Machinery and Tools, Plates OP - Synthetic resin mix paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Completely remove rust, moisture, oil and other impurities by sander, cleaner and scraper |  |  |
| 2. First coating | 2 | Rust-proof synthetic resin | Longer than 15 hrs. | 0.12-0.15 |
| 3. Second Coating | 1 | Synthetic resin mix paint | Longer than 15 hrs. | 0.11-0.13 |
| 4. Finish Coating | 1 | Synthetic resin mix paint | Longer than 15 hrs. | 0.11-0.13 |

Notes:

(a) Wash primer shall be omitted when surface is treated by phosphoric acid in process No.1.

(b) Paint for processes up to No.4 and No.5 shall be similar paint used for first coat in process No.3 or that recommended by a manufacturer.

|  | Inside of Steel, Inside of Water Tank EXP - Epoxy resin paint finish |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Remove rust by sand burst or shot burst and clean by volatilizer |  |  |
| 2. First coating | 2 | Rust-proof epoxy resin | Longer than 24 hrs. | 0.15-0.20 |
| 3. Second Coating | 1 | Second coating paint for epoxy resin paint | Longer than 24 hrs. | 0.12-0.15 |
| 4. Finish Coating | 1 | Finish coating paint for epoxy resin paint | Longer than 24 hrs. | 0.12-0.15 |

Notes:

- First coat shall be applied once within 5 hrs. after surface preparation.

- Paint for inside of potable water tank shall be that recommended by a manufacturer.

- After finish paint is applied inside of water tank shall be kept out of water for 7 days.

|  | Apply two coats aluminum primer on concealed side of plywood panels |
| --- | --- |

| Coating Process | No. of Coats | Type of Paint | Drying hour | Amount (kg/m²) |
| --- | --- | --- | --- | --- |
| 1. Surface treatment |  | Dry, clean and free from impurities |  |  |
| 2. First coating | 1 | First coating paint for epoxy | Longer than 24 hrs. |  |
| 3. Finish Coating | 2 | Epoxy resin paint | Longer than 24 hrs. |  |

Notes:

- Degree of dryness on the surface to be painted shall be kept under 6% in water content and below PH 9.5.

- Amount of paint and number of paints shall be as directed by the Project manager as they vary with the conditions of surface and required thickness of coating.

- Painted surface shall be kept out of use for more than 7 days after application of final coat.

| - Electrical installations |  |
| --- | --- |
| ## General |  |
|  | The work shall be carried out strictly in accordance with the standard specifications and shall also conform to the requirements of Electricity Rules in force in Male’, Republic of Maldives. |
|  | All materials to be used in the Works shall be of standard make and shall bear the certification marks of local authorities. All materials shall be approved by the Project manager before use in the Works |
|  | Earthing shall invariably be done in the presence of the Project manager or his representative. |
|  | All the conduits shall be continuously earthed. Check nuts shall be provided at the point where the conduct enter the I.C. box and junction box |
|  | The Contractor shall arrange for the inspection of all Medium Pressure Installation by the Electrical inspector of the local electric supply authority from where the electricity connections has to be obtained, and see that they are passed by him |
|  | The Contractor shall be responsible for all necessary permits, approvals, fees, deposits etc., required to complete the Electrical works in accordance with the Contract |
|  | Scope of work |
|  | The work consists of furnishing all tools, plants, labour, materials and equipment and performing the internal electrical Works comprising of: (a) Light and power wiring (b) Fans and fixtures (c) Wires and Cables (d) Sub- Station Equipment: (e) Distribution Fuse gear (f) Earthing System |
|  | Prequalification |
|  | The Electrification Work shall be carried out only by a licensed contractor authorized to undertake such work under the Maldives Electricity Board |
|  | Qualification |
|  | A licensed Electrical Contractors should have the following qualifications: (a) Must have in his employment a competent Electrical Engineer registered with Maldives Electricity Board. (b) Must have in its employment an Electrical Project manager having certificate of competency who will exclusively supervise this work. (c) Must have necessary tools, plant and instruments. (d) Must have adequate experience of similar works. (e) If a contractor does not possess the above qualifications, he shall be allowed to sublet the Work to a competent Sub-Contractor provided an application for his prequalification is made to the engineer for his approval. Decision of the Engineer in this case shall be binding on the Contractor. |
|  | Rules and Regulations |
|  | The installation in general shall be carried out in conformity with the guidelines, rules & regulations of the Utility Regularity Authority (URA) of Maldives and the latest edition of the Regulations for the Electrical Equipment of Buildings issued by the Institution of Electrical Engineers, London (I.E.). However, in case of conflict between these Specifications and the I.E. Regulations, these Specifications shall be followed. |
|  | Standards |
|  | The latest relevant British Specifications, and I.E. recommendations shall be applicable and be followed for the equipment specified herein. |
|  | Climatic conditions |
|  | All equipment supplied shall withstand, without developing any detect, the following climatic conditions:- Maximum Ambient Temperature = 113° F or 45° C Minimum Ambient Temperature = 28° F or - 2.2° C Maximum Humidity = 90% |
|  | Specifications |
|  | The Contractor shall furnish all material and equipment at site, confirming fully to the specifications given herein and to the accepted standards, the Institution of Electrical Engineers, London, and the Maldives Electricity Board. It is not the intent of these Specifications to include all details of design and construction of various material and equipment to be supplied under this contract. The Contractor shall supply and install all material and equipment specified herein and also all installation and small material such as nuts, bolts, washers, shims angles, leveling material, insulation, tape, solder, etc. and all such required for complete installation as intended by the Specifications |
|  | The contractor shall provide for all the required technical and non - technical personnel, skilled and non - skilled labour, construction equipment, transportation etc., as required for the completion of Work in strict accordance the Technical Specifications laid herein-after. All material and equipment supplied by the Contractor shall be new and, in all respects, conforming to the high standard of engineering design and workmanship. All material and equipment which have to be supplied and installed by the Contractor shall be passed/approved by the Project manager; even if the same is exactly in accordance with the Bill of Quantities and Drawings. |
|  | Submittal |
|  | The Contractor, after the award of work, shall submit for approval of the Project manager all drawings and cuts of equipment, appliances, fixtures and accessories. Cuts, catalogues and drawings shall be clearly marked to indicate, the items furnished |
|  | Approval of Drawings and Data |
|  | The Contractor shall provide detailed electrical drawings, wire diagrams, etc. for all electrical switchgear, fuse gear and all other systems etc. for the Project manager to review and approval. Three sets of equipment drawings shall be provided for obtaining approval. |
|  | Drawings & Data |
|  | Three sets of drawings and data for each equipment shall be furnished by the Contractor for the Project manager approval before commencement of work. The drawings to be supplied by the Contractor shall be as follows: - Electrical Drawings showing: - (a) One-Line diagram (b) Detailed wiring diagram (c) All interconnections (d) Relays, their locations, and internal wiring diagrams (e) Other electrical devices including meters instruments and their wiring diagram |
|  | Shop Drawings |
|  | The design drawings do not show conduit routes and depict only the position of various fixtures and outlets. All the planning for the conduit routes shall be carries out, well in advance of the actual execution of work, by the Contractor to the satisfaction of the Project manager. For this purpose, the Contractor shall prepare shop drawings and obtain prior approval of the Project manager. There prints of each shop drawings shall be submitted for obtaining approval. work |
|  | No piece of work shall be allowed to be executed at site without the availability of these approved shops drawings. These shop drawings shall clearly depict the load balancing chart of each Distribution Board. Time required for the preparation and approval of shop drawings shall be considered to have been included in the total time allowed for the completion of the work |
|  | Spare Parts list |
|  | A list of spare parts required for the one year’s operation of each equipment where deemed necessary together with unit price of each part, shall be supplied by the contractor |
|  | Guarantee |
|  | The Contractor shall furnish written guarantee in triplicate of the manufacturer for successful performance of each equipment. Such guarantee shall be for replacement which may be found defective in material or workmanship. The guarantee shall cover a minimum period of 12 months effective from the date of completion certificate |
|  | As-Built Drawings |
|  | The Contractor shall, during the progress of work keep a careful record of all changes and where the actual installation differs from that shown on shop drawings. These changes and revisions where the actual installation differs from that shown on shop drawings. These changes and revisions shall be accurately carried out on the shop drawings and submitted to the Project manager for approval. After approval these drawings shall become the property of the Owner. These updated and approved shop drawings depicting clearly all changes and revisions made on site shall be called As-Built Drawings. Reproducible tracings of all these As-Built Drawings shall be handed over to the Project manager. Final payment will be withheld until the receipt of the approved As-Built Drawings |
|  | Test Reports |
|  | The Contractor shall be responsible for the submitting the test reports/certificates and get the installation inspected passed by the Utility Regulations Authority of Maldives. |
|  | Electricity Board Requirement |
|  | The Contractor shall assist the Owner in sponsoring the application for the Electrical connections and carry out all the necessary formalities |
| ## Conduit and Conduit Accessories |  |
|  | Conduit Pipe |
|  | The conduit for the wiring of lights, socket outlets and other systems shall be made of PVC confirming to BSS 3505/1968 Class-D (or similar) The conduit shall have following wall thickness and standard weights: |

| Pipe Size | Wt/100Rft. | Wall thickness |
| --- | --- | --- |
| 20mm dia | 3.4 Kg | 0.04 to 0.05 |
| 25mm dia | 4.5 Kg | 0.045 to 0.055 |

|  | Steel conduit shall conform to BS 31, BS 4568 / latest (or similar). The conduit shall be enameled with good quality non- cracking and non-flaking black paint |
| --- | --- |
|  | Conduit Accessories |
|  | The use of factory made round PVC junction boxes shall be used and should have nipples to receive PVC pipe with force fit, shall be used for ceiling outlets. The wall type junction box shall also be PVC. Each junction box shall be provided with one-piece cover which shall be fitted on the box with screws |
|  | Conduit accessories such as switch boxes, socket outlet boxes, pull boxes and inspection boxes shall be made of PVC having dust tight covers. All boxes shall have required number of conduit entry holes. All the rectangular or square shaped boxes shall have nipples to receive PVC conduit force fit |
|  | Manufactured smooth bends shall be used where conduit changes direction. Bending of Conduit by heating or otherwise shall be allowed only at special situations with the permission of the Project manager. Use of sharp 90-degree bends and tees is prohibited. Bends shall have enlarged ends to receive the conduit without any reduction in the internal diameter of the PVC pipe |
|  | All accessories e.g. boxes, coupling, bends, solid plugs, bushes, reducers, check nuts etc. shall be equal in quality to the specified conduit |
|  | The drawings do not show conduit routes and all the planning for arranging conduit routes shall be carried out by the Contractor to the satisfaction of the Project manager |
|  | The entire conduit system shall be essentially completed before the wiring pulling is taken in hand. Each conduit run shall be tested for continuity and obstructions. All obstructions shall be cleared in an approved manner. Water and moisture that has entered any section of the conduit installation must be dried with suitable swabs to the satisfaction of the Project manager |
|  | Adequate expansion joints shall be provided in all conduit runs passing across the expansion joints in the concrete slab of the buildings |
|  | All the free ends of conduit shall be solidly plugged till such time as final and proper terminations are made |
| ## Wires, Cables and Cords |  |
|  | Wires & Cords |
|  | The wires & cords for the conduit wiring shall be single core, made of stranded copper conductors, PVC insulated, tested to B.S. 6004, 1975. The voltage grade shall be 300/500 volts or 450/750 V unless otherwise specified on Drawings and Bills of Quantities. (a) For light or fan point wiring with 1.5 mm square or as specified in the BOQ. (b) For wall sockets and power plugs of 13A, wiring with 2.5 mm square or as specified in the BOQ. (c) For power plug 15A wiring with 4mm square or as specified in the BOQ. |
|  | Installation Instructions |
|  | All wiring shall be continuous between terminations and use of connectors or joints is not be allowed. Spur and tee connections are strictly prohibited. |
|  | Manufacturers recommended lubricant shall be allowed to facilitate pulling of wires. Use of any kind of oil and soap is prohibited |
| ## Wiring Accessories |  |
|  | Switches |
|  | Indoor switches controlling lights and fans shall be single pole, 5A, one or two way, suitable for 250V,50 Hz. The body of the switches shall be made of molded plastic, one, two, three or four gang with integral built in molded plastic face plate |
|  | Weatherproof switches shall conform to B.S. standard |
|  | Switch Socket Outlet Units |
|  | Switch & socket units shall be single, pole, 3 pin rated 5A. 15A or 20A, 250V, 50 Hz. These shall be molded plastic type with white integral built-in face plate. Each socket shall have its control switch by the side of it on a common face plate. Thus, the complete unit specified in BOQ shall be as switch and a socket outlet unit |
|  | Fans |
|  | All fans shall be capacitor type Deluxe models and suitable for operation on 200/220 volts, 50 Hz, A.C Supply. All ceilings fans shall have five speed dimmers. The air displacement shall be 10,000 c.f.m for 48” (1,219 mm) Sweep and 12,000 c.f.m. for 56” (1,423 mm) Sweep at maximum speed. The fan motor shall be capacitor type and bearings shall be groove type to give noiseless and quiet operation. The noise level relative to a frequency of range 1000 Hz should be within the limits of +3 dB. |
|  | Dimmer |
|  | The dimmer shall be recessed type as required and shall be approved by the Project manager |
|  | Fan Hook |
|  | The fan hook shall be made of 12 dia Stainless Steel (Grade 304) rod bent to shape of approved design. It should be in the form of a loop about 3-1/4” (87.5 mm) long and about 2” (50 mm) wide. The rod shall be bend to have at least 8” (200 mm) extension on both sides for ceiling to the reinforcement steel of the slab. All ceiling fan shall be of one make only. |
| ## Light Fixtures |  |
|  | General |
|  | The description of light fixtures is given in the Bills of Quantities, and stated on the Drawings, and all relevant material are described in this Section. The determination of quality is based on certified photometric data covering the coefficient of utilization, light distribution curves, construction material, shape, finish, operation, etc. |
|  | The Contractor shall submit samples of each and every lighting fixture specified for approval of the Project manager |
|  | The type of fixtures with manufacturer catalogue reference are given in Bill of Quantities. The lighting fixtures shall be manufactured by M/s. Philips, M/s.RZB Lighting as approved by Project manager |
|  | Incandescent Light Fixture |
|  | The glass globes/ shades/ diffusers of the incandescent light fixtures shall be first class quality glass free from any air bubbles or voids. The glass shall generally be of opal white colour unless otherwise specified. The shape of the glass may be spherical, hemispherical, flattened bottom or tablet shaped as required. |
|  | Surface mounted fixture shall have stove enameled sheet steel body. It may also be satin brass or aluminum anodized finish as required. The fixing holes shall match the outlet box. Wall bracket light fixtures shall have back plates with matching holes of the outlet box and decorative finish as required |
|  | All the lighting fixtures shall be suitable for local climatic conditions |
|  | Fluorescent Light Fixture |
|  | All the light fixtures shall have lamps and electronic ballasts of the wattage specified. The fluorescent lamp shall be either 2 ft - 18 watts or 4 - 35 watts and the colour shall generally be day light, cool day light in the order of preference or as mentioned specifically. The fluorescent lamps shall be Philips to BSS 1853 but having a minimum useful life of 5000 hours. The new generation of 26mm dia 18 watts and 36 watts energy efficient lamps shall be preferred |
|  | The ballast shall be totally enclosed electronic type suitable for operation on 220 V, 50 Hz, single phase supply, a wiring diagram, wattage, voltage and current ratings shall be printed on the body of the ballasts. The power loss shall not more than 10 watts for 36 watts ballast. The ballast shall be noiseless in operation without any whistling sound. The manufacture shall be called upon to guarantee a trouble-free life of 3 years, effective from the date of completion certificate. |
|  | The starters shall have radio-interference suppressers. |
|  | The internal wiring of the light fixtures shall be carried out at manufacturers factory with heat resistance wires of size not less than 1.5 mm square |
|  | The louvers of light fixtures shall be made of anodized aluminum and/or molded plastic. The diffusers shall be made of acrylic Perspex. |
|  | All the lighting fixtures shall be suitable for local climatic conditions |
|  | Installation Instructions |
|  | The light fitting shall be installed according to manufacturer’s recommendations or as approved by the Project manager. |
|  | Flexible connecting wires from outlet box to the fixture shall be provided by the contractor; connector made of porcelain or thermoplastic material shall be provided and installed in the outlet boxes for connecting flexible wires to the point wires |
|  | Outlet boxes or any openings in the ceilings and walls shall be covered with appropriately fabricated accessories to provide an architectural entity to conceal them |
|  | Main L.T. Switchboard |
|  | The L.T. switchboard shall be indoor type, free standing, free supporting, floor mounted, totally enclosed, sheet clad, dust and suitable for operation on 3 phase 4 wire system, 415 v, 50 Hz, AC supply. The board shall be suitable for installation back to the wall and capable of front attendance. The switch board shall be designed to suit service conditions and ensure security and safety during operation, inspection, operation, cleaning and maintenance. The switch board shall be designed and tested to IEC recommendations. Each panel shall withstand strain of 2000 volts insulation level for one-minute power frequency test |
|  | The L.T. switch board shall consist of the following: (a) STELCO ( State Electric Company) of Maldives incoming panel. (b) Stand by generator incoming panel with A.M.F. |
|  | Distribution Feeder Panel |
|  | Single diagram of the L.T. switch board shall be approved by the Project manager before placing order for the switch board. |
|  | Earthing |
|  | The switchboard shall be effectively earth by means of a copper strip of 25mm x 3mm (1” x 1/8”) cross -section bolted to connections near the bottom of the switchboard. |
|  | Accessories |
|  | Designations labels, lifting lugs, foundation bolts, interconnecting nuts blots, and washers, thimbles, lugs, levelling shims cable glands and/or cable end box for all the sizes of incoming and outgoing cable shall be supplied with the switchboard |
| ## Testing |  |
|  | The following tests shall be conducted on each completed switchboard |
|  | Type Tests (a) Temperature rise test (b) Mechanical endurance test (c) Making/Breaking Capacity test |
|  | Routing Test (a) High Voltage test The Switchboard shall be tested to British/Electricity Council Standard 41-5. Preference shall, however, be given to Switchboards fabricated from all components manufactured by only one manufacturer. |
|  | Installation Instruction |
|  | All labor, equipment’s, tools and plants required to complete the installation shall be provided by the contractor. The Switchboard shall be fixed firmly on the floor in perfect line, plumb and level position. All incoming and outgoing cable connections shall be made from the bottom including Earth connections |
| ## Distribution Board |  |
|  | The distribution boards shall be either free standing, cubical type or wall mounting type suitable for recessed mounting. Each distribution board (d.b.) shall be tropical in design, fully dust and vermin proof and liquid repellent. |
| ## Cable Ladder System |  |
|  | General The cable ladder system shall generally be installed in vertical riser ducts provided for the purpose for parallel runs of cables of various services. The Contractor shall be under obligation to supply all labor, material and accessories for the completion of cable ladder installation strictly in accordance with the specification laid as under and as illustrated on drawing to the entire satisfaction of the Project manager. |
|  | Design The cable ladder system shall be fabricated from 16SWG (2.5 mm) thick sheet steel strip and then hot dip galvanized. All fixing accessories e.g. raw bolts, cable clamps, nuts and bolts used for the cable ladder system shall be hot dip galvanized. All cable ladder shall have standard length of 4000 mm and a width of 500 mm. The ladder and accessories shall be subject to the prior approval of the Project Manager before mass production is taken in hand. |
|  | Installation The cable ladders shall be installed in perfect line and plumb on the surface of walls in riser ducts by means of galvanized rawl bolts 1/2” dia x 3” long. Alternate ladder step in each length of ladder shall be clamped to the ladder in a neat and orderly manner by means of cable clamps. Depending upon the number of multiple cables runs two or three parallel ladders may be installed, side by side, in the same riser ducts in case one ladder is unable to accommodate all the cable runs. Each cable ladder (or an assembly of two or three parallel cable ladders laid side by side) shall be solidly earthed with 1” x 1/8” copper tapes on both sides. |
| - Fencing |  |
| ## General | The works and materials specified in clauses below shall comply with the sections stated, unless otherwise stated in this Section. |
| ## Material |  |
|  | (1) Wire for fencing, including plastic coated wire, shall be galvanized mild steel complying with BS 4102. (2) Galvanized coating to steel wire shall comply with BS EN 10244-2:2001. (3) Plastic coating to steel wire shall be green and shall comply with BS 4102, Section 6. |
|  | Chain link fence shall comply with BS 1722: Part 1 unless otherwise stated in this Section. |
|  | Steel for fencing shall comply with the following: Hot rolled sections : BS 4: Part 1 Hot rolled structural steel sections Equal and unequal angles: BS 4848: Part 4 Hollow sections: BS 4848: Part 2 Weldable structural steel :BS 436 |
| ## Bolts, Nuts & Washers | (1) Bolts, nuts and washers for fencing shall comply with the following: - ISO metric black hexagon bolts, screws and nuts : BS 4190 - ISO metric black cup and countersunk head, bolts and screws with hexagon nuts: BS 4933 - Metal washers for general engineering purposes: BS 4320 (2) The length of bolts shall be such that the threaded portion of each bolt projects through the nut by at least one thread and by not more than four threads. (3) Fittings, including eye bolt strainers, cleats, winding brackets, stretcher bars, extension arms, hook bolts and base plates, shall be galvanized mild steel. (4) Bolts, nuts, washers and fittings for fixing to concrete and timber shall be galvanized. Bolts, nuts, washers and fittings for fixing to steel shall have the same protective treatment as the steel. (5) Staples shall be D-section galvanized wire. |
| ## Posts & gates for fencing |  |
|  | Concrete posts and struts for fencing shall be precast using Grade 30/10 concrete. The finish to the formed surfaces shall be Class F4 and the finish to the unformed surfaces shall be Class U5. The tops of posts and all arises shall be rounded or chamfered. Reinforcement for concrete posts and struts shall be Grade 250 plain round steel bars. |
|  | Steel gates shall be of welded construction. Square with the corners mitered or saddled. The frame shall be Chain link infilling in gates shall be of the same type and size as in the adjoining fence and shall be attached to the framework by stretcher bars. |
|  | The following particulars of the proposed fencing shall be submitted to the Project Manager at least 14 days before the fencing is erected - Drawings showing the fabrication details of gates, and - Details of the source, type and properties of the proposed materials. |
|  | Gates, concrete columns, steel posts and struts for fencing shall be stored off the ground on level supports and in a manner, which will not result in damage or deformation to the materials or in contamination of the materials. Fencing shall be free from any defects and damages. Any defective or damaged fencing shall not be used in the permanent works. |
| ## Erecting of Fences |  |
|  | Fencing shall be erected to a smooth alignment with no abrupt irregularities. The ground shall be trimmed or filled in such a manner that the bottom of the fence will follow the level of the ground. The distance between the bottom of chain link mesh and hoardings and the ground shall not exceed 100 mm and any gap between the bottom of hoardings and the ground shall be sealed. |
|  | Straining posts for fencing shall be provided at all ends and corners, at changes in direction, at abrupt changes in level, at gate posts and at intervals not exceeding 30 m along straight lengths of fencing. Struts shall be fitted to straining posts in the direction of each wire secured to the post. Intermediate posts shall be provided at intervals not exceeding 3.5 m. |
|  | Posts and struts for fencing shall be set in excavations for foundations and the excavations shall be filled with Grade 30/20 concrete up to 50 mm below ground level. Struts shall be fitted into slots in concrete posts and shall be bolted to steel posts. The ground surface around posts shall be made good with the same material as in the adjoining area. |
|  | Line wire, chain link mesh and barbed wire for fencing shall be strained tightly between straining posts. Winding brackets shall be used for straining between steel posts and winding brackets or eye bolt strainers shall be used for straining between concrete posts. The tension in the wire on each side of straining posts shall be equal. Wire shall not be strained until at least 14 days after concrete has been placed in the foundation. Chain link mesh shall be secured at each straining post by a stretcher bar and shall be tied to the line wire by tying wire at 150 mm intervals. Each line wire and each line of barbed wire shall be secured to each intermediate post by one of the following methods as stated in Table 2.1. A hairpin staple shall be passed through a hole in the post and secured to the wire by three complete turns on each side of the post. A stirrup shall be passed through a hole in the post and the ends bent over twice. The wire shall be threaded through a hole in the post. The wire shall be stapled to the post. A hook bolt shall be passed through a hole in the post and secured with a nut and washer. |

Table 2.1:	Method of securing wire to intermediate posts

| Type of fence | Type of wire | Type of post | Method of securing wire |
| --- | --- | --- | --- |
| Strained wire | Line wire | Concrete | (a), (b) or (c) |
|  |  | Steel | (a), (b) or (c) |
|  | Barbed wire | Concrete | (a) or (b) |
|  |  | Steel | (a) |
| Chain link | Line wire | Concrete | (a), (b) or (d) |
|  | Mesh wire | Steel | (a) or (c) |
|  | Barbed wire | Concrete | (a), (b) or (d) |
|  |  | Steel | (a) |

| ## Tolerances | Fencing shall comply with the following requirements: The position of posts shall be within 75 mm of the specified position. The level of the top of posts shall be within 25 mm of the specified level. Posts shall be vertical to within 5 mm in the height of the post. |
| --- | --- |

- Water Tank

| ## General | A black HDPE stationary water storage tank. This vertical water storage tank is required for rainwater collection, for general purposes like washing, composting and ﬁre suppression. Tanks shall be rotationally molded, vertical, high density cross-linked polyethylene, one-piece seamless construction, cylindrical in cross-section and vertical with flat bottoms. Tanks shall be adequately vented as per drawings. It should be made of seamless construction, durable and resistant to cracks, chips, and ruptures. It should be made with FDA approved resin that complies with FDA standards 21 CFR 177.1520 (1) 3.1 and 3.2 for the storage of potable water. The tank must have a perfectly smooth inner surface which can be easily washed by means of traditional detergents. It should be made with UV inhibitors that help protect liquid contents from direct sunlight making it ideal for both indoor and outdoor use. It should be ﬁtted with 75mm rainwater inlet, 18mm draw out tap, 35mm release outlet for cleaning and a standard manhole access from top. Vent pipe should be provided as given. It should be backed with a 10-year manufacturer warranty. The capacity should be 7500 liters and mounted on a base as given in the Drawings. The water tank must be hydro-tested for 24 hours prior to commissioning. |
| --- | --- |

Contractor’s Documents

| ## General | The Contractor shall submit to the Project Manager the documents listed below unless otherwise instructed by the Employer or the Project Manager. Any request for additional documentation by the EPA or another authority that is dealing with the permitting shall be forwarded to the Contractor by the Project Manager. All those documents shall be submitted by the Contractor in due course considering the program and the review period. The Project Manager shall be entitled to request any other document if reasonable and if required for the program. |
| --- | --- |
| ## Documents to be kept onsite | The Contractor shall keep the following documentation on Site: - A copy of all permits and licenses. - Sampling and testing records, calibration records. - Safety records. - A daily logbook of all construction activities. The format and content of the logbook shall be subject to the approval of the Project Manager. |
| ## Contractors program | The Contractor shall prepare a works program describing the sequences in which tasks had to be carried out so that a project (or part of a project) can be completed on time. The program shall be elaborated according the critical path method on with a common tool (Excel or Microsoft project). particular attention should be given to: - Pre-contract works (such as demolition or site clearance). - Prefabricated elements - Sub-contractors work - Sectional Completion - Milestones |

Site delineation, use, access, and possession details

| ## General | This section describes the location and boundaries of the Site and the location of the parts of the Site that the Contractor will be granted possession as well as of all access restrictions which may affect the Site. Approximate coordinates are given for each island, but the exact location will be given by the relevant authorities |
| --- | --- |
| ## Location | Lot 2 K. Maafushi 3°56'22.81"N 73°29'25.29"E K. Guraidhoo 3°53'54.12"N 73°28'7.24"E Lot 3 V. Thinadhoo 3°29'12.34"N 73°32'16.32"E V. Felidhoo 3°28'23.56"N 73°32'55.76"E Lot 4 V. Keyodhoo 3°27'48.57"N 73°33'5.25"E V. Rakeedhoo 3°18'51.99"N 73°28'8.97"E Lot 5 AD. Mahibadhoo 3°45'30.02"N 72°58'21.44"E AD. Hangnamedhoo 3°50'54.7"N 72°57'34.21"E Lot 6 AA. Himandhoo 3°55'14.94"N 72°44'50.50"E AA. Feridhoo 4°2'56.58"N 72°43'25.44"E Lot 7 AA. Thoddoo 4°25'48.81"N 72°57'47.54"E Lot 8 K. Kaashidhoo 4°57'17.1"N 73°28'5.22"E |
| ## Site delineation | The Site boundaries are shown on the layout drawing. The sites have the following surface and shape |

| ## Site restrictions | There are no site restrictions |
| --- | --- |
| ## Access to the Site | All sites are easily accessible through main roads (mainly unpaved) |
| ## Site Utilities | Water supply connection point: To be defined with respective authority Sewerage connection: Not currently existing Electricity connection point: To be defined with respective authority During the construction phase, the Contractor shall provide his own power supply system according to his needs. |

Site Organization

| ## General | This Section describes the requirements for the Contractor during the construction period particularly to organize his works based on effective and quality standards. |
| --- | --- |
| ## Site delineation and description | See section 7 of Employers requirement (Site delineation, use, access, and possession details) |
| ## Site program | The Contractor shall develop and submit a site Program according the requirements of chapter Phasing and section requirements and chapter Contractor’s document |
| ## Health, Safety, Environmental and social requirements | See section 11 of Employers Requirement |
| ## Works organization (sub-contractors etc…) | The Contractor shall maintain proper co-ordination and liaison between the Sub-Contractors (if any) for the civil works and other work parts and ensure the following: - Proper fixing of equipment in general accordance - The provision of holes or openings through walls for ducts or sleeves and sealing up around the duct or sleeve after completion of installation by the Contractor; - Provision of proper chases in concrete or block work or brickwork surfaces and making good thereof; and - Provision of temporary power facilities. |
| ## Plant and Labour Returns | The Contractor shall submit to the Project Manager every month a statement of the Contractor’s Equipment on Site. The Contractor shall submit every month statements of the Contractor’s Personnel on Site. |
| ## Site use | The Contractor shall not undertake any activities on the Site, other than those necessary to fulfil the purposes of this contract. Access and entry to the Site shall be granted by the Contractor to authorized personnel and vehicles only that are necessary to carry out the Works. All temporary Site installations shall comply with the requirements of local utility companies, and the general regulations concerning legal and industrial procedures for health and safety and protection of the environment. Arrangements for temporary power supply and motive power for Contractor’s and Project Manager’s facilities shall be the responsibility of the Contractor, who shall also bear the maintenance and consumption costs. The Contractor shall, if so required, decide with the local electricity provider to obtain the supply of electricity from existing installations. The site installation shall be independently protected according to local legislation. The Contractor shall ensure the protection of the Site against power failure. Alarm signals which may be necessary for the protection of the Site shall be provided by the Contractor. In case the electricity provider requires inspecting and approving the installations, the Contractor shall arrange for these. |
| ## Contractor’s Site Facilities | The Site arrangements, equipment, and facilities to be provided by the Contractor for his own purposes as well as for the Employer and Project Manager shall be developed and submitted for approval after contract award. Location The Contractor’s temporary site offices, stores and parking areas shall be located as close as possible to the Site, consistent with the requirement for him to minimize the environmental impact on the Site. Contractor’s Office The Contractor shall, before commencing work, setup an office for his own use. It shall be properly secure to keep safe the papers, documents and drawings handed to the Contractor by the Project Manager for use in carrying out the Works. |
| ## Security/fencing and signboards | The Contractor shall deliver, install, and maintain a security fence around the Site. Unless otherwise agreed with the Project Manager, project signboards shall be erected not more than 4 weeks after the date for commencement of the Works. Other advertising signs shall not be erected on the Site unless permitted by the Project Manager. |
| ## Fire protection | The Contractor shall provide and maintain all required temporary fire protection equipment during the performance of work according to local regulations and by laws. Burning rubbish and construction waste materials is not permitted, except land clearing-slash that may be allowed in strict conformance with existing regulations. |

Health & Safety Plan

Please refer to ITB Section 2 Clause 16.1 and Section 8 Particular Conditions of Contract Clause 24.2 The bidder’s Technical Proposal shall also include a Health and Safety COVID-19 Plan (HS-C19 Plan), in accordance with the relevant government regulations and guidelines on COVID-19 prevention and control or in the absence thereof, to international good practice guidelines, such as World Health Organization. 2020. Considerations for public health and social measures in the workplace in the context of COVID-19. Geneva. Available here: https://www.who.int/publications-detail/considerations-for-public-health-and-social-measures-in-the-workplace-in-the-context-of-covid-19. The bidder may also refer to the COVID-19 health and safety guidance given in the IEE report attached to this bidding document.

| ## General | The Contractor shall prepare a Health and Safety notice (H&S notice) describing all specific features that will ensure the health and safety protection of his staff (and subcontractor’s staff) and all other persons accessing the Site, for each of the various construction activities, during the implementation of the Works. The scope of the H&S plan shall address all of the issues itemized and committed in the National legal context with regard to : - Labour - Occupational and Community Health and Safety and shall be aligned with at least national standards for the management of E&S risks: Core Labour Standards from the International Labour Organization (ILO) ADB Environmental and Social Safeguards: Guidelines from the World Health Organization (WHO): The H&S plan shall be fixed, unchanged and valid during the complete construction period |
| --- | --- |
| ## Commitment | The Contractor shall ensure that his Project Manager and all key personnel including but not limited to professional engineers, site supervisors and all persons responsible for directing work on the site are familiar with the H&S notice and are required to adhere to its requirements. |
| ## Submission | The H&S plan shall be submitted to the Project Manager not later than 21 days after the Notice to Proceed and no physical work shall be carried out until the H&S plan has been approved by the Project Manager |
| ## Draft Content of the H&S notice | The plan shall detail all site-specific measures the Contractor shall implement during the construction period to identify, manage and reduce all accidents and nuisance caused by the lack of security, labour standards and health protection resulting from the construction activities including from project’s traffic along the access roads. |

Table 3.9.1: H&S content (to be updated by the Contractor before start of the Works)

| Topic/ Potential Impact | Mitigation, Management and Enhancement Measures | Means of Verification | Responsibility | Monitoring Procedure |
| --- | --- | --- | --- | --- |
| ## Occupational Health and Safety | Ensure site premises are provided with appropriate fencing (where applicable) and lighting. Use hazard notices/signs/barriers to prevent access to dangerous areas. | H&S planning of construction site done; items installed | Contractor | Random site inspection |
|  | Ensure the use of Personal Protective Equipment (PPE) for workers. | PPE used on-site by workers | Contractor | Random site inspection |
|  | Maintain high standard in housekeeping on site. | Good housekeeping on-site | Contractor | Random site inspection |
|  | Ensure provision of Health and Safety (H&S) facilities at the Project site | H&S Facilities provided at site | Contractor | Random site inspection |
|  | Ensure that the workers camp and construction areas are open only to formal employees. | Access controlled | Contractor | Random site inspection |
| ## Fire Prevention | Provide necessary fire prevention equipment on site in line with applicable regulations. | Fire prevention equipment in place | Contractor | Regular site inspection |
| ## Labour Rights | Ensure that workers have access to and are aware about the Grievance Mechanism | Grievance Mechanism in place and grievances recorded | PIA/ Contractor | Review of grievance register |
|  | Ensure minimum legal labour standards as per ILO regulations (child/forced labour, no discrimination, working hours, minimum wages) are met | Grievance Mechanism Records, Training recorded | Contractor | Inspection reports (also from labour authorities), Review of grievance register and training record |
|  | Provide hygienic, adequate facilities for workers | Appropriate facilities in place | Contractor | Random site inspection |
|  | Ensure the workforce has access to primary healthcare on site | First Aid Kit | Contractor | Random site inspection |
| ## Community Health and Safety | Ensure all contractors implement codes of conduct concerning employment and workforce behavior (including but not limited to safety rules, zero tolerance for substance abuse, environmental sensitivity of the area, dangers of sexually transmissible diseases and HIV/AIDS, gender equality and sexual harassment, respect for the beliefs and customs of the populations and community relations in general). | Workers Code of Conduct Grievance Mechanism records | Contractor/ ER | Worker interviews, Review of grievance register |
| ## Communicable Diseases | Report any occurrence of any communicable diseases amongst the workforce (STD, HIV/AIDS, TB, malaria and Hepatitis B and C) and set up disease prevention program if needed. | Communicable Diseases Register | Contractor | Review of diseases register and disease prevention program if available. |

# Site-Specific Environmental Management Plan (SEMP)

Consistent with PCC Clause 28, within 21 days from Notice to Proceed, the Contractor shall submit all specific management plans per Environmental Management Plan (EMP), including a detailed Site-Specific EMP (SEMP) for the Employer’s (through the PMU) no objection showing how the Contractor intends to comply with environmental laws and regulations and other specific requirements prescribed in the Contract, addressing all the mitigation measures and monitoring plan set forth in the final or updated Initial Environmental Examination (IEE) and the EMP of the project Work shall not commence on the Site until the no objection of SEMP has been obtained from the PMU and is being implemented. Such acceptance by the Employer, through the PMU, shall not relieve the Contractor of any of his obligations or responsibilities under the Contract.

Reporting and progress monitoring

| ## General | This section shall describe the Employer’s requirements for reporting and progress monitoring |
| --- | --- |

Table 3.10.1: Reporting requirements

| NO. | Name of the report | Number of originals/copies | Submission format | amendments | Frequency |
| --- | --- | --- | --- | --- | --- |
| 1 | Monthly or bi-monthly progress report (including a Monthly EHS activity report) | 1 original/2 copies | Hardcopy/softcopy |  | On the last day of each working month |
| 2 | Changes in the Contractor’s financial situation | 1 original | Hardcopy |  | - |
| 3 | On site logbook | 1 original | Hardcopy |  | On the last day of each working month |
| 4 | Records of Contractor’s personnel and Equipment | 1 original |  |  | On the last day of each working month |
| 5 | Commissioning test report | 1 original/2 copies | Hardcopy/softcopy |  | Once |

Table 3-10.2: Meeting requirements

| NO. | Name of the Meeting | Description | Frequency |
| --- | --- | --- | --- |
| 1 | Site meeting | A regular site meeting to discuss and resolve day to day issues amongst the Contractor and the Project Manager, a periodical technical site meeting shall be held on a fixe day (“jour fixe”) agreed between the Contractor and the Project Manager throughout the construction period | As possible 2 times per month |
| 2 | Monthly progress meeting | Apart from regular site meetings to discuss and resolve day to day issues amongst the Contractor and the Project Manager, Progress Meetings shall be held on a monthly bases unless agreed otherwise with the Employer/Project Manager throughout the construction period. The Contractor shall be notified at least 5 days prior to the meeting. The Contractor shall present the work process with reference to the work program, take detailed minutes and distribute them accordingly. The agenda shall be agreed amongst all parties in advance. | Upon agreement at a specific end of a month |
| 3 | Other specific meetings | In case meetings with outside bodies, e.g. presentation of the project to the public or any involved regulating authorities, the Contractor is obliged to send appropriate members of staff and assist the Project Manager with any required documentation. For specific meetings in the presence of senior/high level Representatives of the parties the Contractor shall be notified at least 14 days in advance of time and place of meeting. | Occasionally |

Testing and inspection requirements during construction

| ## General | During construction, the Contractor shall, as part of the Works, perform or cause to be performed any tests, procedures, as may be required by the laws, regulations, codes and standards to demonstrate or ensure that the Works are in conformity with, the Contract Documents, the laws and regulations, and these Employer’s Requirements respectively. The Employer reserves his right to request any additional test which is not explicitly listed in this chapter |
| --- | --- |
| ## Requested samples, tests, and procedures | In addition to the tests, studies and investigations required, the Contractor shall also perform, such tests, procedures, studies and investigations as may be reasonably requested by the Project Manager, prior to and during performance of each portion of the Work, and shall provide to the Project Manager, two (2) copies of each report made in connection with such tests, procedures, studies or investigations. Samples, tests and inspection requirements shall comply with the applicable laws and standards mentioned in chapter of laws, norms and standards particularly but without limiting: - For earthworks: BS 6031:2009 or similar; - For civil works: BS EN 12350-1:2000 and BS 1881-108:1983 or similar; - For drainage and water works: BS EN 1610:2015 or similar; - For installation works : BS 6700:2006 or similar; - For steel works (relevant steel codes according BS could be found on https://mdmetric.com/tech/bssteelcode.pdf)) or similar; |
| ## Inspection of reinforcement | The Contractor shall allow the Project Manager to inspect the completed reinforcement before carrying out any work, including erecting formwork adjacent to reinforcement. The Contractor shall inform the Project Manager 24 hours, or such shorter period agreed by the Project Manager, before carrying out such work. |

Commissioning

| ## General | The intention of the commissioning is to demonstrate that each element of the Works can be operated safely under all available operating conditions. The Contractor shall perform all necessary commissioning activities to ensure satisfactory operation and compliance with these Employer’s Requirements. All inspections and commissioning shall be clearly identified identifying the witness, inspection and hold points as required by the Contractor, the Project Manager or both. The Contractor shall elaborate a detailed program and shall give not less than 5 working days advance notice (in writing) of any testing and/or commissioning for the Employer or Project Manager to witness tests. Testing procedures shall be in accordance with requirements of this section, and the Employer’s Requirements and as determined by current national standards. All costs associated with testing shall be borne by the Contractor, including any expenses incurred due to re-testing caused by defects or failure of equipment to meet the requirements in the first instance. |
| --- | --- |
| ## Program on Tests on Completion of works | The Contractor shall submit for approval a commissioning and testing program that shall include full details of all tests to be carried out, standards or limits to be achieved, and the requirements to be fulfilled prior to each test program. No tests shall be carried out until the schedule has been approved by the Project Manager. The schedule may be submitted in stages, provided a list of stages has previously been approved. Test procedures shall show unambiguously the extent of testing covered by each submission, the method of testing, acceptance criteria, the relevant drawing (or modification) status, and the location. The Contractor shall assign in his program the responsibilities and roles of his personnel clearly and shall also define the requirements the Employer’s Personnel have to fulfil. The program of Tests on Completion shall consist of the following elements: - Pre-commissioning tests to satisfy the Employer’s requirement with respect to the functionally coherent and correct arrangement of the Works and to verify that all components of the Works are safe and fit for the purpose for which they were designed. |
| ## Test Reports | The Contractor shall provide reports on the Tests on Completion which shall record that the appropriate tests have been completed to demonstrate that the Works has been constructed in accordance with these Employer’s Requirements. The Contractor shall prepare and forward to the Project Manager an original and 3 copies of a test report no later than 14 days after completion of each test, whether witnessed by the Project Manager or not. |  |

2. Drawings

Attached separately.

3. Supplementary Information

(Regarding Works to Be Procured)

# Site-Specific Environmental Management Plan (SEMP)

| General | The Contractor shall prepare a Site-Specific Contractors Environmental Management Plan (SCEMP) describing specific design features that will ensure environmental protection and protection and setting out the working methods, management, and mitigation and monitoring measures that will be put in place, for each of the various construction activities, during the implementation of the Works. The scope of the SCEMP shall address all of the issues itemised in the project EMP contained with the Initial Environmental Examination as per Annex of this bid document |
| --- | --- |
| Commitment | The Contractor shall ensure that his Project Manager and all key personnel including but not limited to engineer, site supervisor and all persons responsible for directing work on the site are familiar with the SEMP and are required to adhere to its requirements. |
| Submission | The SEMP shall be submitted to the Employer’s Representative not later than 21 days after the Notice to Proceed and no physical work shall be carried out until the SEMP has been approved by the Employer’s Representative. |
| Monitoring and Reporting | The SEMP shall be monitored in accordance with project EMP contained with the Initial Environmental Examination. Should any environmental or Health and Safety incidents be observed or reported by the workers, this shall be reported to the Employer’s Representative immediately. |
| Draft Content of the SEMP | The plan shall detail all site-specific measures the Contractor shall implement during the construction period to identify, manage and reduce all nuisances caused from the construction activities. |

Table 1: 1st draft SEMP content (to be updated by the Contractor before the construction and if required during construction

| Impacts | Location | Mitigation Measures | Source of Funds | Responsibility for Implementation | Responsibility for Supervision |
| --- | --- | --- | --- | --- | --- |
| Pre-Construction Stage |  |  |  |  |  |
| Environmental degradation due to poor project planning | IWMC site | Preparation of SEMP including Covid-19 H&S plan and approval by PMU prior to start of construction activities. EMP included in the IEE can be used for this purpose with the approval of ADB and PMU. | Project fund | Contractor | PMDCSC |
| Construction stage impacts |  |  |  |  |  |
| Noise pollution and vibration | Nearest residential area | Identifying potentially affected households, providing information on operations, limiting construction activities to daylight hours, adhering to schedule, maintenance of construction equipment and vehicles in good operable order. | Construction Cost | Contractor | PMDCSC |
| Construction waste | IWMC area | All solid waste must be disposed of at the RWEMF/Thilafushi. Importation of any materials rated as hazardous under the Globally Harmonized System of Classification and Labelling of Chemicals to be subject to approval by PMDSC, which will be conditional on stating adequate arrangements for disposal. Prohibit burning of construction and/or domestic waste. Conduct site clearance and restoration to original condition after the completion of construction works. | Construction Cost | Contractor | PMDCSC |
| Release of silt | IWMC construction site | Excavated areas to be rapidly refilled on completion of works. Use of silt fences around temporary piles of excavated material. Avoid excavation in wet weather to the extent practicable. | Construction Cost | Contractor | PMDCSC |
| Water pollution | IWMC construction site | Vehicles and plant are to be maintained in sound operable condition, free of leaks. The condition of vehicles and equipment will be periodically checked. Contractor to prepare and submit a plan for spill management, including provision of spill kits, training/briefing of workers on procedures on handling spills and allocation of responsibility within the contractor's team for ensuring that spill kits are available and that workers know how to use them. | Construction Cost | Contractor | PMDCSC |
| Vegetation | Proposed IWMC area | The trees proposed to be removed can be relocated. There is empty area just outside the land plot where the material storage is temporarily proposed. After the commencement of the project, subject to issuance of permits a green belt could be installed surrounding the waste site, under the responsibility of the island council. | Construction Cost | Island council | PMDCSC |
| Community health and safety hazards | IWMC construction site and immediate surrounds | Restriction of access to work site, warning notices to the public on hazards, barriers when warranted. If the workforce is sourced from an island with COVID-19 community spread, the workers must be tested negative for COVID-19 before the start of the construction work. | Construction Cost | Contractor | PMDCSC |
| Occupational health and safety hazards | IWMC construction site | Contractor to focal point for health and safety at site and to ensure regular briefing of construction workforce on health and safety issues. Adequate personal protective equipment to be provided to the workforce. | Construction Cost | Contractor | PMDCSC |

4. Personnel Requirements (per lot)

Using Form PER - 1 and PER - 2 in Section 4 (Bidding Forms), the Bidder must demonstrate that it has personnel who meet the following requirements:

Per Lot (in case the bidder wants to apply for more than one lot he should provide the number of staff required below x amount of lots (maximum 3 lots))

| No. | Position | No. | Professional Qualification / Work Experience [years] | Experience in Similar Work [years] |
| --- | --- | --- | --- | --- |
| 1 | Construction Manager | 1 per Lot | Min. Diploma or equivalent in Civil Engineering, Construction Management or related field | 5 |
| 2 | Construction Supervisor | 1 per Site | Suitable qualification (professional certificate) or equivalent experience | 3 |
| 3 | Skilled labour | 3 per site | Experience in masonry, structural steel works, electrical works | 3 |
| 4 | Unskilled labour | 5 per site |  | 3 |

5. Equipment Requirements

Using Form EQU in Section 4 (Bidding Forms), the Bidder must demonstrate that it has the key equipment listed below:

Per Lot (in case the bidder wants to apply for more than one lot he should provide the number of equipment required below x amount of lots (maximum 3 lots))

| No. | Equipment Type and Characteristics | Minimum Number Required per lot (Lot 1 to 6) |
| --- | --- | --- |
| 1 | Concrete Mixer | 2 |
| 2 | Vibrator / Plate Compactor | 2 |
| 3 | Welding Genset / Welding Transformer | 2 |

| No. | Equipment Type and Characteristics | Minimum Number Required per lot (Lot 7 & 8) |
| --- | --- | --- |
| 1 | Concrete Mixer | 2 |
| 2 | Vibrator / Plate Compactor | 2 |
| 3 | Welding Genset / Welding Transformer | 2 |

Part 3

Section 7, 8 and 9

Contract Data

Section 7 - General Conditions of Contract

|  | A. General |
| --- | --- |
| 1. Definitions | 1.1 Boldface type is used to identify defined terms. - The Accepted Contract Amount means the amount accepted in the Letter of Acceptance for the execution and completion of the Works and the remedying of any defects. - The Activity Schedule is a schedule of the activities comprising the construction, installation, testing, and commissioning of the Works in a lump sum contract. It includes a lump sum price for each activity, which is used for valuations and for assessing the effects of Variations and Compensation Events. - The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in GCC 29.1 [Appointment of Adjudicator] hereunder. - Bank means the financing institutions named in the Particular Conditions of Contract (PCC). - Bill of Quantities means the priced and completed Bill of Quantities forming part of the Bid. - Compensation Events are those defined in GCC 51.1 [Compensation Events] hereunder. - The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with GCC 69.1 [Completion]. - The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in GCC 2.3 below. - The Contractor is the party whose Bid to carry out the Works has been accepted by the Employer. - The Contractor’s Bid is the completed bidding document submitted by the Contractor to the Employer. - The Contract Price is the Accepted Contract Amount stated in the Letter of Acceptance and thereafter as adjusted in accordance with the Contract. - Days are calendar days; months are calendar months. - Dayworks are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant. - A Defect is any part of the Works not completed in accordance with the Contract. - The Defects Liability Certificate is the certificate issued by the Project Manager upon correction of defects by the Contractor. - The Defects Liability Period is the period calculated from the Completion Date where the Contractor remains responsible for remedying defects. - Drawings include calculations and other information provided or approved by the Project Manager for the execution of the Contract. - The Employer is the party who employs the Contractor to carry out the Works, as specified in the PCC. - Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. - Force Majeure means an exceptional event or circumstance: which is beyond a Party's control; which such Party could not reasonably have provided against before entering into the Contract; which, having arisen, such Party could not reasonably have avoided or overcome; and, which is not substantially attributable to the other Party. - In writing or written means hand-written, type-written, printed or electronically made, and resulting in a permanent record. - The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. - The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the PCC. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. - Letter of Acceptance means the formal acceptance by the Employer of the Bid and denotes the formation of the Contract at the date of acceptance. - Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. - Party means the Employer or the Contractor, as the context requires. - PCC means Particular Conditions of Contract. - Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. - The Project Manager is the person named in the PCC (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. - Retention Money means the aggregate of all monies retained by the Employer pursuant to GCC 55.1 [Retention]. - Schedules means the document(s) entitled schedules, completed by the Contractor and submitted with the Letter of Tender, as included in the Contract. Such document may include the Bill of Quantities, data, lists, and schedules of rates and/or prices. - The Site is the area defined as such in the PCC. - Site Investigation Reports are those that were included in the bidding documents and are factual and interpretive reports about the surface and subsurface conditions at the Site. - Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. - The Start Date is given in the PCC. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. - A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. - Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. - A Variation is an instruction given by the Project Manager which varies the Works. - The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the PCC. |
| 2. Interpretation | 2.1 In interpreting these GCC, singular also means plural, male also means female or neuter, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager shall provide instructions clarifying queries about these GCC. |
|  | 2.2 If sectional completion is specified in the PCC, references in the GCC to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). |
|  | 2.3 The documents forming the Contract shall be interpreted in the following order of priority: - Contract Agreement, - Letter of Acceptance, - Letter of Bid, - Particular Conditions of Contract, - the List of Eligible Countries that was specified in Section 5 of the bidding document, - General Conditions of Contract, - Specifications, - Drawings, - Completed Activity Schedules or Bill of Quantities, and - any other document listed in the PCC as forming part of the Contract. |
| 3. Language and Law | 3.1 The language of the Contract and the law governing the Contract are stated in the PCC. 3.2 Throughout the execution of the Contract, the Contractor shall comply with the import of goods and services prohibitions in the Employer’s country when - by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from, or any payments to, a particular country, person, or entity. Where the borrower’s country prohibits payments to a particular firm or for particular goods by such an act of compliance, that firm may be excluded. |
| 4. Contract Agreement | 4.1 The Parties shall enter into a Contract Agreement within 28 days after the Contractor receives the Letter of Acceptance, unless the Particular Conditions establish otherwise. The Contract Agreement shall be based upon the attached Contract forms in Section 8. The costs of stamp duties and similar charges (if any) imposed by law in connection with entry into the Contract Agreement shall be borne by the Employer. |
| 5. Assignment | 5.1 Neither Party shall assign the whole or any part of the Contract or any benefit or interest in or under the Contract. However, either Party - may assign the whole or any part with the prior agreement of the other Party, at the sole discretion of such other Party; and - may, as security in favor of a bank or financial institution, assign its right to any moneys due, or to become due, under the Contract. |
| 6. Care and Supply of Documents | 6.1 The Specification and Drawings shall be in the custody and care of the Employer. Unless otherwise stated in the Contract, two copies of the Contract and of each subsequent Drawing shall be supplied to the Contractor, who may make or request further copies at the cost of the Contractor. |
|  | 6.2 Each of the Contractor’s Documents shall be in the custody and care of the Contractor, unless and until taken over by the Employer. Unless otherwise stated in the Contract, the Contractor shall supply to the Engineer six copies of each of the Contractor’s Documents. |
|  | 6.3 The Contractor shall keep, on the Site, a copy of the Contract, publications named in the Specification, the Contractor’s Documents (if any), the Drawings and Variations and other communications given under the Contract. The Employer’s Personnel shall have the right of access to all these documents at all reasonable times. 6.4 If a Party becomes aware of an error or defect in a document which was prepared for use in executing the Works, the Party shall promptly give notice to the other Party of such error or defect. |
| 7. Confidential Details | 7.1 The Contractor’s and the Employer’s Personnel shall disclose all such confidential and other information as may be reasonably required in order to verify the Contractor’s compliance with the Contract and allow its proper implementation. |
|  | 7.2 Each of them shall treat the details of the Contract as private and confidential, except to the extent necessary to carry out their respective obligations under the Contract or to comply with applicable Laws. Each of them shall not publish or disclose any particulars of the Works prepared by the other Party without the previous agreement of the other Party. However, the Contractor shall be permitted to disclose any publicly available information, or information otherwise required to establish his qualifications to compete for other projects. |
|  | 7.3 Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor under this Clause. |
| 8. Compliance with Laws | 8.1 The Contractor shall, in performing the Contract, comply with applicable Laws. |
|  | 8.2 Unless otherwise stated in the Particular Conditions, - the Employer shall acquire and pay for all permits, approvals, and/or licenses from all local, state, or national government authorities or public service undertakings in the [Employer’s Country or country where the Site is located] which (i) such authorities or undertakings require the Employer to obtain in the Employer’s name, and (ii) are necessary for the execution of the Contract, including those required for the performance by both the Contractor and the Employer of their respective obligations under the Contract; - the Contractor shall acquire and pay for all permits, approvals, and/or licenses from all local, state, or national government authorities or public service undertakings in the [Employer’s Country or country where the Site is located] which such authorities or undertakings require the Contractor to obtain in its name and which are necessary for the performance of the Contract, including, without limitation, visas for the Contractor’s and Subcontractor’s personnel and entry permits for all imported Contractor’s Equipment. The Contractor shall acquire all other permits, approvals, and/or licenses that are not the responsibility of the Employer under Subclause 8.2(a) hereof and that are necessary for the performance of the Contract. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties, and expenses of whatever nature arising or resulting from the violation of such laws by the Employer or its personnel, including the Subcontractors and their personnel, but without prejudice to Subclause 8.1 hereof. |
| 9. Joint and Several Liability | 9.1 If the Contractor is a joint venture of two or more persons, all such persons shall be jointly and severally liable to the Employer for the fulfillment of the provisions of the Contract, and shall designate one of such persons to act as a leader with authority to bind the joint venture. The composition or the constitution of the joint venture shall not be altered without the prior consent of the Employer. |
| 10. Project Manager’s Decisions | 10.1 Except where otherwise specifically stated, the Project Manager shall decide contractual matters between the Employer and the Contractor in the role representing the Employer. |
| 11. Delegation | 11.1 The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. |
| 12. Communications | 12.1 Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| 13. Subcontracting | 13.1 The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations. |
| 14. Other Contractors | 14.1 The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the PCC. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification. |
| 15. Personnel and Equipment | 15.1 The Contractor shall employ the key personnel and use the equipment identified in its Bid to carry out the functions stated in the Schedule or other personnel and equipment approved by the Project Manager. The Project Manager shall approve any proposed replacement of key personnel and equipment only if their relevant qualifications or characteristics are substantially equal to or better than those proposed in the Bid. |
|  | 15.2 If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within 7 days and has no further connection with the work in the Contract. 15.3 If the Employer, Project Manager, or Contractor determines, that any employee of the Contractor be determined to have engaged in corrupt, fraudulent, collusive, coercive, or other prohibited practices during the execution of the Works, then that employee shall be removed in accordance with Clause 15.2 above. |
| 16. Employer’s and Contractor’s Risks | 16.1 The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| 17. Employer’s Risks | 17.1 From the Start Date until the Defects Liability Certificate has been issued, the following are Employer’s risks: (a) The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to (i) use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or (ii) negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor. (b) The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed. |
|  | 17.2 From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to (a) a Defect which existed on the Completion Date, (b) an event occurring before the Completion Date, which was not itself an Employer’s risk, or (c) the activities of the Contractor on the Site after the Completion Date. |
| 18. Contractor’s Risks | 18.1 From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks, are Contractor’s risks. |
| 19. Insurance | 19.1 The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the PCC for the following events, which are due to the Contractor’s risks: (a) loss of or damage to the Works, Plant, and Materials; (b) loss of or damage to Equipment; (c) loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and (d) personal injury or death. |
|  | 19.2 Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. |
|  | 19.3 If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance, which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
|  | 19.4 Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
|  | 19.5 Both parties shall comply with any conditions of the insurance policies. |
| 20. Site Investigation Reports | 20.1 The Contractor, in preparing the Bid, shall rely on any Site Investigation Reports referred to in the PCC, supplemented by any information available to the Contractor. |
| 21. Contractor to Construct the Works | 21.1 The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| 22. The Works to Be Completed by the Intended Completion Date | 22.1 The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| 23. Designs by Contractor and Approval by the Project Manager | 23.1 The Contractor shall carry out design to the extent specified in the PCC. The Contractor shall promptly submit to the Employer all designs prepared by him. Within 14 days of receipt, the Employer shall notify any comments. The Contractor shall not construct any element of the permanent work designed by him within 14 days after the design has been submitted to the Employer or where the design for that element has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on, taking these comments into account as necessary. |
|  | 23.2 The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, who is to approve them if they comply with the Specifications and Drawings.. |
|  | 23.3 The Contractor shall be responsible for design of Temporary Works. |
|  | 23.4 The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. |
|  | 23.5 The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required. |
|  | 23.6 All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before this use. |
| 24. Safety | 24.1 The Contractor shall be responsible for the safety of all activities on the Site. |
| 25. Discoveries | 25.1 Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| 26. Possession of the Site | 26.1 The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the PCC, the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event. |
| 27. Access to the Site | 27.1 The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |
| 28. Instructions, Inspections, and Audits | 28.1 The Contractor shall carry out all instructions of the Project Manager, which comply with the applicable laws where the Site is located. 28.2 The Contractor shall keep, and shall make all reasonable efforts to cause its Subcontractors and subconsultants to keep accurate and systematic accounts and records in respect of the Works in such form and details as will clearly identify relevant time changes and costs. |
|  | 28.3 The Contractor shall permit ADB to inspect the Contractor’s accounts, records, and other documents relating to the submission of bids and contract performance and to have them audited by auditors appointed by ADB. The Contractor shall maintain all documents and records related to the Contract for a period of three (3) years after completion of the Works. The Contractor shall provide any documents necessary for the investigation of allegations of fraud, collusion, coercion, or corruption and require its employees or agents with knowledge of the Contract to respond to questions from ADB. |
| 29. Appointment of the Adjudicator | 29.1 The Adjudicator shall be appointed jointly by the Employer and the Contractor, at the time of the Employer’s issuance of the Letter of Acceptance. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator, the Employer will request the Appointing Authority designated in the PCC, to appoint the Adjudicator within 14 days of receipt of such request. |
|  | 29.2 Should the Adjudicator resign or die, or should the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator shall be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within 30 days, the Adjudicator shall be designated by the Appointing Authority at the request of either party, within 14 days of receipt of such request. |
| 30. Procedure for Disputes | 30.1 If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within 14 days of the notification of the Project Manager’s decision. |
|  | 30.2 The Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute. |
|  | 30.3 The Adjudicator shall be paid by the hour at the rate specified in the PCC, together with reimbursable expenses of the types specified in the PCC, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s decision shall be final and binding. |
|  | 30.4 The arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place specified in the PCC. |
| B. Staff and Labor |  |
| 31. Forced Labor | 31.1 The Contractor shall not employ forced labor, which consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty. This covers any kind of involuntary or compulsory labor, such as indentured labor, bonded labor, or similar labor–contracting arrangements. |
| 32. Child Labor | 32.1 The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. Where national laws have provisions for employment of minors, the Contractor shall follow those laws applicable to the Contractor. Children below the age of 18 years shall not be employed in dangerous work. |
| 33. Workers’ Organizations | 33.1 In countries where national law recognizes workers’ rights to form and to join workers’ organizations of their choosing without interference and to bargain collectively, the Contractor shall comply with national law. Where national law substantially restricts workers’ organizations, the Contractor shall enable alternative means for the Contractor’s Personnel to express their grievances and protect their rights regarding working conditions and terms of employment. In either case described above, and where national law is silent, the Contractor shall not discourage the Contractor’s Personnel from forming or joining workers’ organizations of their choosing or from bargaining collectively, and shall not discriminate or retaliate against the Contractor’s Personnel who participate, or seek to participate, in such organizations and bargain collectively. The Contractor shall engage with such workers representatives. Worker organizations are expected to fairly represent the workers in the workforce. |
| 34. Nondiscrimination and Equal Opportunity | 34.1 The Contractor shall not make employment decisions on the basis of personal characteristics unrelated to inherent job requirements. The Contractor shall base the employment relationship on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, promotion, termination of employment or retirement, and discipline. In countries where national law provides for non-discrimination in employment, the Contractor shall comply with national law. When national laws are silent on nondiscrimination in employment, the Contractor shall meet this Subclause’s requirements. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. |

| C. Time Control |  |
| --- | --- |
| 35. Program | 35.1 Within the time stated in the PCC, after the date of the Letter of Acceptance, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. In the case of a lump sum contract, the activities in the Program shall be consistent with those in the Activity Schedule. |
|  | 35.2 An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. |
|  | 35.3 The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the PCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the PCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted. In the case of a lump sum contract, the Contractor shall provide an updated Activity Schedule within 14 days of being instructed to by the Project Manager. |
|  | 35.4 The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| 36. Extension of the Intended Completion Date | 36.1 The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
|  | 36.2 The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |
| 37. Acceleration | 37.1 When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager shall obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date shall be adjusted accordingly and confirmed by both the Employer and the Contractor. |
|  | 37.2 If the Contractor’s priced proposals for an acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation. |
| 38. Delays Ordered by the Project Manager | 38.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| 39. Management Meetings | 39.1 Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure. |
|  | 39.2 The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| 40. Early Warning | 40.1 The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price, or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. |
|  | 40.2 The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |

|  | D. Quality Control |
| --- | --- |
| 41. Identifying Defects | 41.1 The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |
| 42. Tests | 42.1 If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| 43. Correction of Defects | 43.1 The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the PCC. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. |
|  | 43.2 Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| 44. Uncorrected Defects | 44.1 If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager shall assess the cost of having the Defect corrected, and the Contractor shall pay this amount. |

|  | E. Cost Control |
| --- | --- |
| 45. Contract Price | 45.1 In the case of an admeasurement contract, the Bill of Quantities shall contain priced items for the Works to be performed by the Contractor. The Bill of Quantities is used to calculate the Contract Price. The Contractor will be paid for the quantity of the work accomplished at the rate in the Bill of Quantities for each item. |
|  | 45.2 In the case of a lump sum contract, the Activity Schedule shall contain the priced activities for the Works to be performed by the Contractor. The Activity Schedule is used to monitor and control the performance of activities on which basis the Contractor will be paid. If payment for Materials on Site shall be made separately, the Contractor shall show delivery of Materials to the Site separately on the Activity Schedule. |
| 46. Changes in the Contract Price | 46.1 In the case of an admeasurement contract: (a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25%, provided the change exceeds 1% of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change. (b) The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15%, except with the prior approval of the Employer. (c) If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. |
|  | 46.2 In the case of a lump sum contract, the Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| 47. Variations | 47.1 All Variations shall be included in updated Programs, and, in the case of a lump sum contract, also in the Activity Schedule, produced by the Contractor. |
|  | 47.2 The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven (7) days of the request or within any longer period stated by the Project Manager and before the Variation is ordered. |
|  | 47.3 If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
|  | 47.4 If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. |
|  | 47.5 The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
|  | 47.6 In the case of an admeasurement contract, if the work in the Variation corresponds to an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in GCC 46.1 [Changes in the Contract Price] or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| 48. Cash Flow Forecasts | 48.1 When the Program, or, in the case of a lump sum contract, the Activity Schedule, is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. The cash flow forecast shall include different currencies, as defined in the Contract, converted as necessary using the Contract exchange rates. |
| 49. Payment Certificates | 49.1 The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously. |
|  | 49.2 The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor. |
|  | 49.3 The value of work executed shall be determined by the Project Manager. |
|  | 49.4 The value of work executed shall comprise, (a) in the case of an admeasurement contract, the value of the quantities of work in the Bill of Quantities that have been completed; or (b) in the case of a lump sum contract, the value of work executed shall comprise the value of completed activities in the Activity Schedule. |
|  | 49.5 The value of work executed shall include the valuation of Variations and Compensation Events. |
|  | 49.6 The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. |
| 50. Payments | 50.1 Payments shall be adjusted for deductions for advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made. |
|  | 50.2 If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. |
|  | 50.3 Unless otherwise stated, all payments and deductions shall be paid or charged in the proportions of currencies comprising the Contract Price. |
|  | 50.4 Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |
| 51. Compensation Events | 51.1 The following shall be Compensation Events: (a) The Employer does not give access to a part of the Site by the Site Possession Date pursuant to GCC 26.1 [Possession of the Site]. (b) The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. (c) The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. (d) The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. (e) The Project Manager unreasonably does not approve a subcontract to be let. (f) Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to Bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site. (g) The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons. (h) Other contractors, public authorities, utilities, or the Employer does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor. (i) The advance payment is delayed. (j) The effects on the Contractor of any of the Employer’s Risks. (k) The Project Manager unreasonably delays issuing a Certificate of Completion. |
|  | 51.2 If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. |
|  | 51.3 As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager shall assume that the Contractor shall react competently and promptly to the event. |
|  | 51.4 The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| 52. Tax | 52.1 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of bids for the Contract and the date of the last Completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of GCC 54.1 [Price Adjustment]. |
| 53. Currencies | 53.1 Where payments are made in currencies other than the currency of the Employer’s country specified in the PCC, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Bid. |
| 54. Price Adjustment | 54.1 Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the PCC. If so provided, the amounts certified in each payment certificate, before deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency. A separate formula of the type indicated below applies to each Contract currency: Pc = Ac + Bc Imc/Ioc where: Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c.” Ac and Bc are coefficients specified in the PCC, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c;” and Imc is a consolidated index prevailing at the end of the month being invoiced and Ioc is the same consolidated index prevailing 28 days before Bid opening for inputs payable; both in the specific currency “c.” |
|  | 54.2 If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs. |
| 55. Retention | 55.1 The Employer shall retain from each payment due to the Contractor the proportion stated in the PCC until Completion of the whole of the Works. |
|  | 55.2 Upon the issue of a Certificate of Completion of the Works by the Project Manager, in accordance with GCC 69.1 [Completion], half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. The Contractor may substitute retention money with an “on demand” bank guarantee. |
| 56. Liquidated Damages | 56.1 The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the PCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the PCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
|  | 56.2 If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC 50.1 [Payments]. |
| 57. Bonus | 57.1 The Contractor shall be paid a Bonus calculated at the rate per calendar day stated in the PCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Project Manager shall certify that the Works are complete, although they may not be due to be complete. |
| 58. Advance Payment | 58.1 The Employer shall make advance payment to the Contractor of the amounts stated in the PCC by the date stated in the PCC, against provision by the Contractor of an unconditional bank guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The guarantee shall remain effective until the advance payment has been repaid, but the amount of the guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest shall not be charged on the advance payment. |
|  | 58.2 The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. |
|  | 58.3 The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages. |
| 59. Securities | 59.1 The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount specified in the PCC, by a bank acceptable to the Employer, and denominated in the types and proportions of the currencies in which the Contract Price is payable. The Performance Security shall be valid until a date 28 days from the date of issue of the Certificate of Completion in the case of a bank guarantee. |
| 60. Dayworks | 60.1 If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. |
|  | 60.2 All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within 2 days of the work being done. |
|  | 60.3 The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| 61. Cost of Repairs | 61.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| F. Force Majeure |  |
| 62. Definition of Force Majeure | 62.1 In this Clause, “Force Majeure” means an exceptional event or circumstance, (a) which is beyond a Party’s control; (b) which such Party could not reasonably have provided against before entering into the Contract; (c) which, having arisen, such Party could not reasonably have avoided or overcome; and (d) which is not substantially attributable to the other Party. |
|  | 62.2 Force Majeure may include, but is not limited to, exceptional events or circumstances of the kind listed below, so long as conditions (a) to (d) above are satisfied: (a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies; (b) rebellion, terrorism, sabotage by persons other than the Contractor’s Personnel, revolution, insurrection, military or usurped power, or civil war; (c) riot, commotion, disorder, strike or lockout by persons other than the Contractor’s Personnel; (d) munitions of war, explosive materials, ionizing radiation or contamination by radio-activity, except as may be attributable to the Contractor’s use of such munitions, explosives, radiation or radio-activity; and (e) natural catastrophes such as earthquake, hurricane, typhoon, or volcanic activity. |
| 63. Notice of Force Majeure | 63.1 If a Party is or will be prevented from performing its substantial obligations under the Contract by Force Majeure, then it shall give notice to the other Party of the event or circumstances constituting the Force Majeure and shall specify the obligations, the performance of which is or will be prevented. The notice shall be given within 14 days after the Party became aware, or should have become aware, of the relevant event or circumstance constituting Force Majeure. |
|  | 63.2 The Party shall, having given notice, be excused performance of its obligations for so long as such Force Majeure prevents it from performing them. |
|  | 63.3 Notwithstanding any other provision of this Clause, Force Majeure shall not apply to obligations of either Party to make payments to the other Party under the Contract. |
| 64. Duty to Minimize Delay | 64.1 Each Party shall at all times use all reasonable endeavors to minimize any delay in the performance of the Contract as a result of Force Majeure. |
|  | 64.2 A Party shall give notice to the other Party when it ceases to be affected by the Force Majeure. |
| 65. Consequences of Force Majeure | 65.1 If the Contractor is prevented from performing its substantial obligations under the Contract by Force Majeure of which notice has been given under GCC Subclause 63 [Notice of Force Majeure], and suffers delay and/or incurs Cost by reason of such Force Majeure, the Contractor shall be entitled subject to GCC Subclause 30.1 [Procedure for Disputes] to (a) an extension of time for any such delay, if completion is or will be delayed, under GCC Subclause 36 [Extension of the Intended Completion Date]; and (b) if the event or circumstance is of the kind described in sub-paragraphs (a) to (d) of GCC Subclause 62.2 [Definition of Force Majeure] and, in the case of subparagraphs (b) to (d), occurs in the Country, payment of any such Cost, including the costs of rectifying or replacing the Works and/or Goods damaged or destructed by Force Majeure, to the extent they are not indemnified through the insurance policy referred to in GCC Subclause 19 [Insurance]. |
|  | 65.2 After receiving this notice, the Project Manager shall proceed in accordance with GCC Subclause 10 [Project Manager’s Decisions] to agree or determine these matters. |
| 66. Force Majeure Affecting Subcontractor | 66.1 If any Subcontractor is entitled under any contract or agreement relating to the Works to relief from force majeure on terms additional to or broader than those specified in this Clause, such additional or broader Force Majeure events or circumstances shall not excuse the Contractor’s nonperformance or entitle him to relief under this Clause. |
| 67. Optional Termination, Payment and Release | 67.1 If the execution of substantially all the Works in progress is prevented for a continuous period of 84 days by reason of Force Majeure of which notice has been given under GCC Subclause 63 [Notice of Force Majeure], or for multiple periods which total more than 140 days due to the same notified Force Majeure, then either Party may give to the other Party a notice of termination of the Contract. In this event, the termination shall take effect 7 days after the notice is given, and the Contractor shall proceed in accordance with GCC Subclause 73.5 [Termination]. |
|  | 67.2 Upon such termination, the Project Manager shall determine the value of the work done and issue a Payment Certificate, which shall include (a) the amounts payable for any work carried out for which a price is stated in the Contract; (b) the Cost of Plant and Materials ordered for the Works which have been delivered to the Contractor, or of which the Contractor is liable to accept delivery: this Plant and Materials shall become the property of (and be at the risk of) the Employer when paid for by the Employer, and the Contractor shall place the same at the Employer’s disposal; (c) other Costs or liabilities which in the circumstances were reasonably and necessarily incurred by the Contractor in the expectation of completing the Works; (d) the Cost of removal of Temporary Works and Contractor’s Equipment from the Site and the return of these items to the Contractor’s works in his country (or to any other destination at no greater cost); and (e) the Cost of repatriation of the Contractor’s staff and labor employed wholly in connection with the Works at the date of termination. |
| 68. Release from Performance | 68.1 Notwithstanding any other provision of this Clause, if any event or circumstance outside the control of the Parties (including, but not limited to, Force Majeure) arises, which makes it impossible or unlawful for either or both Parties to fulfill its or their contractual obligations or which, under the law governing the Contract, entitles the Parties to be released from further performance of the Contract, then upon notice by either Party to the other Party of such event or circumstance, (a) the Parties shall be discharged from further performance, without prejudice to the rights of either Party in respect of any previous breach of the Contract; and (b) the sum payable by the Employer to the Contractor shall be the same as would have been payable under GCC Subclause 67 [Optional Termination, Payment and Release] if the Contract had been terminated under GCC Subclause 67. |

|  | G. Finishing the Contract |
| --- | --- |
| 69. Completion | 69.1 The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager shall do so upon deciding that the work is completed. |
| 70. Taking Over | 70.1 The Employer shall take over the Site and the Works within 7 days of the Project Manager’s issuing a certificate of Completion. |
| 71. Final Account | 71.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| 72. Operating and Maintenance Manuals | 72.1 If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the PCC. |
|  | 72.2 If the Contractor does not supply the Drawings and/or manuals by the dates stated in the PCC pursuant to GCC 72.1, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the PCC from payments due to the Contractor. |
| 73. Termination | 73.1 The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. |
|  | 73.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following: (a) the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager. (b) the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days; (c) the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation. (d) a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate. (e) the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager. (f) the Project Manager gives two consecutive Notices to update the Program and accelerate the works to ensure compliance with GCC Subclause 22.1 [The Works to be Completed by the Intended Completion Date] and the Contractor fails to update the Program and demonstrate acceleration of the works within a reasonable period of time determined by the Project Manager. (g) the Contractor does not maintain a Security, which is required; (h) the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the PCC; and (i) if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract, pursuant to GCC 74.1 [Fraud and Corruption]. |
|  | 73.3 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC 73.2 above, the Project Manager shall decide whether the breach is fundamental or not. |
|  | 73.4 Notwithstanding the above, the Employer may terminate the Contract for convenience. |
|  | 73.5 If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| 74. Fraud and Corruption | 74.1 ADB’s Anticorruption Policy requires Borrowers (including beneficiaries of ADB-financed activity), as well as Contractors, Subcontractors, Manufacturers, and Consultants under ADB-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the ADB - defines, for the purposes of this provision, the terms set forth below as follows: #### “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; #### “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; #### “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; #### “collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party; #### “obstructive practice” means (a) deliberately destroying, falsifying, altering, or concealing of evidence material to an ADB investigation; (b) making false statements to investigators in order to materially impede an ADB investigation; (c) failing to comply with requests to provide information, documents, or records in connection with an Office of Anticorruption and Integrity (OAI) investigation; (d) threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or (e) materially impeding ADBʼs contractual rights of audit or access to information; and #### “integrity violation" is any act which violates ADB’s Anticorruption Policy, including (i) to (v) above and the following: abuse, conflict of interest, violations of ADB sanctions, retaliation against whistleblowers or witnesses, and other violations of ADB's Anticorruption Policy, including failure to adhere to the highest ethical standard. - will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations in competing for the Contract; - will cancel the portion of the financing allocated to a contract if it determines at any time that representatives of the borrower or of a beneficiary of ADB-financing engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations during the procurement or the execution of that contract, without the borrower having taken timely and appropriate action satisfactory to ADB to remedy the situation; and - will impose remedial actions on a firm or an individual, at any time, in accordance with ADB’s Anticorruption Policy and Integrity Principles and Guidelines (both as amended from time to time), including declaring ineligible, either indefinitely or for a stated period of time, to participate in ADB-financed, -administered, or -supported activities or to benefit from an ADB-financed, -administered, or -supported contract, financially or otherwise, if it at any time determines that the firm or individual has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations. |
| 75. Payment upon Termination | 75.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the PCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. |
|  | 75.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| 76. Property | 76.1 All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |
| 77. Release from Performance | 77.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterward to which a commitment was made. |
| 78. Suspension of ADB Loan or Credit | 78.1 In the event that ADB suspends the Loan or Credit to the Employer, from which part of the payments to the Contractor are being made, (a) the Employer is obligated to notify the Contractor, with copy to the Project Manager, of such suspension within 7 days of having received ADB’s suspension notice. (b) if the Contractor has not received sums due it within the 28 days for payment provided for in GCC 50.1 [Payments], the Contractor may immediately issue a 14-day termination notice. |
| 79. Eligibility | 79.1 The Contractor shall have the nationality of an eligible country as specified in Section 5 [Eligible Countries] of the bidding document. The Contractor shall be deemed to have the nationality of a country if the Contractor is a citizen or is constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract including related services. |
|  | 79.2 The materials, equipment, and services to be supplied under the Contract shall have their origin in eligible source countries as specified in Section 5 [Eligible Countries] of the bidding document and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, the Contractor may be required to provide evidence of the origin of materials, equipment, and services. |
|  | 79.3 For purposes of GCC 79.2, “origin” means the place where the materials and equipment are mined, grown, produced, or manufactured, and from which the services are provided. Materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that differs substantially in its basic characteristics or in purpose or utility from its components. |

Section 8 - Particular Conditions of Contract

The following Particular Conditions of Contract shall supplement the GCC. Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| A. General |  |
| --- | --- |
| GCC 1.1 (d) | The financing institutions is Asian Development Bank |
| GCC 1.1 (r) | The Employer is Ministry of Environment, Climate Change and Technology of the Republic of the Maldives |
| GCC 1.1 (w) | The Intended Completion Date for the whole of the Works shall be Lot 2: 120 days from contract signing Lot 3: 120 days from contract signing Lot 4: 120 days from contract signing Lot 5: 150 days from contract signing Lot 6: 150 days Months from contract signing Lot 7: 150 days from contract signing Lot 8: 150 days from contract signing In case of a contractor being awarded more than 1 lot or multiple lots, the works on these lots shall be carried out simultaneously & not consecutively. |
| GCC 1.1 (cc) | The Project Manager will be Project Management, Design and Construction Supervision Consultants. |
| GCC 1.1 (ff) | The Site is located at; Lot 2: K. Maafushi & K. Guraidhoo Lot 3: V. Thinadhoo & V. Felidhoo Lot 4: V. Keyodhoo & V. Rakeedhoo Lot 5: AD. Mahibadhoo & AD. Hangnameedhoo Lot 6: AA. Himandhoo & AA. Feridhoo Lot 7: AA. Thoddoo Lot 8: K. Kaashidhoo and is defined in drawings: See complete list of drawings as per section 6 |
| GCC 1.1 (ii) | The Start Date shall be latest the same date as site handover. The commencement of work is subject to fulfillment of GCC 24.2 (ii). |
| GCC 1.1 (mm) | The Works consist of - Site clearance from vegetation, top soil, existing buildings, waste and other debris (if needed) - Site levelling, grading, compacting - Earthworks (cutting, backfilling, compacting) for the preparation of foundations, supply and surface water drainage works - Fencing, supply, and installation of gates - Roads and carriageways (block pavement for collection vehicles, staff, and site visitors) - Concrete works: Building of concrete platforms for storage, handling, treatment of different waste streams and waste facilities - Steel works: Building of steel sheds for coverage of waste processing areas - Civil works: Construction of a Guardroom (if needed), an Office building including all connections to site utilities (Alternatively: Procurement, installation, and connection of prefabricated buildings) - Construction of site infrastructure: Lighting, rainwater drainage, water supply facilities, sewerage water, electrical provision, distribution, and connections - Landscaping works |
| GCC 2.2 | Sectional Completions are: NA |
| GCC 2.3 (j) | The following documents also form part of the Contract: - Employers’ requirement as per section 6 - Detailed drawings - Environmental notice - Environment Impact Assessment Report (EIA/ESMP) - And any other documents listed or referenced in part or full in the contract documents |
| GCC 3.1 | The language of the contract is English The law that applies to the Contract is the law of the Republic of Maldives |
| GCC 8.1 | Add the following after the existing sentence in GCC 8.1. “The Contractor shall also comply with all reasonable requests of the national and local authorities responsible for enforcing environmental health and safety controls.” |
| GCC 11.1 | The Project Manager may delegate any of his duties and responsibilities. |
| GCC 14.1 | Schedule of other contractors: NA |
| GCC 19.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: for loss or damage to the Works, Plant and Materials: 100% of contract value per lot (b) for loss or damage to Equipment: (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract 20% of contract value per lot (d) for personal injury or death: - of the Contractor’s employees: 500,000 USD (or equivalent in local currency) - of other people: 500,000 USD (or equivalent in local currency) |
| GCC 20.1 | Site Investigation Reports are: NA |
| GCC 22 | Please add the following at the end of this clause: “The Contractor shall adequately record the condition of roads, agricultural land and other infrastructure prior to the start of transporting materials, goods and equipment, and construction.” |
| GCC 23.1 | The following shall be designed by the Contractor: Electrical installation works (overall site and buildings) |
| GCC 24 | After Sub-clause 24.1, add the following as Sub-Clause 24.2: - The Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease. This includes the establishment of preventive and emergency preparedness and response measures to avoid, and where avoidance is not possible, to minimize, adverse impacts and risks of the construction site work to the health and safety of local communities. - Within 28 days from the date of the Letter of Acceptance, the Contractor shall submit a detailed Site-Specific Environmental Management Plan (SEMP), including final health and safety plan (H&S Plan) and other plans as required, including an updated Health and Safety COVID-19 Plan (HS-C19 Plan) for the Project Manager’s no objection showing how it intends to comply with environmental, health and safety laws and regulations and other specific requirements prescribed in the Contract, addressing all the monitoring and mitigation measures set forth in the final or updated Initial Environmental Examination (“IEE”), including the Environmental Management Plan (“EMP”) of the project as well as related Supplementary Information attached in Section 6- Employer’s Requirements. Work shall not commence on the Site until the no objection of SEMP has been obtained from the Project Manager. Such confirmation of no objection by the Project Manager shall not relieve the Contractor of any of his obligations or responsibilities under the Contract. - the Contractor is required to provide all personnel on site including Employer’s Personnel and visitors with personal protective equipment, including protection for feet (safety boots), head, eyes, ears (safety helmets) and hands, etc., in accordance with the Contractor’s SEMP. The Contractor should ensure that his Subcontractors comply with the SEMP and provide all such necessary equipment to their personnel. - The Contractor shall (a) establish an operational system for managing environmental, health and safety impacts, (b) comply with the approved SEMP and any corrective or preventative actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor the implementation of the project EMP through the SEMP, (c) allocate the budget required to ensure that such measures, requirements and actions are carried out, (d) submit semi-annual reports on the compliance of such measures to the Project Manager and the Employer. - Where unanticipated health and safety hazards, or environmental risks or impacts become apparent during the Contract, the Contractor is required to update the SEMP, H&S Plan and HS-C19 Plan to outline the potential impacts to site works and associated mitigation measures for the Project Manager’s approval. - The Contractor shall provide at cost all labor and materials related to implementation of the SEMP, final H&S Plan and updated HS-C19 Plan throughout the construction activities. These include construction/installation and maintenance of site safety, hard barricading, flexible green net, signboards, temporary day/light traffic diversions, etc. in accordance with specifications; and provision of appropriate Personal Protective Equipment (PPEs) to all the laborers working at the construction site. The Contractor shall bear all the costs, including costs of PPEs, to ensure that such measures, requirements and actions are carried out. Contractor must take special precautions for public safety to minimize the scale and extent of disruption to public and commercial life. - In the event of a significant injury involving medical treatment or hospitalization and fatal accident the Contractor shall notify the Project Manager immediately by verbal communication and submit a formal report as soon as practicable after its occurrence. For all accidents, whether fatal or not, the Contractor shall also notify the appropriate local authorities in accordance with the Laws of the Country. |
| GCC 24.3 | Please add the following as Sub-Clause 24.3: The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personal and to provide a safe work environment. The Contractor shall conduct health and safety programs for workers employed under the project, and shall include information on the trafficking of women and the risk of sexually transmitted diseases, including HIV/AIDs in such programs. In particular, the Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease. |
| GCC 26.1 | The Site Possession Date(s) shall be: latest 14 days after contract signing |
| GCC 29.1 | Appointing Authority for the Adjudicator: Ministry of Finance, Republic of Maldives. |
| GCC 30.3 | The Adjudicator shall be paid by the hour at the rate of: TBD |
| GCC 30.4 | Disputes shall be referred to arbitration in accordance with the Arbitration Act of the Republic of Maldives [10/2013]. The place of arbitration shall be: Republic of Maldives In case, an Arbitration system is not yet established, Court of Law of Republic of Maldives shall prevail. |
| GCC 32 | Please add the following at the end of Sub-Clause 32.1: “’Child’ means a child below the statutory minimum age of 18 under applicable national, provincial or law of the Republic of Maldives.” |
| GCC 34.2 | The following sentence shall apply: Respectful Work Environment The Contractor shall ensure that its employees and sub-contractors observe the highest ethical standards and refrain from any form of bullying, discrimination, misconduct and harassment, including sexual harassment and shall, at all times, behave in a manner that creates an environment free of unethical behavior, bullying, misconduct and harassment, including sexual harassment. The Contractor shall take appropriate action against any employees or sub-contractors, including suspension or termination of employment or sub-contract, if any form of unethical or inappropriate behavior is identified. The Contractor shall conduct training programs for its employees and sub-contractors to raise awareness on and prevent any form of bullying, discrimination, misconduct and harassment including sexual harassment, and to promote a respectful work environment. The Contractor shall keep an up-to-date record of its employees and subcontractors who have attended and completed such training programs and provide such records to the Employer or the Engineer at their first written request. |

| C. Time Control |  |
| --- | --- |
| GCC 35.1 | The Contractor shall submit for approval a Program for the Works within 14 days from the date of the Letter of Acceptance. Such Program submission should include the environmental, health and safety information required in 24.2 (ii). |
| GCC 35.3 | The period between Program updates is 15 days. The amount to be withheld for late submission of an updated Program is 10% of the monthly progress bill. |
| GCC 40 | Please add the following at the end of Sub-Clause 40.1: In addition to the foregoing, the Contractor shall provide the Project Manager with a written notice of any unanticipated environmental or resettlement risks or impacts that arise during construction, which were not considered in the initial environmental examination (IEE), the environmental management plan (EMP), and the resettlement plan (RP) attached hereto as Supplementary Information, Part 2, Employers Requirement |
| D. Quality Control |  |
| GCC 43.1 | The Defects Liability Period is: 365 days. |
| E. Cost Control |  |
| GCC 53.1 | The currency of the Employer’s country is: Maldivian Rufiyaa |
| GCC 54.1 | The Contract is not subject to price adjustment in accordance with GCC Clause 54, and the following information regarding coefficients does not apply. The coefficients and indexes for adjustment of prices in local and international currencies shall be as specified in the Table(s) of Adjustment Data submitted together with the Letter of Bid. |
| GCC 55.1 | The proportion of payments retained is: 5% |
| GCC 56.1 | The liquidated damages for the whole of the Works are 0.1% of the final contract price per day. The maximum amount of liquidated damages for the whole of the Works is 10% of the final Contract Price. |
| GCC 57.1 | Not Applicable |
| GCC 58.1 | The Advance Payments shall be 10% and shall be paid to the Contractor no later than 14 days after submission of Advance Payment Guarantee |
| GCC 58.3 | Repayment of the Advance Payments shall be: 10% from each payment certificate. |
| GCC 59.1 | The Performance Security amount is 15% of the contract price If the institution issuing the Performance Security is located outside the Employer’s country, it shall have a correspondent financial institution located in the Employer’s country to make it enforceable. |
| G. Finishing the Contract |  |
| GCC 72.1 | The date by which operation and maintenance manuals are required is: NIL The date by which “as built” drawings are required is latest 14 days after date of commissioning |
| GCC 72.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required in GCC 72.1 is 100,000 MVR |
| GCC 73.2 (h) | The maximum number of days is: 200 days |
| GCC 75.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is 5% |
| GCC 80 | Please add the following as new sub-paragraph 80: # The Contractor shall comply with all applicable national, provincial, and local environmental laws and regulations. # The Contractor shall also comply with all reasonable requests of the national and local authorities responsible for enforcing environmental controls. # Within 28 days of the Commencement Date the Contractor shall submit a detailed Site Specific Environmental Management Plan (SSEMP) for the Engineer’s no objection showing how he/she intends to comply with environmental laws and regulations and other specific requirements prescribed in the Contract, addressing all the monitoring and mitigation measures set forth in the Environmental Impact Assessment (“EIA”) and the Environmental Management Plan (“EMP”) of the project attached in Section 6- Employer’s Requirements. Work shall not commence on the Site until the no objection of SSEMP has been obtained from the Engineer and is being implemented. Such acceptance by the Engineer shall not relive the Contractor of any of his obligations or responsibilities under the Contract. # The Contractor shall (a) establish an operational system for managing environmental impacts, (b) comply with the approved SSEMP and any corrective or preventative actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor the implementation of the project EMP through the SSEMP, (c) allocate the budget required to ensure that such measures, requirements and actions are carried out, (d) submit semi-annual reports on the compliance of such measures to the Employer. # Where unanticipated environmental risks or impacts become apparent during the Contract, the Contractor is required to update the SSEMP to outline the potential impacts to site works and associated mitigation measures for the Engineer’s approval.” |
| GCC 81 | Please add the following as new sub-paragraph 81: The Contractor shall comply with all relevant (a) labor laws and regulations applicable to the Contractors personnel, including staff, consultants, contractors, and agents; and (b) workplace health and safety laws. The Contractor shall not make employment decisions based upon personal characteristics unrelated to job requirements. The Contractor shall base the employment relationship upon equal opportunity and fair treatment, and shall not discriminate with respect to aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment or retirement, and discipline. The Contractor shall provide equal wages and benefits to men and woman for work of equal value or type. |

Section 9 - Contract Forms

This section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Notification of Award

---- on letterhead paper of the employer ----

Letter of Acceptance

. . . . . . . date. . . . . . .

To:	. . . . . . . . . .   Name and address of the contractor . . . . . . . . . .

Subject:	. . . . . . . . . .   Notification of Award Contract No.  . . . . . . . . . .

This is to notify you that your Bid dated . . . . date . . . .  for execution of the . . . . . . . . . .name of the contract and identification number, as given in the Bid Data Sheet . . . . . . . . . . for the Accepted Contract Amount of the equivalent of . . . . . . . . .amount in words and figures and name of currency . . . . . . . . ., as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract, using for that purpose the Performance Security Form included in Section 9 (Contract Forms) of the Bidding Document.

[Choose one of the following statements:]

We accept that [insert the name of adjudicator proposed by the bidder]  be appointed as the Adjudicator.

[or]

We do not accept that [insert the name of the adjudicator proposed by the bidder] be appointed as the Adjudicator, and by sending a copy of this Letter of Acceptance to [insert name of the appointing authority], the Appointing Authority, we are hereby requesting such Authority to appoint the Adjudicator in accordance with GCC 29.1.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Contract Agreement

Contract Agreement

HIS AGREEMENT made the . . . . . .day of . . . . . . . . . . . . . . . . ., . . . . . . ., between . . . . . name of the employer. . . . .. . . . . (hereinafter “the Employer”), of the one part, and . . . . . name of the contractor. . . . .(hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as . . . . . name of the contract. . . . .should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

the Contract Agreement,

the Letter of Acceptance,

the Letter of Bid,

the Particular Conditions of Contract,

the List of Eligible Countries that was specified in Section 5 of the bidding document,

the General Conditions of Contract,

the Specifications,

the Drawings,

the Completed Activity Schedules or Bill of Quantities, and

any other documents shall be added here.

3.	In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of . . . . . name of the borrowing country. . . . .on the day, month and year indicated above.

Signed by 		Signed by

for and on behalf of the Employer		for and on behalf the Contractor

in the presence of:		in the presence of:

Witness, Name, Signature, Address, Date		Witness, Name, Signature, Address, Date

Performance Security

Bank’s name, and address of issuing branch or office

Beneficiary: 	Name and address of the employer

Date:

Performance Guarantee No.:

We have been informed that . . . . . name of the contractor. . . . .  (hereinafter called “the Contractor”) has  entered into Contract No. . . . . . reference number of the contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of works. . . . .  (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we . . . . . name of the bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . . . . .  name of the currency and amount in words . . . . . . (. . . . . amount in figures. . . . .  ) such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the . . . . . Day of . . . . . . . . . . , . . . . . .  , and any demand for payment under it must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . 
Signature(s) and seal of bank (where appropriate)

-- Note to Bidder --

If the institution issuing the performance security is located outside the country of the employer, it shall have a correspondent financial institution located in the country of the employer to make it enforceable.

Advance Payment Security

Bank’s name, and address of issuing branch or office

Beneficiary: 	Name and address of the employer

Date:

Advance Payment Guarantee No.:

We have been informed that . . . . . name of the contractor. . . . .  (hereinafter called “the Contractor”) has  entered into Contract No. . . . . . reference number of the contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of works. . . . .  (hereinafter called “the Contract”).

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum  . . . . . name of the currency and amount in words . . . . . . (. . . . . amount in figures. . . . .  ) is to be made against an advance payment guarantee.

At the request of the Contractor, we . . . . . name of the bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . name of the currency and amount in words. . . . . . (. . . . . amount in figures. . . . .  ) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number . . . . . contractor’s account number. . . . .   at . . . . . name and address of the bank. . . . .  .

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that eighty percent (80%) of the Contract Price has been certified for payment, or on the . . . day of . . . . . . . , . . . . . , whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458 (or ICC Publication No. 758 as applicable).

. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
Signature(s) and seal of bank (where appropriate)

-- Note to Bidder --If the institution issuing the advance payment security is located outside the country of the employer, it shall have a correspondent financial institution located in the country of the employer to make it enforceable.

Whether as a Contractor, Nominated Subcontractor, Consultant, Manufacturer or Supplier, or Service Provider; or in any other capacity (different names are used depending on the particular Bidding Document). A Nominated Subcontractor is one that either has been (i) included by the Bidder in its prequalification application or bid because it brings specific and critical experience and know-how that are accounted for in the evaluation of the bidder’s prequalification application or the bid; or (ii) appointed by the Employer.

Use one of the two options as appropriate.

If none has been paid or is to be paid, indicate “None”.

All italicized text is for use in preparing this form and shall be deleted from the final document.

Or 758 as applicable.

The sum of the two coefficients Ac and Bc should be 1 (one) in the formula for each currency.  Normally, both coefficients shall be the same in the formulas for all currencies, since coefficient A, for the nonadjustable portion of the payments, is a very approximate figure (usually 0.10 ~ 0.20) to take account of fixed cost elements or other nonadjustable components. The sum of the adjustments for each currency is added to the Contract Price.

Whether as a Contractor, Nominated Subcontractor, Consultant, Manufacturer or Supplier, or Service Provider; or in any other capacity (different names are used depending on the particular Bidding Document).  A Nominated Subcontractor is one which either has been (i) included by the Bidder in its prequalification application or bid because it brings specific and critical experience and know-how that are accounted for in the evaluation of the Bidder’s prequalification application or the bid; or (ii) appointed by the Employer.

Tables of Adjustment Data may be added if the contract provides for price adjustment (see GCC 54.1).

All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

The guarantor shall insert an amount representing the percentage of the contract price specified in the contract and denominated either in the currency(ies) of the contract or a freely convertible currency acceptable to the employer. If the bank issuing the performance security is located outside the country of the employer, it shall have a correspondent financial institution located in the country of the employer.

Insert the date 28 days after the expected completion date. The employer should note that in the event of an extension of the time for completion of the contract, the employer would need to request an extension of this guarantee from the guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [6 months][1 year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

Or the same or similar to this clause specified in the Uniform Rules for Demand Guarantees, ICC Publication No. 758 where applicable.

All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

The guarantor shall insert an amount representing the amount of the advance payment denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the employer.

Footnote 2.

Insert the expected expiration date of the time for completion. The employer should note that in the event of an extension of the time for completion of the contract, the employer would need to request an extension of this guarantee from the guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [6 months][1 year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.