Section 9: Contract Forms

**Table of Forms**

[Letter of Acceptance 3](#_Toc161832320)

[Contract Agreement 4](#_Toc161832321)

[Appendix 1: Terms and Procedures of Payment 7](#_Toc161832322)

[Appendix 2: Price Adjustment 11](#_Toc161832323)

[Appendix 3: Insurance Requirements 12](#_Toc161832324)

[Appendix 4: Time Schedule 14](#_Toc161832325)

[Appendix 5: List of Major Items of Plant and Services and List of Approved Subcontractors 16](#_Toc161832326)

[Appendix 6: Scope of Works and Supply by the Employer 17](#_Toc161832327)

[Appendix 7: List of Documents for Approval or Review 18](#_Toc161832328)

[Appendix 8: Functional Guarantees 19](#_Toc161832329)

[Performance Security 20](#_Toc161832330)

[Advance Payment Security 22](#_Toc161832331)

Notice of Intention for Award of Contract

[*on letterhead paper of the Employer*]

[*date of notification*]

To: [*name of the Bidder*]

Attention: [*insert name of the Bidder’s authorized representative*]

Address: [*insert address of the Bidder’s authorized representative*]

Telephone/Fax numbers: [*insert telephone/fax numbers of the Bidder’s authorized representative*]

E-mail Address: [*insert e-mail address of the Bidder’s authorized representative*]

This is to notify you of our intention to award the contract [*insert name of the contract and identification number, as given in the Bid Data Sheet*]. You have [*insert number of days as specified in ITB 42.1 of the BDS*] days, from the date of this notification to (i) request for a debriefing in relation to the evaluation of your Bid, and/or (ii) submit a bidding-related complaint in relation to the intention for award of contract, in accordance with the procedures specified in ITB 45.1.

The summary of the evaluation are as follows:

1. **List of Bidders**

|  |  |  |
| --- | --- | --- |
| Name of Bidder | Bid Price as Read Out at Opening | Evaluated Bid Price |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

1. **Reason/s Why Your Bid Was Unsuccessful**

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

1. **The Successful Bidder**

|  |  |
| --- | --- |
| Name of Bidder: |  |
| Address: |  |
| Accepted Contract Amount: |  |
| Duration of Contract: |  |
| Scope of the Contract Awarded: |  |
| Amount Performance Security Required: |  |

Authorized Signature: ……………………………………………………………

Name and Title of Signatory: ……………………………………………………

Name of Agency: …………………………………………………………………

# Letter of Acceptance

[*date*]

To: [*Name and address of the contractor*]

Subject: Contract No. [please specify]

This is to notify you that your Bid dated [*date*] for execution of the [*name of the contract and identification number, as given in the Bid Data Sheet*] for the Contract Price in the aggregate of [*amounts in words and figures*] [*name of currency*], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract and any additional security required as a result of the evaluation of your bid, using for that purpose one of the Performance Security Forms included in Section 9 (Contract Forms) of the Bidding Document.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment: Contract Agreement

# Contract Agreement

THIS AGREEMENT made on the [ *insert number* ] day of [ *insert month* ], [ *insert year* ],

BETWEEN

(1) [ *name of the employer* ], a corporation incorporated under the laws of [ *country of the Employer* ] and having its principal place of business at [  *address of the Employer* ] (hereinafter called “the Employer”), and (2) [ *name of the contractor*], a corporation incorporated under the laws of [*country of the contractor* ] and having its principal place of business at [ *address of the contractor* ] (hereinafter called “the Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver, install, complete and commission certain Facilities, viz. [*list of facilities* ] (“the Facilities”) and the Contractor have agreed to such engagement upon and subject to the terms and conditions hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

|  |  |
| --- | --- |
| **Article 1**  **Contract Documents** | 1.1 **Contract Documents** (Reference GCC Clause 2)  The following documents shall constitute the Contract between the Employer and the Contractor, and each shall be read and construed as an integral part of the Contract:  (a) This Contract Agreement and the Appendixes hereto  (b) Letter of Bid and Price Schedules submitted by the Contractor  (c) Special Conditions of Contract  (d) List of Eligible Countries that was specified in Section 5 of the Bidding Document  (e) General Conditions of Contract  (f) Specifications  (g) Drawings  (h) Other completed Bidding Forms submitted with the Letter of Bid  (i) Any other documents forming part of the Employer’s Requirements  (j) Any other documents shall be added here**[[1]](#footnote-2)**  1.2 **Order of Precedence** (Reference GCC Clause 2)  In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above.  1.3 **Definitions** (Reference GCC Clause 1)  Capitalized words and phrases used herein shall have the same meanings as are ascribed to them in the General Conditions. |

|  |  |
| --- | --- |
| **Article 2**  **Contract Price and Terms of Payment** | 2.1 **Contract Price** (Reference GCC Clause 11)  The Employer hereby agrees to pay to the Contractor the Contract Price in consideration of the performance by the Contractor of its obligations hereunder. The Contract Price shall be the aggregate of [*amounts of foreign currency in words*], [*amounts in figures*] as specified in Price Schedule No. 5 (Grand Summary), [*amounts of local currency in words*], [*amounts in figures*], or such other sums as may be determined in accordance with the terms and conditions of the Contract.  2.2 **Terms of Payment** (Reference GCC Clause 12)  The terms and procedures of payment according to which the Employer will reimburse the Contractor are given in the Appendix (Terms and Procedures of Payment) hereto.  The Employer shall instruct its bank to issue an irrevocable confirmed documentary credit made available to the Contractor in a bank in the country of the Contractor. The credit shall be for an amount of [*amount equal to the total named in Schedule 1 less the advance payment to be made for plant and mandatory spare parts supplied from abroad*]; and shall be subject to the Uniform Customs and Practice for Documentary Credits 1993 Revision, ICC Publication No. 500.**2**  In the event that the amount payable under Schedule No. 1 is adjusted in accordance with GCC 11.2 or with any of the other terms of the Contract, the Employer shall arrange for the documentary credit to be amended accordingly |
| **Article 3**  **Effective Date** | 3.1 **Effective Date** (Reference GCC Clause 1)  The Effective Date upon which the period until the Time for Completion of the Facilities shall be counted from is the date when all of the following conditions have been fulfilled:  (a) This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor.  (b) The Contractor has submitted to the Employer the performance security and the advance payment guarantee.  (c) The Employer has paid the Contractor the advance payment.  (d) The Contractor has been advised that the documentary credit referred to in Article 2.2 above has been issued in its favor.  Each party shall use its best efforts to fulfill the above conditions for which it is responsible as soon as practicable.  3.2 If the conditions listed under 3.1 are not fulfilled within 2 months from the date of this Contract notification because of reasons not attributable to the Contractor, the parties shall discuss and agree on an equitable adjustment to the Contract Price and the Time for Completion and/or other relevant conditions of the Contract. |
| **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**  **2** Or Uniform Customs and Practice for Documentary Credits 2007 Revision, ICC Publication No. 600 (or the latest version). | |
| **Article 4 Communications** | 4.1 The address of the Employer for notice purposes, pursuant to GCC 4.1 is: [ *Employer's address* ].  4.2 The address of the Contractor for notice purposes, pursuant to GCC 4.1 is: [ *Contractor's address* ]. |
| **Article 5. Appendixes** | 5.1 The Appendixes listed in the attached List of Appendixes shall be deemed to form an integral part of this Contract Agreement.  5.2 Reference in the Contract to any Appendix shall mean the Appendixes attached hereto, and the Contract shall be read and construed accordingly. |

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

Signed by, for and on behalf of the Employer

[ *Signature* ]

[ *Title* ]

in the presence of

[ *Signature* ]

[ *Title* ]

Signed by, for and on behalf of the Contractor

[ *Signature* ]

[ *Title* ]

in the presence of

[ *Signature* ]

[ *Title* ]

**APPENDIXES**

Appendix 1: Terms and Procedures of Payment

Appendix 2: Price Adjustment

Appendix 3: Insurance Requirements

Appendix 4: Time Schedule

Appendix 5: List of Major Items of Plant and Services and List of Approved Subcontractors

Appendix 6: Scope of Works and Supply by the Employer

Appendix 7: List of Documents for Approval or Review

Appendix 8: Functional Guarantees

## Appendix 1: Terms and Procedures of Payment

In accordance with the provisions of GCC Clause 12 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, based on the Price Breakdown given in the section on Price Schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. Applications for payment in respect of part deliveries may be made by the Contractor as work proceeds.

The following is applicable for payments for all lots (Lot 1, 2 and 3) separately.

**(A) Terms of Payment**

**Schedule No. 1 - Plant and Mandatory Spare Parts Supplied from Abroad**

In respect of plant and mandatory spare parts supplied from abroad, the following payments shall be made:

Ten percent (10%) of the total CIP amount as an advance payment against receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and mandatory spare parts delivered to the site, as evidenced by delivery documents.

Sixty percent (60%) of the total or pro rata CIP or amount upon Incoterm “CIP,” upon delivery and acceptance at the site and within 45 days after receipt of invoice.

Twenty percent (20%) of the total or pro rata CIP or amount upon issue of the Completion Certificate, within 45 days after receipt of invoice.

Ten percent (10%) of the total or pro rata CIP or amount upon issue of the Operational Acceptance Certificate and within 45 days after receipt of invoice.

**Schedule No. 2 - Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country**

In respect of plant and mandatory spare parts supplied from within the Employer’s country, the following payments shall be made:

Ten percent (10%) of the total EXW amount as an advance payment against receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and mandatory spare parts delivered to the site, as evidenced by delivery documents.

Eighty percent (80%) of the total or pro rata EXW amount upon Incoterm “Ex-Works,” upon delivery to the site within 45 days after receipt of invoice.

Five percent (5%) of the total or pro rata EXW amount upon issue of the Completion Certificate, within 45 days after receipt of invoice.

Five percent (5%) of the total or pro rata EXW amount upon issue of the Operational Acceptance Certificate, within 45 days after receipt of invoice.

**Schedule No. 3 - Design Services**

In respect of design services for both the foreign currency and the local currency portions, the following payments shall be made:

Ten percent (10%) of the total design services amount as an advance payment against receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

Ninety percent (90%) of the total or pro rata design services amount upon submission of complete survey details, design details, drawings, maps, updated equipment schedules and cost estimates and acceptance by the Project Manager within 45 days after receipt of invoice.

**Schedule No. 4 - Installation and Other Services**

In respect of installation services for both the foreign and local currency portions, the following payments shall be made:

Ten percent (10%) of the total installation and other services amount as an advance payment against receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of work performed by the Contractor as evidenced by the invoices for installation services.

Sixty percent (60%) of the measured value of work performed by the Contractor, as identified in the said Program of Performance, during the preceding month, as evidenced by the Employer’s authorization of the Contractor’s application, will be made monthly within 45 days after receipt of invoice.

Twenty percent (20%) of the total or pro rata value of installation and other services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Completion Certificate, within 45 days after receipt of invoice.

Ten percent (10%) of the total or pro rata value of installation and other services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Operational Acceptance Certificate, within 45 days after receipt of invoice.

Ten percent (10%) of the total or pro rata value of installation and other services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Operational Acceptance Certificate, within 45 days after receipt of invoice.

In the event that the Employer fails to make any payment on its respective due date, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate of LIBOR plus 0.1 percent (0.1 %) per month for period of delay until payment has been made in full.

**(B) Payment Procedures**

When applying for certification and making payments, the procedures shall be as follows:

The following is applicable for payments for all lots (Lot 1, 2 and 3) separately.

Payments shall be made as direct payment.

All documents and packages have to be marked as follows:

***Accelerating Sustainable Systems Development Using Renewable Energy (ASSURE) Project, Microgrid Modifications and Expansions, Ministry of Climate Change, Environment and Energy, Republic of Maldives***

**Schedule No. 1 - Plant and Mandatory Spare Parts Supplied from Abroad**

In respect of plant and mandatory spare parts supplied from abroad, the following documents shall be provided to the Employer:

For clearance of goods: three (3) original sets of the following documents shall be provided, latest fifteen (15) prior to arrival of the goods at the point of clearance (seaport of entrance):

* Invoice
* Bill of lading
* Packing list
* Insurance certificate

The Contractor is free to choose the seaport of entrance. There are three of these seaports. Upon arrival at one of these ports the Employer will take care of clearance. After clearance it is the Contractor’s obligation to continue delivery up to the final destination at the respective islands. The seaports have limited availability to rearrange the supply into smaller consignments suitable for the islands. Some islands have limited lifting facilities.

For advance payment: invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

On CIP delivery: the following documents shall be submitted in one (1) original and two (2) copies:

* Invoice
* Bill of lading
* Packing list
* Insurance certificate
* Certificate of origin of each item
* Third party conformity certificate \*
* Manufacturer’s guarantee certificate

\* It is the Contractor’s responsibility to have all goods inspected for quality and quantity prior to transport by an independent third party acceptable to the Employer.

On Completion per island: invoice and completion certificate issued by the Employer.

On Operational Acceptance per island: invoice and operational acceptance certificate issued by the Employer.

**Schedule No. 2 - Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country**

In respect of plant and mandatory spare parts supplied from within the Employer’s country, the following documents shall be provided to the Employer:

For advance payment: invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

On EXW delivery: the following documents shall be submitted in one (1) original and two (2) copies:

* Invoice
* Transportation document
* Packing list
* Insurance certificate
* Third party conformity certificate \*
* Manufacturer’s guarantee certificate

\* It is the Contractor’s responsibility to have all goods inspected for quality and quantity prior to transport by an independent third party acceptable to the Employer.

On Completion per island: invoice and completion certificate issued by the Employer.

On Operational Acceptance per island: invoice and operational acceptance certificate issued by the Employer.

**Schedule No. 3 - Design Services**

For advance payment: invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

Upon acceptance of survey and design per island: invoice and statement of acceptance of design issued by the Employer.

**Schedule No. 4 - Installation and Other Services**

For advance payment: invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

For progress payment (60%) of the measured value of services): invoice and approved Contractor’s application.

Upon completion per island: invoice and completion certificate issued by the Employer.

Upon operation acceptance per island: invoice and operational acceptance certificate issued by the Employer.

## Appendix 2: Price Adjustment

Not Applicable.

## Appendix 3: Insurance Requirements

**(A) Types of Insurance to Be Taken Out by the Contractor**

In accordance with the provisions of GCC Clause 34, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the types of insurance set forth below in the sums and with the deductibles and other conditions specified. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, such approval not to be unreasonably withheld.

**(a) Cargo Insurance**

Covering loss or damage occurring, while in transit from the supplier’s or manufacturer’s works or stores until arrival at the Site, to the Facilities (including spare parts therefore) and to the construction equipment to be provided by the Contractor or its Subcontractors.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Amount** | **Deductible limits** | **Parties insured** | **From** | **To** |
| **[in currency(ies)]** | **[in currency(ies)]** | **[names]** | **[place]** | **[place]** |
| United States Dollars 110% of the cost of goods / equipment to be supplied | United States Dollars (not to exceed 10,000 for each and every loss) | [Employer and Name of Contractor] | Supplier’s or Manufacturer’s store/warehouse | [destination] |

**(b) Installation All Risks Insurance**

Covering physical loss or damage to the Facilities at the Site, occurring prior to completion of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the defect liability period while the Contractor is on the Site for the purpose of performing its obligations during the defect liability period.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Amount** | **Deductible limits** | **Parties insured** | **From** | **To** |
| **[in currency(ies)]** | **[in currency(ies)]** | **[names]** | **[place]** | **[place]** |
| United States Dollars (total contract value) | United States Dollars 50,000 each and every occurrence caused by a defect in design, plan, specification, materials or workmanship prior to Completion, during Pre-commissioning and Commissioning and during the Defect Liability Period  United States Dollars 50,000 each and every loss in respect of cyclone, storm, flood or earthquake.  United States Dollars 50,000 each and every occurrence caused by a defect in the design, plan, specification, materials or workmanship prior to Completion and during Pre-commissioning and Commissioning and during the Defect Liability Period in connection with all other property insured  United States Dollars 10,000 in respect of all other losses. | [Employer, Name of Contractor and Name of Subcontractors] |  | [destination] |

**(c) Third Party Liability Insurance**

Covering bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities that have been accepted by the Employer) occurring in connection with the supply and installation of the Facilities.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Amount** | **Deductible limits** | **Parties insured** | **From** | **To** |
| **[in currency(ies)]** | **[in currency(ies)]** | **[names]** | **[place]** | **[place]** |
| United States Dollars 100,000,000 any one occurrence and unlimited in the aggregate during the period of insurance | Unites States Dollars 80,000 (costs inclusive) any one occurrence in respect of personal injury  United States Dollars 15,000 (costs inclusive) of any one occurrence in respect of damage to property surrounding the works site.  United States Dollars 15,000 (cost inclusive) any one occurrence in respect of all other losses. | [Name of Contractor, Employer, island inhabitants were panels will be installed and Name of Subcontractors] |  |  |

**(d) Automobile Liability Insurance**

Covering use of all vehicles used by the Contractor or its Subcontractors (whether owned by them or not) in connection with the supply and installation of the Facilities. Comprehensive insurance in accordance with statutory requirements.

**(e) Workers’ Compensation**

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

**(f) Employer’s Liability**

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

**(g) Other Insurance**

The Contractor is also required to take out and maintain at its own cost the following types of insurance:

Details:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Amount** | **Deductible limits** | **Parties insured** | **From** | **To** |
| **[in currency(ies)]** | **[in currency(ies)]** | **[names]** | **[place]** | **[place]** |
| None |  |  |  |  |
|  |  |  |  |  |

The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GCC Subclause 34.1, except for the Third Party Liability, Workers’ Compensation, and Employer’s Liability Insurance, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GCC Subclause 34.1, except for the Cargo, Workers’ Compensation and Employer’s Liability Insurance. All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies.

**(B) Types of Insurance to Be Taken Out by the Employer**

The Employer shall at its expense take out and maintain in effect during the performance of the Contract the following insurance policies.

Details:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Amount** | **Deductible limits** | **Parties insured** | **From** | **To** |
| **[in currency(ies)]** | **[in currency(ies)]** | **[names]** | **[place]** | **[place]** |
| None |  |  |  |  |
|  |  |  |  |  |

## Appendix 4: Time Schedule

The successful bidder shall execute the contract works and complete the facilities within the time schedule indicated below. The timeline is applicable whether the bidder is successful for 1 or more/all lots.

|  |  |  |  |
| --- | --- | --- | --- |
| # | **Applicable Lots** | **Facilities** | **Time for Completion from effective date (months)** |
|  | Lot 1, Lot 2, Lot 3 | Site Survey and Design, submission of all data, drawings, maps, updated equipment schedules and cost estimates | 4 Months |
|  | Lot 1, Lot 2, Lot 3 | Procurement and supply of all materials and equipment | 12 Months |
|  | Lot 1, Lot 2, Lot 3 | Completion of civil works for powerhouse building modifications | 12 months |
|  | Lot 1, Lot 2, Lot 3 | Erection /Installation, integration, testing and commissioning of all equipment, switchgear panels (MVDB / LVDB) and transformers at Powerhouses | 16 Months |
|  | Lot 1, Lot 2, Lot 3 | Erection /Installation, testing and commissioning of all equipment, including Package Substations, RMUs, underground cables, LV distribution Boxes in field | 18 Months |
|  | Lot 1, Lot 2, Lot 3 | Provision of Training | 18 Months |
|  | Lot 1, Lot 2, Lot 3 | Completion of all implementation activities, documentation and handing over | 18 Months |

## Appendix 5: List of Major Items of Plant and Services and List of Approved Subcontractors

A list of major items of plant and services is provided below.

The following Subcontractors and Manufacturers are approved for carrying out the item of the facilities indicated. Where more than one Subcontractor is listed, the Contractor is free to choose between them, but it must notify the Employer of its choice in good time prior to appointing any selected Subcontractor. In accordance with GCC Subclause 19.1, the Contractor is free to submit proposals for Subcontractors for additional items from time to time. No Subcontracts shall be placed with any such Subcontractors for additional items until the Subcontractors have been approved in writing by the Employer and their names have been added to this list of Approved Subcontractors.

|  |  |  |
| --- | --- | --- |
| **Major Items of Plant and Services** | **Approved Subcontractors and Manufacturers** | **Nationality** |
| LVDB - Extension |  |  |
| MVDB |  |  |
| LV Underground Cables and Accessories |  |  |
| MV Underground Cables and Accessories |  |  |
| Step-up transformers |  |  |
| Packaged Substations (PSS) |  |  |
| LV Distribution Boxes |  |  |
| Civil Works |  |  |

## Appendix 6: Scope of Works and Supply by the Employer

The following personnel, facilities, works, and supplies will be provided or supplied by the Employer, and the provisions of GCC Clauses 10, 21, and 24 shall apply as appropriate.

All personnel, facilities, works, and supplies will be provided by the Employer in good time so as not to delay the performance of the Contractor, in accordance with the approved Time Schedule and Program of Performance pursuant to GCC Subclause 18.2.

Unless otherwise indicated, all personnel, facilities, works, and supplies will be provided free of charge to the Contractor.

|  |  |
| --- | --- |
| **Personnel** | **Charge to Contractor (if any)** |
| Not applicable |  |
|  |  |

|  |  |
| --- | --- |
| **Facilities** | **Charge to Contractor (if any)** |
| Not applicable |  |
|  |  |

|  |  |
| --- | --- |
| **Works** | **Charge to Contractor (if any)** |
| Not applicable |  |
|  |  |

|  |  |
| --- | --- |
| **Supplies** | **Charge to Contractor (if any)** |
| Not applicable |  |
|  |  |

## Appendix 7: List of Documents for Approval or Review

Pursuant to GCC Subclause 20.3.1, the Contractor shall prepare, or cause its Subcontractor to prepare, and present to the Project Manager in accordance with the requirements of GCC Subclause 18.2 (Program of Performance), the following documents for

**(A) Approval (**Project Manager shall be responsible for approval of the following):

1. Survey details including data, drawings and maps for each Island

2. Design details including data, drawings and maps for each Island

3. Updated equipment schedules and Cost Estimates for each Island

4. BAR Chart/Time Schedule

5. Safety plan

6. Training plan

7. Guaranteed Technical Particulars

8. Schedule of Deviations

9. Dispatch schedules

10. Manufacturer / subcontractor information

11.Equipment specifications catalogs and drawings

12. EHS Management Plan

13. Change in facilities (variation order requests)

14. Testing Plan & Commissioning Schedules

15. CVs of key staff / skilled workers.

16. Any other document/s required as per the Contract.

**(B) Review**

1. Statutory clearances and approvals

2. Test reports

3. Organization chart

4. Operation and Maintenance Manuals

5. Progress reports

6. Procurement plan

7. Minutes of meeting

8. As build drawings and maps

## Appendix 8: Functional Guarantees

Not Applicable.

# Performance Security

[*Bank’s name, and address of issuing branch or office*]

**Beneficiary: *MINISTRY OF CLIMATE CHANGE, ENVIRONMENT AND ENERGY***

**Date:**

**Performance Guarantee No.:**

We have been informed that [*name of the contractor*](hereinafter called “the Contractor”) has entered into Contract No. [*reference number of the contract*]dated [*date*] with you, for the execution of [*name of contract and brief description of plant and services*](hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we [*name of the bank*] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [*name of the currency and amount in words*]**[[2]](#footnote-3)** [*amount in figures*] such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire no later than the earlier of

(a) 18 months after our receipt of

(i) a copy of the Completion Certificate; or

(ii) a registered letter from the Contractor, attaching a copy of the notice to the project manager that the Facilities are ready for commissioning, and stating that 14 days have elapsed from receipt of such notice (or 7 days have elapsed if the notice was a repeated notice) and the project manager has failed to issue a Completion Certificate or inform the Contractor in writing of any defects or deficiencies; or

(iii) a registered letter from the Contractor stating that no Completion Certificate has been issued but the Employer is making use of the Facilities; or

(b) the [*date*] day of [*month*], [*year*][[3]](#footnote-4).

Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15 (a) is hereby excluded.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .  
[*Signature(s) and seal of bank (where appropriate)*]

-- Note to Bidder --

*If the bank issuing performance security is located outside the Employer’s country, it shall be counter-guaranteed or encashable by a bank in the Employer’s country.*

# Advance Payment Security

[*Bankʼs name, and address of issuing branch or office*]

**Beneficiary: *MINISTRY OF CLIMATE CHANGE, ENVIRONMENT AND ENERGY***

**Date:**

**Advance Payment Guarantee No.:**

We have been informed that [*name of the contractor*](hereinafter called "the Contractor") has entered into Contract No. [*reference number of the contract*]dated [*date*] with you, for the execution of [*name of contract and brief description of plant and services*](hereinafter called "the Contract").

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum [*name of the currency and amount in words*]**[[4]](#footnote-5)** [*amount in figures*] is to be made against an advance payment guarantee.

At the request of the Contractor, we [*name of the bank*]hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [*name of the currency and amount in words*]**[[5]](#footnote-6)** [*amount in figures*] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor:

(a) used the advance payment for purposes other than the costs of mobilization and cash flow support in respect of the Works; or

(b) has failed to repay the advance payment when it has become due and payable in accordance with the conditions of the Contract, specifying the amount payable by the Contractor.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number [*contractorʼs account number*]at [*name and address of the bank*].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates, which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate, indicating that 80% of the Contract Price has been certified for payment, or on the [*date*] day of [*month*], [*year*],**[[6]](#footnote-7)** whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revisions, ICC Publication No. 758 , except that the supporting statement under Article 15(a) is hereby excluded.[[7]](#footnote-8)

. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .   
[*Signature(s) and seal of bank (where appropriate)*]

-- Note to Bidder --

*If the bank issuing advance payment security is located outside the Employer’s country, it shall be counter-guaranteed or encashable by a bank in the Employer’s country.*

1. Tables of Adjustment Data may be added if the contract provides for price adjustment (see GCC 11). [↑](#footnote-ref-2)
2. The guarantor shall insert an amount representing the percentage of the accepted contract amount specified in the contract and denominated either in the currency(ies) of the contract or in any freely convertible currency acceptable to the Employer. [↑](#footnote-ref-3)
3. Insert the expected expiration date of the Defect Liability Period. The employer should note that in the event of an extension of the time for completion of the contract, the Employer would need to request an extension of this guarantee from the guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [6 months][1 year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-4)
4. The guarantor shall insert an amount representing the amount of the advance payment denominated either in the currency(ies) of the advance payment as specified in the contract, or in any freely convertible currency acceptable to the Employer. [↑](#footnote-ref-5)
5. Footnote 1. [↑](#footnote-ref-6)
6. Insert the expected expiration date of the time for completion. The Employer should note that in the event of an extension of the time for completion of the contract, the Employer would need to request an extension of this guarantee from the guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [6 months] [1 year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-7)
7. Or the Employer may use “Uniform Rules for Demand Guarantees (URDG), ICC Publication No. 458, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded” as appropriate. [↑](#footnote-ref-8)