## Th.Omadhoo
ISLAND | Th.Omadhoo COST ESTIMATE
SIZE
Bill No.1 - PRELIMINARIES
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
1.1 | Securities, Insurance, etc
1.1.1 | Provision of performance security | Item | 1
| Provision of insurance (Contractor to specify) | Item | 1
| Other security bonds, etc (Contractor to specify) | Item | 1
1.2 | Contractors Equipment, Personal and Site Facilities
1.2.1 | Mobilisation and demobilisation of Contractor's dredging equipment and construction plant | Item | 1
1.2.2 | Mobilisation and demobilisation of contractor's personal | Item | 1
1.2.3 | Time related charges for contractor personal. (Incl. food, lodging, etc) | Days | 540
1.2.4 | Establisment and removal of the Contractor's facilities, incl. laboratory, office, workshop, etc | Item | 1
1.2.5 | Operation and maintenance of Contractor's facilities incl. laboratory, office, workshop, etc | Days | 540
1.3 | Design and others
1.3.1 | provide as-built drawings, Quality assurance documentation, Material certificates, Technical brochures | Item | 1
1.3.2 | Provide detailed in-survey prior to commencement of physical works | Item | 1
1.3.3 | Provide detailed out-survey upon completion, prior to hand over | Item | 1
Total of bill No.1 (Carried to summary of Bills)
Bill No.2 - DREDGING, EXCAVATION & EARTHWORKS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
2.1 | Dredging and Excavation
2.1.1 | Dredging / Excavation of any material from the new harbour basin Maximum specified depth -3m MSL | cbm | 25583.84
2.1.2 | Dredging / Excavation of any material for the new harbour entrance Channel. Maximum specified depth -4m MSL | cbm | 4858
2.1.3 | Dredging / Excavation of any material for the existing beaching area basin. Maximum specified depth -3 MSL | cbm | 7076
2.1.4 | Dredging / Excavation of any material for the existing beaching area channel. Maximum specified depth -3 MSL | cbm | 2344
Total of bill No.1 (Carried to summary of Bills)
Bill No.3 - BREAKWATER AND REVETMENTS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
3.1 | Breakwaters
3.1.1 | for breakwaters; Armour rocks laidto the slopes defined in drawings and to lines and levels indicated in the cross section drawings. Rate shall include levelling and placing armour rocks | m | 25
3.1.2 | Armour rocks laid to the slopes with backfilled material and geotextile as defined in the drawing. Rate shall include back filling | m | 282
3.2 | Revetments
3.2.1 | Armour rocks laid to slopes with backfilled material and geotextile material as defined in the drawings | m | 123
3.3 | Beacons, Supply and Installing
3.3.1 | Supply and placing navigational aids at a minimum nominal light range of 2 nautical miles as shown on harbour layout drawing and as directed by Engineer. | No | 2
Total of bill No.1 (Carried to summary of Bills)
Bill No.4 - BREAKWATER AND REVETMENTS | QUAY WALL STRUCTURE
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
4.1 | L-Section Quay Wall (new harbour basin)
4.1.1 | Supply and install precast RC quaywall unit as per detail drawing. | m | 388
4.1.2 | Supply and install precast RC anchor blocks and fix anchor rods as per detail drawing. | m | 97
4.1.3 | Cast in-situ concrete coping in quaywall to grades, levels as indicated in the drawing | m | 388
4.1.4 | Supply and fix mooring rings in 5m intervals as per the detailed drawing | No | 77.6
4.1.5 | Supply and placing geotextile material to full length of the quaywall blocks covering the entire span of the quaywall length as shown in the cross section drawings | m | 388
Total of bill No.1 (Carried to summary of Bills)
Bill No.5 - BREAKWATER AND REVETMENTS | ADDITIONAL COMPONENTS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
5.1 | Harbour Pavement
5.1.1 | Supply and install two arm street lights along the quaywall line | Nos. | 19.4
5.1.2 | Supply and installation of settlement tanks with steel grating @6m intervals along the paving area | Nos. | 64.6667
5.1.3 | Supply and install storm water drainage pipes through quaywall from each settlement tank | Nos. | 64.6667
5.1.4 | Supply and lay kerbs | m | 388
5.1.5 | Supply and placing of paving blocks as per the drawing | sqm | 1940
5.1.6 | Mooring Bouys tied to a concrete block by 4m long nylone rope and epoxy coated hook in the harbour basin including concrete works as specifed and shown on drawings. | Nos. | 19.4
5.1.7 | Ramp for Landing Crafts:Construction of 11m x 11m, | LS | 1
Total of bill No.1 (Carried to summary of Bills)
Bill No.6 - ENVIRONMENTAL CONTROL | ENVIRONMENTAL CONTROL
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
6.1 | Implement necessary mitigation measures as outlined in the technical specifications | Item | 1
Total of bill No.1 (Carried to summary of Bills)
Bill No.6 - ENVIRONMENTAL CONTROL | ADDITIONS AND / OR OMISSIONS
Item no. | Description | Unit | Qty | Rate (MVR) | Amount (MVR)
A | The accuracy of the quantities given in this Bills of Quantities is not guaranteed and the Contractor should satisfy himself as to their accuracy |  |  |  | 0
B | Any adjustments that he may consider necessary should be written below and on similar continuation sheets if required, and the net amount of the adjustments is to be carried to the summary
Additions
1
2
3
4
5
Omissions
1
2
3
4
5
Total of bill No.1 (Carried to summary of Bills) |  |  |  |  | 0
SUMMARY OF BILLS
Bill No. | Description |  |  |  | Amount (MVR)
1 | Preliminaries
2 | Dredging, excavation and earth work
3 | Breakwaters and revetments
4 | Quay wall structure
5 | Additional components
6 | Environmental control
Goods and Services Tax
Grand total of Bills