## Hdh.Nolhivaram
Design and Build Basis for Construction of Water Supply and Sewerage Facilities in Hdh.Nolhivaram
Summary
Schedule no: | Description | Total
1 | Schedule 1- Design
2 | Schedule 2- General Works
3 | Schedule 3- Water Supply System Works
4 | Schedule 4- Provsional Sums
Subtotal
GST (6%)
Total
Schedule 1- Design
Item | Description | Unit | Rate | Total
1 | Survey
| Carrying out the Topographic, Bathymatric and Social Surveys as specified in the Employers Requirment | LS
2 | Concept Design
| Preperation of Concept Design for Water Supply System as specified in the Employers Requirment | LS
3 | EIA
Carrying out the EIA for the project based on concept Design Report and as specified in the Employers Requirement
4 | Detailed Design
| Preperation of Detailed Design for Water Supply System as specified in the Employer's Requirment | LS
Total
Schedule 2- General Works
Item | Description | Unit | Rate | Total
1 | Contractual Requirements | LS
Provide & Maintain all necessary Insurances, Guarantees and Securities.
2 | Project Management | LS
Allow for all on and off site management cost including costs of foreman and assistants, temporary services, telephone, fax, hoardings & similar.
3 | Mobilisation | LS
Allow for Establishment of Contractors office, Labour Camps and transportaion of Equipment and Materials etc
4 | Site Preperation | LS
Clearing grass, bushes, shrubs, saplings, uprooting rank vegetation all along the pipeline route and removal & disposal of rubbish to approved tips anywhere in the island as directed by the Engineer-in-charge, etc
5 | Construction of Administration and RO plant Building | LS
Foundation works , Structural Works, Masonry, Plastering, Plot boundary works and Finishing works etc as per the approved drawings and Employers Requirements
Total
Schedule 3- Water Supply System Works
Item | Description | Unit | Rate | Total
1 | Distribution Network | LS
Supply and Installation of HDPE pipe network as per the design including provision of house connections with meters
2 | RW Collection Network | LS
Supply and Installation of Pipes for gravity rainwater collection networ k from all public buildings
3 | Water Intake Boreholes | LS
Construction of boreholes as per the employers requirement and approved designs
4 | RO Plant & Pumping System | LS
Supply and Installation of RO plants, Distribiution Pumps as per Employers Requirement
5 | Brine Discharge outfall | LS
Installation of HDPE brine discharge line as per the Employers Requirment
6 | Storage tanks | LS
Supply and Installation of Storage tanks as per the Employers Requirement
7 | Mechanical and Electrical Works | LS
Supply and Installation of electrical and mechanical components required as per approved drawings including provision of power supply from feeder cable
8 | Solar PV | LS
Provision of Solar Panels on Plant building Roof Catchment and provision of Neccesary Equipments to utilise PV in RO plant operation
9 | Testing & Commissioning | LS
Carrying out testing and commissioning as per the employers requirment for all components of the system
Total
Schedule 4- Provsional Sums
Item | Description | Unit | Qty | Rate | Total
1 | Schedule 3- Water Supply System Works
1.1 | Provision of house connections with meters | nos | 53
Total