Format for Mid the Term Evaluation of the Achievement of Sector Outcomes of the Strategic Action Plan (2009 – 2013) of the Government of Maldives

Agriculture Sector

- Sector Overall Progress (500 words)

{A description of the extent to which the Sector Outcomes as specified in the policy goals were realized in the period under review}

Agriculture sector’s role in the economy is minor however, its contribution to the livelihood of the rural population is important despite the sectors constraints. Limited availability of cultivable land and lack of appropriate infrastructure are barriers to development of the sector in addition to the natural causes that are related to the fragile island ecosystem. Currently, agricultural activities are conducted in small-scale home gardens by individual farmers and community groups as well as in commercial islands leased for long-term. There is potential for the agricultural sector to grow through the sustainable use resources, appropriate use of technology and diversification of the sector, such as egg production and value addition. The Ministry of Fisheries and Agriculture (MoFA) has been the investing into the agricultural sector to ensure its long term sustainability by utilizing resources effectively, expanding into new sectors, strengthening institutional capacity and technical skills of the agricultural workforce. Much progress has already been achieved in recent years. MOFA as a policy priority encourage farmers to transition from marginal to commercial scale production and facilitate foreign, private and public sector investments. MoFA also gives priority to enhance food security which is essential to reduce reliance on imported crops through increased cultivation of economically important crops that are productive in the agro-ecological climate. A central activity that contributes towards achieving this goal is conducting woman focused training programs and providing information on new technology and climate smart agriculture methods. This has direct impact on empowering women groups at the island level (e.g. Women’s Committee, NGOs and cooperatives) to achieve better living standards income earning opportunities. Recent introduction of Virgin Coconut Oil and Maldivian Chili Sauce to the market are achievements in this regard. This partly demonstrates the potential of women engaged in agricultural activities. Furthermore, these outcomes align with the United Nations Millennium Development Goal of achieving gender equality, and are clearly reflected in the inclusion of gender focused activities in projects supported by UNDP, IFAD and FAO. To improve sustainable farming in all regions, increased availability of agricultural inputs and environment friendly technology, such as biological and organic crop protection mechanisms, were established in the country. Progress has also been made in developing physical infrastructure and networking channels to strengthen trade and marketing for agricultural commodities. This was achieved provision of information packages Male ‘and by linking agricultural data with the rapid response SMS systems maintained by the Ministry of Economic Development (MED). This market information system facilitates communication of market related information. Another main activity under this sector outcome was to strengthen farmer’s institutions such as farmer’s associations and other NGO’s. Technical capacity was strengthened within the agricultural sector by conducting improved knowledge and skills through trainings programs community based training, training of trainers and target specific training in crop and animal production and protection, food processing and value addition as well as business management for small entrepreneurs. MoFA has also achieved progress in strengthening the legal framework for the agricultural sector which is vital to regulate the use of natural resources and develop services related to agriculture development. The Ministry is currently working together with FAO on formulating an Agriculture Act, Pesticides Act, Plant Protection Act, Animal Health Act and Agriculture Land Act of Maldives. It is important that these legal documents get the necessary support from the Parliament for the sector administration.

  - Progress on Key Sector Outcomes

{For each sector outcome briefly describe the achievement made and the extent to which implementation was carried out as envisaged by the Strategies / Intervention List of the SAP. If there were any deviations what were they and the causes}

| Outcome |  | Progress | Issues |
| --- | --- | --- | --- |
| 1. | Commercial agriculture strengthened, enhancing food security and reducing reliance on imported food | 5 farmer groups that accessed agriculture business services was an achievement to the sector. Introduction of poultry. Subsidies / loans are will be issued to farmers to progress from marginal to commercial level. Gender participation in the agriculture sector is increasing (women focused training programs are conducted every year ) | Farmers / groups lack trainings. |
| 2. | Sustainable farming in all regions through increased availability of agricultural inputs and environment friendly technology | Introduction of bio control agents / environment friendly devices. Training was focused on climate smart agriculture production systems. | Financial constraint. |
| 3. | Physical infrastructure and networking channels developed for strengthened trade and marketing of agriculture produce | Development of infrastructure of nursery. |  |
| 4. | Institutional capacity strengthened to support growth of agriculture sector |  |  |
| 5. | Legal framework strengthened to regulate use of agriculture natural resources and develop services related to agriculture development | Draft National Plant Protection Legislation drafted & it was sent to people’s Majlis. Pesticides Bill is on the way to Majlis. Agricultural Land Legislation drat completed. |  |

  - Institutional Achievements in relation to the Sector Outcomes

{Briefly describe the role of key institutions in relation to the key sector outcomes and their achievements}

| Name of Institution(s) |  | Major Responsibilities towards outcomes | Achievement |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |

- Overall Assessment of Sector Performance related to key aspects

Operational Progress (300 words) {Explain the Extent to which implementation was carried out as envisaged by the Strategies/ Intervention List of the SAP. If there were any deviations why was this and what where they.}

Since the finalization of SAP, agriculture sector work has involved achieving results defined in SAP. Budgeting for the years, since then, has also been formulated according to SAP targets.

Financial Performance (200 words) {To what extent was the budget allocation utilized and if budgetary shortfalls were encountered what were the likely causes what impact did it have in regard to pursuing the Strategies / Intervention List of the SAP}

Budget reductions of the requested budget prevented the sector from achieving many targets defined for the year 2010.

Institutional Linkages (100 words) {If any institutional linkages were expected to be developed during the implementation, to what extent were they achieved. If not what were the main causes and what was the affect on the implementation.}

Institutional linkages were established with UNDP, MoED, FAO, and IFAD.

Sustainability (100 words) {To what degree could the operational aspects; including institutional linkages if any can be carried forward and describe any essential criteria required to facilitate this}

A knowledge management and sharing network will be established to purse further collaboration and linkages to achieve the targets.

3.0	Key Issues encountered

Institutional (200 words) {Discuss the Strategic position of the Lead Agency and how it affected the Implementation of Strategies/ Operational Performance}:

The lead agency is the Ministry of Agriculture and Fisheries, who is the government’s policy making and implementing body for agriculture. This contributed to more effective implementation of agriculture related SAP targets. However, lack of funding and poor capacity of the rural sector hinders progress to the sector.

Implementation (200 words) {Matters relating to implementation finances, human resources, monitoring and oversight}

Budgetary constraints and lack of trained staffs, especially graduate extension staffs.

Environmental : (100 words) {Environmental 9including Operational aspects) aspects which were encountered and need to be addressed}

Considering environmental aspects when using chemical pesticides and fertilizers by the individual farmers. More awareness programs should target on the environmental factors.

Political (100 words) {Political considerations encountered and to be addressed}

Political polarization of the communities and rural administration (local councils) hinders progress to the sector.

Socio/ Cultural (100 words) {Socio Cultural considerations encountered in respect of operation and implementation}

Fundamental religious organization plays a detrimental role limiting women’s involvement in the decision making and implementing powers of women communities.

Gender (100 words) {Gender related issues encountered during operation and implementation}

Lack of enthusiasm seen from both men and women in the communities toward gender sensitive programs. More awareness programs should be target on the importance of gender entrepreneurships and economic empowerment and decision making.

Statistical and Data Collection (100 words) {All the data sources used. Other factors which surfaced in the operation and implementation}

Earlier, administrative officials from the office of the Island Chiefs collected production data from their respective islands. The filled in forms were sent from the islands to the Atoll Office, which in turn forwarded them to MoFA without any consolidation. The ministry realized that production estimates made based on this system of data gathering was highly unreliable. The ministry has now discontinued it and production data are no longer collected. This reflects poor linkages and coordination between MoFA and island authorities. Production data are now collecting only from the Male’ local market, where the ministry estimates, only one fourth of the total local production being traded in Male’ market. Out of total 59 islands leased for the agriculture activities, only 15 islands send their annual reports and data on a regular basis.

- Lessons Learnt  (300 words)

{Discuss the Lessons Learnt in the process of carrying out interventions relevant to realization of the Sector Outcomes as specified in the SAP. Focus on the involved agencies and other stakeholders (including beneficiaries) and their willingness and capability to continue the interventions. If not what additional measures would need to be taken to strengthen them}

Developing the agriculture sector through introducing commercial farming is challenging due to the financial constraints and lack of enthusiasm from the private sector to invest in the agricultural activities.

- Partnerships (200 words)

{Describe any partnerships established with a donor, private sector of civil society organization to achieve an outcome(s)}

The Ministry’s main international partner in development is the Food and Agriculture Organisation (FAO) of the United Nations, and United Nations Development Programme (UNDP). The Ministry gets support from the International Fund for Agriculture Development (IFAD) where the Minister for Fisheries and Agriculture is the Governor appointed for IFAD. The Maldives is a member of the WTO, OIE, SAARC Agriculture Information Centre (SAIC), and SAARC Forestry Centre for which the Ministry is the focal point.

- Follow-up Actions & Recommendations  (400 words)

{Recommendations for strengthening, reorienting and/or revising the implementation mechanisms and strengthening the key agencies and other stakeholders for achieving Sector Outcomes in future periods}

Initial step for strengthening the implementation should start by maintaining a more strengthened network among the key agencies, stakeholders and beneficiaries. Build in an information sharing network between the local government authorities to share information, providing reliable statistics and data of their respective islands. Reliable data critically needed for formulating more efficient plans for the development of the agricultural sector. Designing and implementing monitoring and evaluation programs for the target activities.

Date: 3 October 2011

Name of Officer: Ibrahim Shabau

Designation: Director