## (8) RF_Regional Development and
Results Framework (RF) – Regional Development and Decentralization
Sector Outcome | Results Indicators | Indicator Type (Event/Op/ | Unit of Measure | Baseline | Targets/ Achievements | [5 empty] | Lead Agency
|  | Oc./Imp) |  |  |  | 2009 | 2010 | 2011 | 2012 | 2013
4. Links between local level functionaries and national authorities strengthened to coordinate and facilitate implementation of national programmes (P5) | 1. Establishing System for Intra Government coordination between central and local government institutions established (P4S1) | Output | Event | e- government / structure/ legal plat form for government | Target | Establishment of regional offices |  |  |  |  | NCIT
Ach.
| 2. Develop a monitoring and evaluation mechanism. (P3S2) | Output | No. |  | Target | [5 empty] | DNP, LGA, MoHA
Ach.
1. Islands, Atolls, and City Councils engaged in planning and implementing development policies in accordance with needs of communities and the decentralized administrative system established through 7 Regions , 188 island councils, 19 atoll councils, 2 city councils. (P1) | 1. Decentralization Law, Local Government Election Law enacted (P1,S1) | Output | Event | Community consultations on local councils. | Target | Consultations on preparing the bill | Draft of 2 bills prepared; 2 Acts passed |  |  |  | MoHA, LGA
[5 empty] | Ach. | Consultations on preparing the bill | Draft of 2 bills prepared; 2 Acts passed
| 2. Regulatory Framework (25 municipal regulation) for local governance, established (P1,S3) | Output | Event | N/A (2008) | Target | N/A | Drafted and shared with ministries for comments | Adopt by 188 island and 19 atoll and 2 city councils |  |  | LGA
[5 empty] | Ach. | N/A | Amendments made as per feedback
| 3. Local Government Rules of Procedure (‘Hinga Gavaidhu'), of elected councils, developed and adopted (P1,S4, P1S2) | Output | Event | N/A (2008) | Target | N/A | Prepare Rule of Procedures documents for LGA, city, atoll and island councils | Adopted by, 188 islands, 19 atolls and 2 city councils
[5 empty] | Ach. | N/A | All drafted and shared with ministries for comments
| 4. Standard Operating Procedures (SOP) for local councils, developed and adopted (P1,S4, P1S2) | Output | Event | N/A (2008) | Target | N/A | N/A | NIL | 2 city council, 120 island council 10 atoll councils. | 2 city council, 188 island council, 19 atoll councils | LGA
[5 empty] | Ach. | N/A | N/A |  |  |  | LGA
| 5. Councils having Service Charters to serve their communities efficiently (P1,S3, P1S5, P1S6) | Outcome | No. of councils | N/A (2008) | Target | N/A | N/A |  |  |  | LGA
[5 empty] | Ach. | N/A | N/A
| 6. Local councils generating their own funds to supplement government funding provisions, increased (P1S6) | Impact | No. of income-generating projects and annual income (Mrf) | N/A (2008) | Target | N/A | N/A |  |  |  | LGA
[5 empty] | Ach. | N/A | N/A
2. Provincial Administration and Commercial Centers setup to provide social and economic opportunities that create a competitive environment (P2) | 1. Regions with National Offices (‘Gaumee Idhaaraa’), established (P2S1) | Event | Event | N/A (2008) | Target | Establishment of 7 province offices | Province offices in operation | Establishment of Atoll National Offices |  |  | MoHA
[5 empty] | Ach. | Establishment of 7 province offices | Province offices in operation | All 7 National Offices in operation
| 2. Development of commercial centers, increased (P2S1, P2S2) | Output | No. | Kulhudhufushi/ Addu International Port | Target | Decentralization of Port Activities, change the management to public company owned | Maamigili Aiport/ Thimarafushi Aiport/ Fuamulah Aiport / Daranvandhoo Aiport / Felivaru Airport | Distribution centres in Vilufushi and Thinadhoo/ Collection Centres |  |  | MED
Ach.
| 3. Mechanisms and Frameworks established for development planning at the regional level (P2S5) | Output | Event |  | Target | [5 empty] | DNP, MoHA
Ach.
| 3. Line Ministries which have decentralized services at the provincial level, increased (P2S6; P2S4) | Outcome | % | hospitals , vocational training (2008) | Target | DNR (ID card and passport), ferry system, public health | Tertiary Education, Public health. |  |  |  | All ministires
Ach.
| 4. Professional and Skilled workers engaged in their vocations in their native regions, increased (P2S3) | Impact | % | N/A (2008) | Target | N/A | N/A
[5 empty] | Ach. | N/A | N/A
3. Increased participation of Civil Society and Private Sector at the Local Government level in social and economic activities (P3) | 1. Local Councils where Civil Society organizations and Private Sector work in close coordination in attending to relevant matters relating to the region, increased (P3S1) | Outcome | No. | No legal status for island development committees, community base organizations (2008) | Target | N/A | Legal authority to WDC | Establish 188 island WDC and 2 city WDC
[5 empty] | Ach. | N/A | Legal authority to WDC
| 2 Create a conductive environment for civil society growth and mobilization. (P3S2) | Output | Event | NGO Law (2008) | Target | Financial support for NGO’s from Gov/ NGO’s support project/ | Financial support for NGO’s from Gov/NGO forum/ | Establish NGO building