## (23) Environment_RF_09Aug 2011
Results Framework (RF) - Environment
Sector Outcome | Results Indicators | Indicator Type | Unit of Measure | Baseline | Targets/ Achievements | [5 empty] | Lead Agency
[6 empty] | 2009 | 2010 | 2011 | 2012 | 2013
1. EIA Strengthened and Monitoring enhanced (P1) | 1. EIA evaluation process and approval mechanism strengthened in accordance with existing policies and regulations (P1S5S6) | Output | documents | EIA regulation 2007 | Target | Develop EIA evaluation framework | Add 5 new EIA reviewers | i) Add 5 new EIA reviewers | i) Develop EIA Monitoring report and monitoring review guidelines | Improve M&E of EIA process | EPA /EIA unit
[7 empty] | Develop generic TORs | ii) Finalize generic TORs | ii) Improve M&E of approved projects
[7 empty] | Conduct 2 training sessions for EIA monitoring | iii) Conduct a training sessions for EIA monitoring | iii) Conduct 2 training sessions for EIA monitoring
[7 empty] | Establish Env. liability regulation | iv) Publish revised EIA reg. | iv) Develop compliance and enforcement guideline
[8 empty] | v)Implementation of fast-track EIA evaluation | v) Conduct an audit of EIA and EIA review Process
vi) Establish a new Legally binding document for EIA reg.
[5 empty] | Ach. | Development of EIA evaluation framework Completed | 2 EIA reviewers added | i) 6 new reviewers assigned
[7 empty] | Draft generic TORs completed | ii) Generic ToRs finalized
[7 empty] | Not achieved due to inadequate budget support | iii)To be carried out in-house, due to budget limitations
[7 empty] | Env. liability regulation draft completed | iv) EIA regulation Final Draft ,90% completed
v)Implementation to be delayed until new EIA regulation is finalized
| 2. Environment information database developed incorporating GIS facility to track other reporting and monitoring performance benchmarks (P1S4) | Output | Data base | Nil | Target | Establishment of GIS | Development of GIS | i) Establish Data base for EIA reporting | i)Establish Data Repository through NGIS | i)Update Data Repository through NGIS | EPA
ii)Incorporate data collection protocols to Generic TORs
iii) Establish GIS system
[5 empty] | Ach. | Establishment of GIS started under MEMP | TORs and trainings completed | i) Some Information collected for database.
[7 empty] | EIA data collection protocols developed. | ii)Finalized generic ToRs
iii) ongoing (MEMP)
| 3. Environment guidelines for selection of sites for development purposes, enhanced (P1S11) | Output | document | N/A | Target | Establish Environment Sensitive Sites. | Updating the list of Env sensitive sites | i)Finalize the list of sensitive areas by publishing on Gazette | Review and update sensitive area list | Implementation by other agencies | EPA, MHE / EnvDept
[8 empty] | ii) consider environmentally sensitive Areas in planning process | Review and revise site selection criteria in EIA regulation
[5 empty] | Ach. | Environment Sensitive sites developed | Updated the draft list of Env. sensitive sites | i)Final Draft completed for Gazette
| 4. Councils to which environment monitoring is decentralized (P1S14) | Outcome | No. of councils | 0 | Target | NA | NA | i)Establish Environment desks at 2 councils (Kulhudhuffushi, Hithadhoo) | i)Establish monitoring mechanism in 5 regions | i)Establish monitoring mechanism in 5 atolls | MHE, EPA Council
[8 empty] | . | ii)Capacity building for 5 regions | ii)Capacity building for 5 atolls
[5 empty] | Ach |  | NA | i)1 trainee from each council identified for the desk
| 5. Strengthening of Atoll and Island Councils on Environment protection (P1S12) | Output | Number of councils | 0 | Target | NA | Training of councilors | Increase Awareness for councilors, on Env. related areas | 3 Training programs for councils and focal points | 3 Training programs for councils and focal points | MHE, EPA Councils
[5 empty] | Ach |  | Planning of training for councilors and atoll level staffs | GDh councilors awareness completed
Awareness for Baa Atoll Council on Env. Mgt. completed
2. Biological diversity sustained for ensuring maximization of eco system benefits (P2) | 1. National government, province and atoll offices and community responsibilities on biodiversity conservation defined and incorporated in all national and sector policies (P2S2) | Output | No. policies, laws and regulation s | NBSAP 2002 and environment act 4/93 | Target |  | Address biodiversity issues in relevant laws and regulations | i)Address biodiversity issues in relevant regulations/ laws | i)Address biodiversity issues in relevant regulations/ laws and policies | Finalize NBSAP | MHE / BD unit
[8 empty] | ii) Revise NBSAP | Revise NBSAP
[5 empty] | Ach. |  | Incorporated in draft Tourism Act | i) Incorporated in Environment Liability regulation; in draft EIA regulation and in draft waste regulation.
ii) not started due to limited budget from the gov. sought financial assistance from GEF
| 2. Formal agreements and market based instruments for bio diversity conservation increased (P2S4) | Output | % and number | 70 bird species, 25 marine areas, 2 islands and 2 wetlands protected | Target | Protect 10% of terrestrial and 5% of Marine area of the Maldives before end of 2010 | i)Protect 10% of terrestrial and 5% of Marine area of the Maldives before end of 2010 | i) Prepare guidelines for protection of species and ecosystems. | i)adopt PPP on protected areas management. | i) Protect at least 17 per cent of terrestrial and inland water, and 10 per cent of coastal and marine areas before 2020 as per Nagoya Targets (2010) | EPA, MHE
[7 empty] | ii) Prepare the 4th National Report to CBD | ii) PPP for managing protected areas adopted | ii) Protect at least 17 per cent of terrestrial and inland water, and 10 per cent of coastal and marine areas before 2020 as per Nagoya Targets (2010)
iii) A Biosphere reserve declared
iv) Protect important and endangered species
v)Maldives to become a member of CITIES, IUCN, ABS and Supplementary Protocol on Liability and Redress.
vi) Prepare and submit the 2nd National Report to the Biosafety Protocol
[5 empty] | Ach | 3marine areas protected (almost 2 % of the total area of Maldives protected by end of 2009) | i) No areas protected in 2010 | i) 10% completed
[7 empty] | ii) completed | ii) PIF document prepared and sent to PO
iii) B.Atoll declared as a UNESCO biosphere reserve
iv) 12 taxa protected under Environment Act
v) Cabinet Paper prepared
vi) Received funding from GEF in August. Two staff appointed to complete the report.
| 3. A fully functional protected area system established providing protection to terrestrial, marine, mangrove and ecosystem threatened species (P2S5) | Output | Number of protected areas | Protected Areas Declared under the Act | Target | i)Declare 5 new protected areas | i)Declare 3 new protected areas | i)Prepare a data base for Protected wetlands | i)Survey the status of protected wetlands | Survey the status of wetlands | MHE, EPA
|  |  |  | 1993-04-01 |  |  | ii)Establish Management plans to be for 5 areas | ii)Declare Fuavahmulak wetland area as protectedfor Protected wetlands on mapsl Managementru MPA | ii)Indentify additional threatened species
|  |  |  | 28 areas |  |  | iii)Increase boundary of existing PAs | iii)Protect Marine Species under Env.Act 4/93 | iii)Develop Mgt plan for Protected areas
iv)Establish B.Atoll Biosphere reserve mngt plan & conservation fund
[5 empty] | Ach | 3 new protected areas declared | i)Not achieved | i)Developing wetland data base.
[7 empty] | ii)Draft Mgt Plan for 5 areas completed | ii)All documents prepared for submission to cabinet
[7 empty] | iii)Boundary reestablished and marked on maps | iii)12 Taxa of marine species protected under Env Act
iv)Documents for B.Atoll Conservation fund prepared
3. Community Resilience to impacts of climate change, and capacity for disaster mitigation and coastal protection increased (P3) | 1. Locally appropriate coastal protection and flood measures developed for implementation in inhabited islands (P3S1) | Output | No. of reports |  | Target | ICCR project signing | Review current practiced methods for coastal protections and flood | i) Complete the coastal adaptation survey | Demonstrate adaption measures on 3 islands (HDh Kulhudhifushi, K Thulusdhoo, GDh Thinadhoo) | Demonstrate the adaptation in the piloted islands of the project | MHE (CCED)
ii) Protect 3 islands using soft adaptation measures
[5 empty] | Ach | Project Signed | Survey for reviewing conducted in the ICCR project | i)Survey Final report published
ii) Bid documents Submitted to establish soft measures
| 2. National adaptation strategies and program reviewed and NAPA implemented (P3S3) | Output | No. of reports | Existing strategy NAPA | Target | Submit the NAPA project to GEF for funding | Launch and start implementing the projects identified in NAPA | (i)Review the Land use Guidelines | Establish Revised guidelines | Implement the guidelines | MHE
[8 empty] | (ii)Develop a National Research Strategy | Identify food security issues due to CC
[5 empty] | Ach | Signed | Project launched | National Research Strategy draft developed
| 3. Current Resilient Islands Program (RIP) reviewed and revised (P3S6) | Output | Event | ICCR project document | Target |  | Sign the agreement and launch the ICCR project | Carry out the activities planned for the year. | Carry out the activities planned for the year. | Carry out the activities planned for the year. | Utilities/ MHE
[5 empty] | Ach |  | Project launched | Activities carried out (14% of the total 4 yr project)
| 4. Civil society engagement in combating climate risks increased (P3S10) | Outcome | events | Nil | Target |  |  | Conduct a workshop for trainers who will provide the training | Information Dissemination information via workshops and web portals | Trainers to conduct training on the native islands
[5 empty] | Ach |  |  | One workshop conducted
Layout of web-portal completed
| 4. Implement National Obligations to UNFCCC | outcome | reports | 1st NC/ NAPA/ TNA/ NCSA | Target |  | Complete National Economic and Environment Development Study (NEEDS) document | Initiate works of second National Communication | Submit Second National Communication document (includes GHG inventory, Vand A study) | Submit Second National Communication document (includes GHG inventory, Vand A study)
[5 empty] | Ach |  | Final Draft of NEEDS completed | Second National Communication project document completed
NEEDS Published
| 5. Reinforce Climate Negotiations | Output | No of Meetings | 8 UNFCCC meetings | Target | Attend formal and relevant negotiations and trainings of UNFCCC | Attend formal and relevant negotiations and trainings of UNFCCC | Attend formal and relevant negotiations and trainings of UNFCCC | Attend formal and relevant negotiations and trainings of UNFCCC | Attend formal and relevant negotiations and trainings of UNFCCC | MHE
Publish a comprehensive CC policy
[5 empty] | Ach | Attended 8 UNFCCC meetings | Attended 8 UNFCCC | Attended 4 UNFCCC meetings
[6 empty] | Organized and conducted the first vulnerable forum in Maldives | 6 IPCC meetings | 6 IPCC meetings
[6 empty] | Attended COP15 | Attended COP16
| 6. Islands in which coastal protection measures are implemented to protect human settlements, increased (P3S9) | Outcome | (No of islands) | Coastal protection in 3 islands | Target | Protect 3 islands | Protect 5 islands | i)Protect 8 islands using hard construction measures | Design coastal protection for 3 islands (islands to be decided) | Design coastal protection for 2 islands (islands to be decided) | MHE
[5 empty] | Ach | 3 island work complete (K. Villingili, M. Naalaafushi, GA Dhaandhoo) | 5 islands completed (M. Maduvari, R. Maduvari, M. Dhiggaru, ADh Kunburudhoo, HDh Kulhudhufushi) | i)2 islands completed (HA Dhidhoo, GN Fuahmulah)
[7 empty] | 6 islands work ongoing | 6 islands (N. Holhudhoo, GDh Gadhoo, GDh Rathafandhoo, K Guraidhoo, Sh Komandoo, GDh Madaveli Hoadeddhoo) contracts signed and to be started
Name of islands to be included
| 7. Locations where appropriate waste water treatment processes are implemented to avoid climate change related risks to fresh water availability (P3S7) | Outcome | No. of islands (3) | NAPA.Existing sewerage project document | Target |  |  | Conduct an Integrated Water management project on 3 islands | Launch the project and implement it (Mahibadhoo, Ihavandhoo, Gadhdhoo) | Continue the demonstration
[5 empty] | Ach |  |  | PIF prepared.
Approved from NPC
Approved by the Adaptation Fund Board
4. Adaptation and Mitigation response to beach erosion strengthened and a system developed to assist communities where livelihood and property are affected by beach erosion (P4) | 1. Guidelines for settlement planning and coastal modification to prevent erosion developed (P4S1) | Output | Event | Existing Land Use Plan Guidelines | Target |  |  | Prepare guidelines for climate risk resilient coastal protection and LUP | Establish Guidelines | Implementation of projects | MHE
Support IMPACT2C study on quantifying CC damage
[5 empty] | Ach |  |  | Recommendations for climate risk LUP completed
Preparation of Coastal protection guidelines in process of procurement (tendered twice).
| 2. Viable alternatives (more cost efficient softer measures identified and developed for prevention of coastal erosion Guidelines for settlement planning and coastal (P4S5) | Output | No. | No Baseline | Target |  | Survey of existing soft coastal adaptation measures conducted | Demonstration of softer adaptation measures | continue the demonstration | Replication of successful outcome | MHE
[5 empty] | Ach |  | Final report published | Open for bidding for design and demonstrate softer adaptation measures
| 3. Settlements protected against coastal erosion, increased (P4S2) | Outcome | No. of island | Site specific | Target |  | Fullfilled in (P3S9) | Fullfilled in (P3S9) | Fullfilled in (P3S9) | Fullfilled in (P3S9) | MHE
Ach.
| 8. Establish a climate research body or intensify Maldives Meteorological Services (MMS) with a specific mandate to gather weather data, and model climate impacts for the Maldives. (P4S6) | outcome | No of stations | Weather and Climate data from 5 manned stations and 13 AWSs | Target | Establish a climate data base | Establish a climate data base | Establish a climate data base | Establish a climate data base | Improve the climate database | MMS/ MHE
[5 empty] | Ach. | Not achieved due to lack of budget support | Not achieved due to lack of budget support | Not achieved due to lack of budget support
|  |  | No. of model output products |  | Target | Establish a Climate modeling system | Establish a Climate modeling system | Establish a Climate modeling system | Establish a Climate modeling system | Improve the modeling capacity
[5 empty] | Ach. | Not achieved due to lack of budget support | Not achieved due to lack of budget support | Not achieved due to lack of budget support
|  |  | No of trained staff | 4 staff completed WMO-II MET, 6 BSc, 3 MSc | Target | Human Resources Development for enhancing Weather and Climate related services | Human Resources Development for enhancing Weather and Climate related services | Human Resources Development for enhancing Weather and Climate related services | Human Resources Development for enhancing Weather and Climate related services | Human Resources Development for enhancing Weather and Climate related services
[5 empty] | Ach. | l staff completed BSc. | 2 staff trained in Meteorology to WMO Class II level and 3 completed BSc. | 1 staff undergoing MSc in meteorology and 1 staff undergoing PhD and 1 personnel undergoing training in meteorology in WMO class II level
|  |  | No of organizations or centres | WMO/ WMO-ESCAP-TROPICAL CYCLONE PANE/ | Target | Strengthen cooperation with international and regional organization s and centers for collection of Meteorological and Seismological information, data and warnings | Strengthen cooperation with international and regional organization s and centers for collection of Meteorological and Seismological information, data and warnings | Strengthen cooperation with international and regional organization s and centers for collection of Meteorological and Seismological information, data and warnings | Strengthen cooperation with international and regional organization s and centers for collection of Meteorological and Seismological information, data and warnings | Strengthen cooperation with international and regional organization s and centers for collection of Meteorological and Seismological information, data and warnings
/PTWC/JMA/
|  |  |  | SMRC/INCOIS-INDIA,UNESCO-IOC | Ach. | Became a member of RIMES
|  |  | % of the systems in operation | 95% of the systems in operation | Target | Uninterrupted operation of Meteorological, seismological observing and communication systems | Uninterrupted operation of Meteorological, seismological observing and communication systems | Uninterrupted operation of Meteorological, seismological observing and communication systems | Uninterrupted operation of Meteorological, seismological observing and communication systems | Uninterrupted operation of Meteorological, seismological observing and communication systems
[5 empty] | Ach. | 90% of the systems in operation | 80% of the systems in operation | 85% of the systems in operation
| 9. Ensure an Effective early warning system is implemented in full with adequate capacity for implementation at all levels (P4S7) | outcome | No of stations to monitor Meteorological, Geological and Marine hazards and no. of equipment operational | 01 Upper air observing station | Target | Establishing an AWS on islands with population above 1000 people | Establishing an AWS on islands with population above 1000 people | Establishing an AWS on islands with population above 1000 people | Establishing an AWS on islands with population above 1000 people | Establishing an AWS on islands with population above 1000 people | MMS / MHE
05 manned / 13 Automatic Weather monitoring stations
|  |  |  | 01 weather radar. | Ach. | 8 AWS installed and operational | 1 AWS installed
|  |  |  | 02 seismometers to monitor earthquakes. | Target | Repair and maintenance of all equipments used for monitoring weather, earthquake and tsunami | Repair and maintenance of all equipments used for monitoring weather, earthquake and tsunami | Repair and maintenance of all equipments used for monitoring weather, earthquake and tsunami | Repair and maintenance of all equipments used for monitoring weather, earthquake and tsunami | Repair and maintenance of all equipments used for monitoring weather, earthquake and tsunami
|  |  |  | 03 tide gauges to measure tide and sea level | Ach. | In adequate budget for repairing the equipments but some repairing was done | In adequate budget for repairing the equipments but some repairing was done | Radar was out of service for a long period due to absence of a service contract, now repaired and operational.
|  |  | No. of awareness campaign and participants |  | Target | Conduct Awareness raising for public and students in 2 atolls on natural hazards | Conduct Awareness raising for public and students in 2 atolls on natural hazards | Conduct Awareness raising for public and students in 2 atolls on natural hazards | Conduct Awareness raising for public and students in 2 atolls on natural hazards | Conduct Awareness raising for public and students in 2 atolls on natural hazards
[5 empty] | Ach. | Conducted Awareness raising on natural hazards for 2 atolls and some students | Conducted Awareness raising on natural hazards for some students due to lack of funds | Conducted Awareness raising on natural hazards for some students due to lack of funds
|  | output | % of operation of multi-hazard early warning system |  | Target |  | Construct a building to facilitate the meteorological facilities for National Meteorological Centre | Construct a new infrastructure to facilitate the meteorological facilities for National Meteorological Centre | Construct a new infrastructure to facilitate the meteorological facilities for National Meteorological Centre
[5 empty] | Ach |  | Not achieved due to lack of budget support | Not achieved due to lack of budget support
5. A solid waste management system to prevent adverse impact on human health and environment through economically viable and locally appropriate approaches, implemented (P5) | 1. A Waste Management Act enacted (P5S2) | Output | Act | Env Act 4/93 | Target | Development of first draft of waste management Act | Stakeholder consultation and reviewing the draft Waste Management Act | Submit the waste management Bill to AG office | Enact Waste management Act | M&E of Compliance and Enforcement of waste management Act | MHE
[8 empty] | Translate the waste Management. Act to AG (englishd by other governmetn | Prepare standards and regulations under Waste management act
[5 empty] | Ach. | Waste Mgmt. Act drafted | Workshop completed | A regulation on waste management drafted
| 2. Policy and Regulatory Framework for PPP in Waste Management, developed (P5S2) | Output | regulation |  | Target | NA | NA | i)Incorporate PPP Policy and Regulatory Framework in to the waste Act | Implementation of PPP through councils and utility companies | Develop policy on waste management.mentation | MHE
ii)Prepare guideline for PPP for councils on waste management
[5 empty] | Ach. |  |  | i)Draft Act finalized
ii)Guideline drafted
| 3. Facilitation for island communities to manage their waste (P5S1) | Output | No.of islands/Atolls | 10 | Target | i)Trainings for 5 island communities | i)Trainings for 5 island communities | i)Trainings for island councils of 2 atolls | i)Establish Regional waste management | i)Establish Regional waste management | EPA, utilities, MEMP project
[7 empty] | ii)Handover of WM equipments | ii)Handover of WM equipments
iii)Preparation of awareness materials
[5 empty] | Ach | i) 5 completed | i)5 completed | i)Training for one atoll completed
[7 empty] | ii)16 islands providedwaste management. | ii)14 islands completed
iii)Parties selected for Documentary & booklet preparation
| 4. Island waste management centres managed by island communities increased (P5S3) | Outcome | No: of islands having waste management facilities | 114 islands | Target | Achieved through P5S1 | Achieved through P5S1 | Achieved through P5S1 | Achieved through P5S1 | Achieved through P5S1
Ach
| 5. Provincial Solid Waste Management facilities established for recovery and recycling, facilitated (P5S4) | Output | No. of facilities established | 01 in Thilafushi | Target | i)Establish Solid Waste Management facilities for recovery and recycling in 7 provinces | i)Establish Solid Waste Management facilities for recovery and recycling in 7 provinces | i)Establish Solid Waste Management facilities for recovery and recycling in 7 provinces | i)Establish Solid Waste Management facilities for recovery and recycling in 6 provinces | i)Establish 5 regional facilities | EPA, utilities, MEMP project
[5 empty] | Ach | i)North province selected under MEMP project | i)Surveying conducted | i)Preparatory work going to build facility including EIA for MEMP site in North province
[7 empty] | Design of the MEMP site developed | Thilafushi Site leased for an International Company
6. People including women, men, boys and girls of different income groups and poverty level and the environment protected from hazardous waste and chemicals (P6) | 1. A National Chemicals Regulation Framework, guidelines and information system developed (P6S1) | Output | Regulation and guideline | Environment Act 1993, has regulation on waste management | Target | - | Revise existing act including chemicals management in the Env act | i)Revise existing act including chemicals management in the Env act | Develop National Chemicals Regulation Framework, guidelines and information system | Develop National Chemicals Regulation Framework, guidelines and information system | MHE/ international relation unit
ii)Developing a Chemical profile of Maldives
iii)Complete National report for 2009-2011 for SAICM
[5 empty] | Ach. | - | Draft prepared | i) Redrafting of the Env act
ii) SAICM proposal prepared to seek funding for the project for developing chemical profile
iii) National Report sent to SAICM
| 2. A communication system for timely updated notification of movement of hazardous waste, meeting international standards developed (P6S2) | Output | Event | Nil | Target | Reporting of international conventions strengthened | i)Send regular notification in accordance with BASEL convention | Prepare guideline for trans boundary movement of hazardous waste | Send reports and notification to conventions | Send reports and notification to conventions
ii) Incorporate transboundary movement of hazardous waste in new Environment Act
[5 empty] | Ach. | Annual reporting | i)Not achieved due to lack of budget. | ii) no budget for this activity
ii) Draft act prepared.
7. Air Quality to safeguard human health, improved (P7) | 1. Densely Populated Islands equipped with ambient air quality monitoring station, increased (P7S1) | Output | Number of stations | 0 | Target | i)Establish monitoring in Male’ | i)Establish Air pollution monitoring in Male’ | i)Establish Male air quality monitoring | i)Establish Air quality monitoring stations in 3 islands | i)Establish Air quality monitoring stations in 3 islands | EPA
[8 empty] | ii)Buying High Volume Sampler | ii)Preparing Standards for vehicular and point source emissions
[5 empty] | Ach. | i)Not achieved | i)Obtained equipment | i)Equipment installed and monitoring to be started
ii)Bidding process completed for buying HV Storing to be startedtemanagment Actent act
| 2. Point and Mobile sources monitored for pollution increased (P7S2) | Outcome | No.of stations | Nil | Target |  | Achieved in (P7S1) | Achieved in (P7S1) | Achieved in (P7S1)
Ach.
8. Functional decentralized environment governance system established (P8) | 1. Mandates for Environmental Administration at the National, Provincial, Atoll and Island Levels established (P8S1) | Output | No. of EPA In the islands | Mandates by PO | Target |  | Fulfilled in (P1S14) | Fulfilled in (P1S14) | Fulfilled in (P1S14) |  | PO
Ach.
| 2. Capacity in Provinces, Atolls, Islands where environment related functions are being carried out, increased | Outcome | No: trained staff/ degree/ diploma |  | Target |  | 10students to complete foundation | 17 enrolled(for foundation) | 17 enrolled(for foundation) | 17 enrolled(for foundation) | MHE / MEMP project
[8 empty] | 20 (for diploma /degree) | 20 (for diploma /degree) | 20 (for diploma /degree)
[5 empty] | Ach. |  | 10 students completed foundation
9. Measures to develop a low carbon economy for achieving carbon neutrality by 2019, implemented (P9) | 1. Legal Framework and Action Plan targeting carbon neutrality by 2019 established (P9S1) | Output | Event | Energy balances 2005 | Target |  | National Energy demand and supply studies 2009 | Initiate market assessment for air conditioners and refrigerators | Assessments of GHG emission reduction from EE LC energy measures | Design consumer awareness plan | MHE
[7 empty] | Carbon Audit | Conduct Carbon Audit | Identify building-integrated renewable energy (RE) & their potential for energy use and GHG emission reduction | Establish an assessment and monitoring system for EE & low carbon (LC) energy buildings technologies
[9 empty] | Conduct Carbon Audit | Conduct Carbon Audit
[9 empty] | Implement projects under | Implement projects under
[9 empty] | GIZ proposal | GIZ proposal
[5 empty] | Ach. |  | Demand and Supply survey Completed
Carbon Audit 2009 completed
| 2. Incentive scheme to encourage businesses offering renewable sources of energy, developed (P9S5) | Output | report | Energy Policies and Strategies | Target | Renewable energy concessional loan scheme | Renewable energy concessional loan scheme | Renewable energy concessional loan scheme | Develop appropriate financial and market based mechanisms that support low carbon buildings. | Fiscal incentives program (such as income tax, duty exemption) to increase market uptake & penetration of EE & LC building technologies | MHE
[5 empty] | Ach |  | 3 loans disbursed
10. Values for Environment friendliness inculcated among the population (P10) | 1. Businesses engaged in establishing and servicing alternate renewable energy system increased (P10S1) | Outcome | No. | (i)Energy Policies and Strategies | Target |  |  | Fulfilled in (P9S1) | Fulfilled in (P9S1) | Fulfilled in (P9S1) | MHE/MEA
(ii)Completed Investment Plan
Ach
| 2. Communities, media, industrial enterprises, government agencies adopting appropriate waste management practices, and other Environmental issues increased (P10S2) | Output | No. of awareness programs conducted | Awareness among the public | Target |  | i)Conduct 5 provincial workshops | i)Conduct 5 provincial workshops | Conduct 4 provincial workshops | Conduct 4 provincial workshops | MHE (awareness unit)
[7 empty] | ii)Publish 12 Pemphis Issues | ii)Publish 12 Pemphis Issues | Publish 12 Pemphis Issues | Publish 12 Pemphis Issues
[5 empty] | Ach. |  | i)5 provincial workshop, | i)2 provincial workshop, no budget for the remaining 3 workshops
[7 empty] | ii)7 issues published | ii)4 issues published as of July 2011
Env. days celebrated, leaflets and booklets published
| 3 Communities, media, industrial enterprises, government agencies engaged in advocating climate change issues and importance and advantages of becoming carbon neutral, increased | Output | No. of awareness program,mes conducted | nil | Target |  | Fulfilled in (P10S2) | Fulfilled in (P10S2) | Fulfilled in (P10S2) | Fulfilled in (P10S2) | MHE
Ach.