## (2) Affordable Living Costs_RF
Results Framework (RF) - Affordable Living Costs
Sector Outcome | Results Indicators | Type of Indicator | Unit of Measure | Baseline | Target/ Achievement | [6 empty] | Lead
[6 empty] | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | Agency
1. Restructure the revenue system towards direct taxation and Rationalization of the tariff regime to reduce burden on the poor (P1) | 1. Legislative Amendments completed for increased Market Competitiveness
| 1(a) Amend Import/Export Law | Output | Event | 1978 import/export law | Target | NA | Ground work on amending the import/export law | Consultation and drafting amendments to the Export Import Law | Implementation of proposed changes to Law | Continuation of implementation | Continuation of implementation | MED
Submit revision to draft to be submitted during 2011
Formulation of relevant Regulations on Import export bill upon approval of Majlis
[5 empty] | Ach. | 2010: Target Achieved; 2011: On Track
Bill tabled in Majlis on July 2011 .
| 1(b) Establish Maldives Monetary Act | Output | Event |  | Target |  | To submit bill to Majilis on new MMA act | Submit bill on new MMA act to Majlis | To formulate relevant regulations on MMA act | Implement new MMA act | Implement new MMA act | MMA
[8 empty] | Expected bill to be passed by end of 2011 | Implementation of MMA Act
[5 empty] | Ach. | 2010: N/A; 2011: On track
Draft bill prepared
| 1(c) Establish Goods and Service Tax (GST) | Output | Event | 2009 draft bill on T-GST | Target | Draft bill on T-GST | Submit T-GST bill to parliament, and obtain parliament approval | Submit Bill on GST to parliament | Implement GST | Implement GST | Implement GST | MIRA
| [The GST Bill brings within its scope the current T-GST regime] |  |  |  |  | 2010: Prepare Regulations on T-GST once the bill is passed | MED
[8 empty] | Target to pass the GST Bill is on 15 August 2011. | Conduct taxpayer awareness programs throughout the country. | Conduct taxpayer awareness programs throughout the country. | Conduct taxpayer awareness programs throughout the country.
Implement GST from 1 October 2011onwards.
To formulate GST regulation
Conduct taxpayer awareness programs throughout the country.
Registration of businesses that falls under GST.
[5 empty] | Ach. | 2010: Target Achieved.; 2011: On Track
[7 empty] | TGST bill approved by parliament & effective from January 2011. Regulations on T-GST completed | T-GST implemented on January,
Revisions to TGST tabled at the Parliament on July 2011
GST Bill submitted to Parliament during June 2011,
| 1(d) Establish Corporate Profit Tax (CPT) | Output | Event | 2004 draft bill on Business Profit Tax (BPT) | Target | To submit a bill on BPT | Seek approval of parliament for BPT | To submit a Bill on CPT | Implement CPT from 1 January 2012 onwards. | Implement CPT from | Implement CPT | MIRA
| [The CPT Bill simplifies the current BPT Act (Law Number 5/2011) by narrowing down its scope to corporate bodies only (companies, partnerships and corporate bodies)]. | [10 empty] | MED
[8 empty] | Target to pass the CPT Bill is on 6 October 2011. | To formulate CPT regulation | . | Conduct taxpayer awareness programs throughout the country.
[8 empty] | To formulate regulation on BPT. |  | Conduct taxpayer awareness programs throughout the country.
[8 empty] | Regulation to be published in August 2011. | Conduct taxpayer awareness programs throughout the country.
To conduct taxpayer education
BPT implementation from 18July 2011.
[5 empty] | Ach. | 2009: Bill submitted to parliament; 2010: Target Achieved; 2011: On Track
CPT Bill submitted to Parliament during June 2011,
BPT effective from 18 July 2011.
Taxpayer education on going.
| 1(e) Establish Personal Income Tax (PIT) | Output | Event | 2004 draft bill on Business Profit Tax (BPT) | Target | 2011: To submit a Bill on PIT.; 2012: Implement PIT from 1 January 2012 onwards. | MIRA
| [The PIT Bill proposes a tax on income earned by individuals as wages, dividends, and certain other types of income, including profits from businesses carried on by that individual. It incorporates all elements in the current BPT Act (Law Number 5/2011) that relates to individuals.] | [10 empty] | MED
[8 empty] | Target to pass the Bill is on 15 November 2011. | To formulate PIT regulation and to
[8 empty] | Registration of taxpayers that falls under PIT. | Conduct taxpayer awareness programs
[5 empty] | Ach.. | 2011: On Track
PIT Bill submitted to Parliament during June 2011, and the Bill is currently on committee discussions.
| 2. Establish Central Business Registration Act | Event | Event |  | Target |  | Prepare ground work on Central Business registration act | Draft bill on Central Business Registration act and to submit it to parliament | Bill passed, prepare regulation for the act and implementation of the act | Implementation of the act |  | MED
[5 empty] | Ach. | 2011: On Track
Bill tabled at Parliament on July 2011
| 3. Strengthen enforcement of business/trade regulations | Impact | No of/ % of businesses checked |  | Target | 3331 (100%) | 3765 (100%) | 100% | 100% | 100% | 100% | MED
(refer to S4 P3 of Programme 5.02 Trade & Investment)
Develop SoP’s for Shop inspections for all retailers and wholesalers
[5 empty] | Ach. | 2009: No inspection done in 2009; 2010: 391 businesses inspected from Oct- Dec; 2011: On track
2. Government expenditure streamlined | 1. E-government network strengthened to enhance efficiency of public service delivery by increasing connectivity of government service institutions (s1)(day 1 public sector reform) | Event |  | Prior to E-gov, what % spent on public service delivery | Target | [6 empty] | NCIT
(i) to match expected revenues |  |  |  |  | Ach.
(ii) towards sustainable, constructive areas (P2) | 2. Debt strategy Developed and perform a debt sustainability analysis performed | Event |  | N/A | Target | 2011: Formulate a Medium Term Debt Management Strategy and start implementing parts of the strategy; 2012: Carry out a Debt Sustainability Analysis ( to monitor the Debt Strategy);; 2013: Enact a Public Debt Law; | MOFT
[9 empty] | Develop an integrated Debt Management Division (DMD) with a distinct front, middle and back office; | Auditor General’s Office to undertake a financial audit of DMD.
[9 empty] | Internal Audit Department to undertake control audit of DMD | Carry out a DSA.
[5 empty] | Ach. | 2011: - First meeting of the Debt Management Committee (DMC) held in February Subsequently, 2 more meetings were held
Draft MTDS and Debt paper reviewed and discussed.
Debt Expert under ADB's TA worked with the debt staff and worked on building capacity of staff in understanding the World bank/IMF MTDS tool and held basic training in using the tool.
Debt Management Reform Plan mission from World Bank in July/ Aug. held more intense training for MMA and MOFT staff working in debt management activities and prepared a draft reform plan in consultation with MOFT and MMA.
| 3. Provinces to which Public Service delivery have been decentralized increased (s2) | Impact | No of Public Service Delivery decentralized |  | Target | 2012: Devolve the functions of all councils; 2013: Monitoring of devolved functions; 2014: Monitoring of devolved functions | LGA, MoHA
Ach.
| 4. Full implementation of Public Accounts System facilitating reduction in payment delays (S3) | Impact | Avg. Time |  | Target | Systems studies for Accounts payable (AP)and Funds Mgt. (FM) Module | (AP) & (FM) Modules Developed | (AP)and (FM) Modules implemented on phased basis | AP, Gl and MM should be implemented fully. | Gl and MM should be implemented fully. | Gl and MM should be implemented fully on | MOFT
[9 empty] | BI reporting functions deployed to the agencies Finance Executives | HR Module full implementation
[5 empty] | Ach. | 2009: Systems Studies completed; 2010: Both Modules Developed; 2011: AP) Module has not been implemented for 7 agencies in Male’ based. All the other Male’ based agencies are online in our SAP system
| 5. MoFT(PAS) Offices operational in Provinces | Output | No | N/A | Target |  |  | 2 of the regional offices, namely HDh. Kulhudhuffushi and S. Hithadhoo full establishment of the offices. | 3 remaining regional offices to be established | 2 remaining regional offices to be established | Full operational of the 7 regional offices. | MOFT
[5 empty] | Ach. | 2011: 2 of the regional offices, namely HDh. Kulhudhuffushi and S. Hithadhoo office furniture procurement done.
| 6. Regions in which infrastructure and storage facilities is developed, increased | Impact | No. of islands where facilities are established | 2010 November 11 | Target |  |  | Launch Baazaaru Bandharu Programme | Execute the programme in 5 islands | Execute the programme in 5 islands | Execute the programme in 5 islands | MED
(refer to S5 P3 of Programme 5.02 Trade & Investment)
[8 empty] | Identify 10 islands to extract private investments | Launch Marketing Concept to promote the concept | Continue Marketing promotion of the programme
[5 empty] | Ach. | 2011: On track
| 7. Liquidity Management through Open Market Operations | Output | Event |  | Target | [6 empty] | MMA
Ach.
| 8. Financial Sector Action Plan |  |  |  | Target | [6 empty] | MMA
Ach.
| 9. Use T-Bills and treasury bonds to improve budgetary financing and avoid recourse into direct monetization | Output | Event | 2009 August Direct monetization stopped | Target | N/A | Auctioning of T Bills | Auctioning of T Bills | Auctioning of T Bills | Auctioning of T Bills |  | MoFT
[5 empty] | Ach. | 2009: N/A; 2010: bonds monetized and repayment schedule identified
Auctioning of T Bills
| 10. Alternative strategies to direct monetization | Output | Event | N/A | Target | N/A | N/A | N/A | Studies for determining a scheme(s) to be undertaken |  |  | MOFT
[5 empty] | Ach. | 2009: N/A; 2010: N/A; 2011: N/A
| 9. Implementation of Real Time Gross Settlement (RTGS) and Automated Clearing House (ACH) | OUTPUT/ IMPACT | Numbers? Percentage? | 2010 | Target | N/A | N/A | Implementation of RTGS and ACH | No. of Interbank Transactions Processed and the number of Cheques Processed | No. of Interbank Transactions Processed and the number of Cheques Processed |  | MMA
| That will increase the number of No. of Interbank Transactions Processed and decline the number of Cheques Processed, respectively |  |  |  | Ach. | 2011: RTGS was launched in April 2011 and ACH is expected to be launched in June 2011
3. Reduce barriers to a competitive market environment, for all sizes of business enterprises to enter the market place (P3) | 1. Identify factors contribute to high cost of goods
| 1 (a) Hold business council meetings to address issues that hinders competitive market environment | Output | Event | 2010 | Target |  | To form business council | To conduct regular (monthly council ) meetings | To conduct regular (monthly council ) meetings | To conduct regular (monthly council ) meetings | To conduct regular (monthly council ) meetings | MED
| (refer to S1 P2 of Programme 5.02 Trade & Investment) |  |  |  | Ach. | 2010: 2010 council formed; 2011: On track
Monthly council meetings held, issues raised, and solved
| 1(b) Publish analysis of annual inflation on DNP website | output | Event | 2010 | Target | 2010: February | DNP
[8 empty] | February | February | February
[5 empty] | Ach. | 2010: Achieved
2. Monitoring systems to gauge fluctuations in cost of goods (s2)
| 2(a) Monitoring measures established |  |  | 2011 | Target |  |  | Monitoring of prices of essential items | Monitoring of prices of essential items in special instances | Regular Monitoring of prices of essential items | Regular Monitoring & publishing of prices of essential items | MED
[8 empty] | Consultations with stakeholders | Monitor impact of taxation on prices of essential items | Publishing of prices of essential items when necessary | Public awareness on fluctuating prices, for consumers and retailers
[9 empty] | Publish prices of essential items when necessary | Revise/Review list of ‘essential items’
Revise/Review list of ‘essential items’
Public awareness on fluctuating prices, for consumers and retailers
[5 empty] | Ach. | 2011: On Track
| 2(b) Produce and publish monthly CPI and improving the quality of CPI (s2) | Output | Event | Monthly inflation figures and 5 yearly rebasing | Target | Monthly dissemination of CPI | Monthly dissemination of CPI | Monthly dissemination of CPI | Monthly dissemination of CPI | Monthly dissemination of CPI |  | DNP
To rebase CPI to 2009
Ach
| 3. A concept for transshipment port development formulated with a designated party to undertake transshipment port development work | Output | Event | Gulhifalhu project 2006/2007 | Target | 2010: To complete draft work to formulate transshipment port; 2011: To find a consultant to develop concept for transshipment port | Privatization Committee (MED/MofT/PO)
Ach.
| 4. Foreign Exchange coming into the country and channeled into the country’s banking system, increased | Output | Value |  | Target | 2011: An exchange control Act to be submitted to the Majlis by end of 2011; 2012: Implementation of the Act; 2013: Implementation of the Act | MMA
[5 empty] | Ach. | 2011: Draft bill prepared and is being discussed in the MMA Board
| 5. Strategies identified and developed in consultation with stakeholders to open up financial markets, put into operation increased | Output | No. |  | Target | 2011: Financial Sector Development Strategy for the Maldives; 2012: Implementation of recommendations; 2013: Implementation of recommendations | MMA and MED
[5 empty] | Ach. | 2011: Financial Sector Development Strategy for the Maldives is being prepared and is to be finalized by the end of May 2011
| 6. Audit firms facilitating the monitoring of business enterprise performance for securing of loans increased (refer to S2 P6 of Programme Small & Medium Enterprises) | Outcome | No. |  | Target |  |  | Consultation with Auditor General Office | Consultation with Auditor General Office | Auditing service firms established in 2 provinces | Auditing service firms established in 2 provinces | MED
Ach.
4. Affordability of Housing increased through additional housing units developed (P4) | 1. Incentive package to encourage private sector participation in housing delivery, developed | Output | No of luxry villas developed(10 unit of housing 1 luxury villa, 500 housing units-1 uninhabited island) | 2010 | Target | 2010: To introduce luxury villa in 2010 | MHE
[5 empty] | Ach. | 2010: Luxury villa introduce
| 2. Partnerships established with International Financial Institutions for lending to housing development (S4) | Output | No. |  | Target | [6 empty] | MHE
Ach.
| 3. HDFC Service Coverage increased | Output | No. | 2004 more than 30% of HDFC in islands | Target | 2009: To provide 500 loans for housing units throughout the Maldives; 2010: 11 (all islands in S. Atoll, Gdh. Thinadhoo, L. Gan and Fonadhoo, HDH. Kulhudhufushi) islands identified in 3 province to provide housing units; 2011: 85 islands identified to provide housing loans(600 housing units) | MHE
3 (a) Provinces in which Operational coverage has been increased (S3? And S4)
[5 empty] | Ach. | 2009: 200 loans were provided for 600 housing units; 2010: 30 housing units in 11 islands identified
| 3 (b)Lending Portfolio increased (S1 and S2) | Outcome | Value |  | Target | [6 empty] | MHE
Ach.
| 4. Housing units developed through PPP, increased (S1 and S2) | Impact | No. |  | Target | [6 empty] | MHE
Ach
5. Affordable basic education and health insurance provided to all citizens and costs of medicine and food items controlled (P5) | 1. Regulation to monitor the level of accessibility, affordability and service quality of health education and other basic service providers established (s3) | Output | Event | 1999 universal access to primary educated. In 2008 government provision of text books and exam fees | Target |  | To Submit education bill on compulsory, and free education (1-10) including curriculum and other issues | To obtain parliament approval on the bill | i)Finalize and implement medicine act (price control regulated by MoHF) | i)Price control mechanism in place, |  | MoHF
Prepare regulations on education and implement it.
[9 empty] | ii)Finalize and implement Health services act | ii) Initiate monitoring for service quality of health.
i) Send medicine act to parliament
[9 empty] | iii) Finalize health professionals act | iii) Implement health professional act
ii)Draft Health services Act (health facility licensing, service/price approval, offences and penalties in respect of license)
iii) Draft health professionals act
[5 empty] | Ach. | 2010: Bill submitted to parliament; 2011: i)Draft medicine act in AG office
English version) MFDA working on the translations
| 2. A Student Loan Scheme developed and established (Education-Social Justice, P5-S1and S2) | Output | Event | Higher education fund 2006 | Target | [6 empty] | MoE
Ach.
| 3. Citizens covered by the universal health insurance scheme (Madhana) increased (s1) | Outcome | % | 8% of the population covered | Target | To increase coverage | 20% of the resident population | Cover 100000 (33%) of the resident population | cover 50% of the resident population | cover 100% of the resident population |  | MoHF
To Open voluntary enrolment for the public
[5 empty] | Ach. | 2009: Voluntary enrolment started in September /16% of population covered; 2010: 21% of population covered (dec 2010); 2011: 66504 (22%) people covered under the scheme as of 28.03.2011
6. Tighten monetary policy to contain inflationary pressures, support the exchange rate and international reserves | 1. Adoption of the new MMA Act which will give MMA increased levels of autonomy that is required for the effective conduct of monetary and exchange rate policy and operations in the Maldives |  |  | MMA Act of 1981 (ammended in 2007) | Target |  | Pass the Bill by December 2010 | Pass the Bill by end of 2011 | Implementation of the MMA Act and formulation of relevant regulations specified under the MMA Act | Implementation of the MMA Act |  | MMA
[5 empty] | Ach. | 2010: Draft bill prepared in consultation with the IMF
| 2. Use of Open Market Operations (OMOs) to manage money supply |  |  | OMOs introduced in Aug 2009 | Target | Reserve Money targets for the year | Reserve Money targets for the year | Reserve Money targets for the year | Reserve Money targets for the year | Reserve Money targets for the year |  | MMA
[5 empty] | Ach. | 2009: No; 2010: Targets for first3 quarters achieved
Target for the fourth quarter was not met.
| 3. Halting of monetization of fiscal deficit |  |  | Direct monetization of the fiscal deficit | Target | Halting of deficit monetization and the introduction of ceiling of Rf100 million on the outstanding balance in the Government’s Ways and Means Account with MMA, at the end of any given month | Ceiling of Rf100 million on the outstanding balance in the Government’s Ways and Means Account with MMA, at the end of any given month | Ceiling of Rf100 million on the outstanding balance in the Government’s Ways and Means Account with MMA, at the end of any given month | Ceiling of Rf100 million on the outstanding balance in the Government’s Ways and Means Account with MMA, at the end of any given month | Ceiling of Rf100 million on the outstanding balance in the Government’s Ways and Means Account with MMA, at the end of any given month |  | MMA
Ach.