## (30) Disaster Risk Management_R
Results Framework (RF) – Disaster Risk Management
Sector Outcome | Results Indicators | Indicator Type | Unit of Measure | Baseline | Targets/ Achievements | [5 empty] | Lead Agency
[6 empty] | 2009 | 2010 | 2011 | 2012 | 2013
1. Disaster Management and mitigation institutionalized and strong institutional base for implementation, created (P1) | 1. DM Act, established (P1 S1) | Output | Event | Draft Bill (2006/7) | Target | Draft Bill revised | Draft bill submitted to AGO | Draft bill to be revised and resubmitted to AGO; and sent to parliament | Bill enacted |  | NDMC, UNDP
[5 empty] | Ach | Draft Bill revised | Draft bill submitted to AGO
| 2. Advocacy to ratify and get policy maker support for DM Bill (P1 S1) | Outcome | Event | 2007 | Target | Sensitization workshops for MP’s and policy makers |  |  |  |  | NDMC, UNDP, MRC, MMS, MoE, MoHE
[5 empty] | Ach | Sensitization workshops for MP’s and Stateministers (regional)
| 3) SNAP for DRR & CCA established. (P1 S2) | Output | Event | 2008 | Target |  | Provisional draft completed |  | To be implemntaed by end of 2011 |  | NDMC, UNDP, MRC, MMS, MoE, MoHE
To be endorsed the government
[5 empty] | Ach |  | Above target achieved
| 4) DRR mainstreamed into all relevant policies in different sectors. (P1 S2) | Outcome | No. of sectoral policies that incorporate DRR | 2009 | Target | Tsunami SOP developed, draft EMS develop by MoHF; |  |  |  | All relevant sectors to incorporate drr in their policies | NDMC, MHE, MoHF
national building code revised with drr integrated, by MHE
[5 empty] | Ach |  | Tsunami SOP developed, draft EMS develop by MoHF;
national building code revised with drr integrated, by MHE
| 5) DRR focal points in all islands, established (P1 S3) | Outcome | No. of islands having focal points | NA | Target | DRR focal points established in all regions | School community DRR focal points established in all islands
[5 empty] | Ach | Achieved above | Except for a few islands target achieved by MoE |  |  |  | NDMC, MoE
| 6) Material for increasing Public awareness on A.e tutional base for implementation creatednlised and strong existing DRR/CCA policies, increased (P1 S3) | Outcome | Type of materials |  | Target |  |  |  | Public awareness on national policies on DRR to be conducted | Public awareness on national policies on DRR to be conducted
Ach
| 7) Establishment of national DRR platform, (P1 S4) | Output | Event | All relevant documents prepared (2008) | Target | working group consultations | working group consultations | Operational Plan shared with key stakeholders. And Platform to be established by end of 2011 | Multi-sectoral platform operational
2. National early warning system for safety and security of Maldivians through information, monitoring, dissemination and coordination (P2) | 1. Risk & vulnerability information are available to all levels. (P2 S1) |  |  | 1986 | Target |  |  |  | Establishment of major hazard weather monitoring system in target islands (popl. Above 1000) | Establishment of major hazard weather monitoring system in target islands (popl. Above 1000)
[9 empty] | Risk and vulnerability assessment to be done on revising the 2006 DPRPM | Risk and vulnerability assessment to be done on revising the 2006 DPRPM
|  | Outcome |  |  | Ach | Seismological monitoring network established
| (i) vulnerability mapped in targetislands (P2 S1) | output | No. of islands mapped | 2006 Risk profile of Maldives developed | Target |  |  |  | Detailed island risk assessment done in 11 target islands complete
Disaster risk information database revised and re-established
[5 empty] | Ach | Community Based disaster preparedness planning done in 37 islands (7 atolls) by UNDP. | Cost Benefit Analysis of risk mitigation measures in 3 islands developed
CBDRR done in 4 islands by Care Society.
| 3. National multi hazard early warning system enhanced to monitor, archive and disseminate data on key hazards and vulnerabilities. (P2 S3) | Output |  | Before 2008 issuing forcasts & Early Warning began | Target |  | SOP Formulation | SOP Formulation | 1 automatic weather stations established | End-to-End early warning system enhanced
[5 empty] | Ach |  | 17 draft Early Warning SOPs developed for 17 agencies(for different sectors) | 1 automatic weather stations established | 1 automatic weather stations established
8 automatic weather stations established
| (ii) |  |  |  |  | Target
Ach
| 4. Trans boundary Risk assessments performed (P2 S4) | Output |  | Case by case assessment | Risk assessment done on identified cases | Target | No incident | No incident | Tsunami in Japan
Ach
3. Culture of safety and resilience built at all levels in the country through innovation, knowledge and education | 1. Natural hazards information made available to the public.
a)
| b) Establishment of GIS. | Output |  |  | Target | [5 empty] | NDMC, UNDP,MHE, MMS
Ach
| c) Increased networks to educate the public on DR/CC resilience | Outcome | No. of advocacy and awareness initiatives | 2005 – 2009 (after tsunami recover programmes) | Target | Rakkaa Campaign lauched |  | National endorsement of Rakka campaign Social Marketing Plan. | MRC CBDRR project | MRC CBDRR project | NDMC, UNDP, MRC, MMS, MoE, MoHE, HRCM
MRC CBDRR project
ToT workshop on Rights-based approach to disaster recovery (UNDP, HRCM)
[5 empty] | Ach | Rakkaa Campaign launched | Rakka campaign, social marketing materials launched.
MRC CBDRR programme launched
| 2. Integration of DRR concepts & practices in the National Curriculum. |  |  |  | Target
Ach
| a) Incorporation of DRR & CCA in the National Curriculum. | Output | Event |  | Target | DRR books for teachers and students drafted and published |  | Development diploma course on DRR for in-search teachers (WHO, MoE, MHF) | Draft DRR books for teachers and students revised and published |  | DRR integrated into curriculum of Faculty of Arts (NUM)
| b) b) Development of educational materials on DRR | [7 empty] | Using the DRR materials developed, educational curriculum rebvised
[5 empty] | Ach |  | DRR books for teachers and students drafted
3 Strengthened research approaches to risk assessments & analysis.
| (i) National climate change research strategy developed | event | Event | 2010 | Target |  |  | National Climate Change Research Strategy, formulated
[5 empty] | Ach |  |  | National Climate Change Research Strategy, formulated
4. Underlying risks to life and property from natural or man-made hazardous events reduced | 1. DRR measures are integrated into all Environmental Policies and plans. | Outcome | No. of Policies |  | Target |  |  | Land use planning guidelines developed | Statistical down-scalling of climate scenarios for the country |  | NDMC, MHE, UNDP
National Building Act developed
Revision of Environment Act done
Statistical down-scalling of climate scenarios for the country
[5 empty] | Ach |  | National building codes revised with DRR integrated | Climate change research strategy deveoped
(a)
| 2. Development of policies to address populations most at risk | Output | No. | 2009 | Target | [5 empty] | MoHF
[5 empty] | Ach |  | Disability Act ratified
| 3. Integration of DRR in the economic & productive sector policies. | Output | Event |  | Target |  |  |  |  | By 2014 climate risk insurance options identified and made available | MED, UNDP, MHE, MTAC
Ach
| (a) Adaptation measures for climate change and disaster mitigation for the tourism industry identified and enforced (SAP: Tourism, Policy 4, Stat 1) | outcome |  | no. of activities | Target |  |  |  | Project on integrating climate change adapational measures into Tourism laws and regulations initiated |  | MTAC, UNDP, MHE
[5 empty] | Ach |  |  | Project on integrating climate change adapational measures into Tourism laws and regulations developed
| 4. Integration of DRR in the post disaster recovery and rehabilitation. |  |  | 2005 tsunami (2004) lessons learned documents developed | Target |  |  | ToT workshopson Rights based approach to disaster recovery to be conducted by UNDP and HRCM | ToT workshopson Rights based approach to disaster recovery to be conducted by UNDP and HRCM |  | UNDP, MHE, HRCM
[5 empty] | Ach |  | National building codes
| 5. Disaster impact assessment to major infrastructure projects. | output | Regulations done/no. of assessments | 2010 | Target | [5 empty] | MHE
[5 empty] | Ach |  | EIA process revised to include DRR aspects
5. Disaster preparedness strengthened fro effective response at all levels | 1. Strengthening technical and institutional capacities for disaster management. |  |  |  | Target | [5 empty] | NDMC
Ach
| (a) DRR integrated into the National Building Codes | Output | Event |  | Target |  | building codes reviewed |  |  |  | UNDP, MHE
[5 empty] | Ach |  | building codes reviewed
| 2 Establishment of Disaster Preparedness Plans and Contingency Plans at all levels. | Output | No. |  | Target
Ach
| 3 Allocation of financial reserves & contingency budget for immediate response and relief efforts. | Output | Event
| 4 Establishment of procedures for exchange of information during disasters. | Outcome | Event |  | Target
Ach
6. Disaster risk reduction integrated in climate change adaptation and vice versa | 1. Pilot Projects developed for involving integration of DRR and CCA stakeholders | Output | No. |  | Target
Ach
| 4. Integration of DRR in the post disaster recovery and rehabilitation. |  |  |  | Target
Ach
| 5. Disaster impact assessment to major infrastructure projects. |  |  |  | Target
Ach
5. Disaster preparedness strengthened for effective response at all levels | 1. Strengthening technical and institutional capacities for disaster management. | outcome | No. of trainings/no.of regulations | 2005 | Target |  |  | 20 trainings by ADPC |  |  | NDMC
[5 empty] | Ach | 15 trainings for ADPC | 15 trainings for ADPC | 1 training on agro-meteorology by SSCTF
Target
Ach
| 2 Establishment of Disaster Preparedness Plans and Contingency Plans at all levels. | Output | No. | 2005 | Target |  |  | Health contingency plans to developed based on existing CBDPPs done | CBDPP’s to in be done in 6 islands (6 atolls) MRC | CBDPP’s to be done in target atolls in the Maldives, UNDP. | UNDP, MRC, MoE, Care Society
[5 empty] | Ach | School emergency operations plan/guideline developed | CBDPP’s done in 37 islands (7 atolls)
SEOP compliant drilols conducted in target schools in south region by MoE.
SEOP compliant drills conducted in 9 islands by MoE and Care Society.
| 3 Allocation of financial reserves & contingency budget for immediate response and relief efforts. | Output |  | 2005, Tsunami Response and Relief Fund (international aid after tsunami) | target | [5 empty] | NDMC, MoFT
ach
| 4 Establishment of procedures for exchange of information during disasters. | Outcome | Event | 2005, MMS SOP | Target | [5 empty] | MMS, NDMC, UNDP, MRC, MoHF, MoE, CAM
[5 empty] | Ach | End to end early warning system SOP’s developed 17 agencies developed
6. Disaster risk reduction integrated in climate change adaptation and vice versa | pilot projects developed to integrated DRR and CCA | Output | No. |  | Target |  |  |  | Project to integrate climate change adaptatiion measures into tourism sector laws and regulations |  | UNDP, MHE, MRC
[5 empty] | Ach | Rakka camapaign | MRC’s CBDRR project.
[6 empty] | Climate Risk management project with RIMES and UNDP | ICCR project under MHE